## Study
SEC order | SEC Number | product | item_type | item | description | req_qty | allocated_qty | balance | source | locater | supply_type | availability_date | demand_type | alternatives | delivery_address | SEC delivery | ROH delivery | delay | supplier | po_remarks | Asn Quantity | Asn Expected Date | Asn Creation Date | transaction_type | transaction_number | Asn Shipment
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 6 | 2 | 4 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076564
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 4 | 2 | 2 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082393
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 2 | 2 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099569
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 16 | 4 | 12 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099668
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 12 | 2 | 10 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099569
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 10 | 2 | 8 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108500
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 8 | 2 | 6 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127265
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 6 | 2 | 4 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127256
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 4 | 4 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 5 | 1 | 4 | 6100K019 | R57-J-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082396
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 4 | 1 | 3 | 6100K019 | R57-J-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082399
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 3 | 1 | 2 | 6100K019 | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108605
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 2 | 1 | 1 | 6100K019 | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108695
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 1 | 1 | 0 | 6100K019 | R57-J-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120188
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 6 | 1 | 5 | 6100K019 | R57-J-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120281
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 5 | 5 | 0 | 6100KDP01 | R57-J-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 6 | 1 | 5 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8077524
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 5 | 1 | 4 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8077518
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 4 | 1 | 3 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082402
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 3 | 1 | 2 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8085892
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 2 | 1 | 1 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8115341
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 1 | 1 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8115356
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 7 | 1 | 6 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128694
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 6 | 1 | 5 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128742
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 5 | 1 | 4 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8140287
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 4 | 1 | 3 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8140326
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 3 | 3 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 1046 | 1046 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 1188 | 1026 | 162 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 162 | 162 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 03366 | STEEL RIVETS T22205/4.8 TS | 114 | 114 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 03366 | STEEL RIVETS T22205/4.8 TS | 146 | 127 | 19 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 03366 | STEEL RIVETS T22205/4.8 TS | 19 | 19 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 68 | 68 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 69 | 59 | 10 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 10 | 9 | 1 | 6100K019 | 1-1-1-1 | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100046
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 1 | 1 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100052
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 07686 | WASHER AC EL DIN137 T22120/8 A | 4 | 4 | 0 | 6100K019 | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 07853 | HEX. HEAD BOLT T21000/3X16 | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 07934 | TOMMY HEAD SCREW ACC T21010/M3x6 | 20 | 20 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 07934 | TOMMY HEAD SCREW ACC T21010/M3x6 | 24 | 20 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 07934 | TOMMY HEAD SCREW ACC T21010/M3x6 | 4 | 4 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 07940 | TOMMY HEAD SCREW ACC T21010/M3X20 | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 07940 | TOMMY HEAD SCREW ACC T21010/M3X20 | 9 | 8 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 07940 | TOMMY HEAD SCREW ACC T21010/M3X20 | 1 | 1 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 07959 | TOMMY HEAD SCREW FULL THREAD T21010/4X25 | 60 | 60 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08017 | TOMMY HEAD SCREW ACC T21010/M4x22 | 20 | 20 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08017 | TOMMY HEAD SCREW ACC T21010/M4x22 | 26 | 22 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08017 | TOMMY HEAD SCREW ACC T21010/M4x22 | 4 | 4 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08222 | COUNTER SUNK SCREW 6X16 ACC T21030/6X16 | 4 | 4 | 0 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08222 | COUNTER SUNK SCREW 6X16 ACC T21030/6X16 | 4 | 4 | 0 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08448 | SQUARE FASTENING NUT TS ACC T21597/5 | 24 | 24 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08448 | SQUARE FASTENING NUT TS ACC T21597/5 | 28 | 24 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08448 | SQUARE FASTENING NUT TS ACC T21597/5 | 4 | 4 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100049
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 25 | 25 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 30 | 15 | 15 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 15 | 10 | 5 | 6100K019 | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 5 | 5 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120200
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08856 | WASHER STEEL T22100/ 6.4 | 24 | 24 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08856 | WASHER STEEL T22100/ 6.4 | 28 | 24 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 08856 | WASHER STEEL T22100/ 6.4 | 4 | 4 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144790
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 09011 | LOCK NUT T21192/M3N - DIN 985 A2K | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 09021 | SELF-LOCKING HEX. NUT,T21192/M10 (LOCAL) | 48 | 48 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 09021 | SELF-LOCKING HEX. NUT,T21192/M10 (LOCAL) | 56 | 48 | 8 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 09021 | SELF-LOCKING HEX. NUT,T21192/M10 (LOCAL) | 8 | 8 | 0 | 6100K019 | 1-1-1-1 | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144145
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 09601 | WASHER, FLAT ACC T22000/3.2X7 | 30 | 30 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 09601 | WASHER, FLAT ACC T22000/3.2X7 | 36 | 30 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 09601 | WASHER, FLAT ACC T22000/3.2X7 | 6 | 6 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 09947 | SPRING WASHER ACC T22104/6 | 4 | 4 | 0 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 09947 | SPRING WASHER ACC T22104/6 | 6 | 6 | 0 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1000057457 | WASHER CU AL M10 | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1000057457 | WASHER CU AL M10 | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1000057457 | WASHER CU AL M10 | 1 | 1 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1020178 | COMBINATION SPANNER SETS | 1 | 1 | 0 | 6100K019 | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1020178 | COMBINATION SPANNER SETS | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 12980 | COUNTERSUNK STEEL SCREW T21065/M6X14 | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 12980 | COUNTERSUNK STEEL SCREW T21065/M6X14 | 14 | 12 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 12980 | COUNTERSUNK STEEL SCREW T21065/M6X14 | 2 | 2 | 0 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 12989 | COUNTERSUNK STEEL SCREW T21065/M8X30 | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 12989 | COUNTERSUNK STEEL SCREW T21065/M8X30 | 14 | 12 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 12989 | COUNTERSUNK STEEL SCREW T21065/M8X30 | 2 | 2 | 0 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 13441 | TORQUES WRENCH | 1 | 1 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 13441 | TORQUES WRENCH | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1420601 | BI-HEXAGON DEEP SOCKET SET | 1 | 1 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1420601 | BI-HEXAGON DEEP SOCKET SET | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1420630 | BI HEXAGON SOCKET SET of RATCHET | 1 | 1 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1420630 | BI HEXAGON SOCKET SET of RATCHET | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1440146 | BALL END ALLEN KEY SET | 1 | 1 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1440146 | BALL END ALLEN KEY SET | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40202 | Busbar, Copper, 80 x 10 mm, R=5 | 326.198 | 326.198 | 0 | 6100KDP01 | BBR-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical | Automated: Replaced 1535 1034-227 by SEP40202. | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40254 | Busbar, Copper, 50 x 10 mm, R=1 | 1.84 | 1.84 | 0 | 6100KDP01 | BBR-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical | Automated: Replaced 1535 1044-120 by SEP40254. | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40196 | Busbar, Copper, 60 x 10 mm, R=5 | 12.24 | 12.24 | 0 | 6100K019 | BBR-1-1-K019_SEP | consumption | 2025-10-21 | Mechanical | Automated: Replaced 1535 1044-125 by SEP40196. | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8233573
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40181 | Busbar, Copper, 32 x 8 mm, R=1 | 11.88 | 8 | 3.88 | 6100K019 | BBR-1-1-K019_SEP | consumption | 2025-10-21 | Mechanical | Automated: Replaced 1535 1044-253 by SEP40181. | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8233585
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40181 | Busbar, Copper, 32 x 8 mm, R=1 | 3.88 | 3.88 | 8.8818e-16 | 6100K019 | BBR-1-1-K019_SEP | consumption | 2025-10-25 | Mechanical | Automated: Replaced 1535 1044-253 by SEP40181. | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8292290
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40181 | Busbar, Copper, 32 x 8 mm, R=1 | 8.8818e-16 | 8.8818e-16 | 0 | free_stock | BBR-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical | Automated: Replaced 1535 1044-253 by SEP40181. | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40187 | Busbar, Copper, 40 x 10 mm, R=1 | 3.288 | 3.288 | 0 | 6100K019 | BBR-1-1-KDP1_SEP | consumption | 2025-10-21 | Mechanical | Automated: Replaced 1535 1044-96 by SEP40187. | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8233579
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40184 | Busbar, Copper, 40 x 5 mm, R=1 | 1.2 | 1 | 0.2 | 6100K019 | BBR-1-1-K019_SEP | consumption | 2025-10-21 | Mechanical | Automated: Replaced 1535 1048-235 by SEP40184. | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8233582
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40184 | Busbar, Copper, 40 x 5 mm, R=1 | 0.2 | 0.2 | 0 | 6100K019 | BBR-1-1-K019_SEP | consumption | 2025-10-25 | Mechanical | Automated: Replaced 1535 1048-235 by SEP40184. | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8292286
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40233 | Busbar, Copper, 50 x 4 mm, R=1 | 1.2 | 1 | 0.2 | 6100K019 | BBR-1-1-K019_SEP | consumption | 2025-10-21 | Mechanical | Automated: Replaced 1535 1048-249 by SEP40233. | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8233576
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40233 | Busbar, Copper, 50 x 4 mm, R=1 | 0.2 | 0.2 | 0 | 6100K019 | BBR-1-1-K019_SEP | consumption | 2025-10-25 | Mechanical | Automated: Replaced 1535 1048-249 by SEP40233. | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8292283
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 16301 | RIVET T22213/4 | 32 | 32 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 16301 | RIVET T22213/4 | 36 | 32 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 16301 | RIVET T22213/4 | 4 | 4 | 0 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 16304 | RIVET TT ALUMINUM T22213/5 | 9 | 9 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 10 | 10 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 12 | 8 | 4 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 4 | 2 | 2 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 2 | 2 | 0 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082408
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 42 | 35 | 7 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 7 | 7 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 49 | 21 | 28 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 28 | 21 | 7 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 7 | 7 | 0 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082414
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1815230000 | 5Pole Plug 2.5mm-1815230000-Cont-loop | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1855030000 | 6Pole Plug 4mm-1855030000-AC looping | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SFA611400R1001 | PILOT LIGHT#ML1-100R | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SFA611400R1002 | PILOT LIGHT#ML1-100G | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SFA611400R1003 | PILOT LIGHT#ML1-100Y | 7 | 7 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SFA611400R1005 | PILOT LIGHT#ML1-100W | 8 | 8 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SFA611605R1100 | HOLDER#MCBH-00 | 23 | 23 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SFA611621R1051 | LAMP BLOCK#MLBL-05R | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SFA611621R1052 | LAMP BLOCK#MLBL-05G | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SFA611621R1053 | LAMP BLOCK#MLBL-05Y | 7 | 7 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SFA611621R1055 | LAMP BLOCK#MLBL-05W | 8 | 8 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 23 | 18 | 5 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 5 | 5 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 23 | 23 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SNA234000R0200 | Use *** 1SNA234041R2600 *** | 60 | 60 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SNK900654R0000 | SC-JB8-4 Short circuit bridges - Yellow | 18 | 18 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR000474F0001 | BLOCK | 11 | 11 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR000474F0001 | BLOCK | 13 | 11 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR000474F0001 | BLOCK | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR002047G0001 | COMPLETE ASSEMBLY KIT FOR DIRAK LOCKUP | 6 | 6 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR002047G0001 | COMPLETE ASSEMBLY KIT FOR DIRAK LOCKUP | 7 | 3 | 4 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR002047G0001 | COMPLETE ASSEMBLY KIT FOR DIRAK LOCKUP | 4 | 3 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR002047G0001 | COMPLETE ASSEMBLY KIT FOR DIRAK LOCKUP | 1 | 1 | 0 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8132321
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR002416G0001 | LOCKUP ROD ASSEMBLY | 7 | 7 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR002416G0001 | LOCKUP ROD ASSEMBLY | 9 | 9 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR002428G0001 | LOCKUP ROD ASSEMBLY | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR002428G0001 | LOCKUP ROD ASSEMBLY | 7 | 5 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR002428G0001 | LOCKUP ROD ASSEMBLY | 2 | 1 | 1 | 6100K019 | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR002428G0001 | LOCKUP ROD ASSEMBLY | 1 | 1 | 0 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144151
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR003760G0001 | Crank EK6- Earthing Switch | 1 | 1 | 0 | 6100K019 | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR008770F0001 | BLOCK PIN | 48 | 48 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR008770F0001 | BLOCK PIN | 56 | 48 | 8 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR008770F0001 | BLOCK PIN | 8 | 8 | 0 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8115719
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7600349P0101 | SHROUD | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7600349P0101 | SHROUD | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7600732P0101 | SPACER TUBE | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7600732P0101 | SPACER TUBE | 14 | 12 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7600732P0101 | SPACER TUBE | 2 | 2 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7601387P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Short | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7601387P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Short | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7601387P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Short | 1 | 1 | 0 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8115722
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7601389P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Long | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7601389P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Long | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7601389P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Long | 1 | 1 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7602006R0101 | TIE ROD W800 CABLE COMPT. | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7602006R0101 | TIE ROD W800 CABLE COMPT. | 14 | 12 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7602006R0101 | TIE ROD W800 CABLE COMPT. | 2 | 2 | 0 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144818
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7607280R0101 | HINGE WITHOUT FASTENERS | 66 | 66 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7607280R0101 | HINGE WITHOUT FASTENERS | 77 | 66 | 11 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7607280R0101 | HINGE WITHOUT FASTENERS | 11 | 11 | 0 | free_stock | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7608266P0101 | CONNECTION PIECE tublar GCE8005046R0101 | 6 | 6 | 0 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB000002-FDV | MIMIC DIAGRAM, INCOMER-2W,VT | 1 | 1 | 0 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8139443
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB000003-FDX | MIMIC , OUTGOING WITH EARTHING | 2 | 1 | 1 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069876
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB000003-FDX | MIMIC , OUTGOING WITH EARTHING | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB000004-BTE | MIMIC BUS SEC WITH EARTHG ON RIGHT SIDE | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB000007-BME | MIMIC, BUS MET. & EARTHING-2W,VT | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB000009-BRM | MIMIC , BUS RISER & MET.-2W,VT | 1 | 1 | 0 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8129015
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010005P0103 | SHROUD, LEFT W800 | 9 | 9 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010005P0103 | SHROUD, LEFT W800 | 12 | 9 | 3 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010005P0103 | SHROUD, LEFT W800 | 3 | 3 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8077527
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010006P0103 | SHROUD, RIGHT W800 | 9 | 9 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010006P0103 | SHROUD, RIGHT W800 | 12 | 9 | 3 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010006P0103 | SHROUD, RIGHT W800 | 3 | 3 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128823
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 7 | 4 | 3 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 3 | 2 | 1 | 6100K019 | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 1 | 1 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082417
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 18 | 18 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 21 | 12 | 9 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 9 | 6 | 3 | 6100K019 | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 3 | 3 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082426
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010025P0101 | HINGE COMPONENT #2 | 36 | 36 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010025P0101 | HINGE COMPONENT #2 | 42 | 36 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010025P0101 | HINGE COMPONENT #2 | 6 | 6 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010029P0122 | CVI DIVIDER, 12-17.5kV, Set 1B (11425) | 3 | 3 | 0 | 6100K019 | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010029P0122 | CVI DIVIDER, 12-17.5kV, Set 1B (11425) | 4 | 3 | 1 | 6100K019 | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010029P0122 | CVI DIVIDER, 12-17.5kV, Set 1B (11425) | 1 | 1 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010032P0101 | CT PLATE,UPPER,W1000 (PAINT RAL7035-STD) | 1 | 1 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010033P0101 | CT MOUNTING PLATE, LOWER, W1000, 3150A | 1 | 1 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010037P0101 | STRENGHTENING SHEET 13.8KV/24KV | 12 | 2 | 10 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-13 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070994
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010037P0101 | STRENGHTENING SHEET 13.8KV/24KV | 10 | 2 | 8 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-13 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082429
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010037P0101 | STRENGHTENING SHEET 13.8KV/24KV | 8 | 2 | 6 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-14 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107722
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010037P0101 | STRENGHTENING SHEET 13.8KV/24KV | 6 | 2 | 4 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-15 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128757
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010037P0101 | STRENGHTENING SHEET 13.8KV/24KV | 4 | 2 | 2 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-16 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144133
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010037P0101 | STRENGHTENING SHEET 13.8KV/24KV | 2 | 2 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010072P0101P | CONTACT PIN 35 DIA, 90L | 18 | 18 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010072P0101P | CONTACT PIN 35 DIA, 90L | 30 | 24 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010072P0101P | CONTACT PIN 35 DIA, 90L | 6 | 6 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010075P0101 | PARTITION PLATE UPPER CT W800 SS STL | 3 | 3 | 0 | 6100KDP01 | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010076P0101 | COVER FOR PARTITION PLATE | 3 | 3 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 22.19 | 22.19 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 27.7 | 12.69 | 15.01 | 6100K019 | R66-H-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 15.01 | 9.91 | 5.1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 5.1 | 5.1 | 0 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108602
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010138P0102 | PROTECTIVE COVER W800 | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010138P0102 | PROTECTIVE COVER W800 | 5 | 4 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010138P0102 | PROTECTIVE COVER W800 | 1 | 1 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010138P0103 | PROTECTIVE COVER W1000 | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010138P0120 | Cover for push button rod | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010138P0120 | Cover for push button rod | 5 | 4 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010138P0120 | Cover for push button rod | 1 | 1 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010145P0102 | DOOR STOPPER ROD 8 MM DIA. | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010145P0102 | DOOR STOPPER ROD 8 MM DIA. | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010145P0102 | DOOR STOPPER ROD 8 MM DIA. | 1 | 1 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010241P0101 | HEX. BOLT M10X20 POLYAMIDE | 18 | 18 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010241P0101 | HEX. BOLT M10X20 POLYAMIDE | 24 | 18 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010241P0101 | HEX. BOLT M10X20 POLYAMIDE | 6 | 6 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076588
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 9 | 9 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 12 | 9 | 3 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 3 | 3 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070967
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010241P0103 | HEX. BOLT M10X30 POLYAMIDE | 9 | 9 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010241P0103 | HEX. BOLT M10X30 POLYAMIDE | 12 | 9 | 3 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010241P0103 | HEX. BOLT M10X30 POLYAMIDE | 3 | 3 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 5 | 2 | 3 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 3 | 1 | 2 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 2 | 1 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 1 | 1 | 0 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082435
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010301P0111 | Label printed in Trafolite 200 x 100 | 6 | 6 | 0 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010301P0111 | Label printed in Trafolite 200 x 100 | 7 | 5 | 2 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010301P0111 | Label printed in Trafolite 200 x 100 | 2 | 1 | 1 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010301P0111 | Label printed in Trafolite 200 x 100 | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010366P0109 | Self tapping screw pan head M4x5mm SS | 300 | 300 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010378P0110 | SEC.FEMALE CONTACTS 1.5,W.SLEEVES 50X | 300 | 300 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010378P0110 | SEC.FEMALE CONTACTS 1.5,W.SLEEVES 50X | 400 | 350 | 50 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010378P0110 | SEC.FEMALE CONTACTS 1.5,W.SLEEVES 50X | 50 | 50 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010378P0111 | SEC. PIN MALE 1.5 MMZS1 | 100 | 100 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010378P0111 | SEC. PIN MALE 1.5 MMZS1 | 150 | 100 | 50 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010378P0111 | SEC. PIN MALE 1.5 MMZS1 | 50 | 50 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010378P0112 | SEC. FEMALE CONTACT PIN 2.5MM | 250 | 250 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010378P0112 | SEC. FEMALE CONTACT PIN 2.5MM | 350 | 300 | 50 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010378P0112 | SEC. FEMALE CONTACT PIN 2.5MM | 50 | 50 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010378P0113 | PIN,CONTACT MALE 2.5 | 100 | 100 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010378P0113 | PIN,CONTACT MALE 2.5 | 100 | 100 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010378P0116 | Lugs, Sleeve 4.0/9mm ( W/O Ins.) 3200302 | 300 | 300 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 10 | 10 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 12 | 6 | 6 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 6 | 4 | 2 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 2 | 2 | 0 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8085898
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010402R0103 | LABELS FOR SHUTTERS BUSBAR-CABLE -FEEDER | 4 | 4 | 0 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010402R0103 | LABELS FOR SHUTTERS BUSBAR-CABLE -FEEDER | 6 | 5 | 1 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010402R0103 | LABELS FOR SHUTTERS BUSBAR-CABLE -FEEDER | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010402R0104 | LABELS FOR SHUTTERS BUSBAR-1,2,3-B/S,B/R | 1 | 1 | 0 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010489P0101 | FLAT BRAIDED, 16SQMM. TIN(13.8kV)6mmdia | 22 | 22 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010489P0101 | FLAT BRAIDED, 16SQMM. TIN(13.8kV)6mmdia | 25 | 18 | 7 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010489P0101 | FLAT BRAIDED, 16SQMM. TIN(13.8kV)6mmdia | 7 | 4 | 3 | 6100K019 | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010489P0101 | FLAT BRAIDED, 16SQMM. TIN(13.8kV)6mmdia | 3 | 3 | 0 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010489P0102 | FLAT BRAIDED CONNECTOR, 16 SQMM. TINNED | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010489P0102 | FLAT BRAIDED CONNECTOR, 16 SQMM. TINNED | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010489P0102 | FLAT BRAIDED CONNECTOR, 16 SQMM. TINNED | 1 | 1 | 0 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010491P0101 | FLEX. CABLE,70MM.SQ, PVC 85 YEL/GRN,85°C | 8.05 | 8.05 | 0 | 6100K019 | R57-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010491P0101 | FLEX. CABLE,70MM.SQ, PVC 85 YEL/GRN,85°C | 9.66 | 8.05 | 1.61 | 6100K019 | R57-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB010491P0101 | FLEX. CABLE,70MM.SQ, PVC 85 YEL/GRN,85°C | 1.61 | 1.61 | 0 | free_stock | R57-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5112XFS00000 | VT 3Nos PRIMARY FUSE 17.5kV, 3A, SIBA | 9 | 9 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | A |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | A |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5320XDB1XN01 | CEWE Elite 440-448 | 2 | 1 | 1 | 6100K019 | R16-B-1-K019_SEP | consumption | 2025-10-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8129021
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5320XDB1XN01 | CEWE Elite 440-448 | 1 | 1 | 0 | free_stock | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | LL10-W | ABB_LL10-W / LL10-W, AC/DC90-264V 50/60HZ | 6 | 6 | 0 | free_stock | R15-I-1-K017_SEP | inventory | 2025-11-03 | LV | Automated: Replaced 1YAB53301XIX0000 by LL10-W. | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 6 | 1 | 5 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8129024
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 5 | 1 | 4 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-16 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8137210
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 4 | 4 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5331XXCX0100 | BREAKER CONTROL SWITCH (Comelectric) | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5331XXCX0210 | CBMODE6P,4Pos.Off-Emer-Local-Rem-Padlock | 2 | 1 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5331XXCX0220 | OFF-EMER-LOCAL-REMOTE 4P4P, PADLCK (COM) | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5331XXCX0300 | SPACE HEATER SEL. SWITCH ( COMELECTRIC ) | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC ) | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC ) | 1 | 1 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5334XXAX1000 | FT-1 SW-Type 129A514G01 | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5334XXAX2000 | RTXP 8, RK 926 002-AG (8P) | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5334XXAX2100 | RTXP18, RK 926 115-BF | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5335XXAX1100 | COMBIFLEX TERMINAL BASE RX 2H -5619625-A | 14 | 14 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5335XXAX1200 | COMBIFLEX TERMINAL BASE RX4 (4U 12C) | 16 | 16 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5336XXAA2E00 | MCB 3A AC -2P,2CDS252001R0317 | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5336XXAA2G00 | MCB S 202-K6 6A AC -2P - 2CDS252001R0377 | 10 | 10 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5336XXAA2L00 | MCB 16A AC -2P - 2CDS252001R0467 | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5336XXAA3F00 | MCB S203-K 4 MC -3P 2CDS253001R0337 | 33 | 33 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5336XXAA3I00 | MCB 10A AC -3P - 2CDS253001R0427 | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5336XXAB2G00 | MCB 6A DC 2P S202M-K6UC -2CDS272061R0377 | 32 | 32 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5336XXACG000 | Aux contact 2NC, S2C-HO2L-for MCB Order # 2CDS200936R0003 | 26 | 26 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5336XXACH000 | Aux contact 1NO+1NC MCB -2CDS200936R0001 | 72 | 72 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5336XXACJ000 | S2C-H01 - 1NC- Bottom Auxiliary Contact 2CDS200970R0031 | 35 | 35 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5340XAJXXN00 | RF-4R_125Vdc_4 C/O_LED | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5340XAJXXN01 | BJ-8RP_Bistable_125Vdc_8 C/O | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5340XBLXXN00 | MVAJ101 RA 0802_ 125VDC (8 NO + 2 NC) | 2 | 1 | 1 | 6100K019 | R16-L-1-K019_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069882
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5340XBLXXN00 | MVAJ101 RA 0802_ 125VDC (8 NO + 2 NC) | 1 | 1 | 0 | 6100K019 | R16-L-1-K019_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070555
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5340XCHXXN00 | LOCKOUT RELAY (86) TYPE 7805F-70-280VDC | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5340XCLXXN00 | MVAJ105 RA 0802_125VDC (8 NO + 2 NC) | 1 | 1 | 0 | free_stock | R16-L-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5340XDAXXN00 | RXMVB 4, RK 251 401-AP | 2 | 2 | 0 | free_stock | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5340XDAXXN01 | RXMVB2, RK 251 204-AP | 3 | 3 | 0 | free_stock | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5340XEAXXN00 | RXMB1 6NO_110-125VDC-1MRK 000 863-AN | 4 | 4 | 0 | free_stock | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5340XIAXXN00 | RXSF1_DC110-125V-MV RK 271 019-AN | 14 | 14 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DM0000000058 | Relay, Auxiliary, 2 Coils, Self Reset Contacts, Hand Reset Flag, 110-125V, DC, 2NO, 1NC, Coil ¦ RXSF1 RK 271 007-AN | 14 | 4 | 10 | 6100K019 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV | Automated: Replaced 1YAB5340XIAXXN01 by DM0000000058. | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5340XJAXXN00 | THREE PHASE FUSE SUPERVISION RELAY Type : RXBA4 (ABB) ORDER NO. : RK 428 004-AA CONTACTS : 2 CHANGE OVER SELF RESET OPERATE TIME : 8mS RATED VOLTAGE : 120V / 1.732 PH/N OVERLOAD CAPACITY : 110% OF Un MOUNTING DIMENSIONS : COMBIFLEX 4U12C | 3 | 3 | 0 | 6100K019 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSABB000 | FLEX.CABLE,1/C,1.5MM BLUE ATC,105 Deg C | 13.1291 | 13.1291 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSABC000 | FLEX.CABLE,1/C,1.5MM BLACK ATC,105 Deg C | 4.267 | 4.267 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSABD000 | FLEX.CABLE,1/C,1.5MM GREY ATC,105 Deg C | 50 | 50 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSABD000 | FLEX.CABLE,1/C,1.5MM GREY ATC,105 Deg C | 99.0153 | 99.0153 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSABR010 | FLEX.CABLE,1/C,1.5MM RED C,105 Deg C | 4.267 | 4.267 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSACB010 | FLEX.CABLE,1/C,2.5MM BLUE ATC,105 Deg C | 17.7243 | 17.7243 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSACC010 | FLEX.CABLE,1/C,2.5MM BLACK ATC,105 Deg C | 11.1597 | 11.1597 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSACD010 | FLEX.CABLE,1/C,2.5MM GREY ATC,105 Deg C | 3.2823 | 3.2823 | 0 | 6100KDP01 | R56-I-1-KDP1_SEP | consumption | 2025-06-28 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Miscellaneous issue | 6172962
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSACN010 | FLEX.CABLE,1/C,2.5MM YE/GN ATC,105 Deg C | 3.337 | 3.337 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSACN010 | FLEX.CABLE,1/C,2.5MM YE/GN ATC,105 Deg C | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSACR010 | FLEX.CABLE,1/C,2.5MM RED ATC,105 Deg C | 17.7243 | 17.7243 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSACY010 | FLEX.CABLE,1/C,2.5MM YELLOW ATC,90 Deg C | 17.7243 | 17.7243 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSADB020 | FLEX.CABLE,1/C,4MM BLUE ATC,105 Deg C | 0.98468 | 0.98468 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSADC020 | FLEX.CABLE,1/C,4MM BLACK ATC,105 Deg C | 1.3129 | 1.3129 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSADD020 | FLEX.CABLE,1/C,4MM GREY ATC,105 Deg C | 1.3129 | 1.3129 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSADR020 | FLEX.CABLE,1/C,4MM RED ATC,105 Deg C | 0.98468 | 0.98468 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5350XSADY020 | FLEX.CABLE,1/C,4MM YELLOW ATC,105 Deg C | 0.98468 | 0.98468 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block OTTA 6-T-P/P - 0790462 | 598 | 598 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 210 | 210 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 270 | 225 | 45 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 45 | 45 | 0 | 6100K019 | R59-G-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355AEA0001 | M 6/8.RS (SpringLoaded) 1SNA115685R1200 | 166 | 166 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 1862 | 1231 | 631 | 6100K019 | PLT-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 631 | 631 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355AFA0001 | M4/6.SNTS Spring Loaded 1SNA115229R2000 | 270 | 270 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 208 | 208 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355AMC0001 | Feed-through terminal block,ZT 4/4AN/2 .Base Terminal Plug AC-DC-4mm 1848350000 | 180 | 180 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 72 | 60 | 12 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 98 | 84 | 14 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 14 | 14 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355CAB0000 | End Cover, D-OTTA6-T - 0790459 | 60 | 60 | 0 | 6100K011B | R15-T-1-KDP1_SEP | consumption | 2025-10-18 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8162031
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355CBA0000 | FEM8T6 End Sections Grey 1SNA215266R0100 | 90 | 90 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355CEA0000 | FEMR8 End Sections Grey 1SNA116987R0200 | 120 | 120 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355CFA0000 | FEM6 End Sections Grey - 1SNA118368R1600 | 60 | 60 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355CMC0000 | Terminal End Plate 1848360000-Wiedmuller | 24 | 24 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355CPC0000 | Terminal End Plate 1816110000-Wiedmuller | 24 | 24 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355CTC0000 | Terminal End Plate 1816070000-Wiedmuller | 14 | 14 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 300 | 300 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355DFA0000 | RC610-VerticalMarking 1SNA233060R0400 | 54 | 54 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 180 | 90 | 90 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 90 | 30 | 60 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8129082
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 60 | 60 | 0 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-20 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Project Transfer | 8212279
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355DXC0000 | 460660001 DEK 5 FSZ 1-10 Z-Terminal 1-10 | 2500 | 2500 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355EEA0000 | JUMPER BAR "BJS8" 20 Poles | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355EFA0000 | PC61-CombTypeJumprBar10 1SNA163311R2200 | 24 | 24 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 48 | 40 | 8 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 8 | 8 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355HAB0000 | Zack Strip-Vertical(1-10) - 1053027:0001 | 72 | 72 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355HAB0001 | Zack Strip-Vertical(11-20)- 1053027:0011 | 72 | 72 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355HAB0002 | Zack Strip-Vertical Labeled(21-30) | 48 | 40 | 8 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355HAB0002 | Zack Strip-Vertical Labeled(21-30) | 8 | 8 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SNA206394R0200 | Screw, EV6I_Screw+PstWasherIP20_M6/8.RS_M4/6.RS Type: EV6I Order no: 1SNA 206 394 R0200 Color: Grey ¦ 1SNA206394R0200 ¦ ABB | 48 | 8 | 40 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV | Automated: Replaced 1YAB5355HEA0000 by 1SNA206394R0200. | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069095
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SNA206394R0200 | Screw, EV6I_Screw+PstWasherIP20_M6/8.RS_M4/6.RS Type: EV6I Order no: 1SNA 206 394 R0200 Color: Grey ¦ 1SNA206394R0200 ¦ ABB | 40 | 8 | 32 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV | Automated: Replaced 1YAB5355HEA0000 by 1SNA206394R0200. | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070477
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SNA206394R0200 | Screw, EV6I_Screw+PstWasherIP20_M6/8.RS_M4/6.RS Type: EV6I Order no: 1SNA 206 394 R0200 Color: Grey ¦ 1SNA206394R0200 ¦ ABB | 32 | 8 | 24 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV | Automated: Replaced 1YAB5355HEA0000 by 1SNA206394R0200. | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071505
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1SNA206394R0200 | Screw, EV6I_Screw+PstWasherIP20_M6/8.RS_M4/6.RS Type: EV6I Order no: 1SNA 206 394 R0200 Color: Grey ¦ 1SNA206394R0200 ¦ ABB | 24 | 24 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV | Automated: Replaced 1YAB5355HEA0000 by 1SNA206394R0200. | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355HXB0000 | BENT LUGS TYPE RF-PPL30 | 4200 | 4200 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355HXB0001 | BENT LUGS TYPE BF-PPL46 | 900 | 900 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355HXB0002 | BENT LUGS TYPE BF-PPL30 | 1800 | 1800 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 36 | 36 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355JPC0000 | 6Pole Plug 2.5mm-1815240000-Cont-loop | 24 | 24 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355JTC0000 | 10Pole Plug 2.5mm-1815280000-Cont-loop | 28 | 28 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 72 | 72 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355KPC0000 | Locking ele. 1816130000 for ZT2.5/4AN/2 | 38 | 38 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355LMC0000 | Coding element 1856860000 - ZT4/4AN/2 | 48 | 48 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355LPC0000 | Coding element 1816150000 | 52 | 52 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355MPC0000 | Strain Relief Wied mulpart # 1816140000 | 38 | 38 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 72 | 72 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB539500002019 | SERV IS LABEL in Stainless Steel Plates | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB60050819P0103 | Braided HARNESS TUBE (D40) | 90 | 90 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB60050819P0106 | Braided HARNESS TUBE (D30) | 120 | 120 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB60050819P0107 | Braided HARNESS TUBE (D20) | 60 | 60 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAZ21500101 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 12 | 12 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAZ21500101 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 17 | 12 | 5 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAZ21500101 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 5 | 5 | 0 | 6100KDP01 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 25541 | USE **** GCE0369214P0100 **** | 182 | 182 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 25541 | USE **** GCE0369214P0100 **** | 261 | 214 | 47 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 25541 | USE **** GCE0369214P0100 **** | 47 | 47 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28100 | SCREW VITE ACTC D7971 T21572/4.2x6.5 | 22 | 22 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28100 | SCREW VITE ACTC D7971 T21572/4.2x6.5 | 28 | 24 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28100 | SCREW VITE ACTC D7971 T21572/4.2x6.5 | 4 | 4 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28132 | RETAINING RING ACC. T22414/3.2 | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28132 | RETAINING RING ACC. T22414/3.2 | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28132 | RETAINING RING ACC. T22414/3.2 | 1 | 1 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 57 | 57 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 66 | 57 | 9 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 9 | 9 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100055
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28373 | LOCK NUT ACC TO T21192/M2.5x0.45 | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28373 | LOCK NUT ACC TO T21192/M2.5x0.45 | 14 | 12 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28373 | LOCK NUT ACC TO T21192/M2.5x0.45 | 2 | 2 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28452 | FLEXIBLE SPIROID PINS T22513/3X26 | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28627 | Rivet NUT ACC T21098/M6 (countersunk) | 71 | 71 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28627 | Rivet NUT ACC T21098/M6 (countersunk) | 91 | 78 | 13 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 28627 | Rivet NUT ACC T21098/M6 (countersunk) | 13 | 13 | 0 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144842
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 29823 | TOMMY HEAD SCREW ACC. T21010/M2.5x20 | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 29823 | TOMMY HEAD SCREW ACC. T21010/M2.5x20 | 14 | 12 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 29823 | TOMMY HEAD SCREW ACC. T21010/M2.5x20 | 2 | 2 | 0 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144872
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 2CSM258163R0721 | M1363-L | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014480P0004 | RETAINING_WASHER_DIN6799_6-SPST/A3K | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014480P0004 | RETAINING_WASHER_DIN6799_6-SPST/A3K | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014480P0004 | RETAINING_WASHER_DIN6799_6-SPST/A3K | 1 | 1 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 10 | 10 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 12 | 8 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 4 | 2 | 2 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 2 | 2 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083033
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014538P0012 | SPIRAL_PIN_ISO8748_4X20-ST/BK | 10 | 10 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014538P0012 | SPIRAL_PIN_ISO8748_4X20-ST/BK | 12 | 10 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014538P0012 | SPIRAL_PIN_ISO8748_4X20-ST/BK | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014538P0014 | SPIRAL_PIN_ISO8748_4X30-ST/BK | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014538P0014 | SPIRAL_PIN_ISO8748_4X30-ST/BK | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014538P0014 | SPIRAL_PIN_ISO8748_4X30-ST/BK | 1 | 1 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014618P0001 | SAFETY_GRIPPER_BFK/A_BN13193_4-SPST/PH | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014618P0001 | SAFETY_GRIPPER_BFK/A_BN13193_4-SPST/PH | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014618P0001 | SAFETY_GRIPPER_BFK/A_BN13193_4-SPST/PH | 1 | 1 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014618P0003 | SAFETY_GRIPPER_BFK/A_BN13193_6-SPST/PH | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014618P0003 | SAFETY_GRIPPER_BFK/A_BN13193_6-SPST/PH | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 3WKA014618P0003 | SAFETY_GRIPPER_BFK/A_BN13193_6-SPST/PH | 1 | 1 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 4CE7000583P0101 | PIN | 5 | 5 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 4CE7000583P0101 | PIN | 6 | 3 | 3 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 4CE7000583P0101 | PIN | 3 | 2 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 4CE7000583P0101 | PIN | 1 | 1 | 0 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8132309
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 500214111 | WASHER T22001/6.8X18 | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 500214111 | WASHER T22001/6.8X18 | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 500214111 | WASHER T22001/6.8X18 | 1 | 1 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 500673075 | PIN T22681/8X54,5-5 | 20 | 20 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 500673075 | PIN T22681/8X54,5-5 | 28 | 24 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 500673075 | PIN T22681/8X54,5-5 | 4 | 4 | 0 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8146135
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 5022 643 | COVER PROFILE, AP3 | 9.6 | 9.6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 150 | 150 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 5217 708-3 | M.CONTACT/HAN-E16M/09330162601 | 2 | 1 | 1 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107650
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 5217 708-3 | M.CONTACT/HAN-E16M/09330162601 | 1 | 1 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 5217 708-7 | F.CONTACT/HAN-E16F/09330162701 | 2 | 1 | 1 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107653
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 5217 708-7 | F.CONTACT/HAN-E16F/09330162701 | 1 | 1 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 564093/001 | BLOCK FOUNDATION - ZINK COATED | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 565937/001 | LEAF SPRING 499355009 | 6 | 6 | 0 | 6100K019 | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 565937/001 | LEAF SPRING 499355009 | 6 | 6 | 0 | 6100K019 | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 593502001 | BUSHING | 7 | 7 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 593502001 | BUSHING | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 593502001 | BUSHING | 1 | 1 | 0 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8117189
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 593503001 | ROLLER | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 593503001 | ROLLER | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 593503001 | ROLLER | 1 | 1 | 0 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144713
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 593509/001 | COMPRESSION SPRING | 10 | 10 | 0 | 6100K019 | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 593509/001 | COMPRESSION SPRING | 13 | 7 | 6 | 6100K019 | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 593509/001 | COMPRESSION SPRING | 6 | 4 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 593509/001 | COMPRESSION SPRING | 2 | 2 | 0 | 6100K019 | R15-T-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8132318
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 9ABA450060P0004 | NUT_ISO7040_M6-8/A3K | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 9ABA450060P0004 | NUT_ISO7040_M6-8/A3K | 6 | 4 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 9ABA450060P0004 | NUT_ISO7040_M6-8/A3K | 2 | 1 | 1 | 6100K019 | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 9ABA450060P0004 | NUT_ISO7040_M6-8/A3K | 1 | 1 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 9ABA450060P0005 | NUT_ISO7040_M8-8/A3K | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 9ABA450060P0005 | NUT_ISO7040_M8-8/A3K | 14 | 12 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 9ABA450060P0005 | NUT_ISO7040_M8-8/A3K | 2 | 2 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100073
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 9ADJ100023P0357 | BLIND_RIVET_ISO15979_6,4x16-ST/ST | 24 | 24 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 9ADJ100023P0357 | BLIND_RIVET_ISO15979_6,4x16-ST/ST | 28 | 24 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 9ADJ100023P0357 | BLIND_RIVET_ISO15979_6,4x16-ST/ST | 4 | 4 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 11342 2100-1 | GLASS,220X350X8.8, GCE8000436P0101 | 8 | 2 | 6 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8077521
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 11342 2100-1 | GLASS,220X350X8.8, GCE8000436P0101 | 6 | 2 | 4 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8077533
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 11342 2100-1 | GLASS,220X350X8.8, GCE8000436P0101 | 4 | 2 | 2 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128700
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 11342 2100-1 | GLASS,220X350X8.8, GCE8000436P0101 | 2 | 2 | 0 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128769
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 11342 2100-1 | GLASS,220X350X8.8, GCE8000436P0101 | 12 | 2 | 10 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150191
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 11342 2100-1 | GLASS,220X350X8.8, GCE8000436P0101 | 10 | 2 | 8 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150245
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 11342 2100-1 | GLASS,220X350X8.8, GCE8000436P0101 | 8 | 8 | 0 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2093 7000-4 | RAYCHEM SHRINKABLE TUBE, BPTM 75/30-A/U | 0.6 | 0.6 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2093 7000-4 | RAYCHEM SHRINKABLE TUBE, BPTM 75/30-A/U | 0.6 | 0.6 | 0 | free_stock | R15-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2093 7000-5 | RAYCHEM SHRINKABLE TUBE, BPTM 100/40-A/U | 11.7 | 11.7 | 0 | free_stock | R15-J-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2093 7000-5 | RAYCHEM SHRINKABLE TUBE, BPTM 100/40-A/U | 23.44 | 23.44 | 0 | free_stock | R15-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2093 7000-6N | RAYCHEM SHRINKABLE TUBE, BPTM 120/50-A/U | 16.67 | 9.9 | 6.77 | 6100K019 | R15-J-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100076
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2093 7000-6N | RAYCHEM SHRINKABLE TUBE, BPTM 120/50-A/U | 6.77 | 6.77 | 0 | free_stock | R15-J-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 100 | 15 | 85 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069188
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 85 | 15 | 70 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070606
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 70 | 15 | 55 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071595
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 55 | 55 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 90 | 15 | 75 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069119
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 75 | 15 | 60 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070570
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 60 | 15 | 45 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071538
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 45 | 45 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 5 | 1 | 4 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071033
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 4 | 1 | 3 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082447
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 3 | 1 | 2 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082444
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 2 | 1 | 1 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107641
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 1 | 1 | 0 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107698
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 6 | 1 | 5 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8117444
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 5 | 1 | 4 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8140329
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 4 | 1 | 3 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8140353
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 3 | 3 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 5 | 1 | 4 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071015
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 4 | 1 | 3 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071036
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 3 | 1 | 2 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082450
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 2 | 1 | 1 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082453
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 1 | 1 | 0 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107644
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 6 | 1 | 5 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107701
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 5 | 1 | 4 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8117438
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 4 | 1 | 3 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128772
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 3 | 1 | 2 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8140332
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 2 | 1 | 1 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8140356
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 12 | 3 | 9 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8087179
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 9 | 2 | 7 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070976
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 7 | 2 | 5 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071018
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 5 | 2 | 3 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082456
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 3 | 2 | 1 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082459
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 1 | 1 | 0 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8087176
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 15 | 1 | 14 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8087176
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 14 | 2 | 12 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107617
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 12 | 2 | 10 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107704
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 10 | 2 | 8 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128685
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 8 | 2 | 6 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8140350
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 6 | 2 | 4 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8140359
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 4 | 4 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-02 | YELLOW TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 90 | 15 | 75 | 6100K019 | R59-B-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069167
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-02 | YELLOW TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 75 | 15 | 60 | 6100K019 | R59-B-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070609
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-02 | YELLOW TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 60 | 15 | 45 | 6100K019 | R59-B-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071598
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-02 | YELLOW TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 45 | 45 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-03 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 60 | 10 | 50 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070612
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-03 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 50 | 10 | 40 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8129070
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-03 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 40 | 10 | 30 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-16 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8139452
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-03 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 30 | 30 | 0 | free_stock | R58-G-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-04 | BLACK TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 60 | 10 | 50 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069191
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-04 | BLACK TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 50 | 10 | 40 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070615
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-04 | BLACK TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 40 | 10 | 30 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071601
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-04 | BLACK TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 30 | 30 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-05 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 60 | 10 | 50 | 6100K019 | R59-B-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8129073
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-05 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 50 | 10 | 40 | 6100K019 | R59-B-1-KDP1_SEP | consumption | 2025-10-16 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8139455
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-05 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 40 | 40 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-13 | BLACK TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 60 | 10 | 50 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069206
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-13 | BLACK TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 50 | 10 | 40 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070618
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-13 | BLACK TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 40 | 10 | 30 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071604
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-1865-13 | BLACK TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 30 | 30 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAZ21500101 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 15 | 15 | 0 | 6100KDP01 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D | Automated: Replaced AE2000-2150-01 by 1YAZ21500101. | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAZ21500101 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 19 | 19 | 0 | 6100KDP01 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical | Automated: Replaced AE2000-2150-01 by 1YAZ21500101. | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 7.8 | 1.3 | 6.5 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069212
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 6.5 | 1.3 | 5.2 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070621
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 5.2 | 1.3 | 3.9 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071607
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 3.9 | 3.9 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 120 | 20 | 100 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8129067
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 100 | 20 | 80 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8139449
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 80 | 80 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 36 | 6 | 30 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070573
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 30 | 6 | 24 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071541
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 24 | 24 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 4.53 | 1.15 | 3.38 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083042
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 3.38 | 1.15 | 2.23 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083039
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 2.23 | 1.15 | 1.08 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108599
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 1.08 | 1.08 | 0 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108608
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 6.47 | 0.36 | 6.11 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099584
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 6.11 | 0.36 | 5.75 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099722
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 5.75 | 0.07 | 5.68 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108608
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 5.68 | 0.36 | 5.32 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120197
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 5.32 | 0.36 | 4.96 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120278
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 4.96 | 4.96 | 0 | free_stock | R66-H-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2522-2000-01 | HOOD HAN-E16,09300161520 | 2 | 1 | 1 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107647
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2522-2000-01 | HOOD HAN-E16,09300161520 | 1 | 1 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301,HAN-E16 | 2 | 1 | 1 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107656
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301,HAN-E16 | 1 | 1 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2522-2000-03 | CABLE SEALING,PG21, | 2 | 2 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 6 | 1 | 5 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069134
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 5 | 1 | 4 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070576
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 4 | 1 | 3 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071544
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 3 | 3 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2632-2000-33 | Spring for Door Combiflex | 0.02 | 0.02 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 6 | 1 | 5 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069137
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 5 | 1 | 4 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070579
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 4 | 1 | 3 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071547
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 3 | 3 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 360 | 60 | 300 | 6100K019 | R15-T-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069140
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 300 | 60 | 240 | 6100K019 | R15-T-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070582
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 240 | 60 | 180 | 6100K019 | R15-T-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071550
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 180 | 60 | 120 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-21 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8230412
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 120 | 120 | 0 | free_stock | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 6 | 1 | 5 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069143
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 5 | 1 | 4 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070585
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 4 | 1 | 3 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071553
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 3 | 3 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | BM0145-1373-ASYP | Step Ladder SEC-Version 650mm (Width) | 1 | 1 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | CDX7005632R1A | EARTHING CONTACT COMPLETE | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | CDX7005632R1A | EARTHING CONTACT COMPLETE | 12 | 10 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | CDX7005632R1A | EARTHING CONTACT COMPLETE | 2 | 2 | 0 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144754
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | CDXN010061R1103 | HANDLE COMPLETE | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | CDXN010061R1103 | HANDLE COMPLETE | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | CDXN010061R1103 | HANDLE COMPLETE | 1 | 1 | 0 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144796
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 1740 | 37 | 1703 | 6100K019 | NEW.FLR-1-1-K019_SEP | consumption | 2025-10-25 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Project Transfer | 8292517
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 1703 | 451.2 | 1251.8 | 6100K013 | R19-S-1-K013_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 1251.8 | 200.9 | 1050.9 | 6100K013 | BOX5-1-1-K013_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 1050.9 | 146.36 | 904.54 | 6100K013 | PLT1-1-1-K013_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 904.54 | 40 | 864.54 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 864.54 | 96 | 768.54 | 6100K013 | 1-1-1-1 | consumption | 2025-09-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Material Issue | 7323474
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 768.54 | 96 | 672.54 | 6100K013 | 1-1-1-1 | consumption | 2025-09-18 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Material Issue | 7402121
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 672.54 | 10 | 662.54 | 6100K007 | NEW.FLR-1-1-K019_SEP | consumption | 2025-10-25 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8300044
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 662.54 | 10 | 652.54 | 6100K011B | NEW.FLR-1-1-K019_SEP | consumption | 2025-10-25 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8302198
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 652.54 | 6 | 646.54 | 6100K012B | NEW.FLR-1-1-K019_SEP | consumption | 2025-10-25 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8295768
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 646.54 | 6 | 640.54 | 6100K012B | NEW.FLR-1-1-K019_SEP | consumption | 2025-10-25 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8299941
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 640.54 | 5 | 635.54 | 6100K012B | NEW.FLR-1-1-K019_SEP | consumption | 2025-10-25 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8293566
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 635.54 | 3 | 632.54 | 6100K008 | NEW.FLR-1-1-MVBM_SEP | consumption | 2025-10-25 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8293428
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DF241126022 | White TUBE, INNER DIA. 4.0MM (1.5 &2.5 WIRE) | 632.54 | 632.54 | 0 | 6100KDP02 | PO-SEP-6055-[130] | GR_in_process | 2025-11-10 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02 // 2L2T SRMU LV Compartment Purchase Parts from DFE for 30 Units | 76800 | 20-08-2025 | 20-08-2025 |  |  | PO-6055/DF250813-30-SEP Xiamen
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DM0000000308 | TEST SWITCH: FT-1 (FOR VT ISOL. ) 8P. Type 129A501G01 | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DM0000000669 | TRIP CIRCUIT SUPERVISION RELAY Type: VDF-10 Voltage supervised circuit : 125Vdc Aux. contact : 2 Changeover Aux. voltage : 125Vdc | 8 | 8 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 37.5 | 6.7 | 30.8 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071030
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 30.8 | 6.7 | 24.1 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071039
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 24.1 | 6.7 | 17.4 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082462
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 17.4 | 6 | 11.4 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082465
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 11.4 | 6.7 | 4.7 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107671
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 4.7 | 4.7 | 0 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107665
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 46.9 | 2 | 44.9 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107665
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 44.9 | 6.7 | 38.2 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8117441
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 38.2 | 6.7 | 31.5 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128787
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 31.5 | 6.7 | 24.8 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144148
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 24.8 | 24.8 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 12 | 2 | 10 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073139
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 10 | 2 | 8 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073184
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 8 | 2 | 6 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083048
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 6 | 2 | 4 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083045
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 4 | 2 | 2 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108497
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 2 | 2 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108704
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 14 | 2 | 12 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120321
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 12 | 2 | 10 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120329
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 10 | 10 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 5 | 1 | 4 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073127
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 4 | 1 | 3 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073187
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 3 | 1 | 2 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083054
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 2 | 1 | 1 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083051
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 1 | 1 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108506
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 6 | 1 | 5 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108707
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 5 | 1 | 4 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120215
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 4 | 1 | 3 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120236
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 3 | 3 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-493 | BOLT HEX HEAD M10X30 | 60 | 20 | 40 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073190
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-493 | BOLT HEX HEAD M10X30 | 40 | 20 | 20 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083057
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-493 | BOLT HEX HEAD M10X30 | 20 | 20 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108710
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-493 | BOLT HEX HEAD M10X30 | 140 | 140 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-494 | BOLT HEX HEAD M10X35 | 6 | 6 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120239
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-494 | BOLT HEX HEAD M10X35 | 6 | 6 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120269
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-496 | BOLT HEX HEAD M10X45 | 9 | 3 | 6 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073145
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-496 | BOLT HEX HEAD M10X45 | 6 | 3 | 3 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073193
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-496 | BOLT HEX HEAD M10X45 | 3 | 3 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083060
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-496 | BOLT HEX HEAD M10X45 | 12 | 3 | 9 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083063
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-496 | BOLT HEX HEAD M10X45 | 9 | 3 | 6 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108533
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-496 | BOLT HEX HEAD M10X45 | 6 | 3 | 3 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108713
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-496 | BOLT HEX HEAD M10X45 | 3 | 3 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 12 | 3 | 9 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073133
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 9 | 3 | 6 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073196
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 6 | 3 | 3 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083066
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 3 | 3 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083069
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 15 | 3 | 12 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108593
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 12 | 3 | 9 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108716
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 9 | 9 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-659 | BOLT HEX HEAD M20X45 | 6 | 6 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120242
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-659 | BOLT HEX HEAD M20X45 | 18 | 6 | 12 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120272
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-659 | BOLT HEX HEAD M20X45 | 12 | 12 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-660 | BOLT HEX HEAD M20X50 | 9 | 3 | 6 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120626
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-660 | BOLT HEX HEAD M20X50 | 6 | 3 | 3 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128679
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-660 | BOLT HEX HEAD M20X50 | 3 | 3 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-660 | BOLT HEX HEAD M20X50 | 9 | 9 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-666 | BOLT HEX HEAD M20X90 | 6 | 6 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2452-293 | SCREW CROSS REC.HEAD M4X16 | 8 | 8 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 327 | 60 | 267 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070970
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 267 | 60 | 207 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071027
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 207 | 60 | 147 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082468
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 147 | 60 | 87 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8082471
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 87 | 60 | 27 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107659
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 27 | 27 | 0 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107707
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 371 | 33 | 338 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107707
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 338 | 35 | 303 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120191
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 303 | 35 | 268 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120245
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 268 | 57 | 211 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144763
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 211 | 24 | 187 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144769
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 187 | 187 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 212 | 22 | 190 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073151
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 190 | 22 | 168 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073199
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 168 | 22 | 146 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083075
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 146 | 22 | 124 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083072
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 124 | 57 | 67 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099605
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 67 | 57 | 10 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099713
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 10 | 10 | 0 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108548
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 276 | 28 | 248 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108548
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 248 | 22 | 226 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108719
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 226 | 57 | 169 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120623
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 169 | 57 | 112 | 6100K019 | R66-P-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120629
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 112 | 112 | 0 | 6100K012B | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 24 | 4 | 20 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076543
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 20 | 4 | 16 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076591
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 16 | 8 | 8 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108596
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 8 | 4 | 4 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100064
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 4 | 4 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100061
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 36 | 4 | 32 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108722
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 32 | 4 | 28 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127238
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 28 | 4 | 24 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127280
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 24 | 4 | 20 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150143
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 20 | 4 | 16 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150248
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 16 | 16 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-291 | BOLT SOCKET CAP HEAD M4X12 | 12 | 6 | 6 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100067
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-291 | BOLT SOCKET CAP HEAD M4X12 | 6 | 6 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127283
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-293 | BOLT SOCKET HEAD M4X16 | 4 | 4 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-295 | BOLT SOCKET HEAD M4X20 | 4 | 2 | 2 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100070
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-295 | BOLT SOCKET HEAD M4X20 | 2 | 2 | 0 | free_stock | R58-A-1-K12B_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-299 | BOLT SOCKET CAP HEAD M4X30 | 8 | 4 | 4 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100182
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-299 | BOLT SOCKET CAP HEAD M4X30 | 4 | 4 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127286
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-325 | BOLT SOCKET CAP M5X10 | 4 | 4 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108566
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-325 | BOLT SOCKET CAP M5X10 | 8 | 2 | 6 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100185
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-325 | BOLT SOCKET CAP M5X10 | 6 | 2 | 4 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127289
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-325 | BOLT SOCKET CAP M5X10 | 4 | 4 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 12 | 2 | 10 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076537
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 10 | 2 | 8 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076594
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 8 | 3 | 5 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100188
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 5 | 2 | 3 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108491
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 3 | 2 | 1 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108725
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 1 | 1 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127292
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 16 | 4 | 12 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127292
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 12 | 2 | 10 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127244
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 10 | 2 | 8 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150176
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 8 | 2 | 6 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150251
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 6 | 6 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-333 | BOLT SOCKET CAP HEAD M5X25 | 1 | 1 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100191
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-333 | BOLT SOCKET CAP HEAD M5X25 | 4 | 1 | 3 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100191
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-333 | BOLT SOCKET CAP HEAD M5X25 | 3 | 2 | 1 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127295
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-333 | BOLT SOCKET CAP HEAD M5X25 | 1 | 1 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-366 | BOLT SOCKET CAP HEAD M6X12 | 15 | 3 | 12 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076558
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-366 | BOLT SOCKET CAP HEAD M6X12 | 12 | 3 | 9 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076597
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-366 | BOLT SOCKET CAP HEAD M6X12 | 9 | 5 | 4 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100194
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-366 | BOLT SOCKET CAP HEAD M6X12 | 4 | 3 | 1 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108476
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-366 | BOLT SOCKET CAP HEAD M6X12 | 1 | 1 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108728
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-366 | BOLT SOCKET CAP HEAD M6X12 | 19 | 2 | 17 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108728
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-366 | BOLT SOCKET CAP HEAD M6X12 | 17 | 3 | 14 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150170
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-366 | BOLT SOCKET CAP HEAD M6X12 | 14 | 3 | 11 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150254
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-366 | BOLT SOCKET CAP HEAD M6X12 | 11 | 11 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 25 | 2 | 23 | 6100K019 | R58-H-1-K11B_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073160
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 23 | 2 | 21 | 6100K019 | R58-H-1-K11B_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073154
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 21 | 2 | 19 | 6100K019 | R58-H-1-K11B_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083078
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 19 | 2 | 17 | 6100K019 | R58-H-1-K11B_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083081
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 17 | 8 | 9 | 6100K019 | R58-H-1-K11B_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099623
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 9 | 2 | 7 | 6100K019 | R58-H-1-K11B_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108551
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 7 | 2 | 5 | 6100K019 | R58-H-1-K11B_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108731
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 5 | 5 | 0 | 6100K019 | R58-H-1-K11B_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120605
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 26 | 8 | 18 | 6100K019 | R58-H-1-K11B_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120632
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 18 | 3 | 15 | 6100K019 | R58-H-1-K11B_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120605
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 15 | 15 | 0 | 6100K006 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-371 | BOLT SOCKET CAP M6X20 | 4 | 2 | 2 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100197
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-371 | BOLT SOCKET CAP M6X20 | 2 | 2 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127253
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-371 | BOLT SOCKET CAP M6X20 | 6 | 2 | 4 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127301
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-371 | BOLT SOCKET CAP M6X20 | 4 | 4 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-372 | BOLT SOCKET CAP M6X25 | 2 | 2 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-379 | BOLT SOCKET CAP HEAD M6X45 | 4 | 2 | 2 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100200
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-379 | BOLT SOCKET CAP HEAD M6X45 | 2 | 2 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127304
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 24 | 4 | 20 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076555
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 20 | 4 | 16 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076600
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 16 | 4 | 12 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100203
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 12 | 4 | 8 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100224
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 8 | 4 | 4 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108464
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 4 | 4 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108734
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 28 | 4 | 24 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127250
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 24 | 4 | 20 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127307
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 20 | 4 | 16 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150167
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 16 | 4 | 12 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150257
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 12 | 12 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 433 | 72 | 361 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073124
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 361 | 72 | 289 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073163
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 289 | 72 | 217 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083084
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 217 | 72 | 145 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083087
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 145 | 72 | 73 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108578
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 73 | 72 | 1 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108737
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 1 | 1 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099599
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 500 | 62 | 438 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099629
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 438 | 61 | 377 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099599
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 377 | 62 | 315 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120620
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 315 | 62 | 253 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120635
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 253 | 253 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 169 | 45 | 124 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073166
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 124 | 45 | 79 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083090
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 79 | 45 | 34 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8083093
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 34 | 34 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108524
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 238 | 45 | 193 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108740
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 193 | 11 | 182 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108524
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 182 | 13 | 169 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120611
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 169 | 13 | 156 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120638
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 156 | 156 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 72 | 17 | 55 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073169
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 55 | 17 | 38 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073202
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 38 | 17 | 21 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084099
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 21 | 17 | 4 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084096
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 4 | 4 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108557
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 143 | 17 | 126 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108611
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 126 | 13 | 113 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108557
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 113 | 7 | 106 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120614
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 106 | 7 | 99 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120641
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 99 | 99 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-457 | BOLT SOCKET CAP M8X35 | 4 | 4 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 10 | 2 | 8 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070985
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 8 | 2 | 6 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071012
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 6 | 2 | 4 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084102
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 4 | 2 | 2 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084105
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 2 | 2 | 0 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107620
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 12 | 2 | 10 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107674
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 10 | 2 | 8 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120266
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 8 | 2 | 6 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120293
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 6 | 6 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 18 | 3 | 15 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073172
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 15 | 3 | 12 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084108
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 12 | 3 | 9 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084111
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 9 | 3 | 6 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099635
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 6 | 3 | 3 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099704
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 3 | 3 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108518
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 21 | 3 | 18 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108614
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 18 | 3 | 15 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120608
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 15 | 3 | 12 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120644
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 12 | 12 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 42 | 6 | 36 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073148
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 36 | 6 | 30 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073175
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 30 | 6 | 24 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084114
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 24 | 6 | 18 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084117
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 18 | 6 | 12 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099638
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 12 | 6 | 6 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099707
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 6 | 6 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108521
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 48 | 6 | 42 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108617
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 42 | 6 | 36 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120617
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 36 | 6 | 30 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120647
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 30 | 30 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 192 | 35 | 157 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073142
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 157 | 35 | 122 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073157
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 122 | 35 | 87 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084120
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 87 | 35 | 52 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084123
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 52 | 47 | 5 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108527
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 5 | 5 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108620
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 311 | 30 | 281 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108620
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 281 | 29 | 252 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099641
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 252 | 29 | 223 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099701
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 223 | 29 | 194 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8119997
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 194 | 29 | 165 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120003
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 165 | 165 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 28 | 4 | 24 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073130
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 24 | 4 | 20 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073178
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 20 | 4 | 16 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084126
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 16 | 4 | 12 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084129
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 12 | 4 | 8 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099611
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 8 | 4 | 4 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099644
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 4 | 4 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108584
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 60 | 4 | 56 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108623
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 56 | 4 | 52 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8119985
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 52 | 4 | 48 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120006
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 48 | 48 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 82 | 29 | 53 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073136
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 53 | 29 | 24 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084135
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 24 | 17 | 7 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8073181
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 7 | 7 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084132
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 157 | 10 | 147 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084132
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 147 | 29 | 118 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108458
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 118 | 17 | 101 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108626
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 101 | 5 | 96 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099647
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 96 | 3 | 93 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099665
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 93 | 21 | 72 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8119991
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 72 | 21 | 51 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120012
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 51 | 51 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-499 | BOLT SOCKET CAP HEAD M10X40 | 27 | 3 | 24 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120000
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-499 | BOLT SOCKET CAP HEAD M10X40 | 24 | 3 | 21 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120015
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-499 | BOLT SOCKET CAP HEAD M10X40 | 21 | 21 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-499 | BOLT SOCKET CAP HEAD M10X40 | 111 | 51 | 60 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-499 | BOLT SOCKET CAP HEAD M10X40 | 60 | 38 | 22 | 606PD013 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-499 | BOLT SOCKET CAP HEAD M10X40 | 22 | 6 | 16 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-500 | BOLT SOCKET CAP HEAD M10X45 | 66 | 12 | 54 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074234
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-500 | BOLT SOCKET CAP HEAD M10X45 | 54 | 12 | 42 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108629
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-500 | BOLT SOCKET CAP HEAD M10X45 | 42 | 12 | 30 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150260
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-500 | BOLT SOCKET CAP HEAD M10X45 | 30 | 30 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-505 | CHEESE HEAD BOLT M10X70 | 36 | 12 | 24 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070988
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-505 | CHEESE HEAD BOLT M10X70 | 24 | 12 | 12 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-14 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107716
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-505 | CHEESE HEAD BOLT M10X70 | 12 | 12 | 0 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-16 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150347
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-508 | BOLT SOCKET CAP HEAD M10X100 | 27 | 9 | 18 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074231
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-508 | BOLT SOCKET CAP HEAD M10X100 | 18 | 9 | 9 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074237
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-508 | BOLT SOCKET CAP HEAD M10X100 | 9 | 9 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108512
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-508 | BOLT SOCKET CAP HEAD M10X100 | 45 | 9 | 36 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108632
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-508 | BOLT SOCKET CAP HEAD M10X100 | 36 | 9 | 27 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150200
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-508 | BOLT SOCKET CAP HEAD M10X100 | 27 | 9 | 18 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150263
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-508 | BOLT SOCKET CAP HEAD M10X100 | 18 | 18 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-531 | BOLT SOCKET CAP M12X16 (C.H.) | 4 | 1 | 3 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8140317
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-531 | BOLT SOCKET CAP M12X16 (C.H.) | 3 | 1 | 2 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8140344
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-531 | BOLT SOCKET CAP M12X16 (C.H.) | 2 | 2 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-531 | BOLT SOCKET CAP M12X16 (C.H.) | 5 | 5 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 13 | 5 | 8 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099617
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 8 | 5 | 3 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099650
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 3 | 1 | 2 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108452
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 2 | 1 | 1 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108635
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 1 | 1 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8119988
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 15 | 5 | 10 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120018
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 10 | 4 | 6 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8119988
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 6 | 1 | 5 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128816
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 5 | 5 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 3 | 3 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127313
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 5 | 3 | 2 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127319
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 2 | 2 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 114 | 27 | 87 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074598
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 87 | 33 | 54 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108638
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 54 | 27 | 27 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108461
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 27 | 1 | 26 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099626
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 26 | 1 | 25 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099686
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 25 | 13 | 12 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8119994
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 12 | 12 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120021
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 155 | 1 | 154 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120021
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 154 | 154 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-540 | BOLT SOCKET CAP HEAD M12X40 | 13 | 3 | 10 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8087182
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-540 | BOLT SOCKET CAP HEAD M12X40 | 10 | 10 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-540 | BOLT SOCKET CAP HEAD M12X40 | 22 | 13 | 9 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-540 | BOLT SOCKET CAP HEAD M12X40 | 9 | 3 | 6 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 36 | 12 | 24 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074646
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 24 | 6 | 18 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074631
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 18 | 12 | 6 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108641
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 6 | 6 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108470
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 48 | 6 | 42 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120009
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 42 | 6 | 36 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120024
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 36 | 12 | 24 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150269
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 24 | 6 | 18 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150224
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 18 | 18 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-542 | BOLT SOCKET CAP HEAD M12X50 | 18 | 18 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-544 | BOLT SOCKET CAP HEAD M12X60 | 12 | 3 | 9 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8087185
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-544 | BOLT SOCKET CAP HEAD M12X60 | 9 | 9 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 69 | 21 | 48 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074628
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 48 | 21 | 27 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074649
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 27 | 21 | 6 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108530
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 6 | 6 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108644
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 90 | 15 | 75 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108644
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 75 | 6 | 69 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120812
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 69 | 6 | 63 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120806
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 63 | 21 | 42 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150203
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 42 | 21 | 21 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150266
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 21 | 21 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-628 | BOLT SOCKET CAP HEAD M16X40 | 9 | 9 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-628 | BOLT SOCKET CAP HEAD M16X40 | 12 | 12 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-630 | **** USE DMS 2121 2519-430 **** | 9 | 9 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099572
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-630 | **** USE DMS 2121 2519-430 **** | 9 | 9 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099632
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 30 | 4 | 26 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8086159
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 26 | 2 | 24 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8086156
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 24 | 24 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 38 | 38 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2852-536 | COUNTERSUNK ALLEN HEAD M12X30 | 12 | 4 | 8 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074634
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2852-536 | COUNTERSUNK ALLEN HEAD M12X30 | 8 | 4 | 4 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108746
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2852-536 | COUNTERSUNK ALLEN HEAD M12X30 | 4 | 4 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150350
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 6 | 2 | 4 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8087188
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 4 | 1 | 3 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070973
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 3 | 1 | 2 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070979
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 2 | 1 | 1 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107629
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 1 | 1 | 0 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107677
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 9 | 1 | 8 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8117435
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 8 | 1 | 7 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128784
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 7 | 1 | 6 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150182
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 6 | 1 | 5 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150272
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 5 | 5 | 0 | free_stock | R58-A-1-K11B_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 14 | 2 | 12 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076546
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 12 | 2 | 10 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076579
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 10 | 9 | 1 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100209
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 1 | 1 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100176
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 24 | 2 | 22 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108563
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 22 | 2 | 20 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108647
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 20 | 1 | 19 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100176
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 19 | 5 | 14 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127322
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 14 | 2 | 12 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127310
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 12 | 2 | 10 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150161
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 10 | 2 | 8 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150275
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 8 | 8 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-114 | NUT, HEX M5 | 2 | 2 | 0 | 6100K019 | INC-1-1-K008_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8087191
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-114 | NUT, HEX M5 | 18 | 7 | 11 | 6100K019 | INC-1-1-K008_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8087191
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-114 | NUT, HEX M5 | 11 | 7 | 4 | 6100K019 | INC-1-1-K008_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128790
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-114 | NUT, HEX M5 | 4 | 4 | 0 | free_stock | R58-A-1-K11B_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 90 | 10 | 80 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076561
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 80 | 29 | 51 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100212
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 51 | 16 | 35 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100170
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 35 | 14 | 21 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107635
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 21 | 10 | 11 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107680
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 11 | 11 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127325
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 97 | 16 | 81 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127259
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 81 | 6 | 75 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127325
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 75 | 10 | 65 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150197
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 65 | 10 | 55 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150278
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 55 | 55 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 112 | 16 | 96 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074592
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 96 | 16 | 80 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074652
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 80 | 16 | 64 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108560
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 64 | 16 | 48 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108650
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 48 | 4 | 44 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099653
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 44 | 2 | 42 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099590
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 42 | 14 | 28 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120803
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 28 | 14 | 14 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120815
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 14 | 14 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150221
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 117 | 16 | 101 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150281
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 101 | 2 | 99 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150221
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 99 | 99 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 89 | 17 | 72 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074595
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 72 | 17 | 55 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074643
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 55 | 21 | 34 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108542
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 34 | 17 | 17 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108653
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 17 | 9 | 8 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099656
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 8 | 3 | 5 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099710
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 5 | 5 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120818
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 362 | 20 | 342 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120809
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 342 | 19 | 323 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120818
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 323 | 17 | 306 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150212
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 306 | 17 | 289 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150284
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 289 | 289 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 62 | 6 | 56 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076549
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 56 | 6 | 50 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076582
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 50 | 7 | 43 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100164
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 43 | 7 | 36 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100218
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 36 | 6 | 30 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107623
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 30 | 6 | 24 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107683
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 24 | 19 | 5 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127262
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 5 | 5 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127268
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 65 | 14 | 51 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127268
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 51 | 6 | 45 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150227
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 45 | 6 | 39 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150287
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 39 | 39 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-124 | NUT, HEX M16 | 9 | 9 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127271
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2011-124 | NUT, HEX M16 | 9 | 9 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127316
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2013-122 | NUT HEX H D GALV M12 | 24 | 24 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2013-122 | NUT HEX H D GALV M12 | 36 | 36 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2013-124 | NUT HEX H D GALV M16 | 54 | 18 | 36 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076552
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2013-124 | NUT HEX H D GALV M16 | 36 | 18 | 18 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076585
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2013-124 | NUT HEX H D GALV M16 | 18 | 18 | 0 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108545
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2013-124 | NUT HEX H D GALV M16 | 72 | 18 | 54 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108656
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2013-124 | NUT HEX H D GALV M16 | 54 | 18 | 36 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150215
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2013-124 | NUT HEX H D GALV M16 | 36 | 18 | 18 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150290
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 2013-124 | NUT HEX H D GALV M16 | 18 | 18 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2126 843-1 | RIVET NUT M6 (HEXAGONAL) | 2 | 2 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-136 | WASHER FLAT BRIR 4.3X8X0.8 | 39 | 39 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-136 | WASHER FLAT BRIR 4.3X8X0.8 | 42 | 42 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 192 | 29 | 163 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076540
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 163 | 29 | 134 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076567
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 134 | 33 | 101 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100179
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 101 | 33 | 68 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100206
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 68 | 29 | 39 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107662
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 39 | 29 | 10 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107686
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 10 | 10 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127241
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 216 | 38 | 178 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127274
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 178 | 28 | 150 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127241
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 150 | 29 | 121 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150152
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 121 | 29 | 92 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150293
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 92 | 92 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 22 | 4 | 18 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076534
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 18 | 4 | 14 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076570
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 14 | 4 | 10 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107626
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 10 | 4 | 6 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107689
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 6 | 2 | 4 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100215
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 4 | 2 | 2 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100227
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 2 | 2 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128691
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 26 | 4 | 22 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128715
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 22 | 2 | 20 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128691
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 20 | 4 | 16 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150233
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 16 | 4 | 12 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150296
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 12 | 12 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 48 | 8 | 40 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074604
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 40 | 8 | 32 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074607
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 32 | 8 | 24 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099659
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 24 | 8 | 16 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099671
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 16 | 8 | 8 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108503
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 8 | 8 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108659
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 56 | 8 | 48 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128718
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 48 | 8 | 40 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128703
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 40 | 8 | 32 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150194
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 32 | 8 | 24 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150299
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 24 | 24 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 529 | 100 | 429 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074586
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 429 | 100 | 329 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074610
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 329 | 118 | 211 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108587
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 211 | 100 | 111 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108662
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 111 | 46 | 65 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099608
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 65 | 65 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127247
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 1197 | 90 | 1107 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127277
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 1107 | 25 | 1082 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127247
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 1082 | 100 | 982 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150155
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 982 | 100 | 882 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150302
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 882 | 882 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 330 | 64 | 266 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074613
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 266 | 52 | 214 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074589
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 214 | 64 | 150 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108665
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 150 | 52 | 98 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108455
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 98 | 8 | 90 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099620
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 90 | 59 | 31 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128682
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 31 | 31 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128721
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 333 | 28 | 305 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128721
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 305 | 64 | 241 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150305
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 241 | 52 | 189 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150146
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 189 | 189 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 153 | 39 | 114 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074616
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 114 | 39 | 75 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074637
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 75 | 39 | 36 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108536
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 36 | 36 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108668
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 189 | 9 | 180 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099575
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 180 | 9 | 171 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099674
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 171 | 3 | 168 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108668
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 168 | 24 | 144 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128724
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 144 | 24 | 120 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128778
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 120 | 39 | 81 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150206
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 81 | 39 | 42 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150308
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 42 | 42 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 27 | 3 | 24 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074619
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 24 | 3 | 21 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074640
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 21 | 9 | 12 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099578
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 12 | 9 | 3 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099677
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 3 | 3 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108539
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 33 | 3 | 30 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108671
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 30 | 6 | 24 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128727
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 24 | 6 | 18 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128781
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 18 | 3 | 15 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150209
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 15 | 3 | 12 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150311
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 12 | 12 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 98 | 13 | 85 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074601
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 85 | 13 | 72 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074622
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 72 | 29 | 43 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099680
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 43 | 14 | 29 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099581
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 29 | 13 | 16 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108479
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 16 | 13 | 3 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108674
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 3 | 3 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128706
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 107 | 15 | 92 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128730
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 92 | 12 | 80 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128706
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 80 | 13 | 67 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150173
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 67 | 13 | 54 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150314
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 54 | 54 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 799 | 152 | 647 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074625
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 647 | 142 | 505 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8074583
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 505 | 152 | 353 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108677
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 353 | 146 | 207 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108575
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 207 | 84 | 123 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099683
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 123 | 81 | 42 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099596
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 42 | 42 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128709
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 957 | 100 | 857 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128733
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 857 | 58 | 799 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128709
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 799 | 799 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 363-1 | WASHER, LOCK 10X5X0.5 | 6 | 1 | 5 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069146
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 363-1 | WASHER, LOCK 10X5X0.5 | 5 | 1 | 4 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070588
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 363-1 | WASHER, LOCK 10X5X0.5 | 4 | 1 | 3 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071556
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2154 363-1 | WASHER, LOCK 10X5X0.5 | 3 | 3 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 2400 | 400 | 2000 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069149
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 2000 | 400 | 1600 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070483
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 1600 | 400 | 1200 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071559
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 1200 | 1200 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 30 | 5 | 25 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069194
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 25 | 5 | 20 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070591
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 20 | 5 | 15 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071610
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 15 | 15 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 6 | 1 | 5 | 6100K019 | R68-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069197
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 5 | 1 | 4 | 6100K019 | R68-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070594
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 4 | 1 | 3 | 6100K019 | R68-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071613
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 3 | 3 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 36 | 6 | 30 | 6100K019 | R68-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069200
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 30 | 6 | 24 | 6100K019 | R68-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070597
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 24 | 6 | 18 | 6100K019 | R68-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071616
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 18 | 18 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 010-91 | UN-INSUL SLeve Lugs KE1510ST (1.5mm) | 120 | 20 | 100 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069152
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 010-91 | UN-INSUL SLeve Lugs KE1510ST (1.5mm) | 100 | 20 | 80 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070486
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 010-91 | UN-INSUL SLeve Lugs KE1510ST (1.5mm) | 80 | 20 | 60 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071562
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 010-91 | UN-INSUL SLeve Lugs KE1510ST (1.5mm) | 60 | 60 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 010-92 | UN-INSUL SLEEVE Lugs for 2.5mm KE2510ST | 300 | 50 | 250 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069155
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 010-92 | UN-INSUL SLEEVE Lugs for 2.5mm KE2510ST | 250 | 50 | 200 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070489
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 010-92 | UN-INSUL SLEEVE Lugs for 2.5mm KE2510ST | 200 | 50 | 150 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071565
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 010-92 | UN-INSUL SLEEVE Lugs for 2.5mm KE2510ST | 150 | 150 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 010-93 | Un-Insul Sleeve Lugs 4.0 mm KE410ST | 300 | 50 | 250 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069122
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 010-93 | Un-Insul Sleeve Lugs 4.0 mm KE410ST | 250 | 50 | 200 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070492
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 010-93 | Un-Insul Sleeve Lugs 4.0 mm KE410ST | 200 | 50 | 150 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071568
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 010-93 | Un-Insul Sleeve Lugs 4.0 mm KE410ST | 150 | 150 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 011-2 | TERM.LUGS BLADE BF-PP12/25 2.5MM | 600 | 100 | 500 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069125
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 011-2 | TERM.LUGS BLADE BF-PP12/25 2.5MM | 500 | 100 | 400 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070495
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 011-2 | TERM.LUGS BLADE BF-PP12/25 2.5MM | 400 | 100 | 300 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071571
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 011-2 | TERM.LUGS BLADE BF-PP12/25 2.5MM | 300 | 300 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 011-51 | TERM.LUGS BLADE RF-PP 12/23 | 1800 | 300 | 1500 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069128
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 011-51 | TERM.LUGS BLADE RF-PP 12/23 | 1500 | 300 | 1200 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070498
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 011-51 | TERM.LUGS BLADE RF-PP 12/23 | 1200 | 300 | 900 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071574
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2634 011-51 | TERM.LUGS BLADE RF-PP 12/23 | 900 | 900 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 0087-19 | CABLE LUGS A14-M10 70MM/M10 | 10 | 2 | 8 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108473
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 0087-19 | CABLE LUGS A14-M10 70MM/M10 | 8 | 2 | 6 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108680
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 0087-19 | CABLE LUGS A14-M10 70MM/M10 | 6 | 2 | 4 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120913
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 0087-19 | CABLE LUGS A14-M10 70MM/M10 | 4 | 2 | 2 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128736
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 0087-19 | CABLE LUGS A14-M10 70MM/M10 | 2 | 2 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150230
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 0087-19 | CABLE LUGS A14-M10 70MM/M10 | 12 | 2 | 10 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150317
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 0087-19 | CABLE LUGS A14-M10 70MM/M10 | 10 | 10 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2026-4 | TERM.LUGS SPADE RF-U4 1.5/M4 | 750 | 125 | 625 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069131
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2026-4 | TERM.LUGS SPADE RF-U4 1.5/M4 | 625 | 125 | 500 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070501
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2026-4 | TERM.LUGS SPADE RF-U4 1.5/M4 | 500 | 125 | 375 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071577
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2026-4 | TERM.LUGS SPADE RF-U4 1.5/M4 | 375 | 375 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 288 | 48 | 240 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069158
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 240 | 48 | 192 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070504
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 192 | 48 | 144 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071580
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 144 | 144 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-11 | RING TYPE LUGS GF-M 5 | 120 | 20 | 100 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069161
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-11 | RING TYPE LUGS GF-M 5 | 100 | 20 | 80 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070507
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-11 | RING TYPE LUGS GF-M 5 | 80 | 20 | 60 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071583
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-11 | RING TYPE LUGS GF-M 5 | 60 | 60 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-2 | TERM.LUGS RING RF-M4 1.5/M4 | 600 | 100 | 500 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069164
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-2 | TERM.LUGS RING RF-M4 1.5/M4 | 500 | 100 | 400 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070510
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-2 | TERM.LUGS RING RF-M4 1.5/M4 | 400 | 100 | 300 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071586
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-2 | TERM.LUGS RING RF-M4 1.5/M4 | 300 | 300 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-4 | TERM.LUGS RING BF-M4 | 1200 | 200 | 1000 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069170
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-4 | TERM.LUGS RING BF-M4 | 1000 | 200 | 800 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070513
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-4 | TERM.LUGS RING BF-M4 | 800 | 200 | 600 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8129000
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-4 | TERM.LUGS RING BF-M4 | 600 | 600 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-7 | TERM.LUGS BF-M5 (RING) | 720 | 120 | 600 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069173
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-7 | TERM.LUGS BF-M5 (RING) | 600 | 120 | 480 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070516
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-7 | TERM.LUGS BF-M5 (RING) | 480 | 120 | 360 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8129003
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-7 | TERM.LUGS BF-M5 (RING) | 360 | 360 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-8 | WIRE LUGS RING TYPE BF-M6 2.5/M6 | 48 | 8 | 40 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069176
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-8 | WIRE LUGS RING TYPE BF-M6 2.5/M6 | 40 | 8 | 32 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070519
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-8 | WIRE LUGS RING TYPE BF-M6 2.5/M6 | 32 | 8 | 24 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8129006
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-8 | WIRE LUGS RING TYPE BF-M6 2.5/M6 | 24 | 24 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-9 | RING TYPE LUGS BF-M 8 | 48 | 8 | 40 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069179
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-9 | RING TYPE LUGS BF-M 8 | 40 | 8 | 32 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070522
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-9 | RING TYPE LUGS BF-M 8 | 32 | 8 | 24 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8129009
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2641 2034-9 | RING TYPE LUGS BF-M 8 | 24 | 24 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 12 | 2 | 10 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076573
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 10 | 2 | 8 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8076576
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 8 | 2 | 6 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100173
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 6 | 2 | 4 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100221
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 4 | 2 | 2 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107638
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 2 | 2 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107692
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 14 | 2 | 12 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128697
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 12 | 2 | 10 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128739
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 10 | 2 | 8 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150158
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 8 | 2 | 6 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150320
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 6 | 6 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 48 | 8 | 40 | 6100K019 | R66-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069203
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 40 | 8 | 32 | 6100K019 | R66-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070600
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 32 | 8 | 24 | 6100K019 | R66-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071589
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 24 | 8 | 16 | 6100K019 | R66-I-1-KDP1_SEP | consumption | 2025-10-16 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8137225
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 16 | 8 | 8 | 6100K019 | R66-I-1-KDP1_SEP | consumption | 2025-10-16 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8137919
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 8 | 8 | 0 | free_stock | R58-G-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 924 0010 | Combiflex wire Socket 1.5mm 1MRK002136-B | 1200 | 1200 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 924 0020 | Combiflex wire Socket 2.5mm 1MRK002136-E | 720 | 720 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 4 | 2 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 2 | 2 | 0 | free_stock | R16-L-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0007249P0100 | GREASE ISOPLEX TOPAS,NB52,1kg | 0.041 | 0.041 | 0 | 6100K019 | OF1-1-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0007249P0100 | GREASE ISOPLEX TOPAS,NB52,1kg | 1.068 | 0.949 | 0.119 | 6100K019 | OF1-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0007249P0100 | GREASE ISOPLEX TOPAS,NB52,1kg | 0.119 | 0.09 | 0.029 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0007249P0100 | GREASE ISOPLEX TOPAS,NB52,1kg | 0.029 | 0.01 | 0.019 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0007249P0100 | GREASE ISOPLEX TOPAS,NB52,1kg | 0.019 | 0.019 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0068009P0100 | BUSHING D8/3 PVC | 6 | 6 | 0 | 6100K019 | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0301012P0100 | CHEESE HEAD B0LT M3X6 | 8 | 8 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0303179P0100 | CYLINDER HEAD BOLT M10X80 DIN 91 | 6 | 6 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0303179P0100 | CYLINDER HEAD BOLT M10X80 DIN 91 | 6 | 6 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0305850P0100 | POLYAMID BOLT M6X20 | 19 | 19 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0305871P0100 | HEX BOLT M8X16 DIN 933-POLY | 30 | 30 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0305871P0100 | HEX BOLT M8X16 DIN 933-POLY | 43 | 35 | 8 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0305871P0100 | HEX BOLT M8X16 DIN 933-POLY | 8 | 5 | 3 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128820
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0305871P0100 | HEX BOLT M8X16 DIN 933-POLY | 3 | 3 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 37 | 37 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 41 | 34 | 7 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 7 | 2 | 5 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8100167
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 5 | 5 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0316044P0100 | HEAD SCREW M8X50, DIN 603-4.3 | 10 | 10 | 0 | 6100K019 | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0316044P0100 | HEAD SCREW M8X50, DIN 603-4.3 | 10 | 8 | 2 | 6100K019 | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0316044P0100 | HEAD SCREW M8X50, DIN 603-4.3 | 2 | 2 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 10 | 10 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 12 | 6 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 6 | 4 | 2 | 6100K019 | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 2 | 2 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084141
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0336970P0100 | BOLT,TAPTITE HEX BOLT M5X12 | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0336985P0100 | TAPPING SCREW M6X16/6KTHEAD | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0336985P0100 | TAPPING SCREW M6X16/6KTHEAD | 8 | 5 | 3 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0336985P0100 | TAPPING SCREW M6X16/6KTHEAD | 3 | 3 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0350009P0100 | NUT M6 DIN 439-04 | 4 | 4 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0365304P0100 | NUT,HEX.NUT MPG 16 | 2 | 1 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0365304P0100 | NUT,HEX.NUT MPG 16 | 1 | 1 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8115350
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0367308P0100 | NUT, HEX - M5, DIN 985-6 ( LOCK NUT ) | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0367309P0100 | HEX. NUT M6, DIN 985-6 ( LOCK NUT ) | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0367309P0100 | HEX. NUT M6, DIN 985-6 ( LOCK NUT ) | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0367402P0100 | HEX. NUT M4, DIN 6925-13 ( LOCK NUT ) | 4 | 4 | 0 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0367402P0100 | HEX. NUT M4, DIN 6925-13 ( LOCK NUT ) | 4 | 4 | 0 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369010P0100 | RIVET NUT M6X16 WITH GROOVE | 19 | 19 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 231 | 231 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 270 | 149 | 121 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 121 | 75 | 46 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 46 | 46 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108590
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 74 | 74 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 108 | 84 | 24 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 24 | 24 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108494
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 211 | 211 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 265 | 195 | 70 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 70 | 43 | 27 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 27 | 25 | 2 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144821
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 2 | 2 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 58 | 58 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 94 | 47 | 47 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 47 | 39 | 8 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 8 | 8 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099692
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0401027P0100 | WASHER FLAT 10.5,DIN433-ST | 16 | 16 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0401027P0100 | WASHER FLAT 10.5,DIN433-ST | 20 | 16 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0401027P0100 | WASHER FLAT 10.5,DIN433-ST | 4 | 4 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0402005P0100 | WASHER,SPRING A3.2 | 8 | 8 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0402008P0100 | WASHER, A5., DIN 125-ST | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0402909P0100 | WASHER POLYAMID, A6.4, DIN 125 | 19 | 19 | 0 | 6100K019 | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0402911P0100 | WASHER POLYAMID, A8.4, DIN 125 | 83 | 83 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0402911P0100 | WASHER POLYAMID, A8.4, DIN 125 | 89 | 80 | 9 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0402911P0100 | WASHER POLYAMID, A8.4, DIN 125 | 9 | 9 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099662
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0402912P0100 | WASHER POLYAMID, A10.5, DIN 125 | 36 | 36 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0402912P0100 | WASHER POLYAMID, A10.5, DIN 125 | 48 | 36 | 12 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0402912P0100 | WASHER POLYAMID, A10.5, DIN 125 | 12 | 12 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0410004P0100 | SPRING RING A3, DIN 127-FST | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0410006P0100 | SPRING A4, DIN 127-FST | 24 | 12 | 12 | 6100K019 | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0410006P0100 | SPRING A4, DIN 127-FST | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0410007P0100 | SPRING RING, A5, DIN 127-FST | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0412007P0100 | SPRING RING 10 DIN 7980-FST | 24 | 24 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0413160P0100 | RETAINING WASHER VS5 | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0413160P0100 | RETAINING WASHER VS5 | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0413160P0100 | RETAINING WASHER VS5 | 1 | 1 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0413307P0100 | CONTACT WASHER 12 | 8 | 8 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0413307P0100 | CONTACT WASHER 12 | 8 | 8 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0417501P0100 | SPLIT PIN FOR FRICK B. CHUCK | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418011P0100 | REVTAINING RING BORE-8 | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 27 | 16 | 11 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 11 | 9 | 2 | 6100K019 | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 2 | 2 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8084144
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418203P0100 | WASHER,RETAINING 6, WN418-FST | 20 | 20 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418203P0100 | WASHER,RETAINING 6, WN418-FST | 28 | 24 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418203P0100 | WASHER,RETAINING 6, WN418-FST | 4 | 4 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418204P0100 | WASHER RETAINING 8/WN 418-FST | 10 | 10 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418204P0100 | WASHER RETAINING 8/WN 418-FST | 11 | 10 | 1 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418204P0100 | WASHER RETAINING 8/WN 418-FST | 1 | 1 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418205P0100 | WASHER RETAINING 10, WN418-FST | 16 | 16 | 0 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418205P0100 | WASHER RETAINING 10, WN418-FST | 20 | 12 | 8 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418205P0100 | WASHER RETAINING 10, WN418-FST | 8 | 4 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0418205P0100 | WASHER RETAINING 10, WN418-FST | 4 | 4 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0438403P0100 | SPRG. PIN 2X10 DIN EN 28748 ST | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0438423P0100 | SPRING PIN 3X16 | 8 | 4 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0438423P0100 | SPRING PIN 3X16 | 4 | 4 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108569
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0438425P0100 | SPRING PIN SLOTTED 3X20 (EQUIV.=28272) | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0438453P0100 | PIN,SPRING (SLOTED) 5X26 | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0438455P0100 | SPRING PIN SLOTTED 5X30 | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0457035P0100 | BLIND RIVET 5X10 AL | 48 | 48 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0457035P0100 | BLIND RIVET 5X10 AL | 56 | 46 | 10 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0457035P0100 | BLIND RIVET 5X10 AL | 10 | 2 | 8 | 6100K019 | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0457035P0100 | BLIND RIVET 5X10 AL | 8 | 8 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8101114
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0457038P0100 | BLIND RIVET 5X16, CIECO, WN457-ALU | 20 | 20 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0457038P0100 | BLIND RIVET 5X16, CIECO, WN457-ALU | 24 | 20 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0457038P0100 | BLIND RIVET 5X16, CIECO, WN457-ALU | 4 | 2 | 2 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144098
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0457038P0100 | BLIND RIVET 5X16, CIECO, WN457-ALU | 2 | 2 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0457040P0100 | BLIND RIVET 6.4X12 STEEL | 67 | 67 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0493108P0100 | BALL SHAPED HANDLE | 1 | 1 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0734028P0100P | K - BALL SHAPED HANDLE (ZINC CHRM) | 4 | 2 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0734028P0100P | K - BALL SHAPED HANDLE (ZINC CHRM) | 2 | 2 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8115344
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0909121P0100 | STRAIN RELIEF TYPE ZE2/10 | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0931008P0100 | POST TYPE INSULATOR 12kV SIZE B 2040384 | 15 | 15 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0931008P0100 | POST TYPE INSULATOR 12kV SIZE B 2040384 | 18 | 3 | 15 | 606PD013 | R13-S-1-PD\-13/MV_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0931306P0100 | BUSHING KD20-30/115(2033335)GJ (LOWER) | 3 | 3 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0931315P0100 | BUSHING INSERT 1XD100 | 18 | 18 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0931316P0100 | BUSBAR INSERT 2XD100 | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990014P0100 | THREADED PLATE M10 | 4 | 4 | 0 | 6100K019 | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990108P0100 | LV Double Bit Key 3.2 | 2 | 2 | 0 | 6100K019 | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 12 | 8 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 4 | 2 | 2 | 6100K019 | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 2 | 2 | 0 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069182
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990162P0102 | PANEL HEATER 240V,100W-Boxin-5MetCable | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990162P0102 | PANEL HEATER 240V,100W-Boxin-5MetCable | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990162P0102 | PANEL HEATER 240V,100W-Boxin-5MetCable | 1 | 1 | 0 | 6100K019 | R16-I-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8094862
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990403P0100 | VENTILATOR QK08A-2EM.50.CH WITH CAPACITO | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990404P0100 | RADIAL FLOW FAN QK08A-2EM.35.CF | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990431P0100 | HANDLE | 96 | 96 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990431P0100 | HANDLE | 103 | 90 | 13 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990431P0100 | HANDLE | 13 | 13 | 0 | 6100K019 | R59-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144103
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0990479P0100 | WHEEL FOR TRUCK 100X35 POLYAMID | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0996027P0100 | PROTECTION CAP M10NR.610 | 18 | 18 | 0 | 6100K019 | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0996027P0100 | PROTECTION CAP M10NR.610 | 24 | 18 | 6 | 6100K019 | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0996027P0100 | PROTECTION CAP M10NR.610 | 6 | 6 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0997050P0100 | Crank CB Truck Rack in/out | 1 | 1 | 0 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128670
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0997050P0100 | HAND CRANK FOR SWITCH TRUCK | 2 | 1 | 1 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128796
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0997050P0100 | HAND CRANK FOR SWITCH TRUCK | 1 | 1 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0997050P0100 | HAND CRANK FOR SWITCH TRUCK | 2 | 2 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998122P0100 | TUBING 28X36 FOR PG29 | 2.1 | 2.1 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998122P0100 | TUBING 28X36 FOR PG29 | 6.6 | 6.6 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998124P0100 | Use *** 1YAB010415P0103 *** | 0.8 | 0.4 | 0.4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998124P0100 | Use *** 1YAB010415P0103 *** | 0.4 | 0.4 | 0 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107668
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998131P0100 | TUBE HOLDER-LK / MPG16 | 2 | 1 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998131P0100 | TUBE HOLDER-LK / MPG16 | 1 | 1 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8115347
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998134P0100 | SEALING RUBBER | 81.64 | 81.64 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998134P0100 | SEALING RUBBER | 93.59 | 80.22 | 13.37 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998134P0100 | SEALING RUBBER | 13.37 | 13.37 | 0 | free_stock | R15-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998162P0100 | REDUCING RING PVC | 104 | 104 | 0 | 6100K019 | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998162P0100 | REDUCING RING PVC | 125 | 87 | 38 | 6100K019 | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998162P0100 | REDUCING RING PVC | 38 | 19 | 19 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998162P0100 | REDUCING RING PVC | 19 | 19 | 0 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0998168P0100 | PLASTIC BUSHING EK/G36 | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4117104P0106 | TUBE G16X100 DIN 490216 | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4117104P0106 | TUBE G16X100 DIN 490216 | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4117104P0106 | TUBE G16X100 DIN 490216 | 1 | 1 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4117104P0117 | TUBE G16X9 | 10 | 10 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4117104P0117 | TUBE G16X9 | 12 | 10 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4117104P0117 | TUBE G16X9 | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4129015P0128P | HEX.PART 17X677 ZINC CHR. | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4129015P0128P | HEX.PART 17X677 ZINC CHR. | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4129015P0128P | HEX.PART 17X677 ZINC CHR. | 1 | 1 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4329220P0100 | THREADED DOWEL M12X37 | 2 | 2 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4329220P0100 | THREADED DOWEL M12X37 | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4366010P0100 | NUT(DADO D'ANCORAGGIO) M10 WN366-ST37-2 | 30 | 30 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4366010P0100 | NUT(DADO D'ANCORAGGIO) M10 WN366-ST37-2 | 38 | 30 | 8 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4366010P0100 | NUT(DADO D'ANCORAGGIO) M10 WN366-ST37-2 | 8 | 8 | 0 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128826
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4395060P0100 | WASHER,PLAIN , LARGE 6.1/18X1 | 24 | 24 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4395060P0100 | WASHER,PLAIN , LARGE 6.1/18X1 | 28 | 28 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4395592P0100 | WASHER FLAT 8 X 11 X 0.5 MM | 36 | 36 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4395592P0100 | WASHER FLAT 8 X 11 X 0.5 MM | 42 | 36 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4395592P0100 | WASHER FLAT 8 X 11 X 0.5 MM | 6 | 6 | 0 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8104591
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4395856P0100 | PLAIN WASHER, LARGE 6.2x12x0.2 | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4396073P0100 | WASHER LARG PLN (12.1/23.5X2.5 | 8 | 4 | 4 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4396073P0100 | WASHER LARG PLN (12.1/23.5X2.5 | 4 | 4 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4520999P0100 | INDICATION LABELS ( HOCK SYSMBLE ) | 8 | 8 | 0 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4520999P0100 | INDICATION LABELS ( HOCK SYSMBLE ) | 8 | 8 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4530250P0100 | DESIGNATION LABEL L1 (RED) | 6 | 6 | 0 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4530250P0100 | DESIGNATION LABEL L1 (RED) | 7 | 5 | 2 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4530250P0100 | DESIGNATION LABEL L1 (RED) | 2 | 1 | 1 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4530250P0100 | DESIGNATION LABEL L1 (RED) | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4530251P0100 | DESIGNATION LABEL L2 (YELLOW) | 6 | 6 | 0 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4530251P0100 | DESIGNATION LABEL L2 (YELLOW) | 7 | 5 | 2 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4530251P0100 | DESIGNATION LABEL L2 (YELLOW) | 2 | 1 | 1 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4530251P0100 | DESIGNATION LABEL L2 (YELLOW) | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4530252P0100 | DESIGNATION LABEL L3 (BLUE) | 6 | 6 | 0 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4530252P0100 | DESIGNATION LABEL L3 (BLUE) | 7 | 5 | 2 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4530252P0100 | DESIGNATION LABEL L3 (BLUE) | 2 | 1 | 1 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4530252P0100 | DESIGNATION LABEL L3 (BLUE) | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 6 | 3 | 3 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 3 | 2 | 1 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 1 | 1 | 0 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8115478
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4539452P0100 | INDICATION LABEL Mech.Operation STICKER | 4 | 4 | 0 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4539452P0100 | INDICATION LABEL Mech.Operation STICKER | 5 | 3 | 2 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4539452P0100 | INDICATION LABEL Mech.Operation STICKER | 2 | 1 | 1 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4539452P0100 | INDICATION LABEL Mech.Operation STICKER | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000495R0101 | SHAFT COMPL. | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000495R0101 | SHAFT COMPL. | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000495R0101 | SHAFT COMPL. | 1 | 1 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000496P0102 | TORSION SPRING | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000496P0102 | TORSION SPRING | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000496P0102 | TORSION SPRING | 1 | 1 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000497R0101 | BEARING HOUSING COMPLETE | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000497R0101 | BEARING HOUSING COMPLETE | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000497R0101 | BEARING HOUSING COMPLETE | 1 | 1 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000508P0101 | GROOVED PIN | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000508P0101 | GROOVED PIN | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000508P0101 | GROOVED PIN | 1 | 1 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000524P0101P | GROOVED PIN | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000524P0101P | GROOVED PIN | 6 | 4 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000524P0101P | GROOVED PIN | 2 | 1 | 1 | 6100K019 | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000524P0101P | GROOVED PIN | 1 | 1 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000525P0101 | WASHER,STOP | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000525P0101 | WASHER,STOP | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000525P0101 | WASHER,STOP | 1 | 1 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000535R0101P | K- BRACKET COMPL. ZINC COATED | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000535R0101P | K- BRACKET COMPL. ZINC COATED | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000535R0101P | K- BRACKET COMPL. ZINC COATED | 1 | 1 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000541P0101P | ADJUSTING RING | 2 | 2 | 0 | 6100K019 | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000542P0101 | BUSH D10/6.2X15 | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000545P0101 | COMPRESSION SPRING | 4 | 2 | 2 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | B |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120224
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000545P0101 | COMPRESSION SPRING | 2 | 2 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000552P0101 | STOP WASHER | 10 | 10 | 0 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000552P0101 | STOP WASHER | 12 | 10 | 2 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000552P0101 | STOP WASHER | 2 | 2 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000553P0101 | ADJUSTING FISH PLATE | 10 | 10 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000553P0101 | ADJUSTING FISH PLATE | 12 | 10 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000553P0101 | ADJUSTING FISH PLATE | 2 | 2 | 0 | 6100KDP01 | R55-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000581P0101 | CANTILEVER SPRING | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000581P0101 | CANTILEVER SPRING | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000581P0101 | CANTILEVER SPRING | 1 | 1 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000582P0101 | SPIRAL SPRING | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000582P0101 | SPIRAL SPRING | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000582P0101 | SPIRAL SPRING | 1 | 1 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000663R0101 | BEVEL GEAR DRIVE FOR EK6 ZS1 | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000663R0101 | BEVEL GEAR DRIVE FOR EK6 ZS1 | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000663R0101 | BEVEL GEAR DRIVE FOR EK6 ZS1 | 1 | 1 | 0 | free_stock | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000835P0101 | BRACKET S=200 | 1 | 1 | 0 | 6100KDP01 | WH2-1-1-K019_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7000847P0101P | K - STUD | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7001026P0101 | INSULATION TUBE; L=45MM. | 10 | 10 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7001026P0101 | INSULATION TUBE; L=45MM. | 12 | 10 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7001026P0101 | INSULATION TUBE; L=45MM. | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7001936P0101P | K - HANDLE (CHROME PLATED) | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7001936P0101P | K - HANDLE (CHROME PLATED) | 4 | 2 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7001936P0101P | K - HANDLE (CHROME PLATED) | 2 | 2 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144855
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7002424P0101P | K - BEARING SHAFT (ZINC CHRM) | 8 | 8 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7002424P0101P | K - BEARING SHAFT (ZINC CHRM) | 8 | 4 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7002424P0101P | K - BEARING SHAFT (ZINC CHRM) | 4 | 4 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144858
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7002453P0102 | LOCK STRIP | 8 | 4 | 4 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-15 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128763
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7002453P0102 | LOCK STRIP | 4 | 4 | 0 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-16 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144139
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7002476P0101 | FIXING BAR | 2 | 1 | 1 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | B |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120227
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7002476P0101 | FIXING BAR | 1 | 1 | 0 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | B |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120221
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7002476P0101 | FIXING BAR | 2 | 1 | 1 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144154
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7002476P0101 | FIXING BAR | 1 | 1 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003008P0101 | RING | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003008P0101 | RING | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003008P0101 | RING | 1 | 1 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003012P0101P | TUBE 8X5.1X25 | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003534P0101 | DETENT (RASTE) | 2 | 1 | 1 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | B |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120230
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003534P0101 | DETENT (RASTE) | 1 | 1 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003535P0102 | SLIDE | 2 | 2 | 0 | 6100KDP01 | WH2-1-1-K019_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003536P0101 | DETENT | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003538P0101 | COVER | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003544P0101 | SPINDLE | 2 | 1 | 1 | 6100K019 | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003544P0101 | SPINDLE | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003553P0101P | HEXAGON BOLT | 8 | 8 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003554P0101 | BRACKET | 2 | 2 | 0 | 6100KDP01 | WH2-1-1-K019_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003556P0101 | SLIDE | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003557P0101 | SLIDE | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003558P0101 | ADJUSTING SCREW | 2 | 1 | 1 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | B |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120233
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003558P0101 | ADJUSTING SCREW | 1 | 1 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003560P0101 | SPACER | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003562P0101P | K - BUSH 10X60 | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003563P0101 | SHAFT | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003568P0101 | NUT SPECIAL | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003572P0101 | TORSION SPRING | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003578P0101 | SQUARE BOLT 4KT8/20 | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003579P0101 | TENSION SPRING 6.5/.9/30/16 | 7 | 7 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003579P0101 | TENSION SPRING 6.5/.9/30/16 | 8 | 7 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003579P0101 | TENSION SPRING 6.5/.9/30/16 | 1 | 1 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8096126
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003579P0102 | TENSION SPRING 6.5/.9/30/16 | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003580P0101 | CCOMPRESSION SPRING | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003581P0101 | COMPRESSION SPRING 7.5/0,8/9/25 | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003582P0101 | NUT | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003694P0102 | CARRIER | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003694P0102 | CARRIER | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003694P0102 | CARRIER | 1 | 1 | 0 | free_stock | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7004025R0102 | DRAW OUT DEVICEP210-S200 ASSY. | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7004046R0101 | RECTIFIER COMPL. | 2 | 1 | 1 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7004046R0101 | RECTIFIER COMPL. | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7102436P0100 | PLUG HOUSING SOCKET/GEHAUSE | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7102436P0100 | PLUG HOUSING SOCKET/GEHAUSE | 8 | 7 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7102436P0100 | PLUG HOUSING SOCKET/GEHAUSE | 1 | 1 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7102438P0100 | COVER OF CONTROL PLUG/SOCKET | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7102438P0100 | COVER OF CONTROL PLUG/SOCKET | 4 | 3 | 1 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7102438P0100 | COVER OF CONTROL PLUG/SOCKET | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7107642P0100 | TENSION SPRING 8.9/0.7/35/10 | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7109399R0101 | AUXILIARY SWITCH 5NO | 10 | 10 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7109399R0101 | AUXILIARY SWITCH 5NO | 12 | 10 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7109399R0101 | AUXILIARY SWITCH 5NO | 2 | 2 | 0 | free_stock | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7109399R0106 | AUXILIARY SWITCH 5NC | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7109399R0106 | AUXILIARY SWITCH 5NC | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7109399R0106 | AUXILIARY SWITCH 5NC | 1 | 1 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7109399R0118 | SLIDE F.AUX.SWICH 5NC | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7109399R0119 | AUX.SWITCH 5NO. (S8,S9) | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7169312R0145 | EARTHING SWITCH: EK6-ZS1-1706-210 | 5 | 5 | 0 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7169312R0145 | EARTHING SWITCH: EK6-ZS1-1706-210 | 6 | 3 | 3 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7169312R0145 | EARTHING SWITCH: EK6-ZS1-1706-210 | 3 | 1 | 2 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7169312R0145 | EARTHING SWITCH: EK6-ZS1-1706-210 | 2 | 2 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7204654P0101 | BOLT 7/4X15 | 8 | 8 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7208367P0100 | DESIGNATION LABEL | 6 | 6 | 0 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7208367P0100 | DESIGNATION LABEL | 6 | 5 | 1 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7208367P0100 | DESIGNATION LABEL | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000336P0101 | K- INTERMEDIATE PIECE 40x6x9(ZINC CHR.) | 12 | 12 | 0 | 6100KDP01 | PO-SEP-5654-[5] | GR_in_process | 2025-12-31 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries) | 96 | 06-09-2025
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000633P0113P | MOUNTING CHANNEL 760mm (GCE8000633P0113) | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000633P0113P | MOUNTING CHANNEL 760mm (GCE8000633P0113) | 8 | 6 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000633P0113P | MOUNTING CHANNEL 760mm (GCE8000633P0113) | 2 | 2 | 0 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8077515
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000633P0115 | MOUNTING CHANNEL L325mm | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000633P0115 | MOUNTING CHANNEL L325mm | 6 | 4 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000633P0115 | MOUNTING CHANNEL L325mm | 2 | 2 | 0 | 6100K019 | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000825P0101 | SPRING | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000825P0101 | SPRING | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000825P0101 | SPRING | 1 | 1 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8117183
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000910P0101 | PACKING PIECE 80X15 | 9 | 9 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000981P0101P | THREADED PIECE | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000981P0101P | THREADED PIECE | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8000981P0101P | THREADED PIECE | 1 | 1 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8001698R0107P | LEVER MECHANISM LEFT-SX 2X R250/55(w1000 | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8001698R0108P | LEVER MECHANISM RIGHT,DX2X R250/55(w1000 | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8001710P0101 | SPECIAL BOLT | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8001975P0101 | WASHER 40X21X10 (LOCAL PUR) | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8001975P0101 | WASHER 40X21X10 (LOCAL PUR) | 18 | 18 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8001976P0101 | WASHER 40X21X2 | 15 | 15 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8001976P0101 | WASHER 40X21X2 | 18 | 18 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002186R0101 | K- FLANGE PLATE, COMPL. ZINC COAT | 12 | 12 | 0 | 6100KDP01 | PO-SEP-5654-[14] | GR_in_process | 2025-12-31 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries) | 114 | 22-09-2025
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002328P0101P | SHROUD PC (ABS MATERIAL) | 3 | 3 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002370P0101 | DOCKING RECEPTANCE | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002370P0101 | DOCKING RECEPTANCE | 14 | 12 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002370P0101 | DOCKING RECEPTANCE | 2 | 2 | 0 | 6100K019 | R59-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8104672
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002372P0101P | BUSHING | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002375P0101 | TENSION SPRING | 1 | 1 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002757P0101 | Insert 1X60X10 (2024231) GJ.GER | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002757P0101 | Insert 1X60X10 (2024231) GJ.GER | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002757P0102 | Insert 80X10 | 18 | 18 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002757P0102 | Insert 80X10 | 30 | 24 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002757P0102 | Insert 80X10 | 6 | 6 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128829
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002866R0102P | PADLOCK ES - NORMAL | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002866R0102P | PADLOCK ES - NORMAL | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002866R0102P | PADLOCK ES - NORMAL | 1 | 1 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002875P0101 | WINDOW PANE 350X220X16,8 (KONEX) | 2 | 2 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002875P0101 | WINDOW PANE 350X220X16,8 (KONEX) | 4 | 4 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003360R0101P | LEVER MECHANISM LEFT, 2xR250/55(W800) | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003360R0101P | LEVER MECHANISM LEFT, 2xR250/55(W800) | 5 | 4 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003360R0101P | LEVER MECHANISM LEFT, 2xR250/55(W800) | 1 | 1 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128832
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003360R0102P | LEVER MECHANISM RIGHT,2xR250/55 (W800) | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003360R0102P | LEVER MECHANISM RIGHT,2xR250/55 (W800) | 5 | 4 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003360R0102P | LEVER MECHANISM RIGHT,2xR250/55 (W800) | 1 | 1 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128835
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003624R0102 | MONOBLOCCO-SPOUT 1250A,ZS1 | 24 | 24 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003624R0102 | MONOBLOCCO-SPOUT 1250A,ZS1 | 36 | 30 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003624R0102 | MONOBLOCCO-SPOUT 1250A,ZS1 | 6 | 6 | 0 | free_stock | R13-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003638P0103P | INTER LOCKING AGLE LEFT | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003638P0103P | INTER LOCKING AGLE LEFT | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003638P0103P | INTER LOCKING AGLE LEFT | 1 | 1 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8094838
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003638P0104P | INTERLOCKING ANGLE RIGHT | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003638P0104P | INTERLOCKING ANGLE RIGHT | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003638P0104P | INTERLOCKING ANGLE RIGHT | 1 | 1 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144095
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003651P0101P | INSULATING CAP | 27 | 27 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003651P0101P | INSULATING CAP | 43 | 35 | 8 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003651P0101P | INSULATING CAP | 8 | 8 | 0 | 6100K019 | R59-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128838
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003671P0116 | SPCEIAL SCREW M12X34/45 | 12 | 12 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003671P0116 | SPCEIAL SCREW M12X34/45 | 20 | 16 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003671P0116 | SPCEIAL SCREW M12X34/45 | 4 | 4 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003671P0120 | SPECIAL SCREW M12X30/101 | 18 | 18 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003671P0120 | SPECIAL SCREW M12X30/101 | 26 | 18 | 8 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003671P0120 | SPECIAL SCREW M12X30/101 | 8 | 4 | 4 | 6100K019 | R13-S-1-K006_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003671P0120 | SPECIAL SCREW M12X30/101 | 4 | 4 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003672P0101 | COVER-COPERTURA 12KV ZS1 1250A | 24 | 24 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003672P0101 | COVER-COPERTURA 12KV ZS1 1250A | 36 | 30 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003672P0101 | COVER-COPERTURA 12KV ZS1 1250A | 6 | 3 | 3 | 6100K019 | R59-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8103575
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003672P0101 | COVER-COPERTURA 12KV ZS1 1250A | 3 | 3 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003824P0101 | K- SUPPORT PLATE YELLOW CHROMATION. | 4 | 1 | 3 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-13 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070997
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003824P0101 | K- SUPPORT PLATE YELLOW CHROMATION. | 3 | 1 | 2 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-14 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107725
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003824P0101 | K- SUPPORT PLATE YELLOW CHROMATION. | 2 | 1 | 1 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-16 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150356
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003824P0101 | K- SUPPORT PLATE YELLOW CHROMATION. | 1 | 1 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003861P0101 | BEARING SHAFT (ZINC CHRM) | 2 | 2 | 0 | 6100K019 | R13-S-1-K006_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8003900P0102 | COVER FOR SPOUT | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004145P0101P | INTERLOCKING BOLT | 4 | 2 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004145P0101P | INTERLOCKING BOLT | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 1 | 1 | 0 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8094459
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004437P0103P | SHROUD (EARTHING CONTACT)GCE8004437P0103 | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004437P0103P | SHROUD (EARTHING CONTACT)GCE8004437P0103 | 8 | 6 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004437P0103P | SHROUD (EARTHING CONTACT)GCE8004437P0103 | 2 | 2 | 0 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004471R0101P | ELECTRODE, ZS1 95kV BIL | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004478P0101 | BUSHING PLATE BELOW / 3 HOLES | 1 | 1 | 0 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004479P0101P | PROTECTIVE COVER (DWG: GCE8004479P0101) | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004479P0101P | PROTECTIVE COVER (DWG: GCE8004479P0101) | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004581P0101 | SPRING COMPRESSION | 4 | 2 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004581P0101 | SPRING COMPRESSION | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004770P0101 | SHROUD 17.5kV | 6 | 3 | 3 | 6100K019 | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004770P0101 | SHROUD 17.5kV | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004944R0101 | SPOUT ZS1 (4000A) | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8004990P0101 | CARRIER FOR BUSBAR SHROUD | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005031R0101 | BUSHING ZS1/ (3 IN 1) DEACE | 4 | 4 | 0 | 6100K019 | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005031R0101 | BUSHING ZS1/ (3 IN 1) DEACE | 25 | 21 | 4 | 6100K019 | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005031R0101 | BUSHING ZS1/ (3 IN 1) DEACE | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005041P0101P | CONTACT PIN 109mm,3150A(GCE8005041P0101) | 6 | 6 | 0 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005042P0101 | CONNECTION PIECE 3150A ZS1 | 3 | 3 | 0 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005112P0103P | OPERATING BOLT | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005117P0101 | CARRIER | 4 | 4 | 0 | 6100KDP01 | R16-L-1-K019_SEP | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005136P0101 | SUPPORT (POLY) | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005164P0101 | SCREENING | 18 | 18 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005250P0101 | K- LIFTING HOOK (ZINC CHROM) | 24 | 4 | 20 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-13 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070991
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005250P0101 | K- LIFTING HOOK (ZINC CHROM) | 20 | 4 | 16 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-14 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107719
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005250P0101 | K- LIFTING HOOK (ZINC CHROM) | 16 | 4 | 12 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-15 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128754
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005250P0101 | K- LIFTING HOOK (ZINC CHROM) | 12 | 4 | 8 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-16 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144130
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005250P0101 | K- LIFTING HOOK (ZINC CHROM) | 8 | 4 | 4 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-16 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150353
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005250P0101 | K- LIFTING HOOK (ZINC CHROM) | 4 | 4 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8005595R0102P | BUSBAR ZS D100, 12THICK,800/800, L=795 | 18 | 18 | 0 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8006031P0101 | COVER FOR BUSBAR JOINTS | 9 | 9 | 0 | 6100K019 | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8006031P0101 | COVER FOR BUSBAR JOINTS | 27 | 18 | 9 | 6100K019 | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8006031P0101 | COVER FOR BUSBAR JOINTS | 9 | 9 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8006587P0101 | LOCK SCREW M6X25 ( ROUND FLAT HEAD ) | 32 | 32 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8006587P0101 | LOCK SCREW M6X25 ( ROUND FLAT HEAD ) | 40 | 32 | 8 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8006587P0101 | LOCK SCREW M6X25 ( ROUND FLAT HEAD ) | 8 | 8 | 0 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8008881P0103 | BRACKET BOTTOM | 8 | 2 | 6 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-13 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071000
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8008881P0103 | BRACKET BOTTOM | 6 | 2 | 4 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-14 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107728
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8008881P0103 | BRACKET BOTTOM | 4 | 2 | 2 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-16 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150359
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8008881P0103 | BRACKET BOTTOM | 2 | 2 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8008881P0104 | SHUTTER BRACKET | 12 | 2 | 10 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-13 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071003
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8008881P0104 | SHUTTER BRACKET | 10 | 2 | 8 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-14 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107731
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8008881P0104 | SHUTTER BRACKET | 8 | 2 | 6 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-15 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128760
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8008881P0104 | SHUTTER BRACKET | 6 | 2 | 4 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-16 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144136
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8008881P0104 | SHUTTER BRACKET | 4 | 2 | 2 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-16 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150236
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8008881P0104 | SHUTTER BRACKET | 2 | 2 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 1 | 1 | 0 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8096042
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010004P0102 | GUIDE RAIL RIGHT 12kV | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010004P0102 | GUIDE RAIL RIGHT 12kV | 7 | 5 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010004P0102 | GUIDE RAIL RIGHT 12kV | 2 | 1 | 1 | 6100K019 | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010004P0102 | GUIDE RAIL RIGHT 12kV | 1 | 1 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010008P0101 | BUSHING PLATE (STAINLESS STEEL) | 5 | 5 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010022P0111R | SHUTTER UPPER W800 (GCE8010022P0111) | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010022P0111R | SHUTTER UPPER W800 (GCE8010022P0111) | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010022P0111R | SHUTTER UPPER W800 (GCE8010022P0111) | 1 | 1 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010022P0112Y | SHUTTER LOWER W800 (GCE8010022P0112) | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010022P0112Y | SHUTTER LOWER W800 (GCE8010022P0112) | 5 | 4 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010022P0112Y | SHUTTER LOWER W800 (GCE8010022P0112) | 1 | 1 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071021
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010022P0113R | SHUTTER UPPER (DWG.GCE8010022P0113) | 1 | 1 | 0 | 6100K019 | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010022P0114Y | SHUTTER LOWER (DWG.GCE8010022P0114) | 1 | 1 | 0 | 6100K019 | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010023P0101 | PIN (ZINC COATED) | 16 | 16 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 9 | 9 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 11 | 9 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 2 | 2 | 0 | 6100K019 | R14-J-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8094536
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010028R0103 | PRESSURE RELIEF FLAP W1000 | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010028R0105 | PRESSURE RELIEF FLAP, REAR | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010028R0106 | PRESSURE RELIEF FLAP W1000 | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010073P0102 | PARTITION WALL | 5 | 1 | 4 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-13 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071006
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010073P0102 | PARTITION WALL | 4 | 1 | 3 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-14 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107734
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010073P0102 | PARTITION WALL | 3 | 1 | 2 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-15 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8128766
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010073P0102 | PARTITION WALL | 2 | 1 | 1 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-16 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144142
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010073P0102 | PARTITION WALL | 1 | 1 | 0 | 6100K019 | NEW.FLR-1-1-KDP1_SEP | consumption | 2025-10-16 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150239
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010073P0103 | BB/CB.PARTITION WALL W1000(PaintRAL7035) | 1 | 1 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010096P0101P | PIN 12DIA(ZINC COAT)DWG:GCE8010096P0101 | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010096P0101P | PIN 12DIA(ZINC COAT)DWG:GCE8010096P0101 | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010097P0102 | MOUNTING PLATE S=310 W1000 | 1 | 1 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010104P0103P | BUSHING D60/49X25 | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010178P0102 | SUPPORT ANGLE | 5 | 5 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8010178P0103 | SUPPORT ANGLE W1000 | 1 | 1 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011408P0101 | MOUNTING PLATE W800, METERING | 2 | 2 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011409R0101 | LEVER COMPLETE LEFT SIDE | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011409R0101 | LEVER COMPLETE LEFT SIDE | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011409R0102 | LEVER COMPLETE RIGHT SIDE | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011409R0102 | LEVER COMPLETE RIGHT SIDE | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011552P0102 | FLAT SCREEN FOR CB.MIDDLE PLATE W800 | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011552P0102 | FLAT SCREEN FOR CB.MIDDLE PLATE W800 | 5 | 4 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011552P0102 | FLAT SCREEN FOR CB.MIDDLE PLATE W800 | 1 | 1 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011642P0101 | SPACER | 21 | 21 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011642P0101 | SPACER | 27 | 21 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011642P0101 | SPACER | 6 | 6 | 0 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011650P0101 | SUPPORT REINFORCEMENT | 1 | 1 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011673P0101 | PARTITION WALL W800 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-5654-[29] | GR_in_process | 2025-12-31 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries) | 4 | 06-09-2025
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011679R0101P | REIFORCING ANGLE COMPLETE LEFT | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011679R0101P | REIFORCING ANGLE COMPLETE LEFT | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8012228P0101 | SUPPORTING SHEET | 6 | 6 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013214P0101 | PARTITION WALL BOTTOM W800 (SS STL)BARE | 3 | 3 | 0 | 6100KDP01 | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013244P0101 | TRANSFORMER PLATE W800mm | 3 | 3 | 0 | 6100KDP01 | PO-SEP-5654-[33] | GR_in_process | 2025-12-31 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries) | 36 | 24-09-2025
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013262P0101 | SHROUD | 8 | 4 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013262P0101 | SHROUD | 4 | 4 | 0 | 6100KDP01 | R56-I-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013263P0101 | SHROUD | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013263P0101 | SHROUD | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013412R0101 | PRESSURE RELIEF FLAP FOR W1000 | 1 | 1 | 0 | 6100K019 | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013414P0101 | FIXING PLATE FOR DUCT | 1 | 1 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013419R0101 | FRAME FOR FLAT SCREEN COMPLETE | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013423P0101 | PARTITION WALL W1000 (PAINTED RAL7035) | 1 | 1 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013427P0101 | GAIN CT PLATE | 1 | 1 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013430P0101 | COOLING PLATE 1 ( small ) | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013431P0101 | COOLING PLATE 2 ( Big ) | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013433P0101P | SHROUD (DWG NO. GCE8013433P0101) | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013434P0101P | SHROUD (DWG NO. GCE8013434P0101) | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013434P0102P | SHROUD (DWG NO. GCE8013434P0102) | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013435P0101P | SPACER DISC (GCE8013435P0101) | 16 | 16 | 0 | 6100K019 | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8013444R0101 | PRESSURE RELIEF FLAP(W1000) | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8381281P0100 | GUIDE ROLLER | 2 | 1 | 1 | 6100K019 | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8381281P0100 | GUIDE ROLLER | 1 | 1 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8487370R0100 | EARTHING CONTACT | 2 | 1 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8487370R0100 | EARTHING CONTACT | 1 | 1 | 0 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8106078
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8494256P0101 | DISTANCE TUBE | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8494256P0101 | DISTANCE TUBE | 6 | 4 | 2 | 6100K019 | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8494256P0101 | DISTANCE TUBE | 2 | 1 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8494256P0101 | DISTANCE TUBE | 1 | 1 | 0 | 6100K019 | R59-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8109419
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 10 | 10 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 10 | 5 | 5 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 5 | 2 | 3 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 3 | 2 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 1 | 1 | 0 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8127548
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8684080P0101 | EARTHING STRIP | 2 | 1 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8684080P0101 | EARTHING STRIP | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8108572
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8685155P0101 | CORNER STRIP JOINT R22/H20 | 28 | 28 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8685778P0121P | CONTACT PIN 800/1200A SIL.COAT = 72L | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8685778P0121P | CONTACT PIN 800/1200A SIL.COAT = 72L | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9371453P0101 | CABLE BUSHING LOWER PART | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9371453P0101 | CABLE BUSHING LOWER PART | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9371454P0101 | CABLE BUSHING UPPER PART | 2 | 2 | 0 | 6100K019 | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9371454P0101 | CABLE BUSHING UPPER PART | 2 | 2 | 0 | 6100K019 | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9401529P0100 | Bush | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9401529P0100 | Bush | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9401529P0100 | Bush | 1 | 1 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9401556P0100 | STOP WASHER | 10 | 10 | 0 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9401556P0100 | STOP WASHER | 12 | 10 | 2 | 6100K019 | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9401556P0100 | STOP WASHER | 2 | 2 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9401678R0101 | HOUSING (PLUG SOCKET)COMPL. | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9401678R0101 | HOUSING (PLUG SOCKET)COMPL. | 3 | 2 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9401678R0101 | HOUSING (PLUG SOCKET)COMPL. | 1 | 1 | 0 | 6100K019 | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9401766P0107 | LOCKING MAGNET DC125 V | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9401766P0107 | LOCKING MAGNET DC125 V | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9401766P0107 | LOCKING MAGNET DC125 V | 1 | 1 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9464131P0100 | EARTHING SWITCH DISPLAY | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9464131P0100 | EARTHING SWITCH DISPLAY | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9464131P0100 | EARTHING SWITCH DISPLAY | 1 | 1 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9476775R0100 | IND.CONTACT/ VAN FLOW SWITCH | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9477367P0102 | FORK D11x20 | 3 | 3 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9478304P0102P | ROLLER | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9478304P0102P | ROLLER | 8 | 4 | 4 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9478304P0102P | ROLLER | 4 | 4 | 0 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8117186
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9478350P0101 | SUPPORTING BOLT 6Kt14/M6X23 | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9478350P0101 | SUPPORTING BOLT 6Kt14/M6X23 | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9478476P0101 | FIXING RING | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9576618P0100 | BUSH D18/12,2X8 | 10 | 10 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9576618P0100 | BUSH D18/12,2X8 | 12 | 10 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE9576618P0100 | BUSH D18/12,2X8 | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCEC830444P0101P | K-SPACER D12/4.5X8,ZS1/ZS3.2Yellow Chrom | 10 | 10 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCEC830444P0101P | K-SPACER D12/4.5X8,ZS1/ZS3.2Yellow Chrom | 12 | 10 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCEC830444P0101P | K-SPACER D12/4.5X8,ZS1/ZS3.2Yellow Chrom | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 12 | 2 | 10 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070982
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 10 | 2 | 8 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8071024
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 8 | 2 | 6 | 6100K019 | R16-I-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107632
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 6 | 2 | 4 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8107713
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 4 | 2 | 2 | 6100K019 | R16-I-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120296
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 2 | 2 | 0 | 6100K019 | R16-I-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8120315
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 14 | 2 | 12 | 6100K019 | R16-I-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8144127
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 12 | 2 | 10 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150188
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 10 | 2 | 8 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8150341
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 8 | 8 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 8 | 2 | 6 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8069891
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 6 | 2 | 4 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8070531
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 4 | 4 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | PKE 1508 | END SLEEVES PKE 1508 (1x1.5sqmm , Black) | 90 | 90 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | PKT 1508 | END SLEEVES PKT 1508 (2x1.5sqmm , Black) | 90 | 90 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | PKT 2512 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 120 | 120 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000024P0001P | BUSHING (LOCAL PUR) | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000024P0001P | BUSHING (LOCAL PUR) | 6 | 4 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000024P0001P | BUSHING (LOCAL PUR) | 2 | 1 | 1 | 6100K019 | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000024P0001P | BUSHING (LOCAL PUR) | 1 | 1 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000025P0001P | BUSHING (LOCAL PUR) | 15 | 15 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000025P0001P | BUSHING (LOCAL PUR) | 18 | 15 | 3 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000025P0001P | BUSHING (LOCAL PUR) | 3 | 3 | 0 | 6100KDP01 | R58-A-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000026P0001P | BUSHING (LOCAL PUR) | 18 | 18 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000026P0001P | BUSHING (LOCAL PUR) | 21 | 18 | 3 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000026P0001P | BUSHING (LOCAL PUR) | 3 | 3 | 0 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000027P0001P | K-PLATE | 11 | 11 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000027P0001P | K-PLATE | 13 | 11 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000027P0001P | K-PLATE | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000047P0001 | INTERLOCKING SCOTCH | 6 | 6 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000047P0001 | INTERLOCKING SCOTCH | 7 | 6 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000047P0001 | INTERLOCKING SCOTCH | 1 | 1 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000048P0001P | PIN (LOCAL PUR) | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000048P0001P | PIN (LOCAL PUR) | 6 | 5 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000048P0001P | PIN (LOCAL PUR) | 1 | 1 | 0 | 6100KDP01 | R58-A-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000049P0001 | COMPRESSION SPRING | 5 | 5 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000049P0001 | COMPRESSION SPRING | 6 | 4 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000049P0001 | COMPRESSION SPRING | 2 | 1 | 1 | 6100K019 | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1000049P0001 | COMPRESSION SPRING | 1 | 1 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1001678P0001 | HOOKING LEVER (ZINC PLATED) | 1 | 1 | 0 | 6100KDP01 | WH2-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1001813R0802P | MECHANICAL OFF BUTTON FOR VD4 - HOR | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1001813R0802P | MECHANICAL OFF BUTTON FOR VD4 - HOR | 5 | 4 | 1 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1001813R0802P | MECHANICAL OFF BUTTON FOR VD4 - HOR | 1 | 1 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1001915P0001P | PIN | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1001916P0001P | INTERLOCK LEVER (LOCAL PUR) | 2 | 2 | 0 | 6100K019 | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SCB1001982P0001 | ROLLER | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | T81722 | Plastic plug for LV Box (Micro. Sw. ) | 36 | 36 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | T81722 | Plastic plug for LV Box (Micro. Sw. ) | 42 | 36 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | T81722 | Plastic plug for LV Box (Micro. Sw. ) | 6 | 6 | 0 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8099716
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | UCT-IC-13.8KV-1250A-1 | Indoor Current Transformer | 9 | 6 | 3 | 6100K019 | INC-1-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | VT-13.8KV-FR | Voltage Transformer (ABB EJF / TJP5H) | 3 | 3 | 0 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | A |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | VT-13.8KV-FR | Singe-pole insulated voltage Transformer | 9 | 8 | 1 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | VT-GUARD-13.8KV | VT GUARD (ANTI FERRO RESONANCE UNIT) | 3 | 1 | 2 | 6100K019 | R16-L-1-K019_SEP | consumption | 2025-10-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8129012
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | VT-GUARD-13.8KV | VT GUARD (ANTI FERRO RESONANCE UNIT) | 2 | 1 | 1 | 6100K019 | R16-L-1-K019_SEP | consumption | 2025-10-16 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | [5 empty] | Work in Process Pick | 8139440
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | VT-GUARD-13.8KV | VT GUARD (ANTI FERRO RESONANCE UNIT) | 1 | 1 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | XM 2050 1500-30 | POLYCARBONATE 2050X1500X3.0 MM | 12.06 | 12.06 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 13-B3 | BA9S ILLUMINATION CONTACT BLOCK HOLDER | 912 | 796 | 116 | free_stock | R57-O-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 13-B3 | BA9S ILLUMINATION CONTACT BLOCK HOLDER | 116 | 116 | 0 | 6100K007 | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 205004178 | ø10 Flat pad Stainless steel | 150 | 150 | 0 | free_stock | R58-B--RMU/\-BULK_SEP | inventory | 2025-11-03 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 205042612 | φ3.2*16 Cotter pin Stainless steel | 150 | 150 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581647
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 13-B3 | BA9S ILLUMINATION CONTACT BLOCK HOLDER | 900 | 533 | 367 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 13-B3 | BA9S ILLUMINATION CONTACT BLOCK HOLDER | 367 | 367 | 0 | 6100K007 | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 13-LED24K | 24V BA9S LED LAMP RED | 450 | 292 | 158 | 6100K006 | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 13-LED24K | 24V BA9S LED LAMP RED | 158 | 158 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 13-LED24Y | 24V BA9S LED LAMP GREEN | 450 | 345 | 105 | 6100K007 | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 13-LED24Y | 24V BA9S LED LAMP GREEN | 105 | 105 | 0 | free_stock | R57-G-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0815.0153 | CVC Common Enclosure Bottom Bar | 300 | 280 | 20 | 6100KDP02 | BOX123-1-1-K013_SEP | inventory | 2025-11-03 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0815.0153 | CVC Common Enclosure Bottom Bar | 20 | 20 | 0 | 6100K013 | 1-1-1-1 | inventory | 2025-11-03 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0815.1085 | CCC Ground bar 5 | 150 | 105 | 45 | 6100K013 | BOX42-1-1-K013_SEP | inventory | 2025-11-03 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0815.1085 | CCC Ground bar 5 | 45 | 10 | 35 | 6100KDP02 | BOX6-1-1-K013_SEP | inventory | 2025-11-03 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0815.1085 | CCC Ground bar 5 | 35 | 35 | 0 | 6100KDP02 | BOX42-1-1-K013_SEP | consumption | 2025-10-13 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Project Transfer | 8080435
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0816.2651 | Lifting Lug | 300 | 226 | 74 | 6100KDP02 | BOX123-1-1-K013_SEP | inventory | 2025-11-03 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0816.2651 | Lifting Lug | 74 | 74 | 0 | 6100K013 | BOX42-1-1-K013_SEP | inventory | 2025-11-03 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0816.2652 | Lifting Lug Holder | 300 | 226 | 74 | 6100KDP02 | BOX123-1-1-K013_SEP | inventory | 2025-11-03 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0816.2652 | Lifting Lug Holder | 74 | 74 | 0 | 6100K013 | BOX42-1-1-K013_SEP | inventory | 2025-11-03 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205040971 | φ4*12 Waterproof blind rivets Stainless steel | 4800 | 2704 | 2096 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581650
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205040971 | φ4*12 Waterproof blind rivets Stainless steel | 2096 | 1428 | 668 | 6100K015 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7592479
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205040971 | φ4*12 Waterproof blind rivets Stainless steel | 668 | 668 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 8296210
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205041100 | Door Lock, Stainless Steel ¦ DF205041100 ¦ DFE | 300 | 300 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205041101 | Door Bolt 5 Inches Stainless steel | 300 | 183 | 117 | 6100K013 | 1-1-1-1 | consumption | 2025-09-22 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7513363
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205041101 | Door Bolt 5 Inches Stainless steel | 117 | 117 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562529
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | DF205041498 | Rectangular Sealing Strip D-07 T-79 EPDM | 561 | 117.6 | 443.4 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562531
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | DF205041498 | Rectangular Sealing Strip D-07 T-79 EPDM | 443.4 | 443.4 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581664
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF209001750 | Dixation Hook Q235A | 150 | 109 | 41 | 6100K013 | 1-1-1-1 | consumption | 2025-09-22 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7513372
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF209001750 | Dixation Hook Q235A | 41 | 41 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562537
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF209001751 | Buckle A104 Stainless Steel Single hole φ12 | 300 | 288 | 12 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562534
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF209001751 | Buckle A104 Stainless Steel Single hole φ12 | 12 | 12 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581666
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF211001964 | φ10-30 large flat pad Stainless steel | 1200 | 755 | 445 | 6100K013 | 1-1-1-1 | consumption | 2025-09-22 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7513360
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF211001964 | φ10-30 large flat pad Stainless steel | 445 | 445 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562526
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1046 | Lock Tongue | 450 | 450 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-10-26 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 8335206
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 8DF.0818.1139 | Lifting Lugs (05mm Stainless Steel-304) | 300 | 300 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-21 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7485825
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1294 | Limiter holder | 300 | 300 | 0 | 6100K013 | INC-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1295 | Door stop tongue | 300 | 300 | 0 | 6100K013 | R58-J-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1296 | Door stop fixing | 300 | 300 | 0 | 6100K013 | INC-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 8DF-128-0009 | Fixed clamp | 150 | 144 | 6 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562541
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 8DF-128-0009 | Fixed clamp | 6 | 6 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581674
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205040952 | M6*20 Phillips countersunk head screw Stainless steel | 600 | 600 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-21 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7485802
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF240110385 | M24 Gran head nylon | 300 | 42 | 258 | 6100K015 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7592489
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF240110385 | M24 Gran head nylon | 258 | 258 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-10-26 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 8329492
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | DF240510027 | Rail | 117 | 117 | 0 | 6100K013 | PLT7-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF240510061 | Relay (RXM2LB2BD) Including base and buckle | 150 | 150 | 0 | 6100K013 | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | mL | DF240603039 | Thread sealant | 22.5 | 22.5 | 0 | 6100K013 | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | KG | DF240929001 | Paste | 1.5 | 1.5 | 0 | 6100K013 | 1-1-1-1 | inventory | 2025-11-03 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF241118007 | Unlock the locking knob | 450 | 416 | 34 | 6100K013 | R17-B-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF241118007 | Unlock the locking knob | 34 | 34 | 0 | 6100K013 | R17-S-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF241118008 | Transfer switch | 150 | 30 | 120 | 6100KDP02 | BOX2-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF241118008 | Transfer switch | 120 | 28 | 92 | 6100K013 | R61-J-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF241118008 | Transfer switch | 92 | 92 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7323482
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF250310001 | Hinge CL209-1 Stainless Steel | 750 | 750 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562540
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 205004178 | ø10 Flat pad Stainless steel | 152 | 152 | 0 | free_stock | R58-B--RMU/\-BULK_SEP | inventory | 2025-11-03 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 8DF.0818.1139 | Lifting Lugs (05mm Stainless Steel-304) | 304 | 304 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-21 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7485825
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 205042612 | φ3.2*16 Cotter pin Stainless steel | 152 | 66 | 86 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581647
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 205042612 | φ3.2*16 Cotter pin Stainless steel | 86 | 60 | 26 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7591044
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 205042612 | φ3.2*16 Cotter pin Stainless steel | 26 | 26 | 0 | 6100K015 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7592476
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 13-LED24Y | 24V BA9S LED LAMP GREEN | 456 | 301 | 155 | 6100K013 | R57-G-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 13-LED24Y | 24V BA9S LED LAMP GREEN | 155 | 155 | 0 | free_stock | R57-O-1-K11B_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1054 | Lower door hook | 456 | 419 | 37 | 6100K013 | 1-1-1-1 | consumption | 2025-09-18 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7406398
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1054 | Lower door hook | 37 | 37 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-21 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7476749
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 13-LED24K | 24V BA9S LED LAMP RED | 456 | 259 | 197 | free_stock | R57-G-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 13-LED24K | 24V BA9S LED LAMP RED | 197 | 197 | 0 | 6100K012B | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1046 | Lock Tongue | 456 | 76 | 380 | 6100K013 | BOX6-1-1-K013_SEP | consumption | 2025-10-26 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Pick | 8332431
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1046 | Lock Tongue | 380 | 50 | 330 | 6100K013 | 1-1-1-1 | consumption | 2025-10-26 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 8335206
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205040971 | φ4*12 Waterproof blind rivets Stainless steel | 4864 | 792 | 4072 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 8296210
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205040971 | φ4*12 Waterproof blind rivets Stainless steel | 4072 | 380 | 3692 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 8298399
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205040971 | φ4*12 Waterproof blind rivets Stainless steel | 3692 | 3692 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-10-26 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 8329482
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF240510040 | EVT (13800/√3/3.25/√3) | 456 | 456 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-17 | Others | Automated: Replaced DF250902001 by DF240510040. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7370412
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU0000000005 | fault indicator (IKI-101light) | 152 | 152 | 0 | 6100K013 | PLT5-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000136 | Operating handle | 152 | 152 | 0 | 6100K013 | BOX12-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10162 | FERRULE TUBE, WHITE , INNER DIA 3.5MM (1.5 WIRE),200 MTRS,KSS | 1650 | 50 | 1600 | free_stock | IFLR-1-1-MVBM_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1052 | Left and right door hooks | 912 | 838 | 74 | 6100K013 | 1-1-1-1 | consumption | 2025-09-18 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7406397
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1052 | Left and right door hooks | 74 | 74 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-21 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7476748
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000220 | UK-2.5B Fixing (E/UK) | 2100 | 2100 | 0 | 6100K013 | R17-A-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1053 | Upper door hook | 456 | 419 | 37 | 6100K013 | 1-1-1-1 | consumption | 2025-09-18 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7406399
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1053 | Upper door hook | 37 | 37 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-21 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7476750
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000221 | Flashlight (LED T5) | 150 | 150 | 0 | 6100K024 | PO-SEP-8335-[2] | GR_in_process | 2025-12-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Saeed Aziz Alsomali Trading Est | SRMU 3L (350) & 2L1T (200) units (LED lamps) | 350 | 02-11-2025
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000221 | Flashlight (LED T5) | 152 | 152 | 0 | 6100K024 | PO-SEP-8335-[2] | GR_in_process | 2025-12-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Saeed Aziz Alsomali Trading Est | SRMU 3L (350) & 2L1T (200) units (LED lamps) | 350 | 02-11-2025
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205039106 | M10 Hex nuts Stainless steel | 1216 | 1216 | 0 | 6100K013 | 1-1-1-1 | inventory | 2025-11-03 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205041101 | Door Bolt 5 Inches Stainless steel | 304 | 304 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562529
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF209001750 | Dixation Hook Q235A | 152 | 152 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562537
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF209001751 | Buckle A104 Stainless Steel Single hole φ12 | 304 | 304 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581666
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF211001964 | φ10-30 large flat pad Stainless steel | 1216 | 1216 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562526
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF240110385 | M24 Gran head nylon | 304 | 132 | 172 | 6100K013 | 1-1-1-1 | consumption | 2025-10-26 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 8329492
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000259 | UK-2.5B voltage terminal partition (D-UK2.5) | 1200 | 250 | 950 | 6100K013 | R53-R-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF240510054 | Temperature Sensor (JWB/PT-100-03) | 150 | 150 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7323452
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | DF240510027 | Rail | 118.56 | 118.56 | 0 | 6100K013 | PLT7-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF240510061 | Relay (RXM2LB2BD) Including base and buckle | 152 | 152 | 0 | 6100K013 | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | mL | DF240603039 | Thread sealant | 22.8 | 22.8 | 0 | 6100K013 | R67-K-1-KDP2_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF241118007 | Unlock the locking knob | 456 | 259 | 197 | 6100K013 | R17-S-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF241118007 | Unlock the locking knob | 197 | 120 | 77 | 6100KDP02 | BOX2-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF241118007 | Unlock the locking knob | 77 | 77 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF241118008 | Transfer switch | 152 | 148 | 4 | 6100K013 | 1-1-1-1 | consumption | 2025-09-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7323482
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF241118008 | Transfer switch | 4 | 4 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-18 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7402129
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF240510040 | EVT (13800/√3/3.25/√3) | 450 | 287 | 163 | 6100K013 | 1-1-1-1 | consumption | 2025-09-17 | Others | Automated: Replaced DF250902001 by DF240510040. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7370412
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF240510040 | EVT (13800/√3/3.25/√3) | 163 | 163 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-18 | Others | Automated: Replaced DF250902001 by DF240510040. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7402094
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU0000000005 | fault indicator (IKI-101light) | 150 | 50 | 100 | 6100K013 | PLT5-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU0000000005 | fault indicator (IKI-101light) | 100 | 42 | 58 | 6100K015 | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU0000000005 | fault indicator (IKI-101light) | 58 | 28 | 30 | 6100K013 | R59-B-1-KDP2_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU0000000005 | fault indicator (IKI-101light) | 30 | 9 | 21 | 6100K013 | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU0000000005 | fault indicator (IKI-101light) | 21 | 21 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7323495
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000136 | Operating handle | 150 | 150 | 0 | 6100K013 | BOX12-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1295 | Door stop tongue | 304 | 304 | 0 | 6100K013 | R58-J-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1296 | Door stop fixing | 304 | 304 | 0 | 6100K013 | INC-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 8DF-128-0009 | Fixed clamp | 152 | 152 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581674
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205040952 | M6*20 Phillips countersunk head screw Stainless steel | 608 | 608 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-21 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7485802
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | DF205041498 | Rectangular Sealing Strip D-07 T-79 EPDM | 568.48 | 568.48 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581664
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF250310001 | Hinge CL209-1 Stainless Steel | 760 | 220 | 540 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562540
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF250310001 | Hinge CL209-1 Stainless Steel | 540 | 540 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581673
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1292 | Copper sets | 304 | 304 | 0 | 6100K013 | R61-A-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1294 | Limiter holder | 304 | 304 | 0 | 6100K013 | R58-J-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000217 | Router (IR302) | 150 | 150 | 0 | 6100KDP02 | R61-R-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000217 | Router (IR302) | 152 | 152 | 0 | 6100KDP02 | R61-R-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | ROH | RMU0000000005 | RMU EFI, Make: KRIES, Ord: 2510201_H007 IKI-10-light-W with LED and Flag | 48 | 48 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7323495
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | RMU000000258 | Name Plate, Stainless Steel | 150 | 150 | 0 | 6100K013 | INC-1-1-K013_SEP | inventory | 2025-11-03 | Outer-enclosure | Automated: Replaced DF250820001 by DF205041560. Automated: Replaced DF205041560 by RMU000000258. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 205004178 | ø10 Flat pad Stainless steel | 48 | 48 | 0 | free_stock | R58-B--RMU/\-BULK_SEP | inventory | 2025-11-03 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 205042612 | φ3.2*16 Cotter pin Stainless steel | 48 | 16 | 32 | 6100K015 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7592476
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 205042612 | φ3.2*16 Cotter pin Stainless steel | 32 | 32 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-10-26 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 8329479
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 8DF-128-0009 | Fixed clamp | 48 | 48 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581674
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1052 | Left and right door hooks | 900 | 886 | 14 | 6100K013 | 1-1-1-1 | consumption | 2025-09-21 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7476748
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1052 | Left and right door hooks | 14 | 14 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7564947
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1053 | Upper door hook | 450 | 443 | 7 | 6100K013 | 1-1-1-1 | consumption | 2025-09-21 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7476750
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1053 | Upper door hook | 7 | 7 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7564949
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1054 | Lower door hook | 450 | 443 | 7 | 6100K013 | 1-1-1-1 | consumption | 2025-09-21 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7476749
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1054 | Lower door hook | 7 | 7 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7564948
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 8DF.0818.1139 | Lifting Lugs (05mm Stainless Steel-304) | 96 | 71 | 25 | 6100K013 | 1-1-1-1 | consumption | 2025-09-21 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7485825
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 8DF.0818.1139 | Lifting Lugs (05mm Stainless Steel-304) | 25 | 25 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-22 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7513371
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1292 | Copper sets | 300 | 300 | 0 | 6100K013 | R61-A-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205039106 | M10 Hex nuts Stainless steel | 1584 | 1584 | 0 | 6100K013 | R55-Q-1-K013_SEP | inventory | 2025-11-03 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205040952 | M6*20 Phillips countersunk head screw Stainless steel | 192 | 192 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-21 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7485802
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205040971 | φ4*12 Waterproof blind rivets Stainless steel | 1536 | 1536 | 0 | 6100K017 | R58-A-1-K12B_SEP | consumption | 2025-10-26 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Pick | 8314531
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205041100 | Door Lock, Stainless Steel ¦ DF205041100 ¦ DFE | 400 | 400 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205041101 | Door Bolt 5 Inches Stainless steel | 96 | 79 | 17 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562529
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF205041101 | Door Bolt 5 Inches Stainless steel | 17 | 17 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581662
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | DF205041498 | Rectangular Sealing Strip D-07 T-79 EPDM | 179.52 | 179.52 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7591060
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF209001750 | Dixation Hook Q235A | 48 | 48 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562537
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF209001751 | Buckle A104 Stainless Steel Single hole φ12 | 96 | 96 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581666
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF211001964 | φ10-30 large flat pad Stainless steel | 384 | 339 | 45 | 6100K013 | 1-1-1-1 | consumption | 2025-09-24 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7562526
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF211001964 | φ10-30 large flat pad Stainless steel | 45 | 45 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581659
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF240510054 | Temperature Sensor (JWB/PT-100-03) | 152 | 152 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7323452
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF250310001 | Hinge CL209-1 Stainless Steel | 240 | 240 | 0 | 6100K013 | 1-1-1-1 | consumption | 2025-09-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Work in Process Material Issue | 7581673
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | RMU000000258 | Name Plate, Stainless Steel | 200 | 200 | 0 | 6100K013 | INC-1-1-K013_SEP | inventory | 2025-11-03 | Outer-enclosure | Automated: Replaced DF250820001 by DF205041560. Automated: Replaced DF205041560 by RMU000000258. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000220 | UK-2.5B Fixing (E/UK) | 2128 | 2128 | 0 | 6100K013 | R17-A-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000290 | Grounding identification 3 φ6 | 1812 | 1812 | 0 | 6100K013 | OF1-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11135 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Red, 105°, 600/1000V , 1 x 91.4 m | 1350 | 35 | 1315 | free_stock | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11135 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Red, 105°, 600/1000V , 1 x 91.4 m | 1315 | 15 | 1300 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11135 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Red, 105°, 600/1000V , 1 x 91.4 m | 1300 | 12 | 1288 | 6100KDP02 | R10-A-1-MVBM_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11135 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Red, 105°, 600/1000V , 1 x 91.4 m | 1288 | 50 | 1238 | 6100K013 | WH2-1-1-K013_SEP | consumption | 2025-09-22 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Material Issue Order_MIO | 7508345
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11136 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Yellow, 105°, 600/1000V, 1 x 91.4 m | 1350 | 50 | 1300 | 6100KDP02 | R11-T-1-MVBM_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11136 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Yellow, 105°, 600/1000V, 1 x 91.4 m | 1300 | 35 | 1265 | free_stock | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11136 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Yellow, 105°, 600/1000V, 1 x 91.4 m | 1265 | 15 | 1250 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11136 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Yellow, 105°, 600/1000V, 1 x 91.4 m | 1250 | 50 | 1200 | 6100K013 | WH2-1-1-K013_SEP | consumption | 2025-09-22 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Material Issue Order_MIO | 7508346
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11137 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Blue, 105°, 600/1000V , 1 x 91.4 m | 13500 | 176 | 13324 | free_stock | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11137 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Blue, 105°, 600/1000V , 1 x 91.4 m | 13324 | 150 | 13174 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11137 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Blue, 105°, 600/1000V , 1 x 91.4 m | 13174 | 127 | 13047 | 6100KDP02 | R10-A-1-MVBM_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11137 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Blue, 105°, 600/1000V , 1 x 91.4 m | 13047 | 50 | 12997 | 6100K013 | WH2-1-1-K013_SEP | consumption | 2025-09-22 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Material Issue Order_MIO | 7508347
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11142 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 23250 | 954 | 22296 | free_stock | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11142 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 22296 | 517 | 21779 | 6100KDP02 | R11-A-1-MVBM_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11142 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 21779 | 258 | 21521 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11142 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 21521 | 9 | 21512 | 6100KDP02 | NEW.FLR-1-1-MVBM_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11142 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 21512 | 50 | 21462 | 6100K013 | WH2-1-1-K013_SEP | consumption | 2025-09-22 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Material Issue Order_MIO | 7508348
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11143 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm, Red, 105°, 600/1000V , 1 x 91.4 m | 525 | 525 | 0 | 6100KDP01 | R57-P-1-KDP1_SEP | consumption | 2025-06-28 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Miscellaneous issue | 6173890
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11143 | Wire harness (Red)BVR-2.5mm² | 532 | 441.6 | 90.4 | 6100KDP01 | R57-P-1-KDP1_SEP | consumption | 2025-06-28 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Miscellaneous issue | 6173890
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11146 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 525 | 525 | 0 | 6100KDP01 | R57-A-1-KDP1_SEP | consumption | 2025-06-28 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Miscellaneous issue | 6173066
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11146 | Wire harness (black)BVR-2.5mm² | 532 | 532 | 0 | 6100KDP01 | R56-I-1-KDP1_SEP | consumption | 2025-06-28 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Miscellaneous issue | 6173065
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11150 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 2700 | 130 | 2570 | free_stock | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11150 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 2570 | 73 | 2497 | 6100KDP02 | R10-A-1-MVBM_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11150 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 2497 | 30 | 2467 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11150 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 2467 | 20 | 2447 | free_stock | R57-S-1-KDP1_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11150 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 2447 | 50 | 2397 | 6100K013 | WH2-1-1-K013_SEP | consumption | 2025-09-22 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Material Issue Order_MIO | 7508351
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11150 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 2397 | 2397 | 0 | 6100KDP01 | R56-I-1-KDP1_SEP | consumption | 2025-06-28 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Miscellaneous issue | 6173703
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11150 | Wire harness (grey)BVR-2.5mm² | 2736 | 2553 | 183 | 6100KDP01 | R56-I-1-KDP1_SEP | consumption | 2025-06-28 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Miscellaneous issue | 6173703
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11152 | Cable, Power, 1 CORE CU/PVC, 4.0 Sq.mm, Red, 105°, 600/1000V , 1 x 91.4 m | 900 | 50 | 850 | 6100KDP02 | NEW.FLR-1-1-MVBM_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11152 | Cable, Power, 1 CORE CU/PVC, 4.0 Sq.mm, Red, 105°, 600/1000V , 1 x 91.4 m | 850 | 50 | 800 | 6100KDP02 | R10-I-1-MVBM_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11152 | Cable, Power, 1 CORE CU/PVC, 4.0 Sq.mm, Red, 105°, 600/1000V , 1 x 91.4 m | 800 | 50 | 750 | 6100K013 | WH2-1-1-K013_SEP | consumption | 2025-09-22 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Material Issue Order_MIO | 7508352
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11155 | Cable, Power, 1 CORE CU/PVC, 4.0 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 900 | 79 | 821 | 6100KDP02 | R10-J-1-MVBM_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11155 | Cable, Power, 1 CORE CU/PVC, 4.0 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 821 | 50 | 771 | 6100KDP02 | NEW.FLR-1-1-MVBM_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11155 | Cable, Power, 1 CORE CU/PVC, 4.0 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 771 | 50 | 721 | 6100K013 | WH2-1-1-K013_SEP | consumption | 2025-09-22 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | [5 empty] | Material Issue Order_MIO | 7508355
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12086 | Lugs, Terminal Ring, 2.5 Sq.mm ¦ R2-6A ¦ Jeesoon | 2416 | 2416 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12118 | Lugs, Terminal Ring, 4.0 Sq.mm ¦ R5-4SA ¦ Jeesoon | 8758 | 8758 | 0 | free_stock | R14-T-1-MVBM_SEP | inventory | 2025-11-03 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AEA0001 | M 6/8.RS (SpringLoaded) 1SNA115685R1200 | 2212 | 2024 | 188 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AEA0001 | M 6/8.RS (SpringLoaded) 1SNA115685R1200 | 188 | 188 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 2295 | 1800 | 495 | free_stock | R66-H-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 495 | 495 | 0 | 6100KDP01 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AFA0001 | M4/6.SNTS Spring Loaded 1SNA115229R2000 | 2295 | 1845 | 450 | free_stock | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AFA0001 | M4/6.SNTS Spring Loaded 1SNA115229R2000 | 450 | 450 | 0 | 6100KDP01 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block OTTA 6-T-P/P - 0790462 | 4012 | 3886 | 126 | free_stock | R56-R-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block OTTA 6-T-P/P - 0790462 | 126 | 126 | 0 | 6100K023 | R53-R-1-K013_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 6550 | 5890 | 660 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 660 | 250 | 410 | free_stock | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 410 | 100 | 310 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 310 | 50 | 260 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 260 | 10 | 250 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8129027
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 16264 | 8750 | 7514 | free_stock | R59-G-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 7514 | 4400 | 3114 | 6100KDP01 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 3114 | 3114 | 0 | free_stock | PLT-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 22 | 16 | 6 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 49 | 45 | 4 | 6100KDP01 | R57-J-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 4 | 4 | 0 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 51 | 47 | 4 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 4 | 4 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 8619 | 6540 | 2079 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 03366 | STEEL RIVETS T22205/4.8 TS | 1218 | 1070 | 148 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 525 | 486 | 39 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 39 | 5 | 34 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 34 | 4 | 30 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8100052
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 07686 | WASHER AC EL DIN137 T22120/8 A | 20 | 20 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 07853 | HEX. HEAD BOLT T21000/3X16 | 30 | 30 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 07934 | TOMMY HEAD SCREW ACC T21010/M3x6 | 196 | 196 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 07940 | TOMMY HEAD SCREW ACC T21010/M3X20 | 63 | 63 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 07959 | TOMMY HEAD SCREW FULL THREAD T21010/4X25 | 300 | 300 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08017 | TOMMY HEAD SCREW ACC T21010/M4x22 | 190 | 154 | 36 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08448 | SQUARE FASTENING NUT TS ACC T21597/5 | 204 | 140 | 64 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08448 | SQUARE FASTENING NUT TS ACC T21597/5 | 64 | 4 | 60 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 245 | 204 | 41 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 41 | 5 | 36 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8120251
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 36 | 5 | 31 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8132315
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 31 | 5 | 26 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8132339
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 26 | 5 | 21 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140308
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 21 | 5 | 16 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140341
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 16 | 5 | 11 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8150179
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 11 | 5 | 6 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8150338
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08856 | WASHER STEEL T22100/ 6.4 | 204 | 140 | 64 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08856 | WASHER STEEL T22100/ 6.4 | 64 | 4 | 60 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 09011 | LOCK NUT T21192/M3N - DIN 985 A2K | 20 | 20 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 09021 | SELF-LOCKING HEX. NUT,T21192/M10 (LOCAL) | 408 | 288 | 120 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 09601 | WASHER, FLAT ACC T22000/3.2X7 | 294 | 210 | 84 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 09929 | STEEL SPRING WASHER ACC T22104/10 | 72 | 72 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 09947 | SPRING WASHER ACC T22104/6 | 16 | 6 | 10 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1000057457 | WASHER CU AL M10 | 51 | 36 | 15 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 12980 | COUNTERSUNK STEEL SCREW T21065/M6X14 | 102 | 102 | 0 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 12989 | COUNTERSUNK STEEL SCREW T21065/M8X30 | 102 | 84 | 18 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16301 | RIVET T22213/4 | 216 | 194 | 22 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16304 | RIVET TT ALUMINUM T22213/5 | 45 | 45 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 99 | 86 | 13 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 13 | 2 | 11 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8082405
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 11 | 1 | 10 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8120254
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 10 | 1 | 9 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8120287
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 9 | 2 | 7 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140311
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 7 | 2 | 5 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140302
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 357 | 303 | 54 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 54 | 7 | 47 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8082411
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 47 | 7 | 40 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140314
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 40 | 7 | 33 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140347
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1815230000 | 5Pole Plug 2.5mm-1815230000-Cont-loop | 50 | 43 | 7 | free_stock | R57-O-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1815230000 | 5Pole Plug 2.5mm-1815230000-Cont-loop | 7 | 7 | 0 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1855030000 | 6Pole Plug 4mm-1855030000-AC looping | 51 | 51 | 0 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611400R1001 | PILOT LIGHT#ML1-100R | 48 | 48 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611400R1002 | PILOT LIGHT#ML1-100G | 48 | 48 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611400R1003 | PILOT LIGHT#ML1-100Y | 52 | 50 | 2 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611400R1003 | PILOT LIGHT#ML1-100Y | 2 | 2 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611400R1005 | PILOT LIGHT#ML1-100W | 108 | 90 | 18 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611400R1005 | PILOT LIGHT#ML1-100W | 18 | 2 | 16 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611605R1100 | HOLDER#MCBH-00 | 250 | 230 | 20 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611605R1100 | HOLDER#MCBH-00 | 20 | 5 | 15 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611605R1100 | HOLDER#MCBH-00 | 15 | 2 | 13 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611621R1051 | LAMP BLOCK#MLBL-05R | 48 | 48 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611621R1052 | LAMP BLOCK#MLBL-05G | 48 | 48 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611621R1053 | LAMP BLOCK#MLBL-05Y | 52 | 50 | 2 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611621R1053 | LAMP BLOCK#MLBL-05Y | 2 | 2 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611621R1055 | LAMP BLOCK#MLBL-05W | 108 | 90 | 18 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611621R1055 | LAMP BLOCK#MLBL-05W | 18 | 2 | 16 | 6100K019 | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611621R1055 | LAMP BLOCK#MLBL-05W | 16 | 2 | 14 | 6100K019 | R14-B-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8069873
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611621R1055 | LAMP BLOCK#MLBL-05W | 14 | 2 | 12 | 6100K019 | R14-B-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8070537
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 250 | 225 | 25 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 25 | 5 | 20 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 20 | 5 | 15 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 15 | 2 | 13 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 13 | 5 | 8 | 6100K019 | R16-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8069098
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 8 | 3 | 5 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8070543
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 5 | 2 | 3 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8070540
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 3 | 1 | 2 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8071511
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 250 | 230 | 20 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 20 | 5 | 15 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 15 | 2 | 13 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 13 | 5 | 8 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8069101
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 8 | 3 | 5 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8070549
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 5 | 2 | 3 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8070546
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 3 | 1 | 2 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8071514
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SNA206394R0200 | *** USE MV-1SNA206394R0200 *** | 408 | 336 | 72 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SNA206394R0200 | *** USE MV-1SNA206394R0200 *** | 72 | 48 | 24 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SNA206394R0200 | *** USE MV-1SNA206394R0200 *** | 24 | 8 | 16 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8070477
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SNA206394R0200 | *** USE MV-1SNA206394R0200 *** | 16 | 8 | 8 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8071505
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SNA234000R0200 | TERMINAL MARKING,RC810,VERTICAL,1-10 | 510 | 410 | 100 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SNA234000R0200 | TERMINAL MARKING,RC810,VERTICAL,1-10 | 100 | 10 | 90 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SNK900654R0000 | SC-JB8-4 Short circuit bridges - Yellow | 153 | 144 | 9 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SNK900654R0000 | SC-JB8-4 Short circuit bridges - Yellow | 9 | 4 | 5 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SNK900654R0000 | SC-JB8-4 Short circuit bridges - Yellow | 5 | 3 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR000474F0001 | BLOCK | 100 | 100 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR002047G0001 | COMPLETE ASSEMBLY KIT FOR DIRAK LOCKUP | 51 | 36 | 15 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR002047G0001 | COMPLETE ASSEMBLY KIT FOR DIRAK LOCKUP | 15 | 7 | 8 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR002416G0001 | LOCKUP ROD ASSEMBLY | 51 | 51 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR002428G0001 | LOCKUP ROD ASSEMBLY | 51 | 34 | 17 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR002428G0001 | LOCKUP ROD ASSEMBLY | 17 | 7 | 10 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR002428G0001 | LOCKUP ROD ASSEMBLY | 10 | 2 | 8 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR002428G0001 | LOCKUP ROD ASSEMBLY | 8 | 1 | 7 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8144677
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR008770F0001 | BLOCK PIN | 408 | 272 | 136 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR008770F0001 | BLOCK PIN | 136 | 136 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7600732P0101 | SPACER TUBE | 102 | 84 | 18 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7601387P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Short | 51 | 50 | 1 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7601387P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Short | 1 | 1 | 0 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7601389P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Long | 51 | 49 | 2 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7601389P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Long | 2 | 2 | 0 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7602006R0101 | TIE ROD W800 CABLE COMPT. | 102 | 70 | 32 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7602006R0101 | TIE ROD W800 CABLE COMPT. | 32 | 32 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7607280R0101 | HINGE WITHOUT FASTENERS | 561 | 385 | 176 | free_stock | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7608266P0101 | CONNECTION PIECE tublar GCE8005046R0101 | 30 | 30 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB000002-FDV | MIMIC DIAGRAM, INCOMER-2W,VT | 3 | 3 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB000003-FDX | MIMIC , OUTGOING WITH EARTHING | 43 | 36 | 7 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB000003-FDX | MIMIC , OUTGOING WITH EARTHING | 7 | 2 | 5 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB000003-FDX | MIMIC , OUTGOING WITH EARTHING | 5 | 1 | 4 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB000004-BTE | MIMIC BUS SEC WITH EARTHG ON RIGHT SIDE | 2 | 1 | 1 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB000004-BTE | MIMIC BUS SEC WITH EARTHG ON RIGHT SIDE | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB000007-BME | MIMIC, BUS MET. & EARTHING-2W,VT | 1 | 1 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB000009-BRM | MIMIC , BUS RISER & MET.-2W,VT | 2 | 1 | 1 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB000009-BRM | MIMIC , BUS RISER & MET.-2W,VT | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010005P0102 | SHROUD, LEFT W1000 | 9 | 9 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010005P0103 | SHROUD, LEFT W800 | 129 | 87 | 42 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010005P0103 | SHROUD, LEFT W800 | 42 | 42 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010006P0102 | SHROUD, RIGHT W1000 | 9 | 9 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010006P0103 | SHROUD, RIGHT W800 | 129 | 87 | 42 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010006P0103 | SHROUD, RIGHT W800 | 42 | 42 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 144 | 99 | 45 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 45 | 3 | 42 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 42 | 3 | 39 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8082423
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 39 | 3 | 36 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8096132
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 36 | 3 | 33 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8096141
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 33 | 3 | 30 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108515
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 30 | 3 | 27 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108752
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 27 | 3 | 24 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8120194
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 24 | 3 | 21 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8120260
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 21 | 3 | 18 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8132365
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 18 | 3 | 15 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140305
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 15 | 3 | 12 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140365
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010025P0101 | HINGE COMPONENT #2 | 288 | 198 | 90 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010025P0101 | HINGE COMPONENT #2 | 90 | 42 | 48 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010029P0122 | CVI DIVIDER, 12-17.5kV, Set 1B (11425) | 46 | 34 | 12 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010029P0122 | CVI DIVIDER, 12-17.5kV, Set 1B (11425) | 12 | 4 | 8 | 6100KDP01 | R16-B-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010029P0122 | CVI DIVIDER, 12-17.5kV, Set 1B (11425) | 8 | 1 | 7 | 606PD013 | R14-I-1-PD\-13/MV_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010032P0101 | CT PLATE,UPPER,W1000 (PAINT RAL7035-STD) | 5 | 5 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010033P0101 | CT MOUNTING PLATE, LOWER, W1000, 3150A | 5 | 5 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010037P0101 | STRENGHTENING SHEET 13.8KV/24KV | 96 | 78 | 18 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010037P0101 | STRENGHTENING SHEET 13.8KV/24KV | 18 | 12 | 6 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010037P0102 | STRENGTHENING SHEET FOR 40KA PANEL | 6 | 4 | 2 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010075P0101 | PARTITION PLATE UPPER CT W800 SS STL | 43 | 33 | 10 | 6100KDP01 | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010076P0101 | COVER FOR PARTITION PLATE | 43 | 33 | 10 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 189.85 | 155.21 | 34.64 | free_stock | R66-H-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 34.64 | 34.64 | 0 | free_stock | R16-L-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010138P0102 | PROTECTIVE COVER W800 | 43 | 35 | 8 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010138P0102 | PROTECTIVE COVER W800 | 8 | 3 | 5 | free_stock | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010138P0103 | PROTECTIVE COVER W1000 | 5 | 5 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010138P0120 | Cover for push button rod | 48 | 48 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010145P0102 | DOOR STOPPER ROD 8 MM DIA. | 51 | 42 | 9 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0101 | HEX. BOLT M10X20 POLYAMIDE | 294 | 240 | 54 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0101 | HEX. BOLT M10X20 POLYAMIDE | 54 | 12 | 42 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0101 | HEX. BOLT M10X20 POLYAMIDE | 42 | 6 | 36 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8076603
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 147 | 120 | 27 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 27 | 6 | 21 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 21 | 3 | 18 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8071009
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 18 | 3 | 15 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108554
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 15 | 3 | 12 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108755
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 12 | 3 | 9 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140299
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 9 | 3 | 6 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140371
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 6 | 3 | 3 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8150218
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 3 | 3 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8150242
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0103 | HEX. BOLT M10X30 POLYAMIDE | 129 | 123 | 6 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0104 | HEX. BOLT M10X40 POLYAMIDE | 18 | 18 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 47 | 38 | 9 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 9 | 1 | 8 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8082432
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 8 | 1 | 7 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8115338
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 7 | 1 | 6 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8115353
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 6 | 1 | 5 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140293
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 5 | 1 | 4 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140374
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010301P0111 | Label printed in Trafolite 200 x 100 | 51 | 42 | 9 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010366P0109 | Self tapping screw pan head M4x5mm SS | 2550 | 2550 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010378P0110 | SEC.FEMALE CONTACTS 1.5,W.SLEEVES 50X | 2550 | 1800 | 750 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010378P0110 | SEC.FEMALE CONTACTS 1.5,W.SLEEVES 50X | 750 | 750 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010378P0112 | SEC. FEMALE CONTACT PIN 2.5MM | 2300 | 1400 | 900 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010378P0112 | SEC. FEMALE CONTACT PIN 2.5MM | 900 | 900 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 99 | 82 | 17 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 17 | 2 | 15 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 15 | 2 | 13 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8085895
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 13 | 2 | 11 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8115484
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 11 | 2 | 9 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8131737
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 9 | 2 | 7 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140284
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 7 | 2 | 5 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140377
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010402R0103 | LABELS FOR SHUTTERS BUSBAR-CABLE -FEEDER | 47 | 34 | 13 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010489P0101 | FLAT BRAIDED, 16SQMM. TIN(13.8kV)6mmdia | 159 | 105 | 54 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010489P0102 | FLAT BRAIDED CONNECTOR, 16 SQMM. TINNED | 48 | 40 | 8 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5112XFS00000 | VT 3Nos PRIMARY FUSE 17.5kV, 3A, SIBA.VT PRIMARY FUSE FOR 17.5kV UG ZS1 Fuse length : 192 mm Fuse dia : 53 mm Rated Voltage: 17.5kV Rated Current: 3A Rated breaking current : 31.5 kA Frequency: 60 Hz Fuse make : SIBA Type: 30 179 11.3 | 18 | 12 | 6 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5112XFS00000 | VT 3Nos PRIMARY FUSE 17.5kV, 3A, SIBA.VT PRIMARY FUSE FOR 17.5kV UG ZS1 Fuse length : 192 mm Fuse dia : 53 mm Rated Voltage: 17.5kV Rated Current: 3A Rated breaking current : 31.5 kA Frequency: 60 Hz Fuse make : SIBA Type: 30 179 11.3 | 6 | 6 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 40 | 13 | 27 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 27 | 1 | 26 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-13 | A |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8082438
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 26 | 1 | 25 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-14 | A |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8107710
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 25 | 1 | 24 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-15 | A |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8132336
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB52333VW6CN00 | VD4/P 171240-p210-125VDC (1VCD400222) | 3 | 2 | 1 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB52371V06CN00 | VD4/P 173225-p275-125VDC (1VCD400222) | 5 | 5 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 48 | 39 | 9 | free_stock | R66-B-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 9 | 4 | 5 | 6100K019 | R66-B-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 5 | 2 | 3 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | A |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 3 | 1 | 2 | 6100K019 | R16-L-1-K019_SEP | consumption | 2025-10-15 | A |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8127541
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 2 | 1 | 1 | 6100K019 | R16-L-1-K019_SEP | consumption | 2025-10-15 | A |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8131740
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 1 | 1 | 0 | 6100K019 | R16-L-1-K019_SEP | consumption | 2025-10-16 | A |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8144845
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5320XDB1XN02 | DIGITAL VOLTMETER, Cl 1.0, 3PH4W, 5-500V, 60Hz, 150% Un CONT, 3 LINE DISPLAY LED, MODBUS ¦ SECURE DPM 96 V300 | 3 | 3 | 0 | 6100K019 | R16-L-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | LL10-W | ABB_LL10-W / LL10-W, AC/DC90-264V 50/60HZ | 51 | 51 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV | Automated: Replaced 1YAB53301XIX0000 by LL10-W. | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 51 | 44 | 7 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 7 | 7 | 0 | 6100KDP01 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXCX0100 | BREAKER CONTROL SWITCH (Comelectric)Breaker Control Switch3-Pole, 3-Position & spring returnDim: 51 X 51 mm Padlockable handle:Colour : Red YellowFront plate:Text Engrave : OPEN- NORMAL-CLOSELettering plate:Text Engrave : BREAKER CONTROL SWITCH Ordering Code: R601 SAM303 011 01-L078+48-30309T133 | 48 | 44 | 4 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXCX0100 | BREAKER CONTROL SWITCH (Comelectric)Breaker Control Switch3-Pole, 3-Position & spring returnDim: 51 X 51 mm Padlockable handle:Colour : Red YellowFront plate:Text Engrave : OPEN- NORMAL-CLOSELettering plate:Text Engrave : BREAKER CONTROL SWITCH Ordering Code: R601 SAM303 011 01-L078+48-30309T133 | 4 | 1 | 3 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXCX0220 | OFF-EMER-LOCAL-REMOTE 4P4P, PADLCK (COMELECTRIC), Breaker Mode Selector Switch 4-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH Ordering Code: R601 SA408 067 27-L071+48-40513T134 20A, 4 pos Stayput 4 contacts in each Pos, TYPE 1: Engraving: OFF-EMERGENCY-LOCAL-REMOTE TOP PLATE: BREAKER MODE PADLOCK SAP PART NO: 1YAB5331XXCX0220 | 40 | 40 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXCX0300 | SPACE HEATER SEL. SWITCH ( COMELECTRIC )R601 SA302 112-W051+48-31090T124 20A, 3Positions without internal links 2pole,3position Engraving (OFF/Auto/Manual) OFF-zero contacts AUTO-2 contacts MANUAL-2contacts TOP PLATE (SPACE HEATER) Single hole mounting FT6 | 51 | 48 | 3 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXCX0300 | SPACE HEATER SEL. SWITCH ( COMELECTRIC )R601 SA302 112-W051+48-31090T124 20A, 3Positions without internal links 2pole,3position Engraving (OFF/Auto/Manual) OFF-zero contacts AUTO-2 contacts MANUAL-2contacts TOP PLATE (SPACE HEATER) Single hole mounting FT6 | 3 | 1 | 2 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC )R601 SAM201 071-W051+48-20547T123 20A SPRING RETAIN WITHOUT INTERNAL LINKS 2 POSITION,1POLE Engraving (OFF-TEST) TOP PLATE Engraving (LAMP TEST) | 51 | 48 | 3 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC )R601 SAM201 071-W051+48-20547T123 20A SPRING RETAIN WITHOUT INTERNAL LINKS 2 POSITION,1POLE Engraving (OFF-TEST) TOP PLATE Engraving (LAMP TEST) | 3 | 1 | 2 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC )R601 SAM201 071-W051+48-20547T123 20A SPRING RETAIN WITHOUT INTERNAL LINKS 2 POSITION,1POLE Engraving (OFF-TEST) TOP PLATE Engraving (LAMP TEST) | 2 | 1 | 1 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8071517
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXKX0700 | Auto Re-close IN-OUT Selector Switch(COMELECTRIC),"Auto Re-close IN-OUT Selector Switch 4-Pole, 2-Positions Dim: 51 X 51 mm Padlockable handle: Colour : Black Front plate: Text Engrave : IN-OUT Lettering plate Text Engrave : A/R IN-OUT SWITCH" CA10-A723-SA0030-E 1YAB5331XXKX0700 | 41 | 20 | 21 | 6100K018 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXKX0700 | Auto Re-close IN-OUT Selector Switch(COMELECTRIC),"Auto Re-close IN-OUT Selector Switch 4-Pole, 2-Positions Dim: 51 X 51 mm Padlockable handle: Colour : Black Front plate: Text Engrave : IN-OUT Lettering plate Text Engrave : A/R IN-OUT SWITCH" CA10-A723-SA0030-E 1YAB5331XXKX0700 | 21 | 16 | 5 | 6100k016 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5332XXAXB000 | PB Black 1NO+1NC-22 dia-1SFA611100R4076 | 60 | 20 | 40 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5334XXAX1000 | FT-1 SW-Type 129A514G01 | 8 | 8 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5335XXAX1100 | COMBIFLEX TERMINAL BASE RX 2H -5619625-A | 243 | 243 | 0 | free_stock | R11-A-1-MVBM_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5335XXAX1200 | COMBIFLEX TERMINAL BASE RX4 (4U 12C) | 14 | 14 | 0 | free_stock | R11-A-1-MVBM_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXAA2E00 | MCB 3A AC -2P,2CDS252001R0317 | 5 | 5 | 0 | free_stock | R16-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXAA2G00 | MCB S 202-K6 6A AC -2P - 2CDS252001R0377 | 103 | 90 | 13 | free_stock | R16-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXAA2G00 | MCB S 202-K6 6A AC -2P - 2CDS252001R0377 | 13 | 1 | 12 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXAA2L00 | MCB 16A AC -2P - 2CDS252001R0467 | 5 | 4 | 1 | free_stock | R16-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXAA2L00 | MCB 16A AC -2P - 2CDS252001R0467 | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXAB2G00 | MCB 6A DC 2P S202M-K6UC -2CDS272061R0377 | 300 | 280 | 20 | free_stock | R16-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXAB2G00 | MCB 6A DC 2P S202M-K6UC -2CDS272061R0377 | 20 | 6 | 14 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXACG000 | Aux contact 2NC, S2C-HO2L-for MCB Order # 2CDS200936R0003 | 245 | 228 | 17 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXACG000 | Aux contact 2NC, S2C-HO2L-for MCB Order # 2CDS200936R0003 | 17 | 3 | 14 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXACG000 | Aux contact 2NC, S2C-HO2L-for MCB Order # 2CDS200936R0003 | 14 | 5 | 9 | 6100K019 | R14-B-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8071520
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXACH000 | Aux contact 1NO+1NC MCB -2CDS200936R0001 | 340 | 340 | 0 | free_stock | R16-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXACJ000 | S2C-H01 - 1NC- Bottom Auxiliary Contact 2CDS200970R0031 | 75 | 75 | 0 | free_stock | R16-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XAJXXN00 | RF-4R_125Vdc_4 C/O_LED | 85 | 71 | 14 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XAJXXN00 | RF-4R_125Vdc_4 C/O_LED | 14 | 7 | 7 | free_stock | R16-L-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XAJXXN00 | RF-4R_125Vdc_4 C/O_LED | 7 | 1 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XAJXXN01 | BJ-8RP_Bistable_125Vdc_8 C/O | 40 | 34 | 6 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XAJXXN01 | BJ-8RP_Bistable_125Vdc_8 C/O | 6 | 2 | 4 | free_stock | R16-L-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XAJXXN01 | BJ-8RP_Bistable_125Vdc_8 C/O | 4 | 1 | 3 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8069879
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XAJXXN01 | BJ-8RP_Bistable_125Vdc_8 C/O | 3 | 1 | 2 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8070552
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XBLXXN00 | MVAJ101 RA 0802_ 125VDC (8 NO + 2 NC) | 2 | 2 | 0 | free_stock | R16-L-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XCLXXN00 | MVAJ205 ,125VDC ) CAT No. MVAJ205TB0808A | 2 | 2 | 0 | free_stock | R16-L-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XDAXXN00 | RXMVB 4, RK 251 401-AP | 8 | 7 | 1 | free_stock | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XDAXXN00 | RXMVB 4, RK 251 401-AP | 1 | 1 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XDAXXN01 | RXMVB2, RK 251 204-AP | 13 | 13 | 0 | free_stock | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XEAXXN00 | RXMB1 6NO_110-125VDC-1MRK 000 863-AN | 16 | 14 | 2 | free_stock | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XEAXXN00 | RXMB1 6NO_110-125VDC-1MRK 000 863-AN | 2 | 2 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XFAXXN00 | RXKL1, TYPE: 1MRK 000 066-AB | 5 | 5 | 0 | free_stock | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XIAXXN00 | RXSF1_DC110-125V-MV RK 271 019-AN | 150 | 150 | 0 | free_stock | R14-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XJAXXN00 | THREE PHASE FUSE SUPERVISION RELAY Type : RXBA4 (ABB) ORDER NO. : RK 428 004-AA CONTACTS : 2 CHANGE OVER SELF RESET | 6 | 1 | 5 | 6100K019 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 1617 | 1318 | 299 | free_stock | R59-G-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 299 | 299 | 0 | 6100KDP01 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AMC0001 | Feed-through terminal block,ZT 4/4AN/2 .Base Terminal Plug AC-DC-4mm 1848350000 | 1530 | 1240 | 290 | free_stock | R57-G-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AMC0001 | Feed-through terminal block,ZT 4/4AN/2 .Base Terminal Plug AC-DC-4mm 1848350000 | 290 | 250 | 40 | 6100KDP01 | R57-G-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AMC0001 | Feed-through terminal block,ZT 4/4AN/2 .Base Terminal Plug AC-DC-4mm 1848350000 | 40 | 30 | 10 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 612 | 516 | 96 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 96 | 96 | 0 | 6100KDP01 | R57-J-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 742 | 588 | 154 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 154 | 150 | 4 | 6100KDP01 | R57-J-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | RMU000000260 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 510 | 82 | 428 | 6100K013 | R53-R-1-K013_SEP | inventory | 2025-11-03 | LV | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CBA0000 | FEM8T6 End Sections Grey 1SNA215266R0100 | 765 | 720 | 45 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CBA0000 | FEM8T6 End Sections Grey 1SNA215266R0100 | 45 | 45 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CEA0000 | FEMR8 End Sections Grey 1SNA116987R0200 | 1020 | 500 | 520 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CEA0000 | FEMR8 End Sections Grey 1SNA116987R0200 | 520 | 460 | 60 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CEA0000 | FEMR8 End Sections Grey 1SNA116987R0200 | 60 | 60 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CFA0000 | FEM6 End Sections Grey - 1SNA118368R1600 | 510 | 480 | 30 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CFA0000 | FEM6 End Sections Grey - 1SNA118368R1600 | 30 | 30 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CMC0000 | Terminal End Plate 1848360000-Wiedmuller | 204 | 172 | 32 | free_stock | R57-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CMC0000 | Terminal End Plate 1848360000-Wiedmuller | 32 | 32 | 0 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CPC0000 | Terminal End Plate 1816110000-Wiedmuller | 204 | 167 | 37 | free_stock | R57-O-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CPC0000 | Terminal End Plate 1816110000-Wiedmuller | 37 | 37 | 0 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CTC0000 | Terminal End Plate 1816070000-Wiedmuller | 106 | 82 | 24 | free_stock | R57-O-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CTC0000 | Terminal End Plate 1816070000-Wiedmuller | 24 | 24 | 0 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 2550 | 2050 | 500 | free_stock | R56-R-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 500 | 500 | 0 | 6100K023 | R17-A-1-K013_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355DFA0000 | RC610-VerticalMarking 1SNA233060R0400 | 459 | 432 | 27 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355DFA0000 | RC610-VerticalMarking 1SNA233060R0400 | 27 | 27 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 1530 | 875 | 655 | 6100K011B | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 655 | 655 | 0 | 6100K006 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355DXC0000 | 460660001 DEK 5 FSZ 1-10 Z-Terminal 1-10 | 20600 | 16600 | 4000 | free_stock | R57-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355DXC0000 | 460660001 DEK 5 FSZ 1-10 Z-Terminal 1-10 | 4000 | 3000 | 1000 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355DXC0000 | 460660001 DEK 5 FSZ 1-10 Z-Terminal 1-10 | 1000 | 400 | 600 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355EEA0000 | JUMPER BAR "BJS8" 20 Poles | 102 | 96 | 6 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355EEA0000 | JUMPER BAR "BJS8" 20 Poles | 6 | 6 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355EFA0000 | PC61-CombTypeJumprBar10 1SNA163311R2200 | 204 | 192 | 12 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355EFA0000 | PC61-CombTypeJumprBar10 1SNA163311R2200 | 12 | 12 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 408 | 364 | 44 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 44 | 44 | 0 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355HAB0000 | Zack Strip-Vertical(1-10) - 1053027:0001 | 612 | 580 | 32 | free_stock | R57-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355HAB0000 | Zack Strip-Vertical(1-10) - 1053027:0001 | 32 | 12 | 20 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355HAB0000 | Zack Strip-Vertical(1-10) - 1053027:0001 | 20 | 6 | 14 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355HAB0001 | Zack Strip-Vertical(11-20)- 1053027:0011 | 612 | 536 | 76 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355HAB0001 | Zack Strip-Vertical(11-20)- 1053027:0011 | 76 | 50 | 26 | free_stock | R57-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355HAB0001 | Zack Strip-Vertical(11-20)- 1053027:0011 | 26 | 12 | 14 | 6100K019 | R57-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355HAB0001 | Zack Strip-Vertical(11-20)- 1053027:0011 | 14 | 12 | 2 | 6100K019 | R57-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8069113
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355HAB0001 | Zack Strip-Vertical(11-20)- 1053027:0011 | 2 | 2 | 0 | 6100K019 | R57-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8070564
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355HAB0002 | Zack Strip-Vertical Labeled(21-30) | 408 | 408 | 0 | 6100KDP01 | R57-J-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 306 | 244 | 62 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 62 | 50 | 12 | 6100KDP01 | R57-J-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 12 | 6 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 6 | 4 | 2 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 2 | 2 | 0 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8069885
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355JPC0000 | 6Pole Plug 2.5mm-1815240000-Cont-loop | 204 | 168 | 36 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355JPC0000 | 6Pole Plug 2.5mm-1815240000-Cont-loop | 36 | 36 | 0 | 6100KDP01 | R57-J-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR |  | 1YAB5355JTC0000 | 10Pole Plug 2.5mm-1815280000-Cont-loop | 212 | 164 | 48 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR |  | 1YAB5355JTC0000 | 10Pole Plug 2.5mm-1815280000-Cont-loop | 48 | 40 | 8 | 6100KDP01 | R57-J-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR |  | 1YAB5355JTC0000 | 10Pole Plug 2.5mm-1815280000-Cont-loop | 8 | 4 | 4 | free_stock | R57-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR |  | 1YAB5355JTC0000 | 10Pole Plug 2.5mm-1815280000-Cont-loop | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 612 | 500 | 112 | free_stock | R57-O-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 112 | 100 | 12 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 12 | 12 | 0 | free_stock | R57-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355KPC0000 | Locking ele. 1816130000 for ZT2.5/4AN/2 | 310 | 256 | 54 | free_stock | R57-O-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355KPC0000 | Locking ele. 1816130000 for ZT2.5/4AN/2 | 54 | 50 | 4 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355KPC0000 | Locking ele. 1816130000 for ZT2.5/4AN/2 | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355LMC0000 | Coding element 1856860000 - ZT4/4AN/2 | 408 | 336 | 72 | free_stock | R57-O-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355LMC0000 | Coding element 1856860000 - ZT4/4AN/2 | 72 | 72 | 0 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355LPC0000 | Coding element 1816150000 | 416 | 340 | 76 | free_stock | R57-O-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355LPC0000 | Coding element 1816150000 | 76 | 76 | 0 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355MPC0000 | Strain Relief Wied mulpart # 1816140000 | 310 | 256 | 54 | free_stock | R57-O-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355MPC0000 | Strain Relief Wied mulpart # 1816140000 | 54 | 50 | 4 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355MPC0000 | Strain Relief Wied mulpart # 1816140000 | 4 | 4 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 612 | 507 | 105 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 105 | 105 | 0 | 6100K023 | R53-R-1-K013_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB60050819P0103 | Braided HARNESS TUBE (D40) | 765 | 765 | 0 | free_stock | R67-A-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 51 | 51 | 0 | free_stock | R67-A-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB60050819P0106 | Braided HARNESS TUBE (D30) | 1020 | 1000 | 20 | free_stock | R67-A-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB60050819P0106 | Braided HARNESS TUBE (D30) | 20 | 20 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB60050819P0107 | Braided HARNESS TUBE (D20) | 510 | 500 | 10 | free_stock | R67-A-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB60050819P0107 | Braided HARNESS TUBE (D20) | 10 | 10 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 25541 | HEX.RIVET NUT M10X24 ( 25541 ) | 2109 | 1397 | 712 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 712 | 496 | 216 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 216 | 10 | 206 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 206 | 12 | 194 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8099593
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 194 | 12 | 182 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8099689
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 182 | 12 | 170 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108689
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 170 | 12 | 158 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8128712
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 158 | 12 | 146 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8128748
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 146 | 12 | 134 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8131679
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 134 | 12 | 122 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8131682
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 122 | 12 | 110 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8150185
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 110 | 10 | 100 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8150329
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 100 | 2 | 98 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8150326
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 28100 | SCREW VITE ACTC D7971 T21572/4.2x6.5 | 194 | 194 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 28132 | RETAINING RING ACC. T22414/3.2 | 49 | 49 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 462 | 246 | 216 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 216 | 18 | 198 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 198 | 9 | 189 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8100079
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 189 | 60 | 129 |  | R58-O-1-KDP1_SEP | consumption | 2025-10-23 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Miscellaneous issue | 8277106
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 28373 | LOCK NUT ACC TO T21192/M2.5x0.45 | 102 | 102 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 28452 | FLEXIBLE SPIROID PINS T22513/3X26 | 10 | 10 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 28627 | Rivet NUT ACC T21098/M6 (countersunk) | 628 | 460 | 168 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 28627 | Rivet NUT ACC T21098/M6 (countersunk) | 168 | 13 | 155 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 29823 | TOMMY HEAD SCREW ACC. T21010/M2.5x20 | 102 | 102 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 2CSM258163R0721 | MV MATERIAL MV-AC-SOCKET-WOA 1YAB53305XAX0000 M1363-L | 2 | 1 | 1 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 2TRE123451P0001 | 3 PIN SOCKET SWITCH,13A,250V,BSRDP-I | 3 | 3 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 3WKA014480P0004 | RETAINING_WASHER_DIN6799_6-SPST/A3K | 49 | 49 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 98 | 98 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 3WKA014538P0012 | SPIRAL_PIN_ISO8748_4X20-ST/BK | 98 | 98 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 3WKA014538P0014 | SPIRAL_PIN_ISO8748_4X30-ST/BK | 49 | 49 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 3WKA014618P0001 | SAFETY_GRIPPER_BFK/A_BN13193_4-SPST/PH | 49 | 49 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 3WKA014618P0003 | SAFETY_GRIPPER_BFK/A_BN13193_6-SPST/PH | 49 | 49 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 4CE7000583P0101 | PIN | 49 | 36 | 13 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 4CE7000583P0101 | PIN | 13 | 1 | 12 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8132327
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 500214111 | WASHER T22001/6.8X18 | 51 | 51 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 500673075 | PIN T22681/8X54,5-5 | 184 | 112 | 72 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 500673075 | PIN T22681/8X54,5-5 | 72 | 28 | 44 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 500673075 | PIN T22681/8X54,5-5 | 44 | 4 | 40 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 5022 643 | COVER PROFILE, AP3 | 81.6 | 81.6 | 0 | free_stock | R15-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 1275 | 1200 | 75 | free_stock | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 75 | 25 | 50 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 50 | 25 | 25 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 25 | 25 | 0 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8069116
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 5217 708-3 | M.CONTACT/HAN-E16M/09330162601 | 3 | 2 | 1 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 5217 708-3 | M.CONTACT/HAN-E16M/09330162601 | 1 | 1 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 5217 708-7 | F.CONTACT/HAN-E16F/09330162701 | 3 | 2 | 1 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 5217 708-7 | F.CONTACT/HAN-E16F/09330162701 | 1 | 1 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 593502001 | BUSHING | 56 | 56 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 593503001 | ROLLER | 46 | 28 | 18 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 593503001 | ROLLER | 18 | 7 | 11 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 593503001 | ROLLER | 11 | 1 | 10 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 593509/001 | COMPRESSION SPRING | 95 | 65 | 30 | free_stock | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 593509/001 | COMPRESSION SPRING | 30 | 13 | 17 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 9ABA450060P0004 | NUT_ISO7040_M6-8/A3K | 49 | 35 | 14 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 9ABA450060P0005 | NUT_ISO7040_M8-8/A3K | 102 | 92 | 10 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 9ABA450060P0005 | NUT_ISO7040_M8-8/A3K | 10 | 4 | 6 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 9ABA450060P0005 | NUT_ISO7040_M8-8/A3K | 6 | 2 | 4 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8100058
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 9ADJ100023P0357 | BLIND_RIVET_ISO15979_6,4x16-ST/ST | 204 | 204 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2093 7000-5 | RAYCHEM SHRINKABLE TUBE, BPTM 100/40-A/U | 109.64 | 89.86 | 19.78 | free_stock | R15-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2093 7000-5 | RAYCHEM SHRINKABLE TUBE, BPTM 100/40-A/U | 19.78 | 19.78 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2093 7000-6N | RAYCHEM SHRINKABLE TUBE, BPTM 120/50-A/U | 44.98 | 44.98 | 0 | free_stock | R15-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 50 | 50 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 815 | 620 | 195 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 195 | 100 | 95 | 606PD013 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 95 | 95 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 765 | 665 | 100 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 100 | 100 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 49 | 35 | 14 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 14 | 8 | 6 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 6 | 6 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 49 | 35 | 14 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 14 | 10 | 4 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 4 | 4 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 102 | 72 | 30 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 30 | 23 | 7 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 7 | 7 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-1865-02-W | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 765 | 400 | 365 | 6100K006 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-1865-02-W | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 365 | 365 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-1865-03 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 510 | 510 | 0 | free_stock | R58-G-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-1865-04 | BLACK TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 510 | 110 | 400 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-1865-04 | BLACK TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 400 | 60 | 340 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-1865-05 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 510 | 40 | 470 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-1865-05 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 470 | 20 | 450 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-1865-13 | BLACK TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 510 | 110 | 400 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-1865-13 | BLACK TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 400 | 60 | 340 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAZ21500101 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 87 | 87 | 0 | 6100KDP01 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical | Automated: Replaced AE2000-2150-01 by 1YAZ21500101. | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 66.3 | 66.3 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 1020 | 840 | 180 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 180 | 40 | 140 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 306 | 228 | 78 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 78 | 78 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 49.96 | 36.85 | 13.11 | free_stock | R66-H-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 13.11 | 9 | 4.11 | free_stock | R16-L-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 4.11 | 4.11 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2522-2000-01 | HOOD HAN-E16,09300161520 | 3 | 2 | 1 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2522-2000-01 | HOOD HAN-E16,09300161520 | 1 | 1 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301,HAN-E16 | 3 | 3 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 8 | 4 | 4 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 4 | 2 | 2 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 2 | 2 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2522-2000-03 | CABLE SEALING,PG21, | 3 | 3 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 51 | 45 | 6 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 6 | 6 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2632-2000-33 | Spring for Door Combiflex | 1.02 | 0.96 | 0.06 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2632-2000-33 | Spring for Door Combiflex | 0.06 | 0.02 | 0.04 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 51 | 39 | 12 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 12 | 7 | 5 | 6100KDP01 | WH2-1-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 5 | 5 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 3060 | 2420 | 640 | free_stock | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 640 | 500 | 140 | 6100K023 | R53-R-1-K013_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 140 | 140 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 51 | 3 | 48 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 48 | 1 | 47 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | CDX7005632R1A | EARTHING CONTACT COMPLETE | 102 | 72 | 30 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | CDX7005632R1A | EARTHING CONTACT COMPLETE | 30 | 12 | 18 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | CDX7005632R1A | EARTHING CONTACT COMPLETE | 18 | 2 | 16 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | CDXN010061R1103 | HANDLE COMPLETE | 51 | 34 | 17 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | CDXN010061R1103 | HANDLE COMPLETE | 17 | 7 | 10 | 6100KDP01 | R59-A-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | CDXN010061R1103 | HANDLE COMPLETE | 10 | 2 | 8 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | CDXN010061R1103 | HANDLE COMPLETE | 8 | 1 | 7 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8144757
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 348.3 | 281.9 | 66.4 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 66.4 | 66.4 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 102 | 66 | 36 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 36 | 20 | 16 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 49 | 33 | 16 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 16 | 10 | 6 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-494 | BOLT HEX HEAD M10X35 | 24 | 12 | 12 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-494 | BOLT HEX HEAD M10X35 | 12 | 12 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 144 | 99 | 45 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 45 | 24 | 21 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-659 | BOLT HEX HEAD M20X45 | 48 | 48 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-666 | BOLT HEX HEAD M20X90 | 48 | 48 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2017-659 | BOLT HEX HEAD H D M20X45 | 9 | 6 | 3 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2452-293 | SCREW CROSS REC.HEAD M4X16 | 12 | 8 | 4 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 2944 | 1970 | 974 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 974 | 631 | 343 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 1325 | 914 | 411 | 6100K011B | PLT-1-1-K017_SEP | consumption | 2025-10-18 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8162040
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 411 | 411 | 0 | 6100K008 | R58-A-1-K11B_SEP | consumption | 2025-10-18 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8161201
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 216 | 136 | 80 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 80 | 56 | 24 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-295 | BOLT SOCKET HEAD M4X20 | 14 | 14 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Material Issue | 8296185
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-325 | BOLT SOCKET CAP M5X10 | 18 | 12 | 6 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-325 | BOLT SOCKET CAP M5X10 | 6 | 6 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 107 | 107 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-366 | BOLT SOCKET CAP HEAD M6X12 | 161 | 161 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 125 | 92 | 33 | 6100K011B | R58-H-1-K11B_SEP | consumption | 2025-10-19 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8171503
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 33 | 33 | 0 | 6100K011B | R58-A-1-K017_SEP | consumption | 2025-10-19 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8173342
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-371 | BOLT SOCKET CAP M6X20 | 16 | 6 | 10 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-371 | BOLT SOCKET CAP M6X20 | 10 | 6 | 4 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-372 | BOLT SOCKET CAP M6X25 | 3 | 2 | 1 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-430 | BOLT SOCKET CAP HEAD M6X50 | 9 | 9 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 204 | 132 | 72 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 72 | 48 | 24 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 3783 | 2531 | 1252 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 1252 | 824 | 428 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 2059 | 1447 | 612 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 612 | 341 | 271 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 803 | 803 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-457 | BOLT SOCKET CAP M8X35 | 6 | 2 | 4 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-457 | BOLT SOCKET CAP M8X35 | 4 | 2 | 2 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 98 | 66 | 32 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 32 | 20 | 12 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 144 | 93 | 51 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 51 | 33 | 18 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 312 | 198 | 114 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 114 | 72 | 42 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 1791 | 1281 | 510 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 510 | 420 | 90 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 384 | 384 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 805 | 485 | 320 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 320 | 234 | 86 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-500 | BOLT SOCKET CAP HEAD M10X45 | 720 | 720 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-531 | BOLT SOCKET CAP M12X16 (C.H.) | 48 | 35 | 13 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-531 | BOLT SOCKET CAP M12X16 (C.H.) | 13 | 2 | 11 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 58 | 58 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 12 | 12 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 1412 | 889 | 523 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 523 | 175 | 348 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 534 | 402 | 132 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 132 | 84 | 48 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-542 | BOLT SOCKET CAP HEAD M12X50 | 54 | 54 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-544 | BOLT SOCKET CAP HEAD M12X60 | 105 | 105 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 855 | 543 | 312 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 312 | 180 | 132 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-628 | BOLT SOCKET CAP HEAD M16X40 | 24 | 21 | 3 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 290 | 204 | 86 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 86 | 6 | 80 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 63 | 63 | 0 | 6100K011B | R58-A-1-K11B_SEP | consumption | 2025-10-19 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8170704
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 126 | 86 | 40 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2126 2011-113 | NUT, HEX M4 | 40 | 34 | 6 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 616 | 616 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 1018 | 795 | 223 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 223 | 162 | 61 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 789 | 789 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 459 | 423 | 36 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 36 | 36 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2126 843-1 | RIVET NUT M6 (HEXAGONAL) | 10 | 10 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2151 2062-136 | WASHER FLAT BRIR 4.3X8X0.8 | 321 | 225 | 96 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 1521 | 1000 | 521 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 521 | 374 | 147 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 200 | 132 | 68 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 68 | 44 | 24 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 408 | 264 | 144 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 144 | 96 | 48 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 4944 | 4944 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 3086 | 2081 | 1005 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 1005 | 590 | 415 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 1644 | 1026 | 618 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 618 | 378 | 240 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 225 | 174 | 51 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 51 | 51 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 725 | 503 | 222 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 222 | 177 | 45 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 7295 | 5626 | 1669 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 1669 | 1255 | 414 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 363-1 | WASHER, LOCK 10X5X0.5 | 51 | 51 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 20400 | 15600 | 4800 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 4800 | 2400 | 2400 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 255 | 225 | 30 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 30 | 30 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 51 | 45 | 6 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 6 | 6 | 0 | free_stock | R68-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 306 | 270 | 36 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 36 | 36 | 0 | free_stock | R68-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2641 0087-19 | CABLE LUGS A14-M10 70MM/M10 | 98 | 66 | 32 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2641 0087-19 | CABLE LUGS A14-M10 70MM/M10 | 32 | 16 | 16 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 2448 | 1868 | 580 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 580 | 400 | 180 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 180 | 180 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 102 | 94 | 8 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 8 | 8 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 408 | 382 | 26 | free_stock | R58-G-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 26 | 26 | 0 | free_stock | R66-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 924 0010 | Combiflex wire Socket 1.5mm 1MRK002136-B | 10200 | 8780 | 1420 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 924 0010 | Combiflex wire Socket 1.5mm 1MRK002136-B | 1420 | 1420 | 0 | free_stock | R14-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 924 0020 | Combiflex wire Socket 2.5mm 1MRK002136-E | 6120 | 5160 | 960 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 924 0020 | Combiflex wire Socket 2.5mm 1MRK002136-E | 960 | 960 | 0 | free_stock | R14-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 6 | 6 | 0 | free_stock | R16-L-1-K019_SEP | inventory | 2025-11-03 | B |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0007249P0100 | GREASE ISOPLEX TOPAS,NB52,1kg | 2 | 1.891 | 0.109 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0068009P0100 | BUSHING D8/3 PVC | 21 | 18 | 3 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0305850P0100 | POLYAMID BOLT M6X20 | 95 | 95 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0305871P0100 | HEX BOLT M8X16 DIN 933-POLY | 356 | 241 | 115 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0305871P0100 | HEX BOLT M8X16 DIN 933-POLY | 115 | 5 | 110 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 347 | 254 | 93 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 93 | 2 | 91 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0316044P0100 | HEAD SCREW M8X50, DIN 603-4.3 | 94 | 68 | 26 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 98 | 72 | 26 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 26 | 2 | 24 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8084138
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 24 | 2 | 22 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108488
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 22 | 2 | 20 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108683
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 20 | 2 | 18 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8120212
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 18 | 2 | 16 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8120248
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 16 | 2 | 14 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140320
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 14 | 2 | 12 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140335
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0336970P0100 | BOLT,TAPTITE HEX BOLT M5X12 | 14 | 14 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0336985P0100 | TAPPING SCREW M6X16/6KTHEAD | 12 | 3 | 9 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0352913P0100 | NUT M10 DIN 555-Polyamide | 18 | 18 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0365304P0100 | NUT,HEX.NUT MPG 16 | 3 | 2 | 1 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0365304P0100 | NUT,HEX.NUT MPG 16 | 1 | 1 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0367309P0100 | HEX. NUT M6, DIN 985-6 ( LOCK NUT ) | 16 | 4 | 12 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369010P0100 | RIVET NUT M6X16 WITH GROOVE | 95 | 95 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 2279 | 1755 | 524 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 524 | 46 | 478 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108686
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 478 | 26 | 452 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8099614
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 452 | 26 | 426 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8099698
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 426 | 46 | 380 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8132324
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 380 | 26 | 354 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8128676
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 354 | 26 | 328 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8128745
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 328 | 46 | 282 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8150164
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 282 | 46 | 236 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8150323
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 658 | 10 | 648 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 648 | 12 | 636 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8099593
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 636 | 12 | 624 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8099689
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 624 | 12 | 612 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108689
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 612 | 12 | 600 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8128712
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 600 | 12 | 588 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8128748
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 588 | 12 | 576 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8131679
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 576 | 12 | 564 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8131682
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 564 | 12 | 552 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8150185
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 552 | 10 | 542 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8150329
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 542 | 2 | 540 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8150326
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 1740 | 1740 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 422 | 372 | 50 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 50 | 8 | 42 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 42 | 8 | 34 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108581
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 34 | 8 | 26 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108692
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 26 | 7 | 19 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8099602
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 19 | 17 | 2 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8128673
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 2 | 2 | 0 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8128751
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0401027P0100 | WASHER FLAT 10.5,DIN433-ST | 192 | 192 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0402909P0100 | WASHER POLYAMID, A6.4, DIN 125 | 95 | 95 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0402911P0100 | WASHER POLYAMID, A8.4, DIN 125 | 802 | 609 | 193 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0402911P0100 | WASHER POLYAMID, A8.4, DIN 125 | 193 | 18 | 175 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0402911P0100 | WASHER POLYAMID, A8.4, DIN 125 | 175 | 9 | 166 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8099695
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0402912P0100 | WASHER POLYAMID, A10.5, DIN 125 | 588 | 516 | 72 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0410004P0100 | SPRING RING A3, DIN 127-FST | 26 | 20 | 6 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0412007P0100 | SPRING RING 10 DIN 7980-FST | 120 | 120 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0413160P0100 | RETAINING WASHER VS5 | 49 | 35 | 14 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 155 | 137 | 18 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 18 | 2 | 16 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8084147
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 16 | 4 | 12 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8096138
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 12 | 2 | 10 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108467
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 10 | 2 | 8 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108758
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 8 | 6 | 2 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8120308
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 2 | 2 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8120290
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418203P0100 | WASHER,RETAINING 6, WN418-FST | 184 | 136 | 48 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418204P0100 | WASHER RETAINING 8/WN 418-FST | 57 | 35 | 22 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418205P0100 | WASHER RETAINING 10, WN418-FST | 192 | 140 | 52 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0438403P0100 | SPRG. PIN 2X10 DIN EN 28748 ST | 51 | 51 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0438423P0100 | SPRING PIN 3X16 | 12 | 8 | 4 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0438423P0100 | SPRING PIN 3X16 | 4 | 4 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0438425P0100 | SPRING PIN SLOTTED 3X20 (EQUIV.=28272) | 30 | 30 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0457035P0100 | BLIND RIVET 5X10 AL | 408 | 326 | 82 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0457035P0100 | BLIND RIVET 5X10 AL | 82 | 16 | 66 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0457035P0100 | BLIND RIVET 5X10 AL | 66 | 8 | 58 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8101117
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0457038P0100 | BLIND RIVET 5X16, CIECO, WN457-ALU | 198 | 164 | 34 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0457038P0100 | BLIND RIVET 5X16, CIECO, WN457-ALU | 34 | 2 | 32 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0457040P0100 | BLIND RIVET 6.4X12 STEEL | 335 | 335 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0734028P0100P | K - BALL SHAPED HANDLE (ZINC CHRM) | 6 | 6 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0909121P0100 | STRAIN RELIEF TYPE ZE2/10 | 10 | 10 | 0 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 51 | 51 | 0 | free_stock | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 102 | 36 | 66 | free_stock | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 66 | 1 | 65 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 65 | 2 | 63 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8084150
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 63 | 1 | 62 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8070525
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 62 | 1 | 61 | 6100K019 | R15-T-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8070528
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 61 | 1 | 60 | 6100K019 | R15-T-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8071508
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 60 | 2 | 58 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8108509
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 58 | 1 | 57 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8094859
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 57 | 2 | 55 | 6100K019 | R15-T-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8132368
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 55 | 1 | 54 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8120218
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 54 | 1 | 53 | 6100K019 | R15-T-1-KDP1_SEP | consumption | 2025-10-16 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8141296
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0102 | PANEL HEATER 240V,100W-Boxin-5MetCable | 51 | 41 | 10 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0102 | PANEL HEATER 240V,100W-Boxin-5MetCable | 10 | 2 | 8 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0102 | PANEL HEATER 240V,100W-Boxin-5MetCable | 8 | 1 | 7 | 6100K019 | R16-I-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8094856
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990403P0100 | VENTILATOR QK08A-2EM.50.CH WITH CAPACITO | 7 | 5 | 2 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990404P0100 | RADIAL FLOW FAN QK08A-2EM.35.CF | 7 | 2 | 5 | 606PD013 | IFLR-1-1-PD\-13/MV_SEP | inventory | 2025-11-03 | B |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990404P0100 | RADIAL FLOW FAN QK08A-2EM.35.CF | 5 | 1 | 4 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990431P0100 | HANDLE | 711 | 711 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0996020P0100 | PROTECTOR CAP M12 SW17-1-G15/H5 | 18 | 18 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0996027P0100 | PROTECTION CAP M10NR.610 | 258 | 174 | 84 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0998122P0100 | TUBING 28X36 FOR PG29 | 4.9 | 4.9 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0998124P0100 | TUBING KUW 17X21,PG16 | 1.2 | 1.2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0998131P0100 | TUBE HOLDER-LK / MPG16 | 3 | 3 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0998134P0100 | SEALING RUBBER | 688.97 | 477.89 | 211.08 | free_stock | R15-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0998162P0100 | REDUCING RING PVC | 876 | 599 | 277 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0998162P0100 | REDUCING RING PVC | 277 | 125 | 152 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0998168P0100 | PLASTIC BUSHING EK/G36 | 5 | 5 | 0 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4117104P0106 | TUBE G16X100 DIN 490216 | 49 | 49 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4117104P0117 | TUBE G16X9 | 98 | 98 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4129015P0128P | HEX.PART 17X677 ZINC CHR. | 49 | 49 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4366010P0100 | NUT(DADO D'ANCORAGGIO) M10 WN366-ST37-2 | 378 | 302 | 76 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4366010P0100 | NUT(DADO D'ANCORAGGIO) M10 WN366-ST37-2 | 76 | 76 | 0 | 6100KDP01 | R56-R-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4395592P0100 | WASHER FLAT 8 X 11 X 0.5 MM | 288 | 216 | 72 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4395592P0100 | WASHER FLAT 8 X 11 X 0.5 MM | 72 | 12 | 60 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4395592P0100 | WASHER FLAT 8 X 11 X 0.5 MM | 60 | 6 | 54 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8104594
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4395856P0100 | PLAIN WASHER, LARGE 6.2x12x0.2 | 30 | 30 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4396073P0100 | WASHER LARG PLN (12.1/23.5X2.5 | 12 | 12 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4530250P0100 | DESIGNATION LABEL L1 (RED) | 51 | 44 | 7 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4530251P0100 | DESIGNATION LABEL L2 (YELLOW) | 51 | 44 | 7 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4530252P0100 | DESIGNATION LABEL L3 (BLUE) | 51 | 44 | 7 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 49 | 42 | 7 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 7 | 1 | 6 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8115490
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 6 | 1 | 5 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8127551
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 5 | 1 | 4 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8127554
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 4 | 1 | 3 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8131734
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 3 | 1 | 2 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8140323
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 2 | 1 | 1 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8137878
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4539452P0100 | INDICATION LABEL Mech.Operation STICKER | 48 | 48 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000495R0101 | SHAFT COMPL. | 49 | 49 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000496P0102 | TORSION SPRING | 49 | 35 | 14 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000496P0102 | TORSION SPRING | 14 | 6 | 8 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000497R0101 | BEARING HOUSING COMPLETE | 49 | 35 | 14 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000497R0101 | BEARING HOUSING COMPLETE | 14 | 6 | 8 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000508P0101 | GROOVED PIN | 49 | 41 | 8 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000524P0101P | GROOVED PIN | 49 | 49 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000525P0101 | WASHER,STOP | 49 | 35 | 14 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000535R0101P | K- BRACKET COMPL. ZINC COATED | 49 | 49 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000552P0101 | STOP WASHER | 98 | 70 | 28 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000553P0101 | ADJUSTING FISH PLATE | 98 | 98 | 0 | 6100KDP01 | R55-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000581P0101 | CANTILEVER SPRING | 59 | 59 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000582P0101 | SPIRAL SPRING | 49 | 49 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000663R0101 | BEVEL GEAR DRIVE FOR EK6 ZS1 | 49 | 35 | 14 | free_stock | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7001026P0101 | INSULATION TUBE; L=45MM. | 98 | 98 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7001732R0105 | EARTHING SWITCH: EK6/ZS1-1710-275 | 5 | 5 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7001732R0106 | EARTHING SWITCH: EK6-ZS1-1710-210 | 3 | 2 | 1 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7001936P0101P | K - HANDLE (CHROME PLATED) | 6 | 6 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7002424P0101P | K - BEARING SHAFT (ZINC CHRM) | 12 | 12 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7003008P0101 | RING | 49 | 35 | 14 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7003008P0101 | RING | 14 | 6 | 8 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7003579P0101 | TENSION SPRING 6.5/.9/30/16 | 51 | 44 | 7 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7003579P0101 | TENSION SPRING 6.5/.9/30/16 | 7 | 2 | 5 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7003579P0101 | TENSION SPRING 6.5/.9/30/16 | 5 | 1 | 4 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8096126
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7003694P0102 | CARRIER | 49 | 35 | 14 | free_stock | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7102436P0100 | PLUG HOUSING SOCKET/GEHAUSE | 51 | 51 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7102438P0100 | COVER OF CONTROL PLUG/SOCKET | 8 | 8 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7109399R0101 | AUXILIARY SWITCH 5NO | 98 | 82 | 16 | free_stock | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7109399R0106 | AUXILIARY SWITCH 5NC | 49 | 35 | 14 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7109399R0106 | AUXILIARY SWITCH 5NC | 14 | 14 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7109399R0118 | SLIDE F.AUX.SWICH 5NC | 5 | 5 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7204654P0101 | BOLT 7/4X15 | 26 | 26 | 0 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7208367P0100 | DESIGNATION LABEL | 49 | 37 | 12 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8000336P0101 | K- INTERMEDIATE PIECE 40x6x9(ZINC CHR.) | 98 | 84 | 14 | 6100KDP01 | PO-SEP-5654-[5] | GR_in_process | 2025-12-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries) | 96 | 06-09-2025
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8000633P0113P | MOUNTING CHANNEL 760mm (GCE8000633P0113) | 92 | 68 | 24 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8000633P0113P | MOUNTING CHANNEL 760mm (GCE8000633P0113) | 24 | 24 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8000801P0101P | CONTACT PIN, RD.79MM L=107MM | 18 | 12 | 6 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8000825P0101 | SPRING | 52 | 52 | 0 | 606PD013 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8000881P0102 | INTERMEDITE PLATE 80x15x125 CU SILVERPLA | 18 | 12 | 6 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8000981P0101P | THREADED PIECE | 49 | 49 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8001698R0107P | LEVER MECHANISM LEFT-SX 2X R250/55(w1000 | 5 | 5 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8001698R0108P | LEVER MECHANISM RIGHT,DX2X R250/55(w1000 | 5 | 5 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8001710P0101 | SPECIAL BOLT | 10 | 10 | 0 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8002370P0101 | DOCKING RECEPTANCE | 102 | 102 | 0 | 606PD013 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8002757P0107 | COVER | 18 | 12 | 6 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8002866R0102P | PADLOCK ES - NORMAL | 49 | 41 | 8 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8002875P0101 | WINDOW PANE 350X220X16,8 (KONEX) | 20 | 20 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003360R0101P | LEVER MECHANISM LEFT, 2xR250/55(W800) | 43 | 43 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003360R0102P | LEVER MECHANISM RIGHT,2xR250/55 (W800) | 43 | 43 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003638P0103P | INTER LOCKING AGLE LEFT | 51 | 34 | 17 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003638P0103P | INTER LOCKING AGLE LEFT | 17 | 2 | 15 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003638P0103P | INTER LOCKING AGLE LEFT | 15 | 1 | 14 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8094835
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003638P0103P | INTER LOCKING AGLE LEFT | 14 | 7 | 7 | 6100KDP01 | PO-SEP-6831-[5] | GR_in_process | 2025-08-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | PP-12 (Mechanical Parts) for 07 Panels with Accessories | 7 | 05-08-2025 | 05-08-2025 |  |  | 6831
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003638P0104P | INTERLOCKING ANGLE RIGHT | 51 | 35 | 16 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003638P0104P | INTERLOCKING ANGLE RIGHT | 16 | 1 | 15 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003638P0104P | INTERLOCKING ANGLE RIGHT | 15 | 7 | 8 | 6100KDP01 | PO-SEP-6831-[6] | GR_in_process | 2025-08-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | PP-12 (Mechanical Parts) for 07 Panels with Accessories | 7 | 05-08-2025 | 05-08-2025 |  |  | 6831
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003651P0101P | INSULATING CAP | 347 | 347 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003671P0102 | SPECIAL SCREW M12 X 50/20 | 6 | 4 | 2 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003671P0116 | SPCEIAL SCREW M12X34/45 | 178 | 136 | 42 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003824P0101 | K- SUPPORT PLATE YELLOW CHROMATION. | 48 | 39 | 9 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003824P0101 | K- SUPPORT PLATE YELLOW CHROMATION. | 9 | 4 | 5 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003899R0101 | SPOUT 12KV, >2500A | 36 | 12 | 24 | free_stock | R58-H-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003900P0101 | COVER FOR SPOUT | 36 | 6 | 30 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003900P0101 | COVER FOR SPOUT | 30 | 6 | 24 | 606PD013 | R59-A-1-PD\-13/MV_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003900P0102 | COVER FOR SPOUT | 60 | 36 | 24 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003900P0102 | COVER FOR SPOUT | 24 | 6 | 18 | 606PD013 | R59-Q-1-PD\-13/MV_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004145P0101P | INTERLOCKING BOLT | 12 | 12 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 102 | 34 | 68 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 68 | 2 | 66 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 66 | 1 | 65 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8094456
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004437P0103P | SHROUD (EARTHING CONTACT)GCE8004437P0103 | 172 | 58 | 114 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004437P0103P | SHROUD (EARTHING CONTACT)GCE8004437P0103 | 114 | 48 | 66 | 6100KDP01 | R56-I-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004471R0101P | ELECTRODE, ZS1 95kV BIL | 48 | 27 | 21 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004478P0101 | BUSHING PLATE BELOW / 3 HOLES | 2 | 2 | 0 | free_stock | R16-L-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004479P0101P | PROTECTIVE COVER (DWG: GCE8004479P0101) | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004581P0101 | SPRING COMPRESSION | 12 | 12 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004944R0101 | SPOUT ZS1 (4000A) | 60 | 42 | 18 | free_stock | R58-H-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005031R0101 | BUSHING ZS1/ (3 IN 1) DEACE | 48 | 48 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005041P0101P | CONTACT PIN 109mm,3150A(GCE8005041P0101) | 60 | 42 | 18 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005042P0101 | CONNECTION PIECE 3150A ZS1 | 30 | 21 | 9 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005049P0101 | SUPPORT (POLY ) T = SHAPE | 18 | 18 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005112P0103P | OPERATING BOLT | 20 | 12 | 8 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005117P0101 | CARRIER | 40 | 24 | 16 | 6100KDP01 | R16-L-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005136P0101 | SUPPORT (POLY) | 12 | 6 | 6 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005164P0101 | SCREENING | 180 | 126 | 54 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005250P0101 | K- LIFTING HOOK (ZINC CHROM) | 408 | 168 | 240 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005250P0101 | K- LIFTING HOOK (ZINC CHROM) | 240 | 24 | 216 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005595R0102P | BUSBAR ZS D100, 12THICK,800/800, L=795 | 228 | 186 | 42 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005595R0102P | BUSBAR ZS D100, 12THICK,800/800, L=795 | 42 | 18 | 24 | 6100KDP01 | R56-I-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005595R0109P | Busbar D100,12mm Thick 800/1000,L=830 | 22 | 22 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005595R0110P | Busbar D100,12mm Thick 800/1000,L=895 | 22 | 22 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005595R0111P | Busbar D100,12mm Thick 800/1000,L=960 | 22 | 22 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005595R0112P | Busbar D100, 12mm Thick 1000/1000 L=995 | 18 | 18 | 0 | 606PD013 | IFLR-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8006587P0101 | LOCK SCREW M6X25 ( ROUND FLAT HEAD ) | 720 | 304 | 416 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8007213P0101 | SHROUD ZS3.2, Middle | 33 | 33 | 0 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8007214P0101 | COVER FOR SHROUD ZS3.2, end side | 66 | 66 | 0 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8008881P0103 | BRACKET BOTTOM | 192 | 78 | 114 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8008881P0103 | BRACKET BOTTOM | 114 | 8 | 106 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8008881P0104 | SHUTTER BRACKET | 204 | 82 | 122 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8008881P0104 | SHUTTER BRACKET | 122 | 12 | 110 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 102 | 34 | 68 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 68 | 7 | 61 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 61 | 2 | 59 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 59 | 1 | 58 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8096039
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010004P0102 | GUIDE RAIL RIGHT 12kV | 102 | 35 | 67 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010004P0102 | GUIDE RAIL RIGHT 12kV | 67 | 7 | 60 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010008P0101 | BUSHING PLATE (STAINLESS STEEL) | 50 | 39 | 11 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010008P0101 | BUSHING PLATE (STAINLESS STEEL) | 11 | 5 | 6 | 6100KDP01 | WH2-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010008P0101 | BUSHING PLATE (STAINLESS STEEL) | 6 | 2 | 4 | 606PD013 | WH2-1-1-PD\-13/MV_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010022P0111R | SHUTTER UPPER W800 (GCE8010022P0111) | 92 | 35 | 57 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010022P0112Y | SHUTTER LOWER W800 (GCE8010022P0112) | 86 | 33 | 53 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010022P0112Y | SHUTTER LOWER W800 (GCE8010022P0112) | 53 | 1 | 52 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010022P0113R | SHUTTER UPPER (DWG.GCE8010022P0113) | 10 | 7 | 3 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010022P0114Y | SHUTTER LOWER (DWG.GCE8010022P0114) | 10 | 7 | 3 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010023P0101 | PIN (ZINC COATED) | 384 | 144 | 240 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010023P0101 | PIN (ZINC COATED) | 240 | 12 | 228 | 6100K019 | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010023P0101 | PIN (ZINC COATED) | 228 | 4 | 224 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0102 | Pressure Relief Flap, W800 , (Cat: B) ¦ GCE8010028R0102 ¦ ABB | 2 | 2 | 0 | free_stock | R14-T-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 184 | 30 | 154 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 154 | 28 | 126 | free_stock | R14-T-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 126 | 12 | 114 | free_stock | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 114 | 3 | 111 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 111 | 1 | 110 | 6100K019 | R14-J-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8094533
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0103 | PRESSURE RELIEF FLAP W1000 | 16 | 13 | 3 | free_stock | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0105 | PRESSURE RELIEF FLAP, REAR | 10 | 7 | 3 | free_stock | R14-T-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0106 | PRESSURE RELIEF FLAP W1000 | 10 | 7 | 3 | free_stock | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010073P0102 | PARTITION WALL | 92 | 34 | 58 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010073P0102 | PARTITION WALL | 58 | 6 | 52 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010073P0103 | BB/CB.PARTITION WALL W1000(PaintRAL7035) | 10 | 7 | 3 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010096P0101P | PIN 12DIA(ZINC COAT)DWG:GCE8010096P0101 | 6 | 4 | 2 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010097P0101 | MOUNTING PLATE W800, S=310 | 6 | 2 | 4 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010097P0102 | MOUNTING PLATE S=310 W1000 | 10 | 3 | 7 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010104P0103P | BUSHING D60/49X25 | 60 | 42 | 18 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010104P0104P | BUSHING D58/47X25 | 36 | 12 | 24 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010178P0102 | SUPPORT ANGLE | 92 | 35 | 57 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010178P0103 | SUPPORT ANGLE W1000 | 10 | 7 | 3 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011408P0101 | MOUNTING PLATE W800, METERING | 3 | 2 | 1 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011409R0101 | LEVER COMPLETE LEFT SIDE | 3 | 3 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011409R0102 | LEVER COMPLETE RIGHT SIDE | 3 | 3 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011552P0102 | FLAT SCREEN FOR CB.MIDDLE PLATE W800 | 40 | 31 | 9 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011552P0102 | FLAT SCREEN FOR CB.MIDDLE PLATE W800 | 9 | 1 | 8 | 606PD013 | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011642P0101 | SPACER | 594 | 246 | 348 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011642P0101 | SPACER | 348 | 200 | 148 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011650P0101 | SUPPORT REINFORCEMENT | 10 | 7 | 3 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011673P0101 | PARTITION WALL W800 | 3 | 2 | 1 | 6100KDP01 | PO-SEP-5654-[29] | GR_in_process | 2025-12-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries) | 4 | 06-09-2025
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011673P0102 | Partition Wall W1000 | 6 | 6 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011679R0101P | REIFORCING ANGLE COMPLETE LEFT | 12 | 12 | 0 | 6100KDP01 | R56-I-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8012228P0101 | SUPPORTING SHEET | 60 | 42 | 18 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013214P0101 | PARTITION WALL BOTTOM W800 (SS STL)BARE | 86 | 33 | 53 | 6100KDP01 | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013244P0101 | TRANSFORMER PLATE W800mm | 86 | 33 | 53 | 6100KDP01 | PO-SEP-5654-[33] | GR_in_process | 2025-12-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries) | 36 | 24-09-2025
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013262P0101 | SHROUD | 12 | 12 | 0 | 6100KDP01 | R56-I-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013263P0101 | SHROUD | 80 | 58 | 22 | free_stock | R14-T-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013263P0101 | SHROUD | 22 | 20 | 2 | 6100KDP01 | R56-I-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013263P0101 | SHROUD | 2 | 2 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013412R0101 | PRESSURE RELIEF FLAP FOR W1000 | 10 | 7 | 3 | free_stock | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013414P0101 | FIXING PLATE FOR DUCT | 10 | 7 | 3 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013419R0101 | FRAME FOR FLAT SCREEN COMPLETE | 10 | 7 | 3 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013419R0101 | FRAME FOR FLAT SCREEN COMPLETE | 3 | 2 | 1 | 606PD013 | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013423P0101 | PARTITION WALL W1000 (PAINTED RAL7035) | 10 | 7 | 3 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013427P0101 | GAIN CT PLATE | 10 | 7 | 3 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013430P0101 | COOLING PLATE 1 ( small ) | 30 | 21 | 9 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013431P0101 | COOLING PLATE 2 ( Big ) | 30 | 21 | 9 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013433P0101P | SHROUD (DWG NO. GCE8013433P0101) | 20 | 14 | 6 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013434P0101P | SHROUD (DWG NO. GCE8013434P0101) | 20 | 14 | 6 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013434P0102P | SHROUD (DWG NO. GCE8013434P0102) | 20 | 14 | 6 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013435P0101P | SPACER DISC (GCE8013435P0101) | 160 | 112 | 48 | free_stock | R15-T-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013444R0101 | PRESSURE RELIEF FLAP(W1000) | 10 | 7 | 3 | free_stock | R14-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8381281P0100 | GUIDE ROLLER | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8487370R0100 | EARTHING CONTACT | 6 | 2 | 4 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8487370R0100 | EARTHING CONTACT | 4 | 2 | 2 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8487370R0100 | EARTHING CONTACT | 2 | 1 | 1 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8494256P0101 | DISTANCE TUBE | 98 | 98 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 120 | 53 | 67 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 67 | 3 | 64 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8128688
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 64 | 2 | 62 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8117180
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 62 | 2 | 60 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8117081
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 60 | 2 | 58 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8127548
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 58 | 1 | 57 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8115481
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 57 | 1 | 56 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8115487
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8684080P0101 | EARTHING STRIP | 6 | 4 | 2 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8684080P0101 | EARTHING STRIP | 2 | 1 | 1 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8685778P0121P | CONTACT PIN 800/1200A SIL.COAT = 72L | 9 | 6 | 3 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9371453P0101 | CABLE BUSHING LOWER PART | 3 | 3 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9371454P0101 | CABLE BUSHING UPPER PART | 3 | 3 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9401529P0100 | Bush | 98 | 98 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9401556P0100 | STOP WASHER | 196 | 70 | 126 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9401678R0101 | HOUSING (PLUG SOCKET)COMPL. | 4 | 4 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9401766P0107 | LOCKING MAGNET DC125 V | 98 | 45 | 53 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9401766P0107 | LOCKING MAGNET DC125 V | 53 | 20 | 33 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9464131P0100 | EARTHING SWITCH DISPLAY | 98 | 98 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9476775R0100 | IND.CONTACT/ VAN FLOW SWITCH | 14 | 6 | 8 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9476775R0100 | IND.CONTACT/ VAN FLOW SWITCH | 8 | 2 | 6 | 606PD013 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9477367P0102 | FORK D11x20 | 30 | 19 | 11 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9478304P0102P | ROLLER | 24 | 24 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9478350P0101 | SUPPORTING BOLT 6Kt14/M6X23 | 3 | 3 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9576618P0100 | BUSH D18/12,2X8 | 196 | 196 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCEC830444P0101P | K-SPACER D12/4.5X8,ZS1/ZS3.2Yellow Chrom | 196 | 196 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 204 | 78 | 126 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 126 | 22 | 104 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 104 | 2 | 102 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-CR-U125DC3 | CR-U125DC3 - 1SVR405622R8200.CR-U125DC3 Pluggable interface relay 3c Ordering Code : 1SVR405622R8200 General: Pluggable interface relay ABB. Type : CR-U125DC3L Ordering Code: OUTPUTS: 3 C/O with LED RATED VOLTAGE: 125 VDC | 3 | 3 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-CR-U125DC3 | CR-U125DC3 - 1SVR405622R8200.CR-U125DC3 Pluggable interface relay 3c Ordering Code : 1SVR405622R8200 General: Pluggable interface relay ABB. Type : CR-U125DC3L Ordering Code: OUTPUTS: 3 C/O with LED RATED VOLTAGE: 125 VDC | 3 | 3 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-CR-U3S | Socket -FOR 3 C/O AND MODULE TIMER | 3 | 3 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-CR-U3S | Socket -FOR 3 C/O AND MODULE TIMER | 3 | 3 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-CR-UH | Holder interface relay 1SVR405669R0000 | 3 | 3 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-CR-UH | Holder interface relay 1SVR405669R0000 | 3 | 3 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-CR-UT | TIME MODULE 1SVR405667R0000 | 3 | 3 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-CR-UT | TIME MODULE 1SVR405667R0000 | 3 | 3 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 96 | 76 | 20 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 20 | 12 | 8 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 8 | 8 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV2000-1685-06-W | WHITE TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 12750 | 7480 | 5270 | 6100K013 | INC-1-1-MVBM_SEP | consumption | 2025-09-22 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Material Issue Order_MIO | 7506468
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV2000-1685-06-W | WHITE TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 5270 | 1000 | 4270 | 6100K006 | INC-1-1-MVBM_SEP | consumption | 2025-09-22 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Material Issue Order_MIO | 7506467
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV2000-1685-06-W | WHITE TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 4270 | 3080 | 1190 | 6100K011B | R58-G-1-K010_SEP | consumption | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8269554
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | PKE 1508 | END SLEEVES PKE 1508 (1x1.5sqmm , Black) | 765 | 765 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | PKT 1508 | END SLEEVES PKT 1508 (2x1.5sqmm , Black) | 765 | 695 | 70 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | PKT 1508 | END SLEEVES PKT 1508 (2x1.5sqmm , Black) | 70 | 70 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | PKT 2512 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 1020 | 860 | 160 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | PKT 2512 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 160 | 160 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | RMU000000339 | PLATE -FOR PANEL FIXING | 204 | 28 | 176 | 6100KDP01 | WH2-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000024P0001P | BUSHING (LOCAL PUR) | 98 | 41 | 57 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000025P0001P | BUSHING (LOCAL PUR) | 294 | 144 | 150 | 6100KDP01 | R58-A-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000025P0001P | BUSHING (LOCAL PUR) | 150 | 126 | 24 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000025P0001P | BUSHING (LOCAL PUR) | 24 | 24 | 0 | 6100K023 | R58-A-1-K023_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000026P0001P | BUSHING (LOCAL PUR) | 306 | 126 | 180 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000027P0001P | K-PLATE | 200 | 200 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000047P0001 | INTERLOCKING SCOTCH | 102 | 42 | 60 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000048P0001P | PIN (LOCAL PUR) | 98 | 48 | 50 | 6100KDP01 | R58-A-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000048P0001P | PIN (LOCAL PUR) | 50 | 46 | 4 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000048P0001P | PIN (LOCAL PUR) | 4 | 4 | 0 | 6100K023 | R58-A-1-K023_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000049P0001 | COMPRESSION SPRING | 98 | 98 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1001678P0001 | HOOKING LEVER (ZINC PLATED) | 2 | 1 | 1 | 6100KDP01 | WH2-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1001813R0802P | MECHANICAL OFF BUTTON FOR VD4 - HOR | 96 | 49 | 47 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1001813R0802P | MECHANICAL OFF BUTTON FOR VD4 - HOR | 47 | 36 | 11 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1001915P0001P | PIN | 20 | 12 | 8 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1001916P0001P | INTERLOCK LEVER (LOCAL PUR) | 20 | 12 | 8 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1001982P0001 | ROLLER | 20 | 12 | 8 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40181 | Busbar, Copper, 32 x 8 mm, R=1, 5.5m | 408.66 | 289.21 | 119.45 | free_stock | BBR-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40181 | Busbar, Copper, 32 x 8 mm, R=1, 5.5m | 119.45 | 11.88 | 107.57 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40181 | Busbar, Copper, 32 x 8 mm, R=1, 5.5m | 107.57 | 3.88 | 103.69 | 6100K019 | BBR-1-1-K019_SEP | consumption | 2025-10-25 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Work in Process Pick | 8292290
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40184 | Busbar, Copper, 40 x 5 mm, R=1, 5.5m | 9.6 | 9.6 | 0 | free_stock | BBR-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40187 | Busbar, Copper, 40 x 10 mm, R=1, 5.5m | 60.08 | 60.08 | 0 | free_stock | BBR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40196 | Busbar, Copper, 60 x 10 mm, R=5, 5.5m | 22.232 | 22.232 | 0 | free_stock | BBR-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40200 | Busbar, Copper, 80 x 5 mm, R=2.5, 5.5m | 28.1 | 28.1 | 0 | 606PD013 | BBR-1-1-PD\-13/MV_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40200 | COPPER BAR 80X5, R=2.5 | 29.9 | 29.9 | 0 | 606PD013 | BBR-1-1-PD\-13/MV_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40202 | Busbar, Copper, 80 x 10 mm, R=5, 5.5m | 8717.76 | 1783.782 | 6933.978 | 6100KDP01 | BBR-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40202 | Busbar, Copper, 80 x 10 mm, R=5, 5.5m | 6933.978 | 114.048 | 6819.93 | 606PD013 | BBR-1-1-PD\-13/MV_SEP | consumption | 2025-08-19 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Material Issue Order_MIO | 6684720
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40210 | Busbar, Copper, 120 x 10 mm, R=5, 5.5m | 2473.512 | 1026.43 | 1447.082 | free_stock | BBR-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40210 | Busbar, Copper, 120 x 10 mm, R=5, 5.5m | 1447.082 | 299.376 | 1147.706 | 606PD013 | BBR-1-1-PD\-13/MV_SEP | consumption | 2025-08-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | [5 empty] | Material Issue Order_MIO | 6645839
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40254 | Busbar, Copper, 50 x 10 mm, R=1 | 11.52 | 11.52 | 0 | 6100KDP01 | BBR-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | T81722 | Plastic plug for LV Box (Micro. Sw. ) | 612 | 612 | 0 | 6100K013 | R58-J-1-K013_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | XM 2050 1500-30 | POLYCARBONATE 2050X1500X3.0 MM | 390.46 | 15.94 | 374.52 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 23 | 23 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 07686 | WASHER AC EL DIN137 T22120/8 A | 20 | 20 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 07853 | HEX. HEAD BOLT T21000/3X16 | 30 | 30 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 07934 | TOMMY HEAD SCREW ACC T21010/M3x6 | 88 | 88 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 07940 | TOMMY HEAD SCREW ACC T21010/M3X20 | 34 | 34 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 07959 | TOMMY HEAD SCREW FULL THREAD T21010/4X25 | 300 | 62 | 238 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 08222 | COUNTER SUNK SCREW 6X16 ACC T21030/6X16 | 4 | 4 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 09011 | LOCK NUT T21192/M3N - DIN 985 A2K | 20 | 20 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 09929 | STEEL SPRING WASHER ACC T22104/10 | 96 | 24 | 72 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1201400000 | CRIMP CONTACTS 2.5mm2 (FEMALE) | 1 | 1 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 12980 | COUNTERSUNK STEEL SCREW T21065/M6X14 | 70 | 6 | 64 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 13441 | TORQUES WRENCH | 1 | 1 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 22 | 22 | 0 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1420601 | BI-HEXAGON DEEP SOCKET SET | 1 | 1 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1420630 | BI HEXAGON SOCKET SET of RATCHET | 1 | 1 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1440146 | BALL END ALLEN KEY SET | 1 | 1 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 16304 | RIVET TT ALUMINUM T22213/5 | 45 | 12 | 33 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1665260000 | HDC 16B DODQ 4BO IP65 COVER | 1 | 1 | 0 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1826800000 | INSERT FEMALE 32POLE TYPE-HDC HEE 32 FC . | 1 | 1 | 0 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611400R1001 | PILOT LIGHT#ML1-100R | 21 | 5 | 16 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611400R1001 | PILOT LIGHT#ML1-100R | 16 | 2 | 14 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611400R1001 | PILOT LIGHT#ML1-100R | 14 | 1 | 13 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611400R1002 | PILOT LIGHT#ML1-100G | 21 | 5 | 16 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611400R1002 | PILOT LIGHT#ML1-100G | 16 | 2 | 14 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611400R1002 | PILOT LIGHT#ML1-100G | 14 | 1 | 13 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611400R1003 | PILOT LIGHT#ML1-100Y | 24 | 1 | 23 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611621R1051 | LAMP BLOCK#MLBL-05R | 21 | 5 | 16 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611621R1051 | LAMP BLOCK#MLBL-05R | 16 | 2 | 14 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611621R1051 | LAMP BLOCK#MLBL-05R | 14 | 1 | 13 | 6100K019 | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611621R1051 | LAMP BLOCK#MLBL-05R | 13 | 1 | 12 | 6100K019 | R14-B-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8069870
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611621R1051 | LAMP BLOCK#MLBL-05R | 12 | 1 | 11 | 6100K019 | R14-B-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8070534
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611621R1052 | LAMP BLOCK#MLBL-05G | 21 | 5 | 16 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611621R1052 | LAMP BLOCK#MLBL-05G | 16 | 2 | 14 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611621R1052 | LAMP BLOCK#MLBL-05G | 14 | 1 | 13 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611621R1053 | LAMP BLOCK#MLBL-05Y | 24 | 1 | 23 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR000474F0001 | BLOCK | 45 | 45 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR002416G0001 | LOCKUP ROD ASSEMBLY | 46 | 14 | 32 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR002416G0001 | LOCKUP ROD ASSEMBLY | 32 | 7 | 25 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR002416G0001 | LOCKUP ROD ASSEMBLY | 25 | 1 | 24 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR002416G0001 | LOCKUP ROD ASSEMBLY | 24 | 1 | 23 | 6100K019 | R14-I-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8144157
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR003760G0001 | CRANK FOR EARTHING SWITCH EK6 | 4 | 1 | 3 | 6100KDP01 | INC-1-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR003760G0001 | CRANK FOR EARTHING SWITCH EK6 | 3 | 1 | 2 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR008770F0001 | BLOCK PIN | 184 | 64 | 120 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR008770F0001 | BLOCK PIN | 120 | 16 | 104 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR008770F0001 | BLOCK PIN | 104 | 8 | 96 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8117192
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7600349P0101 | SHROUD | 2 | 2 | 0 | 6100KDP01 | R56-I-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7601387P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Short | 23 | 23 | 0 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7601389P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Long | 23 | 23 | 0 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7602006R0101 | TIE ROD W800 CABLE COMPT. | 46 | 18 | 28 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7602006R0101 | TIE ROD W800 CABLE COMPT. | 28 | 2 | 26 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7608266P0101 | CONNECTION PIECE tublar GCE8005046R0101 | 30 | 12 | 18 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB000002-FDV | MIMIC DIAGRAM, INCOMER-2W,VT | 2 | 2 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB000007-BME | MIMIC, BUS MET. & EARTHING-2W,VT | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB000009-BRM | MIMIC , BUS RISER & MET.-2W,VT | 1 | 1 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010005P0102 | SHROUD, LEFT W1000 | 12 | 9 | 3 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010005P0103 | SHROUD, LEFT W800 | 48 | 8 | 40 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010005P0103 | SHROUD, LEFT W800 | 40 | 3 | 37 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010006P0102 | SHROUD, RIGHT W1000 | 12 | 9 | 3 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010006P0103 | SHROUD, RIGHT W800 | 48 | 8 | 40 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010006P0103 | SHROUD, RIGHT W800 | 40 | 3 | 37 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 23 | 23 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010072P0101P | CONTACT PIN 35 DIA, 90L | 84 | 84 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 93.65 | 65.36 | 28.29 | free_stock | R16-L-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 28.29 | 28.29 | 0 |  | R16-L-1-K019_SEP | consumption | 2025-10-14 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109209
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010138P0103 | PROTECTIVE COVER W1000 | 5 | 2 | 3 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010138P0120 | Cover for push button rod | 21 | 21 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010241P0104 | HEX. BOLT M10X40 POLYAMIDE | 24 | 6 | 18 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010366P0109 | Self tapping screw pan head M4x5mm SS | 1150 | 1150 | 0 | free_stock | R13-S-1-K006_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010378P0110 | SEC.FEMALE CONTACTS 1.5,W.SLEEVES 50X | 1200 | 250 | 950 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010378P0111 | SEC. PIN MALE 1.5 MMZS1 | 150 | 150 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010378P0112 | SEC. FEMALE CONTACT PIN 2.5MM | 900 | 100 | 800 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010378P0113 | PIN,CONTACT MALE 2.5 | 100 | 100 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010378P0116 | Lugs, Sleeve 4.0/9mm ( W/O Ins.) 3200302 | 1150 | 1150 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010402R0104 | LABELS FOR SHUTTERS BUSBAR-1,2,3-B/S,B/R | 1 | 1 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010491P0101 | FLEX. CABLE,70MM.SQ, PVC 85 YEL/GRN,85°C | 0.38753 | 0.38753 | 0 | free_stock | R57-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5112XFS00000 | VT 3Nos PRIMARY FUSE 17.5kV, 3A, SIBA | 12 | 6 | 6 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5112XFS00000 | VT 3Nos PRIMARY FUSE 17.5kV, 3A, SIBA | 6 | 3 | 3 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5112XFS00000 | VT 3Nos PRIMARY FUSE 17.5kV, 3A, SIBA | 3 | 3 | 0 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8129018
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB52322VW60N00 | VD4/PW 171225-p210-125VDC-ZS1 | 12 | 12 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB52371V06CN00 | VD4/P 173225-p275-125VDC (1VCD400222) | 5 | 2 | 3 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB52371V06CN00 | VD4/P 173225-p275-125VDC (1VCD400222) | 3 | 1 | 2 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 23 | 1 | 22 | 6100K019 | R16-L-1-K019_SEP | consumption | 2025-10-16 | A |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8150335
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5320XDB1XN01 | CEWE Elite 440-448 | 21 | 6 | 15 | free_stock | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5320XDB1XN01 | CEWE Elite 440-448 | 15 | 1 | 14 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | LL10-W | ABB_LL10-W / LL10-W, AC/DC90-264V 50/60HZ | 23 | 23 | 0 | 6100K012B | 1-1-1-1 | inventory | 2025-11-03 | LV | Automated: Replaced 1YAB53301XIX0000 by LL10-W. | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 23 | 13 | 10 | 6100KDP01 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 10 | 7 | 3 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5331XXCX0220 | OFF-EMER-LOCAL-REMOTE 4P4P, PADLCK (COM) | 16 | 4 | 12 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5334XXAX1000 | FT-1 SW-Type 129A514G01 | 23 | 23 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5334XXAX2000 | RTXP 8, RK 926 002-AG (8P) | 21 | 21 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5334XXAX2100 | RTXP18, RK 926 115-BF | 21 | 21 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5334XXAX2200 | RTXP18 TEST SW-TYPE RK 926 115-AN (18P) | 6 | 6 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5334XXAX2300 | RTXP18, RK 926 115-AH | 2 | 2 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5335XXAX1100 | COMBIFLEX TERMINAL BASE RX 2H -5619625-A | 50 | 50 | 0 | free_stock | R11-A-1-MVBM_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5335XXAX1200 | COMBIFLEX TERMINAL BASE RX4 (4U 12C) | 48 | 48 | 0 | free_stock | R11-A-1-MVBM_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXAA2E00 | MCB 3A AC -2P,2CDS252001R0317 | 3 | 1 | 2 | free_stock | R16-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXAA3F00 | MCB S203-K 4 MC -3P 2CDS253001R0337 | 73 | 73 | 0 | free_stock | R16-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXAA3I00 | MCB 10A AC -3P - 2CDS253001R0427 | 8 | 8 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXACH000 | Aux contact 1NO+1NC MCB -2CDS200936R0001 | 169 | 17 | 152 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXACH000 | Aux contact 1NO+1NC MCB -2CDS200936R0001 | 152 | 8 | 144 | free_stock | R16-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXACH000 | Aux contact 1NO+1NC MCB -2CDS200936R0001 | 144 | 16 | 128 | 6100K019 | R16-L-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8071523
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXACJ000 | S2C-H01 - 1NC- Bottom Auxiliary Contact 2CDS200970R0031 | 50 | 25 | 25 | free_stock | R16-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXACJ000 | S2C-H01 - 1NC- Bottom Auxiliary Contact 2CDS200970R0031 | 25 | 15 | 10 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XBLXXN00 | MVAJ101 RA 0802_ 125VDC (8 NO + 2 NC) | 2 | 2 | 0 | free_stock | R16-L-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XCHXXN00 | LOCKOUT RELAY (86) TYPE 7805F-70-280VDC | 21 | 21 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XDAXXN00 | RXMVB 4, RK 251 401-AP | 5 | 1 | 4 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XDAXXN01 | RXMVB2, RK 251 204-AP | 8 | 8 | 0 | free_stock | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XEAXXN00 | RXMB1 6NO_110-125VDC-1MRK 000 863-AN | 10 | 2 | 8 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XFAXXN00 | DIN Timer (RXKL1, TYPE: 1MRK 000 066-AB) | 3 | 1 | 2 | free_stock | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XIAXXN00 | RXSF1_DC110-125V-MV RK 271 019-AN | 67 | 43 | 24 | free_stock | R14-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XIAXXN00 | RXSF1_DC110-125V-MV RK 271 019-AN | 24 | 3 | 21 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSABB000 | FLEX.CABLE,1/C,1.5MM BLUE ATC,105 Deg C | 50.3282 | 50.3282 | 0 | free_stock | R56-F-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSABC000 | FLEX.CABLE,1/C,1.5MM BLACK ATC,105 Deg C | 16.3567 | 16.3567 | 0 | free_stock | R56-N-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSABD000 | FLEX.CABLE,1/C,1.5MM GREY ATC,105 Deg C | 0.54705 | 0.54705 | 0 | free_stock | R56-H-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSABD000 | FLEX.CABLE,1/C,1.5MM GREY ATC,105 Deg C | 377.4617 | 377.4617 | 0 | free_stock | R56-H-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSABR010 | FLEX.CABLE,1/C,1.5MM RED C,105 Deg C | 16.3567 | 16.3567 | 0 | free_stock | R56-K-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSACB010 | FLEX.CABLE,1/C,2.5MM BLUE ATC,105 Deg C | 67.9431 | 67.9431 | 0 | free_stock | R56-A-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSACC010 | FLEX.CABLE,1/C,2.5MM BLACK ATC,105 Deg C | 42.779 | 42.779 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSACD010 | FLEX.CABLE,1/C,2.5MM GREY ATC,105 Deg C | 12.5821 | 12.5821 | 0 | 6100KDP01 | R56-I-1-KDP1_SEP | consumption | 2025-06-28 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Miscellaneous issue | 6172962
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSACN010 | FLEX.CABLE,1/C,2.5MM YE/GN ATC,105 Deg C | 0.054705 | 0.054705 | 0 | free_stock | R57-P-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSACN010 | FLEX.CABLE,1/C,2.5MM YE/GN ATC,105 Deg C | 12.5821 | 12.5821 | 0 | free_stock | R57-P-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSACR010 | FLEX.CABLE,1/C,2.5MM RED ATC,105 Deg C | 67.9431 | 67.9431 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSACY010 | FLEX.CABLE,1/C,2.5MM YELLOW ATC,90 Deg C | 67.9431 | 67.9431 | 0 | free_stock | R57-K-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSADB020 | FLEX.CABLE,1/C,4MM BLUE ATC,105 Deg C | 3.7746 | 3.7746 | 0 | free_stock | R57-H-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSADC020 | FLEX.CABLE,1/C,4MM BLACK ATC,105 Deg C | 5.0328 | 5.0328 | 0 | free_stock | R57-N-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSADD020 | FLEX.CABLE,1/C,4MM GREY ATC,105 Deg C | 5.0328 | 5.0328 | 0 | free_stock | R60-C-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSADR020 | FLEX.CABLE,1/C,4MM RED ATC,105 Deg C | 3.7746 | 3.7746 | 0 | free_stock | R57-C-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5350XSADY020 | FLEX.CABLE,1/C,4MM YELLOW ATC,105 Deg C | 3.7746 | 3.7746 | 0 | free_stock | R57-F-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block OTTA 6-T-P/P - 0790462 | 1878 | 1878 | 0 | 6100K023 | R53-R-1-K013_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 1035 | 145 | 890 | 6100KDP01 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 890 | 45 | 845 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 845 | 43 | 802 | 6100K019 | R66-H-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 802 | 2 | 800 | 6100K019 | R59-G-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 800 | 45 | 755 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8069104
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 755 | 45 | 710 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8070558
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 710 | 47 | 663 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109211
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 663 | 45 | 618 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8131187
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AEA0001 | M 6/8.RS (SpringLoaded) 1SNA115685R1200 | 965 | 49 | 916 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AEA0001 | M 6/8.RS (SpringLoaded) 1SNA115685R1200 | 916 | 47 | 869 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 7252 | 1108 | 6144 | free_stock | PLT-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 6144 | 330 | 5814 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 5814 | 5814 | 0 |  | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109215
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AFA0001 | M4/6.SNTS Spring Loaded 1SNA115229R2000 | 1035 | 200 | 835 | 6100KDP01 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AFA0001 | M4/6.SNTS Spring Loaded 1SNA115229R2000 | 835 | 45 | 790 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 748 | 213 | 535 | 6100KDP01 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 535 | 30 | 505 | 6100K019 | R66-H-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 505 | 30 | 475 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8069107
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 475 | 30 | 445 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8070561
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 445 | 445 | 0 |  | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109217
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 276 | 12 | 264 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 264 | 4 | 260 | 6100KDP01 | R57-J-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 260 | 12 | 248 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8131116
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 248 | 12 | 236 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-16 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8137216
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 336 | 10 | 326 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 326 | 14 | 312 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8129079
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 312 | 14 | 298 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-16 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8137219
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CBA0000 | FEM8T6 End Sections Grey 1SNA215266R0100 | 345 | 150 | 195 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CBA0000 | FEM8T6 End Sections Grey 1SNA215266R0100 | 195 | 15 | 180 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CEA0000 | FEMR8 End Sections Grey 1SNA116987R0200 | 460 | 100 | 360 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CEA0000 | FEMR8 End Sections Grey 1SNA116987R0200 | 360 | 20 | 340 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CFA0000 | FEM6 End Sections Grey - 1SNA118368R1600 | 230 | 100 | 130 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CFA0000 | FEM6 End Sections Grey - 1SNA118368R1600 | 130 | 10 | 120 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CFA0000 | FEM6 End Sections Grey - 1SNA118368R1600 | 120 | 10 | 110 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8071526
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CMC0000 | Terminal End Plate 1848360000-Wiedmuller | 92 | 18 | 74 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CMC0000 | Terminal End Plate 1848360000-Wiedmuller | 74 | 4 | 70 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CPC0000 | Terminal End Plate 1816110000-Wiedmuller | 92 | 13 | 79 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CPC0000 | Terminal End Plate 1816110000-Wiedmuller | 79 | 5 | 74 | free_stock | R57-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CPC0000 | Terminal End Plate 1816110000-Wiedmuller | 74 | 4 | 70 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CPC0000 | Terminal End Plate 1816110000-Wiedmuller | 70 | 70 | 0 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109223
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CTC0000 | Terminal End Plate 1816070000-Wiedmuller | 48 | 26 | 22 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CTC0000 | Terminal End Plate 1816070000-Wiedmuller | 22 | 2 | 20 | free_stock | R57-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CTC0000 | Terminal End Plate 1816070000-Wiedmuller | 20 | 2 | 18 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CTC0000 | Terminal End Plate 1816070000-Wiedmuller | 18 | 18 | 0 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109225
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 1150 | 1150 | 0 | 6100K023 | R17-A-1-K013_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355DFA0000 | RC610-VerticalMarking 1SNA233060R0400 | 207 | 40 | 167 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355DFA0000 | RC610-VerticalMarking 1SNA233060R0400 | 167 | 9 | 158 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 690 | 460 | 230 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 230 | 230 | 0 | 6100K013 | R59-J-1-MVBM_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355EEA0000 | JUMPER BAR "BJS8" 20 Poles | 46 | 10 | 36 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355EEA0000 | JUMPER BAR "BJS8" 20 Poles | 36 | 2 | 34 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355EFA0000 | PC61-CombTypeJumprBar10 1SNA163311R2200 | 92 | 20 | 72 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355EFA0000 | PC61-CombTypeJumprBar10 1SNA163311R2200 | 72 | 4 | 68 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 184 | 36 | 148 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 148 | 8 | 140 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 140 | 8 | 132 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8129085
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 132 | 8 | 124 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-16 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8137222
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355HAB0001 | Zack Strip-Vertical(11-20)- 1053027:0011 | 276 | 12 | 264 | 6100K019 | R57-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8071529
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355HAB0001 | Zack Strip-Vertical(11-20)- 1053027:0011 | 264 | 10 | 254 | 6100K019 | R57-J-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8070564
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355HAB0001 | Zack Strip-Vertical(11-20)- 1053027:0011 | 254 | 254 | 0 |  | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109229
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355HAB0002 | Zack Strip-Vertical Labeled(21-30) | 184 | 184 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355HXB0000 | BENT LUGS TYPE RF-PPL30 | 16100 | 16100 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355HXB0001 | BENT LUGS TYPE BF-PPL46 | 3450 | 3450 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355HXB0002 | BENT LUGS TYPE BF-PPL30 | 6900 | 6900 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 138 | 4 | 134 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8069885
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 134 | 134 | 0 |  | R13-S-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109233
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355JPC0000 | 6Pole Plug 2.5mm-1815240000-Cont-loop | 92 | 14 | 78 | 6100KDP01 | R57-J-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355JPC0000 | 6Pole Plug 2.5mm-1815240000-Cont-loop | 78 | 4 | 74 | free_stock | R57-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355JPC0000 | 6Pole Plug 2.5mm-1815240000-Cont-loop | 74 | 4 | 70 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355JPC0000 | 6Pole Plug 2.5mm-1815240000-Cont-loop | 70 | 70 | 0 |  | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109235
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355JTC0000 | 10Pole Plug 2.5mm-1815280000-Cont-loop | 96 | 96 | 0 |  | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109237
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 276 | 12 | 264 | 6100K019 | R57-O-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 264 | 4 | 260 | free_stock | R57-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 260 | 260 | 0 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109241
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355KPC0000 | Locking ele. 1816130000 for ZT2.5/4AN/2 | 140 | 2 | 138 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355KPC0000 | Locking ele. 1816130000 for ZT2.5/4AN/2 | 138 | 138 | 0 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109243
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355LMC0000 | Coding element 1856860000 - ZT4/4AN/2 | 184 | 28 | 156 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355LMC0000 | Coding element 1856860000 - ZT4/4AN/2 | 156 | 8 | 148 | free_stock | R57-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355LMC0000 | Coding element 1856860000 - ZT4/4AN/2 | 148 | 8 | 140 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355LMC0000 | Coding element 1856860000 - ZT4/4AN/2 | 140 | 140 | 0 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109245
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355LPC0000 | Coding element 1816150000 | 188 | 24 | 164 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355LPC0000 | Coding element 1816150000 | 164 | 8 | 156 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355LPC0000 | Coding element 1816150000 | 156 | 156 | 0 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109247
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355MPC0000 | Strain Relief Wied mulpart # 1816140000 | 140 | 2 | 138 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355MPC0000 | Strain Relief Wied mulpart # 1816140000 | 138 | 138 | 0 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109249
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 276 | 276 | 0 | 6100K023 | R53-R-1-K013_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB539500002019 | SERV IS LABEL in Stainless Steel Plates | 23 | 23 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB60050819P0103 | Braided HARNESS TUBE (D40) | 345 | 95 | 250 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB60050819P0103 | Braided HARNESS TUBE (D40) | 250 | 35 | 215 | free_stock | R67-A-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB60050819P0103 | Braided HARNESS TUBE (D40) | 215 | 15 | 200 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 23 | 23 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB60050819P0106 | Braided HARNESS TUBE (D30) | 460 | 40 | 420 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB60050819P0106 | Braided HARNESS TUBE (D30) | 420 | 20 | 400 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB60050819P0107 | Braided HARNESS TUBE (D20) | 230 | 20 | 210 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB60050819P0107 | Braided HARNESS TUBE (D20) | 210 | 10 | 200 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAZ21500101 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 73 | 50 | 23 | 6100KDP01 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 28100 | SCREW VITE ACTC D7971 T21572/4.2x6.5 | 82 | 82 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 28132 | RETAINING RING ACC. T22414/3.2 | 22 | 22 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 28373 | LOCK NUT ACC TO T21192/M2.5x0.45 | 46 | 46 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 28452 | FLEXIBLE SPIROID PINS T22513/3X26 | 10 | 2 | 8 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 29823 | TOMMY HEAD SCREW ACC. T21010/M2.5x20 | 46 | 46 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 2TRE123451P0001 | 3 PIN SOCKET SWITCH,13A,250V,BSRDP-I | 2 | 1 | 1 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014480P0004 | RETAINING_WASHER_DIN6799_6-SPST/A3K | 46 | 10 | 36 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 98 | 26 | 72 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 72 | 2 | 70 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 70 | 2 | 68 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8083036
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 68 | 2 | 66 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8108485
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 66 | 2 | 64 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8108701
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 64 | 2 | 62 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8120209
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 62 | 2 | 60 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8120275
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 60 | 2 | 58 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8132312
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 58 | 2 | 56 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8132353
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014538P0012 | SPIRAL_PIN_ISO8748_4X20-ST/BK | 44 | 44 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014538P0014 | SPIRAL_PIN_ISO8748_4X30-ST/BK | 22 | 22 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014618P0001 | SAFETY_GRIPPER_BFK/A_BN13193_4-SPST/PH | 22 | 22 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014618P0003 | SAFETY_GRIPPER_BFK/A_BN13193_6-SPST/PH | 22 | 22 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 500214111 | WASHER T22001/6.8X18 | 77 | 38 | 39 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 5022 643 | COVER PROFILE, AP3 | 36.8 | 2.8 | 34 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 5022 643 | COVER PROFILE, AP3 | 34 | 2.4 | 31.6 | free_stock | R15-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 5022 643 | COVER PROFILE, AP3 | 31.6 | 1.2 | 30.4 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 5022 643 | COVER PROFILE, AP3 | 30.4 | 0.4 | 30 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 575 | 25 | 550 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8071535
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 5217 708-3 | M.CONTACT/HAN-E16M/09330162601 | 4 | 1 | 3 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 5217 708-3 | M.CONTACT/HAN-E16M/09330162601 | 3 | 1 | 2 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 5217 708-7 | F.CONTACT/HAN-E16F/09330162701 | 4 | 1 | 3 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 5217 708-7 | F.CONTACT/HAN-E16F/09330162701 | 3 | 1 | 2 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 564093/001 | BLOCK FOUNDATION - ZINK COATED | 92 | 92 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 565937/001 | LEAF SPRING 499355009 | 6 | 6 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 593502001 | BUSHING | 25 | 25 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 9ADJ100023P0357 | BLIND_RIVET_ISO15979_6,4x16-ST/ST | 190 | 34 | 156 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 11342 2100-1 | GLASS,220X350X8.8, GCE8000436P0101 | 30 | 30 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2093 7000-4 | RAYCHEM SHRINKABLE TUBE, BPTM 75/30-A/U | 6.6 | 6.6 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2093 7000-5 | RAYCHEM SHRINKABLE TUBE, BPTM 100/40-A/U | 43.92 | 43.92 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2093 7000-6N | RAYCHEM SHRINKABLE TUBE, BPTM 120/50-A/U | 82.19 | 63.35 | 18.84 | free_stock | R15-J-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2093 7000-6N | RAYCHEM SHRINKABLE TUBE, BPTM 120/50-A/U | 18.84 | 9.9 | 8.94 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 50 | 50 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 345 | 25 | 320 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 320 | 5 | 315 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 345 | 100 | 245 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 245 | 90 | 155 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 22 | 2 | 20 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 49 | 7 | 42 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-1865-02 | YELLOW TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 345 | 90 | 255 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-1865-02 | YELLOW TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 255 | 65 | 190 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-1865-03 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 230 | 230 | 0 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 29.9 | 29.9 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 138 | 36 | 102 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 102 | 22 | 80 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 19.34 | 4.08 | 15.26 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2522-2000-01 | HOOD HAN-E16,09300161520 | 4 | 1 | 3 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2522-2000-01 | HOOD HAN-E16,09300161520 | 3 | 1 | 2 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2522-2000-03 | CABLE SEALING,PG21, | 4 | 4 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 23 | 1 | 22 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 23 | 1 | 22 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 1380 | 390 | 990 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 990 | 280 | 710 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 167.4 | 50 | 117.4 | 606PD013 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 117.4 | 50 | 67.4 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 67.4 | 6.9 | 60.5 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 60.5 | 60.5 | 0 | 6100KDP01 | PO-SEP-8392-[3] | GR_in_process | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i | 349 | 02-11-2025
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-493 | BOLT HEX HEAD M10X30 | 484 | 484 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-496 | BOLT HEX HEAD M10X45 | 66 | 66 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-659 | BOLT HEX HEAD M20X45 | 66 | 24 | 42 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-659 | BOLT HEX HEAD M20X45 | 42 | 12 | 30 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-660 | BOLT HEX HEAD M20X50 | 9 | 6 | 3 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-666 | BOLT HEX HEAD M20X90 | 42 | 6 | 36 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 754 | 123 | 631 | 6100K008 | R58-A-1-K11B_SEP | consumption | 2025-10-18 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8161201
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 631 | 631 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Material Issue | 8296184
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-291 | BOLT SOCKET CAP HEAD M4X12 | 44 | 12 | 32 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-291 | BOLT SOCKET CAP HEAD M4X12 | 32 | 12 | 20 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-293 | BOLT SOCKET HEAD M4X16 | 4 | 4 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-295 | BOLT SOCKET HEAD M4X20 | 12 | 12 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Material Issue | 8296185
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-299 | BOLT SOCKET CAP HEAD M4X30 | 8 | 8 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-325 | BOLT SOCKET CAP M5X10 | 20 | 2 | 18 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 66 | 66 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-333 | BOLT SOCKET CAP HEAD M5X25 | 6 | 4 | 2 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-333 | BOLT SOCKET CAP HEAD M5X25 | 2 | 2 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-366 | BOLT SOCKET CAP HEAD M6X12 | 80 | 80 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 63 | 30 | 33 | 6100K011B | R58-A-1-K017_SEP | consumption | 2025-10-19 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8173342
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 33 | 33 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Material Issue | 8296186
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-379 | BOLT SOCKET CAP HEAD M6X45 | 4 | 4 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-430 | BOLT SOCKET CAP HEAD M6X50 | 12 | 9 | 3 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 590 | 184 | 406 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 406 | 150 | 256 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 296 | 48 | 248 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 248 | 24 | 224 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-500 | BOLT SOCKET CAP HEAD M10X45 | 480 | 54 | 426 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-500 | BOLT SOCKET CAP HEAD M10X45 | 426 | 48 | 378 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-505 | CHEESE HEAD BOLT M10X70 | 276 | 276 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-508 | BOLT SOCKET CAP HEAD M10X100 | 126 | 126 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 58 | 25 | 33 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 45 | 24 | 21 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 21 | 6 | 15 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-542 | BOLT SOCKET CAP HEAD M12X50 | 66 | 24 | 42 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-544 | BOLT SOCKET CAP HEAD M12X60 | 120 | 57 | 63 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-544 | BOLT SOCKET CAP HEAD M12X60 | 63 | 3 | 60 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-630 | **** USE DMS 2121 2519-430 **** | 9 | 9 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2852-536 | COUNTERSUNK ALLEN HEAD M12X30 | 92 | 92 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 34 | 34 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Material Issue | 8296717
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2011-114 | NUT, HEX M5 | 18 | 18 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 325 | 325 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 1190 | 972 | 218 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 218 | 200 | 18 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 18 | 18 | 0 | 606PD013 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 329 | 64 | 265 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2011-124 | NUT, HEX M16 | 9 | 9 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2013-122 | NUT HEX H D GALV M12 | 114 | 114 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2013-124 | NUT HEX H D GALV M16 | 276 | 276 | 0 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 843-1 | RIVET NUT M6 (HEXAGONAL) | 10 | 4 | 6 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 3845 | 1116 | 2729 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 2729 | 1062 | 1667 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 1667 | 148 | 1519 | 606PD013 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 132 | 3 | 129 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 363-1 | WASHER, LOCK 10X5X0.5 | 23 | 23 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 115 | 115 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 23 | 23 | 0 | free_stock | R68-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 138 | 138 | 0 | free_stock | R68-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2634 010-91 | UN-INSUL SLeve Lugs KE1510ST (1.5mm) | 460 | 460 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2634 010-92 | UN-INSUL SLEEVE Lugs for 2.5mm KE2510ST | 1150 | 1150 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2634 010-93 | Un-Insul Sleeve Lugs 4.0 mm KE410ST | 1150 | 1150 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2634 011-2 | TERM.LUGS BLADE BF-PP12/25 2.5MM | 2300 | 2300 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2634 011-51 | TERM.LUGS BLADE RF-PP 12/23 | 6900 | 6900 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2641 2026-4 | TERM.LUGS SPADE RF-U4 1.5/M4 | 2875 | 2875 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 1104 | 108 | 996 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2641 2034-11 | RING TYPE LUGS GF-M 5 | 460 | 460 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2641 2034-2 | TERM.LUGS RING RF-M4 1.5/M4 | 2300 | 2300 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2641 2034-4 | TERM.LUGS RING BF-M4 | 4600 | 4600 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2641 2034-7 | TERM.LUGS BF-M5 (RING) | 2760 | 2760 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2641 2034-8 | WIRE LUGS RING TYPE BF-M6 2.5/M6 | 184 | 184 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2641 2034-9 | RING TYPE LUGS BF-M 8 | 184 | 184 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 46 | 46 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 184 | 184 | 0 | free_stock | R66-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 924 0010 | Combiflex wire Socket 1.5mm 1MRK002136-B | 4600 | 580 | 4020 | free_stock | R14-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 924 0010 | Combiflex wire Socket 1.5mm 1MRK002136-B | 4020 | 20 | 4000 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 924 0010 | Combiflex wire Socket 1.5mm 1MRK002136-B | 4000 | 200 | 3800 | 6100K019 | R14-B-1-KDP1_SEP | consumption | 2025-10-13 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8069888
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 924 0020 | Combiflex wire Socket 2.5mm 1MRK002136-E | 2760 | 120 | 2640 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 924 0020 | Combiflex wire Socket 2.5mm 1MRK002136-E | 2640 | 40 | 2600 | free_stock | R14-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0301012P0100 | CHEESE HEAD B0LT M3X6 | 8 | 8 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0303179P0100 | CYLINDER HEAD BOLT M10X80 DIN 91 | 6 | 6 | 0 | 606PD013 | PO-SEP-3097-[4] | GR_in_process | 2023-12-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST | PO#7061 | 10 | 21-12-2023 |  |  |  | PO#7061
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0305850P0100 | POLYAMID BOLT M6X20 | 119 | 62 | 57 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0336970P0100 | BOLT,TAPTITE HEX BOLT M5X12 | 12 | 6 | 6 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0350009P0100 | NUT M6 DIN 439-04 | 4 | 4 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0352913P0100 | NUT M10 DIN 555-Polyamide | 36 | 18 | 18 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0367308P0100 | NUT, HEX - M5, DIN 985-6 ( LOCK NUT ) | 4 | 4 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369010P0100 | RIVET NUT M6X16 WITH GROOVE | 119 | 62 | 57 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369215P0100 | RIVET NUT , M12 | 56 | 24 | 32 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 1064 | 190 | 874 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 874 | 25 | 849 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 282 | 15 | 267 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8128751
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 267 | 8 | 259 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8132356
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 259 | 8 | 251 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8131788
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 251 | 8 | 243 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8150149
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 243 | 8 | 235 | 6100K019 | R58-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8150332
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0401027P0100 | WASHER FLAT 10.5,DIN433-ST | 138 | 2 | 136 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0402005P0100 | WASHER,SPRING A3.2 | 8 | 8 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0402008P0100 | WASHER, A5., DIN 125-ST | 20 | 4 | 16 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0402909P0100 | WASHER POLYAMID, A6.4, DIN 125 | 119 | 62 | 57 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0410006P0100 | SPRING A4, DIN 127-FST | 64 | 52 | 12 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0410006P0100 | SPRING A4, DIN 127-FST | 12 | 12 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0410007P0100 | SPRING RING, A5, DIN 127-FST | 14 | 14 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0412007P0100 | SPRING RING 10 DIN 7980-FST | 120 | 48 | 72 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0413307P0100 | CONTACT WASHER 12 | 40 | 32 | 8 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0417501P0100 | SPLIT PIN FOR FRICK B. CHUCK | 34 | 34 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0418011P0100 | REVTAINING RING BORE-8 | 4 | 4 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 97 | 2 | 95 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8132306
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 95 | 2 | 93 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8132330
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 93 | 2 | 91 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8140338
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 91 | 2 | 89 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8140383
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0422025P0100 | RETAINING RING (SHAFT)30X1.5 | 8 | 8 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0438403P0100 | SPRG. PIN 2X10 DIN EN 28748 ST | 23 | 23 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0438423P0100 | SPRING PIN 3X16 | 16 | 4 | 12 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8140296
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0438425P0100 | SPRING PIN SLOTTED 3X20 (EQUIV.=28272) | 30 | 6 | 24 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0438432P0100 | PIN,SPRING (SLOTED) 4X10 | 32 | 32 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0438453P0100 | PIN,SPRING (SLOTED) 5X26 | 42 | 42 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0438455P0100 | SPRING PIN SLOTTED 5X30 | 10 | 10 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0457040P0100 | BLIND RIVET 6.4X12 STEEL | 389 | 188 | 201 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0493108P0100 | BALL SHAPED HANDLE | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0734028P0100P | K - BALL SHAPED HANDLE (ZINC CHRM) | 8 | 8 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0909121P0100 | STRAIN RELIEF TYPE ZE2/10 | 10 | 2 | 8 | 606PD013 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0931306P0100 | BUSHING KD20-30/115(2033335)GJ (LOWER) | 3 | 3 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0931316P0100 | BUSBAR INSERT 2XD100 | 75 | 75 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0990108P0100 | DOUBLE BIT KEY 3.2 | 12 | 12 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0990431P0100 | HANDLE | 341 | 341 | 0 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0990479P0100 | WHEEL FOR TRUCK 100X35 POLYAMID | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0996020P0100 | PROTECTOR CAP M12 SW17-1-G15/H5 | 24 | 24 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0997050P0100 | HAND CRANK FOR SWITCH TRUCK | 6 | 6 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0998122P0100 | TUBING 28X36 FOR PG29 | 9.1 | 9.1 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0998124P0100 | TUBING KUW 17X21,PG16 (Use ** 1YAB010415P0103 **) | 1.6 | 1.6 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0998131P0100 | TUBE HOLDER-LK / MPG16 | 4 | 4 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0998168P0100 | PLASTIC BUSHING EK/G36 | 5 | 2 | 3 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4117104P0106 | TUBE G16X100 DIN 490216 | 22 | 22 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4117104P0117 | TUBE G16X9 | 44 | 44 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4129015P0128P | HEX.PART 17X677 ZINC CHR. | 22 | 22 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4329220P0100 | THREADED DOWEL M12X37 | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4366010P0100 | NUT(DADO D'ANCORAGGIO) M10 WN366-ST37-2 | 190 | 190 | 0 | 6100KDP01 | R56-R-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4395060P0100 | WASHER,PLAIN , LARGE 6.1/18X1 | 44 | 4 | 40 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4395856P0100 | PLAIN WASHER, LARGE 6.2x12x0.2 | 54 | 32 | 22 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4396073P0100 | WASHER LARG PLN (12.1/23.5X2.5 | 40 | 20 | 20 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4520999P0100 | INDICATION LABELS ( HOCK SYSMBLE ) | 8 | 7 | 1 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4520999P0100 | INDICATION LABELS ( HOCK SYSMBLE ) | 1 | 1 | 0 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8127538
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4539452P0100 | INDICATION LABEL Mech.Operation STICKER | 75 | 46 | 29 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000495R0101 | SHAFT COMPL. | 22 | 22 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000524P0101P | GROOVED PIN | 22 | 22 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000535R0101P | K- BRACKET COMPL. ZINC COATED | 22 | 22 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000541P0101P | ADJUSTING RING | 10 | 2 | 8 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000542P0101 | BUSH D10/6.2X15 | 20 | 4 | 16 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000545P0101 | COMPRESSION SPRING | 20 | 20 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000553P0101 | ADJUSTING FISH PLATE | 44 | 44 | 0 | 6100KDP01 | R55-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000581P0101 | CANTILEVER SPRING | 32 | 32 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000582P0101 | SPIRAL SPRING | 22 | 22 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000847P0101P | K - STUD | 10 | 2 | 8 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7001026P0101 | INSULATION TUBE; L=45MM. | 44 | 44 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7001732R0105 | EARTHING SWITCH: EK6/ZS1-1710-275 | 5 | 2 | 3 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7001732R0105 | EARTHING SWITCH: EK6/ZS1-1710-275 | 3 | 1 | 2 | 6100K019 | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7001936P0101P | K - HANDLE (CHROME PLATED) | 28 | 28 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7002424P0101P | K - BEARING SHAFT (ZINC CHRM) | 56 | 56 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7002476P0101 | FIXING BAR | 2 | 2 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003012P0101P | TUBE 8X5.1X25 | 10 | 2 | 8 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003534P0101 | DETENT (RASTE) | 10 | 10 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003536P0101 | DETENT | 10 | 2 | 8 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003538P0101 | COVER | 2 | 2 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003544P0101 | SPINDLE | 10 | 1 | 9 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003544P0101 | SPINDLE | 9 | 1 | 8 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003544P0101 | SPINDLE | 8 | 1 | 7 | 6100K019 | R59-Q-1-KDP1_SEP | consumption | 2025-10-16 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8144861
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003553P0101P | HEXAGON BOLT | 78 | 62 | 16 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003556P0101 | SLIDE | 20 | 2 | 18 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003556P0101 | SLIDE | 18 | 1 | 17 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8120300
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003557P0101 | SLIDE | 4 | 2 | 2 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003557P0101 | SLIDE | 2 | 1 | 1 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8120263
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003558P0101 | ADJUSTING SCREW | 2 | 2 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003560P0101 | SPACER | 1 | 1 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003562P0101P | K - BUSH 10X60 | 2 | 2 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003563P0101 | SHAFT | 2 | 2 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003568P0101 | NUT SPECIAL | 10 | 2 | 8 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003572P0101 | TORSION SPRING | 1 | 1 | 0 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003578P0101 | SQUARE BOLT 4KT8/20 | 20 | 4 | 16 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003579P0102 | TENSION SPRING 6.5/.9/30/16 | 10 | 2 | 8 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003580P0101 | CCOMPRESSION SPRING | 2 | 2 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003581P0101 | COMPRESSION SPRING 7.5/0,8/9/25 | 20 | 4 | 16 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003582P0101 | NUT | 20 | 4 | 16 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7004025R0102 | DRAW OUT DEVICEP210-S200 ASSY. | 2 | 2 | 0 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7004046R0101 | RECTIFIER COMPL. | 2 | 2 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7102436P0100 | PLUG HOUSING SOCKET/GEHAUSE | 24 | 24 | 0 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7102438P0100 | COVER OF CONTROL PLUG/SOCKET | 9 | 9 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7107642P0100 | TENSION SPRING 8.9/0.7/35/10 | 10 | 2 | 8 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7109399R0106 | AUXILIARY SWITCH 5NC | 22 | 6 | 16 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7109399R0118 | SLIDE F.AUX.SWICH 5NC | 5 | 2 | 3 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7109399R0119 | AUX.SWITCH 5NO. (S8,S9) | 4 | 4 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7169312R0145 | EARTHING SWITCH: EK6-ZS1-1706-210 | 15 | 15 | 0 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7204654P0101 | BOLT 7/4X15 | 24 | 2 | 22 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8000633P0113P | MOUNTING CHANNEL 760mm (GCE8000633P0113) | 40 | 26 | 14 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8000633P0113P | MOUNTING CHANNEL 760mm (GCE8000633P0113) | 14 | 4 | 10 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8000633P0113P | MOUNTING CHANNEL 760mm (GCE8000633P0113) | 10 | 2 | 8 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-13 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Work in Process Pick | 8077530
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8000633P0115 | MOUNTING CHANNEL L325mm | 6 | 6 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8000825P0101 | SPRING | 25 | 25 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8000910P0101 | PACKING PIECE 80X15 | 51 | 51 | 0 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8000981P0101P | THREADED PIECE | 22 | 22 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8001698R0107P | LEVER MECHANISM LEFT-SX 2X R250/55(w1000 | 5 | 2 | 3 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8001698R0108P | LEVER MECHANISM RIGHT,DX2X R250/55(w1000 | 5 | 2 | 3 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8001710P0101 | SPECIAL BOLT | 10 | 2 | 8 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8001975P0101 | WASHER 40X21X10 (LOCAL PUR) | 36 | 18 | 18 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8001976P0101 | WASHER 40X21X2 | 18 | 3 | 15 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8002370P0101 | DOCKING RECEPTANCE | 46 | 46 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8002372P0101P | BUSHING | 11 | 11 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8002375P0101 | TENSION SPRING | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8002757P0101 | Insert 1X60X10 (2024231) GJ.GER | 6 | 6 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8002757P0102 | Insert 80X10 | 96 | 96 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8002875P0101 | WINDOW PANE 350X220X16,8 (KONEX) | 16 | 16 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003360R0101P | LEVER MECHANISM LEFT, 2xR250/55(W800) | 16 | 16 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003360R0102P | LEVER MECHANISM RIGHT,2xR250/55 (W800) | 16 | 16 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003624R0102 | MONOBLOCCO-SPOUT 1250A,ZS1 | 90 | 90 | 0 | free_stock | R13-A-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003651P0101P | INSULATING CAP | 131 | 131 | 0 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003671P0120 | SPECIAL SCREW M12X30/101 | 62 | 62 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003672P0101 | COVER-COPERTURA 12KV ZS1 1250A | 90 | 90 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003861P0101 | BEARING SHAFT (ZINC CHRM) | 4 | 4 | 0 | 6100K023 | R58-A-1-K023_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004145P0101P | INTERLOCKING BOLT | 8 | 8 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004478P0101 | BUSHING PLATE BELOW / 3 HOLES | 1 | 1 | 0 | free_stock | R16-L-1-K019_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004479P0101P | PROTECTIVE COVER (DWG: GCE8004479P0101) | 6 | 6 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004581P0101 | SPRING COMPRESSION | 8 | 8 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004633P0101 | ANGLE LEFT ( POLY ) | 8 | 8 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004633P0102 | ANGLE RIGHT ( POLY ) | 8 | 8 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004770P0101 | SHROUD 17.5kV | 21 | 21 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004990P0101 | CARRIER FOR BUSBAR SHROUD | 33 | 30 | 3 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005031R0101 | BUSHING ZS1/ (3 IN 1) DEACE | 23 | 23 | 0 | free_stock | R59-H-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005595R0109P | Busbar D100,12mm Thick 800/1000,L=830 | 18 | 4 | 14 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005595R0110P | Busbar D100,12mm Thick 800/1000,L=895 | 18 | 4 | 14 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005595R0111P | Busbar D100,12mm Thick 800/1000,L=960 | 18 | 4 | 14 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8006031P0101 | COVER FOR BUSBAR JOINTS | 51 | 51 | 0 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8007213P0101 | SHROUD ZS3.2, Middle | 18 | 3 | 15 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8007214P0101 | COVER FOR SHROUD ZS3.2, end side | 36 | 6 | 30 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8011409R0101 | LEVER COMPLETE LEFT SIDE | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8011409R0102 | LEVER COMPLETE RIGHT SIDE | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8011679R0101P | REIFORCING ANGLE COMPLETE LEFT | 4 | 4 | 0 | 6100KDP01 | R56-I-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013262P0101 | SHROUD | 4 | 4 | 0 | 6100KDP01 | R56-I-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8381281P0100 | GUIDE ROLLER | 5 | 5 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8494256P0101 | DISTANCE TUBE | 22 | 22 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9371453P0101 | CABLE BUSHING LOWER PART | 26 | 26 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9371454P0101 | CABLE BUSHING UPPER PART | 2 | 2 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9401529P0100 | Bush | 22 | 22 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9401678R0101 | HOUSING (PLUG SOCKET)COMPL. | 3 | 3 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9464131P0100 | EARTHING SWITCH DISPLAY | 22 | 22 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9478304P0102P | ROLLER | 56 | 56 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9478350P0101 | SUPPORTING BOLT 6Kt14/M6X23 | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9478476P0101 | FIXING RING | 10 | 2 | 8 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9576618P0100 | BUSH D18/12,2X8 | 44 | 44 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCEC830444P0101P | K-SPACER D12/4.5X8,ZS1/ZS3.2Yellow Chrom | 44 | 44 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | MV RK 926 011-AE | TEST PLUG HANDLE, RTXH 8 | 1 | 1 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | MV RK 926 011-BC | TEST PLUG HANDLE: RTXH 18; RK 926 011-BC | 1 | 1 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | MV-CR-U125DC3 | CR-U125DC3 - 1SVR405622R8200 | 2 | 2 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | MV-CR-U3S | Socket -FOR 3 C/O AND MODULE TIMER | 2 | 2 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | MV-CR-UH | Holder interface relay 1SVR405669R0000 | 2 | 2 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | MV-CR-UT | TIME MODULE 1SVR405667R0000 | 2 | 2 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | PKE 1508 | END SLEEVES PKE 1508 (1x1.5sqmm , Black) | 345 | 345 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | PKT 1508 | END SLEEVES PKT 1508 (2x1.5sqmm , Black) | 345 | 345 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | PKT 2512 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 460 | 340 | 120 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | PKT 2512 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 120 | 20 | 100 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1000025P0001P | BUSHING (LOCAL PUR) | 66 | 66 | 0 | 6100K023 | R58-A-1-K023_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1000027P0001P | K-PLATE | 45 | 45 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1000048P0001P | PIN (LOCAL PUR) | 22 | 22 | 0 | 6100K023 | R58-A-1-K023_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1000049P0001 | COMPRESSION SPRING | 22 | 22 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | T81722 | Plastic plug for LV Box (Micro. Sw. ) | 138 | 138 | 0 | 6100K013 | R58-J-1-K013_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1815230000 | 5Pole Plug 2.5mm-1815230000-Cont-loop | 22 | 18 | 4 | 6100KDP01 | R57-O-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1815230000 | 5Pole Plug 2.5mm-1815230000-Cont-loop | 4 | 1 | 3 | free_stock | R57-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1815230000 | 5Pole Plug 2.5mm-1815230000-Cont-loop | 3 | 1 | 2 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1815230000 | 5Pole Plug 2.5mm-1815230000-Cont-loop | 2 | 2 | 0 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | [5 empty] | Subinventory Transfer | 8109405
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1855030000 | 6Pole Plug 4mm-1855030000-AC looping | 23 | 20 | 3 | 6100KDP01 | R57-J-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1855030000 | 6Pole Plug 4mm-1855030000-AC looping | 3 | 1 | 2 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1855030000 | 6Pole Plug 4mm-1855030000-AC looping | 2 | 1 | 1 | free_stock | R57-J-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1855030000 | 6Pole Plug 4mm-1855030000-AC looping | 1 | 1 | 0 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 40 | 14 | 26 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 26 | 8 | 18 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 18 | 2 | 16 | free_stock | R57-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 16 | 16 | 0 |  | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109411
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 41 | 11 | 30 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 30 | 10 | 20 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 07686 | WASHER AC EL DIN137 T22120/8 A | 12 | 12 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 07853 | HEX. HEAD BOLT T21000/3X16 | 18 | 18 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 07934 | TOMMY HEAD SCREW ACC T21010/M3x6 | 160 | 160 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 07940 | TOMMY HEAD SCREW ACC T21010/M3X20 | 48 | 48 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 08222 | COUNTER SUNK SCREW 6X16 ACC T21030/6X16 | 4 | 4 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 09011 | LOCK NUT T21192/M3N - DIN 985 A2K | 12 | 12 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP40200 | Busbar, Copper, 80 x 5 mm, R=2.5 | 6.23 | 6.23 | 0 | 606PD013 | BBR-1-1-PD\-13/MV_SEP | inventory | 2025-11-03 | Mechanical | Automated: Replaced 1535 1034-222 by SEP40200. | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP40200 | Busbar, Copper, 80 x 5 mm, R=2.5 | 51.4 | 51.4 | 0 | 606PD013 | BBR-1-1-PD\-13/MV_SEP | inventory | 2025-11-03 | Mechanical - Accessories | Automated: Replaced 1535 1034-222 by SEP40200. | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP40254 | Busbar, Copper, 50 x 10 mm, R=1 | 3.84 | 3.84 | 0 | 6100KDP01 | BBR-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical | Automated: Replaced 1535 1044-120 by SEP40254. | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP40196 | Busbar, Copper, 60 x 10 mm, R=5 | 71.561 | 71.561 | 0 | free_stock | BBR-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical | Automated: Replaced 1535 1044-125 by SEP40196. | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP40187 | Busbar, Copper, 40 x 10 mm, R=1 | 19.864 | 19.864 | 0 | free_stock | BBR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical | Automated: Replaced 1535 1044-96 by SEP40187. | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP40184 | Busbar, Copper, 40 x 5 mm, R=1 | 3.2 | 3.2 | 0 | free_stock | BBR-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical | Automated: Replaced 1535 1048-235 by SEP40184. | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1815230000 | 5Pole Plug 2.5mm-1815230000-Cont-loop | 40 | 40 | 0 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109405
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1855030000 | 6Pole Plug 4mm-1855030000-AC looping | 41 | 41 | 0 |  | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109403
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VCR000474F0001 | BLOCK | 81 | 72 | 9 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VCR000474F0001 | BLOCK | 9 | 9 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7600349P0101 | SHROUD | 2 | 2 | 0 | 6100KDP01 | R56-I-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7601387P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Short | 41 | 11 | 30 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7601387P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Short | 30 | 1 | 29 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7601389P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Long | 41 | 11 | 30 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB000002-FDV | MIMIC DIAGRAM, INCOMER-2W,VT | 2 | 1 | 1 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 41 | 12 | 29 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 29 | 1 | 28 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 28 | 1 | 27 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-13 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8082420
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 27 | 1 | 26 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8096129
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 26 | 1 | 25 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8096144
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 25 | 1 | 24 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8107930
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 24 | 1 | 23 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8108749
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 23 | 1 | 22 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8120203
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 22 | 1 | 21 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8120257
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 21 | 1 | 20 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8132362
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 20 | 1 | 19 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8140290
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 19 | 1 | 18 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8140362
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010032P0101 | CT PLATE,UPPER,W1000 (PAINT RAL7035-STD) | 3 | 2 | 1 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010033P0101 | CT MOUNTING PLATE, LOWER, W1000, 3150A | 3 | 2 | 1 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010072P0101P | CONTACT PIN 35 DIA, 90L | 204 | 72 | 132 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010072P0101P | CONTACT PIN 35 DIA, 90L | 132 | 30 | 102 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 150.67 | 71.71 | 78.96 |  | R16-L-1-K019_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109209
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 78.96 | 3.5 | 75.46 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8099587
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 75.46 | 3.5 | 71.96 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8099719
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 71.96 | 3.5 | 68.46 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8108698
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 68.46 | 0.2 | 68.26 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8108602
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 68.26 | 3.5 | 64.76 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8120206
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 64.76 | 3.5 | 61.26 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8120284
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010138P0120 | Cover for push button rod | 39 | 36 | 3 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010138P0120 | Cover for push button rod | 3 | 3 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010366P0109 | Self tapping screw pan head M4x5mm SS | 2050 | 2050 | 0 | free_stock | R13-S-1-K006_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010378P0111 | SEC. PIN MALE 1.5 MMZS1 | 50 | 50 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010378P0111 | SEC. PIN MALE 1.5 MMZS1 | 100 | 100 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010378P0113 | PIN,CONTACT MALE 2.5 | 100 | 100 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010491P0101 | FLEX. CABLE,70MM.SQ, PVC 85 YEL/GRN,85°C | 64.4 | 64.4 | 0 | free_stock | R57-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB52322VW60N00 | VD4/PW 171225-p210-125VDC-ZS1-1250A @ 60Hz, in UG ZS1- with upper CTs as per NG Stanadrad | 4 | 4 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5320XDB1XN02 | DIGITAL VOLTMETER, Cl 1.0, 3PH4W, 5-500V, 60Hz, 150% Un CONT, 3 LINE DISPLAY LED, MODBUS ¦ SECURE DPM 96 V300 | 2 | 2 | 0 | 6100KDP01 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | LL10-W | ABB_LL10-W / LL10-W, AC/DC90-264V 50/60HZ | 41 | 41 | 0 | free_stock | R58-I-1-K11B_SEP | inventory | 2025-11-03 | LVA | Automated: Replaced 1YAB53301XIX0000 by LL10-W. | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5334XXAX1000 | FT-1 SW-Type 129A514G01 | 5 | 5 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5335XXAX1100 | COMBIFLEX TERMINAL BASE RX 2H -5619625-A | 191 | 128 | 63 | free_stock | R11-A-1-MVBM_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5335XXAX1100 | COMBIFLEX TERMINAL BASE RX 2H -5619625-A | 63 | 63 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5335XXAX1200 | COMBIFLEX TERMINAL BASE RX4 (4U 12C) | 9 | 9 | 0 | free_stock | R11-A-1-MVBM_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5336XXAA3F00 | MCB S203-K 4 MC -3P 2CDS253001R0337 | 109 | 77 | 32 | free_stock | R16-L-1-KDP1_SEP | inventory | 2025-11-03 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5336XXAA3F00 | MCB S203-K 4 MC -3P 2CDS253001R0337 | 32 | 8 | 24 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5336XXAA3I00 | MCB 10A AC -3P - 2CDS253001R0427 | 8 | 8 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XBLXXN00 | MVAJ101 RA 0802_ 125VDC (8 NO + 2 NC) | 2 | 2 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XDAXXN01 | RXMVB2, RK 251 204-AP | 8 | 2 | 6 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5350XSABD000 | FLEX.CABLE,1/C,1.5MM GREY ATC,105 Deg C | 50 | 50 | 0 | free_stock | R56-H-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5350XSACN010 | FLEX.CABLE,1/C,2.5MM YE/GN ATC,105 Deg C | 5 | 5 | 0 | free_stock | R57-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block OTTA 6-T-P/P - 0790462 | 3174 | 1196 | 1978 | 6100K023 | R53-R-1-K013_SEP | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block OTTA 6-T-P/P - 0790462 | 1978 | 166 | 1812 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block OTTA 6-T-P/P - 0790462 | 1812 | 100 | 1712 | 6100K019 | R53-R-1-K013_SEP | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block OTTA 6-T-P/P - 0790462 | 1712 | 100 | 1612 | 6100KDP02 | R53-R-1-K013_SEP | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 13192 | 2936 | 10256 |  | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109215
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 10256 | 301 | 9955 | 6100K019 | PLT-1-1-KDP1_SEP | consumption | 2025-10-15 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8132097
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 9955 | 330 | 9625 | 6100K019 | PLT-1-1-KDP1_SEP | consumption | 2025-10-16 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8137213
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 1288 | 873 | 415 |  | R66-H-1-KDP1_SEP | consumption | 2025-10-14 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109217
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 415 | 44 | 371 | 6100K019 | R66-H-1-KDP1_SEP | consumption | 2025-10-15 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8131113
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355CPC0000 | Terminal End Plate 1816110000-Wiedmuller | 164 | 97 | 67 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109223
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355CTC0000 | Terminal End Plate 1816070000-Wiedmuller | 84 | 64 | 20 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109225
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 2050 | 400 | 1650 | 6100K023 | R17-A-1-K013_SEP | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 1650 | 50 | 1600 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 1230 | 400 | 830 | 6100K023 | R59-J-1-MVBM_SEP | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 830 | 195 | 635 | 6100K023 | R59-O-1-MVBM_SEP | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 635 | 170 | 465 | 6100K013 | R59-J-1-MVBM_SEP | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 465 | 135 | 330 | 6100K006 | 1-1-1-1 | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 330 | 110 | 220 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 220 | 110 | 110 | 6100K012B | R59-G-1-MVBM_SEP | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 110 | 100 | 10 | 6100K007 | 1-1-1-1 | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 10 | 10 | 0 | 6100K011B | R59-G-1-MVBM_SEP | consumption | 2025-10-18 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8162025
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355HAB0001 | Zack Strip-Vertical(11-20)- 1053027:0011 | 492 | 242 | 250 |  | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109229
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355HAB0001 | Zack Strip-Vertical(11-20)- 1053027:0011 | 250 | 40 | 210 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109231
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355HAB0002 | Zack Strip-Vertical Labeled(21-30) | 328 | 260 | 68 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355HAB0002 | Zack Strip-Vertical Labeled(21-30) | 68 | 68 | 0 | 6100KDP01 | R57-J-1-K019_SEP | inventory | 2025-11-03 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 246 | 110 | 136 |  | R13-S-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109233
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355JPC0000 | 6Pole Plug 2.5mm-1815240000-Cont-loop | 164 | 98 | 66 |  | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109235
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355JTC0000 | 10Pole Plug 2.5mm-1815280000-Cont-loop | 168 | 68 | 100 |  | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109237
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 492 | 240 | 252 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109241
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 252 | 12 | 240 | 6100K019 | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109239
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355KPC0000 | Locking ele. 1816130000 for ZT2.5/4AN/2 | 248 | 118 | 130 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109243
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355LMC0000 | Coding element 1856860000 - ZT4/4AN/2 | 328 | 196 | 132 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109245
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355LPC0000 | Coding element 1816150000 | 332 | 184 | 148 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109247
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355MPC0000 | Strain Relief Wied mulpart # 1816140000 | 248 | 118 | 130 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109249
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 492 | 119 | 373 | 6100K023 | R53-R-1-K013_SEP | inventory | 2025-11-03 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 373 | 73 | 300 | free_stock | R57-J-1-KDP1_SEP | inventory | 2025-11-03 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 300 | 12 | 288 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 288 | 6 | 282 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 282 | 12 | 270 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8069110
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 270 | 12 | 258 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8070567
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 258 | 12 | 246 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8071532
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 246 | 246 | 0 |  | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Subinventory Transfer | 8109251
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 41 | 41 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 28100 | SCREW VITE ACTC D7971 T21572/4.2x6.5 | 158 | 158 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 28132 | RETAINING RING ACC. T22414/3.2 | 40 | 40 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 28373 | LOCK NUT ACC TO T21192/M2.5x0.45 | 82 | 26 | 56 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 29823 | TOMMY HEAD SCREW ACC. T21010/M2.5x20 | 82 | 26 | 56 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 29823 | TOMMY HEAD SCREW ACC. T21010/M2.5x20 | 56 | 2 | 54 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 3WKA014538P0012 | SPIRAL_PIN_ISO8748_4X20-ST/BK | 80 | 28 | 52 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 3WKA014538P0014 | SPIRAL_PIN_ISO8748_4X30-ST/BK | 40 | 36 | 4 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 3WKA014538P0014 | SPIRAL_PIN_ISO8748_4X30-ST/BK | 4 | 4 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 3WKA014618P0001 | SAFETY_GRIPPER_BFK/A_BN13193_4-SPST/PH | 40 | 40 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 3WKA014618P0003 | SAFETY_GRIPPER_BFK/A_BN13193_6-SPST/PH | 40 | 40 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 564093/001 | BLOCK FOUNDATION - ZINK COATED | 164 | 28 | 136 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 564093/001 | BLOCK FOUNDATION - ZINK COATED | 136 | 4 | 132 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 564093/001 | BLOCK FOUNDATION - ZINK COATED | 132 | 4 | 128 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8108743
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 564093/001 | BLOCK FOUNDATION - ZINK COATED | 128 | 4 | 124 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8132359
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 564093/001 | BLOCK FOUNDATION - ZINK COATED | 124 | 4 | 120 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8140368
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 564093/001 | BLOCK FOUNDATION - ZINK COATED | 120 | 4 | 116 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8150344
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 593502001 | BUSHING | 44 | 40 | 4 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 593502001 | BUSHING | 4 | 4 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 11342 2100-1 | GLASS,220X350X8.8, GCE8000436P0101 | 70 | 48 | 22 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 11342 2100-1 | GLASS,220X350X8.8, GCE8000436P0101 | 22 | 20 | 2 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 11342 2100-1 | GLASS,220X350X8.8, GCE8000436P0101 | 2 | 2 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 2093 7000-4 | RAYCHEM SHRINKABLE TUBE, BPTM 75/30-A/U | 0.6 | 0.6 | 0 | free_stock | R15-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 2093 7000-5 | RAYCHEM SHRINKABLE TUBE, BPTM 100/40-A/U | 92.32 | 11.3 | 81.02 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 53.3 | 43.4 | 9.9 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 9.9 | 6.5 | 3.4 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2522-2000-03 | CABLE SEALING,PG21, | 2 | 2 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | BM0145-1373-ASYP | Step Ladder SEC-Version 650mm Width | 1 | 1 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DM0000003059 | ‭CT SUPERVISION RELAY, 40msec DELAY, 125V DC, 4NC (TYPE: AR901) / 7PG1110-7AE10-0AF0‬ | 2 | 2 | 0 | 6010J577 | R14-S-1-MVBM_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 280 | 280 | 0 | 6100K023 | PO-SEP-8392-[1] | GR_in_process | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i | 280 | 02-11-2025
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-493 | BOLT HEX HEAD M10X30 | 820 | 820 | 0 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-496 | BOLT HEX HEAD M10X45 | 102 | 33 | 69 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-496 | BOLT HEX HEAD M10X45 | 69 | 24 | 45 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 40 | 40 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Material Issue | 8296184
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 1034 | 788 | 246 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Material Issue | 8296184
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 246 | 246 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Material Issue | 8298385
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-295 | BOLT SOCKET HEAD M4X20 | 8 | 8 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Material Issue | 8296185
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-299 | BOLT SOCKET CAP HEAD M4X30 | 8 | 8 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 86 | 86 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-333 | BOLT SOCKET CAP HEAD M5X25 | 2 | 1 | 1 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-366 | BOLT SOCKET CAP HEAD M6X12 | 126 | 126 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 97 | 97 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Material Issue | 8296186
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-505 | CHEESE HEAD BOLT M10X70 | 516 | 516 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-508 | BOLT SOCKET CAP HEAD M10X100 | 306 | 90 | 216 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-508 | BOLT SOCKET CAP HEAD M10X100 | 216 | 72 | 144 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-630 | **** USE DMS 2121 2519-430 **** | 9 | 9 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2852-536 | COUNTERSUNK ALLEN HEAD M12X30 | 164 | 28 | 136 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2852-536 | COUNTERSUNK ALLEN HEAD M12X30 | 136 | 16 | 120 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 48 | 48 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Material Issue | 8296717
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2011-114 | NUT, HEX M5 | 4 | 4 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2011-114 | NUT, HEX M5 | 4 | 4 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 473 | 473 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 654 | 56 | 598 | 606PD013 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 598 | 598 | 0 | free_stock | PO-SEP-5971-[44] | GR_in_process | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST | LV-BULK/ MECHANICAL ASSEMBLY | 5000 | 03-11-2025
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 1356 | 1356 | 0 | free_stock | PO-SEP-5971-[44] | GR_in_process | 2025-10-30 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST | LV-BULK/ MECHANICAL ASSEMBLY | 5000 | 03-11-2025
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2011-124 | NUT, HEX M16 | 9 | 9 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2013-122 | NUT HEX H D GALV M12 | 210 | 66 | 144 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2013-124 | NUT HEX H D GALV M16 | 612 | 198 | 414 | free_stock | R58-J-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2013-124 | NUT HEX H D GALV M16 | 414 | 144 | 270 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2154 363-1 | WASHER, LOCK 10X5X0.5 | 41 | 41 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 205 | 65 | 140 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 140 | 36 | 104 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 104 | 30 | 74 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 41 | 13 | 28 | free_stock | R68-I-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 28 | 8 | 20 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 20 | 6 | 14 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 246 | 78 | 168 | free_stock | R68-I-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 168 | 42 | 126 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 126 | 36 | 90 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 82 | 24 | 58 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2658 665-6 | TERM.LUGS RECPTACLE RF-F 608P | 58 | 22 | 36 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 328 | 132 | 196 | free_stock | R66-I-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 196 | 60 | 136 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 136 | 48 | 88 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0303179P0100 | CYLINDER HEAD BOLT M10X80 DIN 91 | 6 | 4 | 2 | 606PD013 | PO-SEP-3097-[4] | GR_in_process | 2023-12-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST | PO#7061 | 10 | 21-12-2023 |  |  |  | PO#7061
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0402005P0100 | WASHER,SPRING A3.2 | 8 | 4 | 4 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8096135
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0402005P0100 | WASHER,SPRING A3.2 | 4 | 4 | 0 | 6100K019 | R15-A-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8120305
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0410006P0100 | SPRING A4, DIN 127-FST | 18 | 12 | 6 | 6100K019 | R58-O-1-KDP1_SEP | consumption | 2025-10-14 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8101108
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0438403P0100 | SPRG. PIN 2X10 DIN EN 28748 ST | 41 | 41 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0493108P0100 | BALL SHAPED HANDLE | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0734028P0100P | K - BALL SHAPED HANDLE (ZINC CHRM) | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0931316P0100 | BUSBAR INSERT 2XD100 | 120 | 72 | 48 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990108P0100 | Double Bit Key 3.2 | 5 | 5 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990431P0100 | HANDLE | 563 | 289 | 274 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990431P0100 | HANDLE | 274 | 150 | 124 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990431P0100 | HANDLE | 124 | 19 | 105 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990431P0100 | HANDLE | 105 | 6 | 99 | 6100K019 | R59-A-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8144103
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990479P0100 | WHEEL FOR TRUCK 100X35 POLYAMID | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0996020P0100 | PROTECTOR CAP M12 SW17-1-G15/H5 | 12 | 12 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0997050P0100 | CB Truck Rack in/out (Crank) | 2 | 2 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0997050P0100 | HAND CRANK FOR SWITCH TRUCK | 2 | 2 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0998122P0100 | TUBING 28X36 FOR PG29 | 3.1 | 3.1 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0998122P0100 | TUBING 28X36 FOR PG29 | 5 | 5 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0998124P0100 | Use *** 1YAB010415P0103 *** | 0.8 | 0.8 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0998131P0100 | TUBE HOLDER-LK / MPG16 | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4117104P0106 | TUBE G16X100 DIN 490216 | 40 | 36 | 4 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4117104P0106 | TUBE G16X100 DIN 490216 | 4 | 4 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4117104P0117 | TUBE G16X9 | 80 | 28 | 52 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4129015P0128P | HEX.PART 17X677 ZINC CHR. | 40 | 36 | 4 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4129015P0128P | HEX.PART 17X677 ZINC CHR. | 4 | 4 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4329220P0100 | THREADED DOWEL M12X37 | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4366010P0100 | NUT(DADO D'ANCORAGGIO) M10 WN366-ST37-2 | 310 | 34 | 276 | 6100KDP01 | R56-R-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4366010P0100 | NUT(DADO D'ANCORAGGIO) M10 WN366-ST37-2 | 276 | 10 | 266 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4366010P0100 | NUT(DADO D'ANCORAGGIO) M10 WN366-ST37-2 | 266 | 2 | 264 | 6100K019 | R59-P-1-KDP1_SEP | consumption | 2025-10-16 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8144835
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4520999P0100 | INDICATION LABELS ( HOCK SYSMBLE ) | 8 | 3 | 5 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8127535
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4520999P0100 | INDICATION LABELS ( HOCK SYSMBLE ) | 5 | 3 | 2 | 6100K019 | INC-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8127538
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4520999P0100 | INDICATION LABELS ( HOCK SYSMBLE ) | 2 | 1 | 1 | 6100K019 | WH2-1-1-KDP1_SEP | consumption | 2025-10-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | [5 empty] | Work in Process Pick | 8127532
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000495R0101 | SHAFT COMPL. | 40 | 14 | 26 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000524P0101P | GROOVED PIN | 40 | 40 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000535R0101P | K- BRACKET COMPL. ZINC COATED | 40 | 40 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000553P0101 | ADJUSTING FISH PLATE | 80 | 80 | 0 | 6100KDP01 | R55-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000581P0101 | CANTILEVER SPRING | 46 | 46 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000582P0101 | SPIRAL SPRING | 40 | 40 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000835P0101 | BRACKET S=200 | 2 | 2 | 0 | 6100KDP01 | WH2-1-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7001026P0101 | INSULATION TUBE; L=45MM. | 80 | 28 | 52 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7001936P0101P | K - HANDLE (CHROME PLATED) | 4 | 4 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7002424P0101P | K - BEARING SHAFT (ZINC CHRM) | 8 | 8 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7002476P0101 | FIXING BAR | 2 | 2 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003572P0101 | TORSION SPRING | 2 | 1 | 1 | free_stock | R15-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7102436P0100 | PLUG HOUSING SOCKET/GEHAUSE | 1 | 1 | 0 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7102436P0100 | PLUG HOUSING SOCKET/GEHAUSE | 41 | 12 | 29 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7102436P0100 | PLUG HOUSING SOCKET/GEHAUSE | 29 | 8 | 21 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7102438P0100 | COVER OF CONTROL PLUG/SOCKET | 2 | 2 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7102438P0100 | COVER OF CONTROL PLUG/SOCKET | 5 | 5 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7169312R0145 | EARTHING SWITCH: EK6-ZS1-1706-210 | 35 | 16 | 19 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8000633P0115 | MOUNTING CHANNEL L325mm | 6 | 6 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8000825P0101 | SPRING | 41 | 41 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8000910P0101 | PACKING PIECE 80X15 | 111 | 111 | 0 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8000981P0101P | THREADED PIECE | 40 | 36 | 4 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8000981P0101P | THREADED PIECE | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8002370P0101 | DOCKING RECEPTANCE | 82 | 82 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8002372P0101P | BUSHING | 8 | 8 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8002375P0101 | TENSION SPRING | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8002757P0101 | Insert 1X60X10 (2024231) GJ.GER | 6 | 6 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8002757P0102 | Insert 80X10 | 204 | 204 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8002875P0101 | WINDOW PANE 350X220X16,8 (KONEX) | 12 | 10 | 2 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8002875P0101 | WINDOW PANE 350X220X16,8 (KONEX) | 2 | 2 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003360R0101P | LEVER MECHANISM LEFT, 2xR250/55(W800) | 36 | 12 | 24 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003360R0101P | LEVER MECHANISM LEFT, 2xR250/55(W800) | 24 | 7 | 17 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003360R0101P | LEVER MECHANISM LEFT, 2xR250/55(W800) | 17 | 1 | 16 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003360R0102P | LEVER MECHANISM RIGHT,2xR250/55 (W800) | 36 | 12 | 24 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003360R0102P | LEVER MECHANISM RIGHT,2xR250/55 (W800) | 24 | 7 | 17 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003360R0102P | LEVER MECHANISM RIGHT,2xR250/55 (W800) | 17 | 1 | 16 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003624R0102 | MONOBLOCCO-SPOUT 1250A,ZS1 | 210 | 66 | 144 | free_stock | R13-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003624R0102 | MONOBLOCCO-SPOUT 1250A,ZS1 | 144 | 36 | 108 | free_stock | R59-H-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003651P0101P | INSULATING CAP | 291 | 153 | 138 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003651P0101P | INSULATING CAP | 138 | 93 | 45 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003651P0101P | INSULATING CAP | 45 | 8 | 37 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003671P0120 | SPECIAL SCREW M12X30/101 | 142 | 68 | 74 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003672P0101 | COVER-COPERTURA 12KV ZS1 1250A | 210 | 153 | 57 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003672P0101 | COVER-COPERTURA 12KV ZS1 1250A | 57 | 57 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8004145P0101P | INTERLOCKING BOLT | 4 | 4 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8004478P0101 | BUSHING PLATE BELOW / 3 HOLES | 1 | 1 | 0 | free_stock | R16-L-1-K019_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8004479P0101P | PROTECTIVE COVER (DWG: GCE8004479P0101) | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8004581P0101 | SPRING COMPRESSION | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005031R0101 | BUSHING ZS1/ (3 IN 1) DEACE | 39 | 8 | 31 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005031R0101 | BUSHING ZS1/ (3 IN 1) DEACE | 31 | 2 | 29 | free_stock | R59-H-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005031R0101 | BUSHING ZS1/ (3 IN 1) DEACE | 29 | 1 | 28 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8006031P0101 | COVER FOR BUSBAR JOINTS | 111 | 111 | 0 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011409R0101 | LEVER COMPLETE LEFT SIDE | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011409R0102 | LEVER COMPLETE RIGHT SIDE | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011679R0101P | REIFORCING ANGLE COMPLETE LEFT | 4 | 4 | 0 | 6100KDP01 | R56-I-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013262P0101 | SHROUD | 4 | 4 | 0 | 6100KDP01 | R56-I-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8381281P0100 | GUIDE ROLLER | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8494256P0101 | DISTANCE TUBE | 40 | 40 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9371453P0101 | CABLE BUSHING LOWER PART | 2 | 2 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9371454P0101 | CABLE BUSHING UPPER PART | 2 | 2 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9401529P0100 | Bush | 40 | 40 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9401678R0101 | HOUSING (PLUG SOCKET)COMPL. | 1 | 1 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9401678R0101 | HOUSING (PLUG SOCKET)COMPL. | 2 | 2 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9464131P0100 | EARTHING SWITCH DISPLAY | 40 | 40 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9478304P0102P | ROLLER | 8 | 8 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9478350P0101 | SUPPORTING BOLT 6Kt14/M6X23 | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9576618P0100 | BUSH D18/12,2X8 | 80 | 80 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCEC830444P0101P | K-SPACER D12/4.5X8,ZS1/ZS3.2Yellow Chrom | 80 | 28 | 52 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCEC830444P0101P | K-SPACER D12/4.5X8,ZS1/ZS3.2Yellow Chrom | 52 | 2 | 50 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV-CR-U125DC3 | CR-U125DC3 - 1SVR405622R8200.CR-U125DC3 Pluggable interface relay 3c Ordering Code : 1SVR405622R8200 General: Pluggable interface relay ABB. Type : CR-U125DC3L Ordering Code: OUTPUTS: 3 C/O with LED RATED VOLTAGE: 125 VDC | 2 | 2 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV-CR-U3S | Socket -FOR 3 C/O AND MODULE TIMER | 2 | 2 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV-CR-UH | Holder interface relay 1SVR405669R0000 | 2 | 2 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV-CR-UT | TIME MODULE 1SVR405667R0000 | 2 | 2 | 0 | free_stock | R16-I-1-KDP1_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000025P0001P | BUSHING (LOCAL PUR) | 120 | 30 | 90 | 6100K023 | R58-A-1-K023_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000027P0001P | K-PLATE | 81 | 81 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000048P0001P | PIN (LOCAL PUR) | 40 | 14 | 26 | 6100K023 | R58-A-1-K023_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000048P0001P | PIN (LOCAL PUR) | 26 | 10 | 16 | free_stock | R13-S-1-K006_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000049P0001 | COMPRESSION SPRING | 40 | 40 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | T81722 | Plastic plug for LV Box (Micro. Sw. ) | 246 | 246 | 0 | 6100K023 | PO-SEP-8392-[2] | GR_in_process | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i | 246 | 02-11-2025
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | VT-GUARD-13.8KV | VT Guard, Anti Ferro Resonance Unit ¦ VT-GUARD-13.8KV | 4 | 3 | 1 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | RVT |  | - | 2026-04-04 | 2026-03-21 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1815230000 | 5Pole Plug 2.5mm-1815230000-Cont-loop | 50 | 1 | 49 |  | R57-O-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | [5 empty] | Subinventory Transfer | 8109405
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1855030000 | 6Pole Plug 4mm-1855030000-AC looping | 51 | 11 | 40 |  | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | [5 empty] | Subinventory Transfer | 8109403
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB010366P0109 | Self tapping screw pan head M4x5mm SS | 2550 | 2550 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB52322VW60N00 | VD4/PW 171225-p210-125VDC-ZS1-1250A @ 60Hz, in UG ZS1- with upper CTs as per NG Stanadrad | 6 | 1 | 5 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | A |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5320XDB1XN02 | DIGITAL VOLTMETER, Cl 1.0, 3PH4W, 5-500V, 60Hz, 150% Un CONT, 3 LINE DISPLAY LED, MODBUS ¦ SECURE DPM 96 V300 | 3 | 1 | 2 | 6100KDP01 | R16-B-1-K019_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5320XDB1XN02 | DIGITAL VOLTMETER, Cl 1.0, 3PH4W, 5-500V, 60Hz, 150% Un CONT, 3 LINE DISPLAY LED, MODBUS ¦ SECURE DPM 96 V300 | 2 | 1 | 1 | 6100K019 | R16-L-1-K019_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | LL10-W | ABB_LL10-W / LL10-W, AC/DC90-264V 50/60HZ | 51 | 51 | 0 | free_stock | R15-I-1-K11B_SEP | inventory | 2025-11-03 | LVA | Automated: Replaced 1YAB53301XIX0000 by LL10-W. | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5334XXAX1000 | FT-1 SW-Type 129A514G01 | 8 | 8 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 1530 | 865 | 665 | 6100K011B | R59-G-1-MVBM_SEP | consumption | 2025-10-18 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | [5 empty] | Work in Process Pick | 8162025
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 665 | 665 | 0 | 6100K007 | R59-G-1-MVBM_SEP | consumption | 2025-10-20 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | [5 empty] | Project Transfer | 8214165
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355HAB0002 | Zack Strip-Vertical Labeled(21-30) | 408 | 24 | 384 | 6100KDP01 | R57-J-1-K019_SEP | inventory | 2025-11-03 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355HAB0002 | Zack Strip-Vertical Labeled(21-30) | 384 | 8 | 376 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355HAB0002 | Zack Strip-Vertical Labeled(21-30) | 376 | 8 | 368 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-15 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | [5 empty] | Work in Process Pick | 8129088
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 612 | 261 | 351 |  | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | [5 empty] | Subinventory Transfer | 8109251
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 51 | 49 | 2 | free_stock | R67-A-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 2 | 2 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DM0000003059 | ‭CT SUPERVISION RELAY, 40msec DELAY, 125V DC, 4NC (TYPE: AR901) / 7PG1110-7AE10-0AF0‬ | 3 | 3 | 0 | 6010J577 | R14-S-1-MVBM_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DMS 2154 363-1 | WASHER, LOCK 10X5X0.5 | 51 | 51 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | GCE0438403P0100 | SPRG. PIN 2X10 DIN EN 28748 ST | 51 | 51 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 013978 | TERMINAL ACC T34262/6Px2.5 7906090000 | 24 | 24 | 0 |  | R57-J-1-KDP1_SEP | consumption | 2025-10-14 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Subinventory Transfer | 8109411
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 07686 | WASHER AC EL DIN137 T22120/8 A | 12 | 12 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 07853 | HEX. HEAD BOLT T21000/3X16 | 18 | 18 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 07934 | TOMMY HEAD SCREW ACC T21010/M3x6 | 96 | 12 | 84 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 07940 | TOMMY HEAD SCREW ACC T21010/M3X20 | 32 | 32 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 09011 | LOCK NUT T21192/M3N - DIN 985 A2K | 12 | 12 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1201400000 | CRIMP CONTACTS 2.5mm2 (FEMALE) | 1 | 1 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1440146 | BALL END ALLEN KEY SET | 1 | 1 | 0 | 6100K019 | R58-J-1-KDP1_SEP | consumption | 2025-10-15 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Work in Process Pick | 8127298
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1665260000 | HDC 16B DODQ 4BO IP65 COVER | 1 | 1 | 0 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1826800000 | INSERT FEMALE 32POLE TYPE-HDC HEE 32 FC . | 1 | 1 | 0 | free_stock | R57-J-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VCR000474F0001 | BLOCK | 49 | 44 | 5 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7600349P0101 | SHROUD | 2 | 2 | 0 | 6100KDP01 | R56-I-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010138P0120 | Cover for push button rod | 23 | 23 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010366P0109 | Self tapping screw pan head M4x5mm SS | 1250 | 1250 | 0 | free_stock | R13-S-1-K006_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010378P0111 | SEC. PIN MALE 1.5 MMZS1 | 150 | 150 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010378P0113 | PIN,CONTACT MALE 2.5 | 100 | 100 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010378P0116 | Lugs, Sleeve 4.0/9mm ( W/O Ins.) 3200302 | 1250 | 1000 | 250 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010378P0116 | Lugs, Sleeve 4.0/9mm ( W/O Ins.) 3200302 | 250 | 250 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010491P0101 | FLEX. CABLE,70MM.SQ, PVC 85 YEL/GRN,85°C | 0.42276 | 0.42276 | 0 | free_stock | R57-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | LL10-W | ABB_LL10-W / LL10-W, AC/DC90-264V 50/60HZ | 25 | 25 | 0 | 6100K012B | 1-1-1-1 | inventory | 2025-11-03 | LV | Automated: Replaced 1YAB53301XIX0000 by LL10-W. | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5334XXAX1000 | FT-1 SW-Type 129A514G01 | 25 | 4 | 21 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5334XXAX1000 | FT-1 SW-Type 129A514G01 | 21 | 1 | 20 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5334XXAX2000 | RTXP 8, RK 926 002-AG (8P) | 23 | 18 | 5 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5334XXAX2000 | RTXP 8, RK 926 002-AG (8P) | 5 | 5 | 0 | free_stock | R16-B-1-K019_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5334XXAX2100 | RTXP18, RK 926 115-BF | 23 | 18 | 5 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5334XXAX2100 | RTXP18, RK 926 115-BF | 5 | 5 | 0 | free_stock | R14-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5334XXAX2200 | RTXP18 TEST SW-TYPE RK 926 115-AN (18P) | 6 | 6 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5334XXAX2300 | RTXP18, RK 926 115-AH | 2 | 2 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5335XXAX1100 | COMBIFLEX TERMINAL BASE RX 2H -5619625-A | 54 | 23 | 31 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5335XXAX1100 | COMBIFLEX TERMINAL BASE RX 2H -5619625-A | 31 | 18 | 13 | free_stock | R14-L-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5335XXAX1100 | COMBIFLEX TERMINAL BASE RX 2H -5619625-A | 13 | 4 | 9 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5335XXAX1200 | COMBIFLEX TERMINAL BASE RX4 (4U 12C) | 38 | 38 | 0 | free_stock | R11-A-1-MVBM_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5336XXAA3I00 | MCB 10A AC -3P - 2CDS253001R0427 | 8 | 2 | 6 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5340XCHXXN00 | LOCKOUT RELAY (86) TYPE 7805F-70-280VDC | 23 | 23 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSABB000 | FLEX.CABLE,1/C,1.5MM BLUE ATC,105 Deg C | 54.7046 | 54.7046 | 0 | free_stock | R56-F-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSABC000 | FLEX.CABLE,1/C,1.5MM BLACK ATC,105 Deg C | 17.779 | 17.779 | 0 | free_stock | R56-N-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSABD000 | FLEX.CABLE,1/C,1.5MM GREY ATC,105 Deg C | 410.8315 | 410.8315 | 0 | free_stock | R56-H-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSABR010 | FLEX.CABLE,1/C,1.5MM RED C,105 Deg C | 17.779 | 17.779 | 0 | free_stock | R56-K-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSACB010 | FLEX.CABLE,1/C,2.5MM BLUE ATC,105 Deg C | 73.8512 | 73.8512 | 0 | free_stock | R56-A-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSACC010 | FLEX.CABLE,1/C,2.5MM BLACK ATC,105 Deg C | 46.4989 | 46.4989 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSACD010 | FLEX.CABLE,1/C,2.5MM GREY ATC,105 Deg C | 13.6761 | 13.6761 | 0 | 6100KDP01 | R56-I-1-KDP1_SEP | consumption | 2025-06-28 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Miscellaneous issue | 6172962
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSACN010 | FLEX.CABLE,1/C,2.5MM YE/GN ATC,105 Deg C | 13.7309 | 13.7309 | 0 | free_stock | R57-P-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSACR010 | FLEX.CABLE,1/C,2.5MM RED ATC,105 Deg C | 73.8512 | 73.8512 | 0 | free_stock | NEW.FLR-1-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSACY010 | FLEX.CABLE,1/C,2.5MM YELLOW ATC,90 Deg C | 73.8512 | 73.8512 | 0 | free_stock | R57-K-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSADB020 | FLEX.CABLE,1/C,4MM BLUE ATC,105 Deg C | 4.1028 | 4.1028 | 0 | free_stock | R57-H-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSADC020 | FLEX.CABLE,1/C,4MM BLACK ATC,105 Deg C | 5.4705 | 5.4705 | 0 | free_stock | R57-N-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSADD020 | FLEX.CABLE,1/C,4MM GREY ATC,105 Deg C | 5.4705 | 5.4705 | 0 | free_stock | R60-C-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSADR020 | FLEX.CABLE,1/C,4MM RED ATC,105 Deg C | 4.1028 | 4.1028 | 0 | free_stock | R57-C-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5350XSADY020 | FLEX.CABLE,1/C,4MM YELLOW ATC,105 Deg C | 4.1028 | 4.1028 | 0 | free_stock | R57-F-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 750 | 750 | 0 | 6100K011B | R59-G-1-MVBM_SEP | consumption | 2025-10-20 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Project Transfer | 8212281
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355HXB0000 | BENT LUGS TYPE RF-PPL30 | 17500 | 12600 | 4900 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355HXB0000 | BENT LUGS TYPE RF-PPL30 | 4900 | 4900 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355HXB0001 | BENT LUGS TYPE BF-PPL46 | 3750 | 2700 | 1050 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355HXB0001 | BENT LUGS TYPE BF-PPL46 | 1050 | 1050 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355HXB0002 | BENT LUGS TYPE BF-PPL30 | 7500 | 7500 | 0 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB539500002019 | SERV IS LABEL in Stainless Steel Plates | 25 | 23 | 2 | free_stock | WH2-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB539500002019 | SERV IS LABEL in Stainless Steel Plates | 2 | 1 | 1 | 6100K019 | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB539500002019 | SERV IS LABEL in Stainless Steel Plates | 1 | 1 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 25 | 25 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 28100 | SCREW VITE ACTC D7971 T21572/4.2x6.5 | 94 | 94 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 28132 | RETAINING RING ACC. T22414/3.2 | 24 | 24 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 3WKA014538P0014 | SPIRAL_PIN_ISO8748_4X30-ST/BK | 24 | 24 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 3WKA014618P0001 | SAFETY_GRIPPER_BFK/A_BN13193_4-SPST/PH | 24 | 24 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 3WKA014618P0003 | SAFETY_GRIPPER_BFK/A_BN13193_6-SPST/PH | 24 | 24 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 593502001 | BUSHING | 25 | 15 | 10 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 593502001 | BUSHING | 10 | 1 | 9 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE 11342 2100-1 | GLASS,220X350X8.8, GCE8000436P0101 | 42 | 14 | 28 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE 2093 7000-4 | RAYCHEM SHRINKABLE TUBE, BPTM 75/30-A/U | 0.6 | 0.6 | 0 | free_stock | R15-J-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2000-1865-03 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 250 | 200 | 50 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2000-1865-03 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 50 | 50 | 0 | free_stock | R66-P-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2522-2000-03 | CABLE SEALING,PG21, | 2 | 2 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | BM0145-1373-ASYP | STEP LADDER SCECO CENTRAL (STANDARD) | 2 | 1 | 1 | 6100KDP01 | WH2-1-1-K019_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 1854 1917-1 | SEALING, 24 X 3mm (SUPERLON) | 172.8 | 172.8 | 0 | 6100KDP01 | PO-SEP-8392-[3] | GR_in_process | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i | 349 | 02-11-2025
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-493 | BOLT HEX HEAD M10X30 | 500 | 180 | 320 | free_stock | R58-A-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-493 | BOLT HEX HEAD M10X30 | 320 | 80 | 240 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 722 | 134 | 588 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Work in Process Material Issue | 8298385
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 588 | 1 | 587 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Work in Process Material Issue | 8296242
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2467-366 | SCREW SELF TAPPING TORX M6 X 12 | 587 | 587 | 0 | 6100K017 | R58-A-1-K11B_SEP | consumption | 2025-10-27 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Work in Process Pick | 8357898
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-295 | BOLT SOCKET HEAD M4X20 | 8 | 8 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Work in Process Material Issue | 8296185
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-327 | BOLT SOCKET CAP HEAD M5X12 | 62 | 62 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-366 | BOLT SOCKET CAP HEAD M6X12 | 84 | 84 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-368 | BOLT SOCKET CAP HEAD M6X16 | 65 | 65 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Work in Process Material Issue | 8296186
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-379 | BOLT SOCKET CAP HEAD M6X45 | 4 | 4 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-505 | CHEESE HEAD BOLT M10X70 | 300 | 192 | 108 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-505 | CHEESE HEAD BOLT M10X70 | 108 | 48 | 60 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-505 | CHEESE HEAD BOLT M10X70 | 60 | 36 | 24 | 606PD013 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 2011-111 | NUT, HEX M3 | 32 | 32 | 0 | 6100K006 | 1-1-1-1 | consumption | 2025-10-25 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Work in Process Material Issue | 8296717
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 2011-114 | NUT, HEX M5 | 18 | 18 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 2011-116 | NUT, HEX M 6 | 317 | 317 | 0 | 6100K013 | NEW.FLR-1-1-K013_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 2011-120 | NUT, HEX M10 | 1212 | 1212 | 0 | free_stock | PO-SEP-5971-[44] | GR_in_process | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST | LV-BULK/ MECHANICAL ASSEMBLY | 5000 | 03-11-2025
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2154 363-1 | WASHER, LOCK 10X5X0.5 | 25 | 25 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2634 010-91 | UN-INSUL SLeve Lugs KE1510ST (1.5mm) | 500 | 500 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2634 010-92 | UN-INSUL SLEEVE Lugs for 2.5mm KE2510ST | 1250 | 900 | 350 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2634 010-92 | UN-INSUL SLEEVE Lugs for 2.5mm KE2510ST | 350 | 350 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2634 010-93 | Un-Insul Sleeve Lugs 4.0 mm KE410ST | 1250 | 900 | 350 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2634 010-93 | Un-Insul Sleeve Lugs 4.0 mm KE410ST | 350 | 350 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2634 011-2 | TERM.LUGS BLADE BF-PP12/25 2.5MM | 2500 | 1600 | 900 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2634 011-2 | TERM.LUGS BLADE BF-PP12/25 2.5MM | 900 | 700 | 200 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2634 011-2 | TERM.LUGS BLADE BF-PP12/25 2.5MM | 200 | 200 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2634 011-51 | TERM.LUGS BLADE RF-PP 12/23 | 7500 | 4800 | 2700 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2634 011-51 | TERM.LUGS BLADE RF-PP 12/23 | 2700 | 2100 | 600 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2634 011-51 | TERM.LUGS BLADE RF-PP 12/23 | 600 | 600 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2026-4 | TERM.LUGS SPADE RF-U4 1.5/M4 | 3125 | 2000 | 1125 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2026-4 | TERM.LUGS SPADE RF-U4 1.5/M4 | 1125 | 900 | 225 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2026-4 | TERM.LUGS SPADE RF-U4 1.5/M4 | 225 | 225 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-11 | RING TYPE LUGS GF-M 5 | 500 | 360 | 140 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-11 | RING TYPE LUGS GF-M 5 | 140 | 140 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-2 | TERM.LUGS RING RF-M4 1.5/M4 | 2500 | 1600 | 900 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-2 | TERM.LUGS RING RF-M4 1.5/M4 | 900 | 700 | 200 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-2 | TERM.LUGS RING RF-M4 1.5/M4 | 200 | 200 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-4 | TERM.LUGS RING BF-M4 | 5000 | 3200 | 1800 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-4 | TERM.LUGS RING BF-M4 | 1800 | 1400 | 400 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-4 | TERM.LUGS RING BF-M4 | 400 | 400 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-7 | TERM.LUGS BF-M5 (RING) | 3000 | 2668 | 332 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-7 | TERM.LUGS BF-M5 (RING) | 332 | 332 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-8 | WIRE LUGS RING TYPE BF-M6 2.5/M6 | 200 | 144 | 56 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-8 | WIRE LUGS RING TYPE BF-M6 2.5/M6 | 56 | 56 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-9 | RING TYPE LUGS BF-M 8 | 200 | 144 | 56 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2034-9 | RING TYPE LUGS BF-M 8 | 56 | 56 | 0 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0438403P0100 | SPRG. PIN 2X10 DIN EN 28748 ST | 25 | 25 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0493108P0100 | BALL SHAPED HANDLE | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0734028P0100P | K - BALL SHAPED HANDLE (ZINC CHRM) | 4 | 4 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0990108P0100 | DOUBLE BIT KEY 3.2 | 6 | 6 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0990479P0100 | WHEEL FOR TRUCK 100X35 POLYAMID | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0996020P0100 | PROTECTOR CAP M12 SW17-1-G15/H5 | 12 | 12 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0997050P0100 | HAND CRANK FOR SWITCH TRUCK | 4 | 4 | 0 | free_stock | INC-1-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0998122P0100 | TUBING 28X36 FOR PG29 | 8.1 | 6 | 2.1 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0998122P0100 | TUBING 28X36 FOR PG29 | 2.1 | 2.1 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0998124P0100 | TUBING KUW 17X21,PG16 (Use ** 1YAB010415P0103 **) | 0.8 | 0.8 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0998131P0100 | TUBE HOLDER-LK / MPG16 | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4117104P0106 | TUBE G16X100 DIN 490216 | 24 | 24 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4129015P0128P | HEX.PART 17X677 ZINC CHR. | 24 | 24 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4329220P0100 | THREADED DOWEL M12X37 | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000524P0101P | GROOVED PIN | 24 | 24 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000535R0101P | K- BRACKET COMPL. ZINC COATED | 24 | 24 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000545P0101 | COMPRESSION SPRING | 12 | 6 | 6 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000545P0101 | COMPRESSION SPRING | 6 | 2 | 4 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000553P0101 | ADJUSTING FISH PLATE | 48 | 48 | 0 | 6100KDP01 | R55-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000581P0101 | CANTILEVER SPRING | 30 | 30 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000582P0101 | SPIRAL SPRING | 24 | 24 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7001936P0101P | K - HANDLE (CHROME PLATED) | 16 | 16 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7002424P0101P | K - BEARING SHAFT (ZINC CHRM) | 32 | 24 | 8 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7002424P0101P | K - BEARING SHAFT (ZINC CHRM) | 8 | 8 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7002476P0101 | FIXING BAR | 2 | 2 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003534P0101 | DETENT (RASTE) | 6 | 6 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003558P0101 | ADJUSTING SCREW | 2 | 2 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003560P0101 | SPACER | 1 | 1 | 0 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7102438P0100 | COVER OF CONTROL PLUG/SOCKET | 7 | 7 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8000633P0115 | MOUNTING CHANNEL L325mm | 6 | 6 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8000825P0101 | SPRING | 27 | 27 | 0 | 606PD013 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8000910P0101 | PACKING PIECE 80X15 | 63 | 48 | 15 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8000910P0101 | PACKING PIECE 80X15 | 15 | 3 | 12 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8000981P0101P | THREADED PIECE | 24 | 24 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8002370P0101 | DOCKING RECEPTANCE | 50 | 50 | 0 | 606PD013 | R56-O-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8002372P0101P | BUSHING | 11 | 11 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8002375P0101 | TENSION SPRING | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8002757P0101 | Insert 1X60X10 (2024231) GJ.GER | 6 | 6 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8002757P0102 | Insert 80X10 | 120 | 120 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003672P0101 | COVER-COPERTURA 12KV ZS1 1250A | 126 | 50 | 76 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003672P0101 | COVER-COPERTURA 12KV ZS1 1250A | 76 | 6 | 70 | 606PD013 | R59-A-1-PD\-13/MV_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003672P0101 | COVER-COPERTURA 12KV ZS1 1250A | 70 | 3 | 67 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004145P0101P | INTERLOCKING BOLT | 4 | 4 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004478P0101 | BUSHING PLATE BELOW / 3 HOLES | 1 | 1 | 0 | free_stock | R16-L-1-K019_SEP | inventory | 2025-11-03 | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004479P0101P | PROTECTIVE COVER (DWG: GCE8004479P0101) | 2 | 2 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004581P0101 | SPRING COMPRESSION | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004770P0101 | SHROUD 17.5kV | 15 | 15 | 0 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8006031P0101 | COVER FOR BUSBAR JOINTS | 63 | 30 | 33 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8006031P0101 | COVER FOR BUSBAR JOINTS | 33 | 21 | 12 | free_stock | R59-A-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8006031P0101 | COVER FOR BUSBAR JOINTS | 12 | 3 | 9 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8011409R0101 | LEVER COMPLETE LEFT SIDE | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8011409R0102 | LEVER COMPLETE RIGHT SIDE | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8011679R0101P | REIFORCING ANGLE COMPLETE LEFT | 2 | 2 | 0 | free_stock | R59-P-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8381281P0100 | GUIDE ROLLER | 4 | 4 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8494256P0101 | DISTANCE TUBE | 24 | 24 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9371453P0101 | CABLE BUSHING LOWER PART | 2 | 2 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9371454P0101 | CABLE BUSHING UPPER PART | 2 | 2 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9401529P0100 | Bush | 24 | 24 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9401678R0101 | HOUSING (PLUG SOCKET)COMPL. | 3 | 3 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9464131P0100 | EARTHING SWITCH DISPLAY | 24 | 24 | 0 | 6100KDP01 | R56-O-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9478304P0102P | ROLLER | 28 | 12 | 16 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9478304P0102P | ROLLER | 16 | 12 | 4 | free_stock | R59-Q-1-KDP1_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9478304P0102P | ROLLER | 4 | 4 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9478350P0101 | SUPPORTING BOLT 6Kt14/M6X23 | 2 | 2 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9576618P0100 | BUSH D18/12,2X8 | 48 | 48 | 0 | 6100KDP01 | R56-Q-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | MV RK 926 011-AE | TEST PLUG HANDLE, RTXH 8 | 1 | 1 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | MV RK 926 011-BC | TEST PLUG HANDLE: RTXH 18; RK 926 011-BC | 1 | 1 | 0 | free_stock | R14-B-1-KDP1_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | PKE 1508 | END SLEEVES PKE 1508 (1x1.5sqmm , Black) | 375 | 155 | 220 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | PKE 1508 | END SLEEVES PKE 1508 (1x1.5sqmm , Black) | 220 | 130 | 90 | free_stock | R58-O-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | PKE 1508 | END SLEEVES PKE 1508 (1x1.5sqmm , Black) | 90 | 15 | 75 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | PKT 1508 | END SLEEVES PKT 1508 (2x1.5sqmm , Black) | 375 | 85 | 290 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | PKT 1508 | END SLEEVES PKT 1508 (2x1.5sqmm , Black) | 290 | 15 | 275 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1000027P0001P | K-PLATE | 49 | 49 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1000049P0001 | COMPRESSION SPRING | 24 | 24 | 0 | 6100KDP01 | R56-P-1-K019_SEP | inventory | 2025-11-03 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | T81722 | Plastic plug for LV Box (Micro. Sw. ) | 150 | 150 | 0 | 6100K013 | R58-J-1-K013_SEP | inventory | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB010366P0109 | Self tapping screw pan head M4x5mm SS | 2550 | 2550 | 0 | free_stock | R13-S-1-K006_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | LL10-W | ABB_LL10-W / LL10-W, AC/DC90-264V 50/60HZ | 51 | 51 | 0 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LVA | Automated: Replaced 1YAB53301XIX0000 by LL10-W. | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 1530 | 1110 | 420 | 6100K012B | R59-G-1-MVBM_SEP | consumption | 2025-10-20 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Project Transfer | 8212291
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 420 | 420 | 0 | 6100K017 | R59-G-1-MVBM_SEP | consumption | 2025-10-20 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Project Transfer | 8214167
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 51 | 2 | 49 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 49 | 1 | 48 | 6100K019 | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 48 | 1 | 47 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Work in Process Pick | 8069185
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 47 | 1 | 46 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Work in Process Pick | 8070603
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 46 | 1 | 45 | 6100K019 | R13-S-1-KDP1_SEP | consumption | 2025-10-13 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | [5 empty] | Work in Process Pick | 8071592
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DM0000003059 | ‭CT SUPERVISION RELAY, 40msec DELAY, 125V DC, 4NC (TYPE: AR901) / 7PG1110-7AE10-0AF0‬ | 3 | 3 | 0 | 6010J577 | R14-S-1-MVBM_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 2154 363-1 | WASHER, LOCK 10X5X0.5 | 51 | 6 | 45 | free_stock | 1-1-1-1 | inventory | 2025-11-03 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | GCE0438403P0100 | SPRG. PIN 2X10 DIN EN 28748 ST | 51 | 2 | 49 | free_stock | R14-I-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | GCE0438403P0100 | SPRG. PIN 2X10 DIN EN 28748 ST | 49 | 1 | 48 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB010366P0109 | Self tapping screw pan head M4x5mm SS | 2550 | 2550 | 0 | free_stock | R13-S-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | LL10-W | ABB_LL10-W / LL10-W, AC/DC90-264V 50/60HZ | 51 | 48 | 3 | 6100K007 | 1-1-1-1 | inventory | 2025-11-03 | LVA | Automated: Replaced 1YAB53301XIX0000 by LL10-W. | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | LL10-W | ABB_LL10-W / LL10-W, AC/DC90-264V 50/60HZ | 3 | 3 | 0 | 6100K012B | 1-1-1-1 | inventory | 2025-11-03 | LVA | Automated: Replaced 1YAB53301XIX0000 by LL10-W. | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 1530 | 835 | 695 | 6100K007 | R59-G-1-MVBM_SEP | consumption | 2025-10-20 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | [5 empty] | Project Transfer | 8214165
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355DXB0000 | Terminal Strip Markers, KLM-A - 1004348 | 695 | 695 | 0 | 6100K011A | R59-G-1-MVBM_SEP | consumption | 2025-10-20 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | [5 empty] | Project Transfer | 8212285
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355HXB0000 | BENT LUGS TYPE RF-PPL30 | 35700 | 700 | 35000 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355HXB0001 | BENT LUGS TYPE BF-PPL46 | 7650 | 150 | 7500 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355HXB0001 | BENT LUGS TYPE BF-PPL46 | 7500 | 50 | 7450 | free_stock | R59-B-1-KDP1_SEP | inventory | 2025-11-03 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355HXB0002 | BENT LUGS TYPE BF-PPL30 | 15300 | 300 | 15000 | 6100K019 | 1-1-1-1 | inventory | 2025-11-03 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DM0000003059 | ‭CT SUPERVISION RELAY, 40msec DELAY, 125V DC, 4NC (TYPE: AR901) / 7PG1110-7AE10-0AF0‬ | 3 | 1 | 2 | 6010J577 | R14-S-1-MVBM_SEP | inventory | 2025-11-03 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1312 1072-535 | B.I. SHEET 2440X1220X2.0 MM | 0.3 | 0 | 0.3 | PR Required | - | PR |  | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1312 1092-461 | B.I. SHEET 2440X1220X3.0 MM | 27.819 | 0 | 27.819 | PR Required | - | PR |  | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1312 1282-463 | G.I. SHEET 2440X1220X3.0 MM | 410.926 | 0 | 410.926 | PR Required | - | PR |  | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1314 1019-501 | B.I. SHEET 2440X1220X4.0 MM | 42.632 | 0 | 42.632 | PR Required | - | PR |  | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1314 1019-574 | B.I. SHEET 2440X1220X6.0 MM | 15.456 | 0 | 15.456 | PR Required | - | PR |  | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1314 1019-734 | B.I. SHEET 2440X1220 X2.5 MM | 5.52 | 0 | 5.52 | PR Required | - | PR |  | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1613 0212 | ALUMINUM SHEET 2440X1220X2 MM | 2.35 | 0 | 2.35 | PR Required | - | PR |  | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1613 0513 | ALUMINUM SHEET 2440X1220X5 MM | 26.744 | 0 | 26.744 | PR Required | - | PR |  | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR000490F0001 | SHEET PROFILE | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8402-[66] | PO | 2025-11-17 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 23 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VCR000491F0001 | SHEET PROFILE | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8402-[61] | PO | 2025-11-17 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 23 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7605506P0101 | ABB LOGO UNIGEAR ZS1 | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8379-[53] | PO | 2025-10-30 | C&D |  | - | 2025-11-08 | 2025-10-25 | 5 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7605506P0102 | ABB LOGO UNIGEAR ZS1 | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8379-[45] | PO | 2025-10-30 | C&D |  | - | 2025-11-08 | 2025-10-25 | 5 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7605506P0102 | ABB LOGO UNIGEAR ZS1 | 7 | 7 | 0 | 6100KDP01 | PO-SEP-8379-[45] | PO | 2025-10-30 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 5 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7623184R0101 | COMPLETE HANDLE | 5 | 5 | 0 | 6100KDP01 | PO-SEP-6826-[1] | PO | 2025-07-24 | C&D |  | - | 2025-11-08 | 2025-10-25 | 0 | SHAMS ALRIYADH INDUSTRIAL FACTORY | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7623184R0101 | COMPLETE HANDLE | 6 | 1 | 5 | 6100KDP01 | PO-SEP-6826-[1] | PO | 2025-07-24 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | SHAMS ALRIYADH INDUSTRIAL FACTORY | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1VL7623184R0101 | COMPLETE HANDLE | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8552-[1] | PO | 2025-11-15 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 21 | SHAMS ALRIYADH INDUSTRIAL FACTORY | AL Azyziyah DMM Project under Dummy 6100KDP01 2nd Lot of Mechanical Componentes for SEC a/c Dammam Aziziya Fast track project 13.8kV MV SWGR.
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5331XXCX0210 | CBMODE6P,4Pos.Off-Emer-Local-Rem-Padlock | 1 | 1 | 0 | 6100K019 | PO-SEP-8398-[8] | PO | 2025-12-31 | LV |  | - | 2025-11-08 | 2025-10-25 | 67 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5335XXAX2400 | BOX ASSEMBLY (4U-36C), RHGX 12 (PAINT RAL) RK 927 003-AB | 2 | 2 | 0 | 6100K019 | PO-SEP-8402-[73] | PO | 2025-11-17 | LV |  | - | 2025-11-08 | 2025-10-25 | 23 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5336XXAA2J00 | MCB S 202-K4 4A AC -2P - 2CDS252001R0337 | 1 | 1 | 0 | 6100K019 | PO-SEP-8041-[63] | PO | 2025-12-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 51 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB539500002004 | CB Adjustable Haydraulic Trolley | 1 | 1 | 0 | 6100KDP01 | PO-SEP-6967-[1] | PO | 2025-07-17 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | Leistung Energie Limited | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 2440 1220-20 | STAINLESS STEEL 2440X1220X2.0 MM (304) | 243.128 | 0 | 243.128 | PR Required | - | PR |  | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 2440 1220-30 | STAINLESS STEEL 2440X1220X3.0 MM (304) | 130.798 | 0 | 130.798 | PR Required | - | PR |  | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 561762/001 | PLATE -FOR PANEL FIXING | 28 | 0 | 28 | PR Required | - | PR |  | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-10 | Label Bus Bar 2 (WHITE letter FOR SEC) | 1 | 1 | 0 | 6100KDP01 | PO-SEP-6543-[65] | PO | 2025-12-31 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 67 | Azm and Tumooh Trading Establishment | Labels for outdoor
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | AE 2941 2000-11 | Label Bus Bar 1 ( for SEC) | 1 | 1 | 0 | 6100KDP01 | PO-SEP-6543-[66] | PO | 2025-12-31 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 67 | Azm and Tumooh Trading Establishment | Labels for outdoor
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-419 | BOLT HEX HEAD M8X45 | 1 | 1 | 0 | 6100K023 | PO-SEP-8378-[148] | PO | 2025-11-17 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 23 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2016-508 | BOLT HEX HEAD M10X130 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-6812-[128] | PO | 2025-08-31 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-499 | BOLT SOCKET CAP HEAD M10X40 | 16 | 16 | 0 | 6100KDP01 | PO-SEP-6812-[114] | PO | 2025-08-31 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-540 | BOLT SOCKET CAP HEAD M12X40 | 6 | 6 | 0 | 6100K023 | PO-SEP-8680-[27] | PO | 2025-11-17 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 23 | ALAM AL NIMA TRADING EST
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2519-648 | BOLT SOCKET CAP HEAD M20X40 | 9 | 9 | 0 | 6100KDP01 | PO-SEP-6812-[137] | PO | 2025-12-31 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 67 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | DMS 2121 2852-500 | COUNTERSUNK SCREW ALLEN HEAD M10X60 | 28 | 28 | 0 | 6100KDP01 | PO-SEP-6812-[37] | PO | 2025-12-31 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 67 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0336984P0100 | TAPPING SCREW M6X12/6KTHEAD | 8 | 8 | 0 | 6100KDP01 | PO-SEP-6812-[36] | PO | 2025-08-31 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0413167P0100 | WASHER VS12 - FST | 2 | 2 | 0 | 6100KDP01 | PO-SEP-6812-[14] | PO | 2025-08-31 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0422013P0100 | WASHER,RETAINING 16X1 | 4 | 4 | 0 | 6100K023 | PO-SEP-8378-[155] | PO | 2025-11-17 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 23 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0518520P0101 | ATTENTION SIGN (SEGNALE DI PERICOLO) | 2 | 2 | 0 | 6100K023 | PO-SEP-8379-[25] | PO | 2025-10-30 | C&D |  | - | 2025-11-08 | 2025-10-25 | 5 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0518520P0101 | ATTENTION SIGN (SEGNALE DI PERICOLO) | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8379-[56] | PO | 2025-10-30 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 5 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0909123P0100 | PLUG-IN CONNECTION - 645060000 | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[185] | PR |  | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0909124P0100 | BUSH STV2/10 ORDER.NO. 0645160000 | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[186] | PR |  | C&D |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE0931008P0100 | POST TYPE INSULATOR 12kV SIZE B 2040384 | 15 | 15 | 0 | 6100KDP01 | PO-SEP-8389-[9] | PO | 2025-11-30 | C&D |  | - | 2025-11-08 | 2025-10-25 | 36 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4396016P0100 | PLAIN WASSHER 9/33X2.5 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-6812-[60] | PO | 2025-08-31 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE4539458P0101A | INFORMATION PLATE ( LOCAL ) | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7003570R0116P | DRWOUT DEVICE P210,MTRG.TRUCK (125VDC) | 2 | 0 | 2 | PR Required | - | PR |  | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7192037R0100 | INSULATOR SGB 24N A1 POT 24kV 2040742 | 3 | 3 | 0 | 6100K023 | PO-SEP-8389-[1] | PO | 2025-11-30 | C&D |  | - | 2025-11-08 | 2025-10-25 | 36 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7208368P0100 | DESIGNATION LABEL | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8379-[35] | PO | 2025-10-30 | LAX |  | - | 2025-11-08 | 2025-10-25 | 5 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE7208368P0100 | DESIGNATION LABEL | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8379-[35] | PO | 2025-10-30 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 5 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8002371P0101 | BOLT GUIDE | 2 | 2 | 0 | 6100K023 | PO-SEP-8385-[105] | PO | 2025-09-21 | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011549P0101 | CT-COOLER (HEAT SINK) | 3 | 3 | 0 | 6100KDP01 | PO-SEP-5542-[56] | PO | 2025-12-05 | B |  | - | 2025-11-08 | 2025-10-25 | 41 | Abb Electrical Industriesco | MV Switchgear component ABB Supply
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | GCE8011710P0103 | RIB | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8402-[62] | PO | 2025-11-17 | Outsource |  | - | 2025-11-08 | 2025-10-25 | 23 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | LCT-IC-13.8KV-1250A-1 | Indoor Current Transformer | 9 | 6 | 3 | 6100K019 | PO-SEP-7676-[2] | PO | 2025-12-01 | LV |  | - | 2025-11-08 | 2025-10-25 | 37 | Ritz Instrument Transformers GMBH | PP-12 (13.8kV MVSG IC CTs)
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | LCT-IC-13.8KV-1250A-1 | Indoor Current Transformer | 3 | 0 | 3 | PR Required | - | PR |  | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | MV-ZB9016765 | resistor(0-820ohms) | 6 | 6 | 0 | 6100K019 | PO-SEP-8376-[1] | PO | 2026-01-30 | LV |  | - | 2025-11-08 | 2025-10-25 | 97 | Grid Solution Middle-East Fze | MV
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP10038 | ‭HUMIDISTAT, 250V AC/01220.0-00/MFR 012‬ | 6 | 6 | 0 | 6100K019 | PO-SEP-8198-[2] | PO | 2025-10-09 | LV |  | - | 2025-11-08 | 2025-10-25 | 0 | STEGO Elektrotechnik GmbH | PP-12 additional components
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | UCT-IC-13.8KV-1250A-1 | Indoor Current Transformer | 3 | 0 | 3 | PR Required | - | PR |  | LV |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | VM 2440 1220-10 | ALUZINC 2440X1220X1.0 MM | 23.735 | 0 | 23.735 | PR Required | - | PR |  | Mechanical |  | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | VT-13.8KV-FR | Singe-pole insulated voltage Transformer | 1 | 1 | 0 | 6100KDP01 | PO-SEP-6985-[8] | PO | 2025-11-15 | LV |  | - | 2025-11-08 | 2025-10-25 | 21 | Ritz Instrument Transformers GMBH | PP12 BSP SS9087 (CT & VT REQUIREMENTS) | 11 | 09-10-2025 | 09-10-2025 |  |  | 6985-2
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40173 | Busbar, Copper, 30 x 5 mm, R=1 | 8.478 | 8.478 | 0 | free_stock | PO-SEP-7505-[4] | PO | 2025-09-30 | Mechanical | Automated: Replaced 1535 1048-217 by SEP40173. Automated: Replaced 1535 1048-217 by SEP40173. | - | 2025-11-08 | 2025-10-25 | 0 | Al Shatara Electricals
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | 1YAB5340XIAXXN01 | Relay, Auxiliary, 2 Coils, Self Reset Contacts, Hand Reset Flag, 110-125V, DC, 2NO, 1NC, Coil ¦ RXSF1 RK 271 007-AN | 10 | 10 | 0 | 6100K019 | PO-SEP-8297-[2] | PO | 2026-01-08 | LV | Automated: Replaced 1YAB5340XIAXXN01 by DM0000000058. | - | 2025-11-08 | 2025-10-25 | 75 | Hitachi Energy Ltd | PP-12 RELAY BASE AND COMBIFLEX BOX
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP10163 | 1.5 Red Wire Gauge Tube 1.5mm² | 60 | 1 | 59 | 6100K024 | PO-SEP-8879-[4] | PO | 2025-12-21 | LV | Automated: Replaced AE2000-1865-14 by SEP10163. Automated: Replaced AE2000-1865-14 by SEP10163. | - | 2025-11-08 | 2025-10-25 | 57 | Sana For Electric And Telephone Co | 6100K024 SMRU 3L Mechanistical Componentes.
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP10163 | 1.5 Red Wire Gauge Tube 1.5mm² | 59 | 37 | 22 | free_stock | PO-SEP-8718-[1] | PO | 2025-12-30 | LV | Automated: Replaced AE2000-1865-14 by SEP10163. Automated: Replaced AE2000-1865-14 by SEP10163. | - | 2025-11-08 | 2025-10-25 | 66 | Sana For Electric And Telephone Co | EBM-BULK/ KANBAN MATERIALS/ TRUNKING 80 x 80 mm/80X80X2/CD8080
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP10163 | 1.5 Red Wire Gauge Tube 1.5mm² | 22 | 3 | 19 | 6100K020 | PO-SEP-8830-[4] | PO | 2025-12-31 | LV | Automated: Replaced AE2000-1865-14 by SEP10163. Automated: Replaced AE2000-1865-14 by SEP10163. | - | 2025-11-08 | 2025-10-25 | 67 | Sana For Electric And Telephone Co | 6100K020 Mahar SS SWGR Electrical components order.
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP10163 | 1.5 Red Wire Gauge Tube 1.5mm² | 19 | 1 | 18 | free_stock | PO-SEP-8502-[30] | PO | 2025-12-31 | LV | Automated: Replaced AE2000-1865-14 by SEP10163. Automated: Replaced AE2000-1865-14 by SEP10163. | - | 2025-11-08 | 2025-10-25 | 67 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP10163 | 1.5 Red Wire Gauge Tube 1.5mm² | 18 | 3 | 15 | free_stock | PO-SEP-8906-[3] | PO | 2026-01-04 | LV | Automated: Replaced AE2000-1865-14 by SEP10163. Automated: Replaced AE2000-1865-14 by SEP10163. | - | 2025-11-08 | 2025-10-25 | 71 | Sana For Electric And Telephone Co | EBM-BULK/ PETTY CASH/ Lugs, Terminal Ring, 1.5 Sq.mm ¦ CEM-RF-M4 ¦ Cembre
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP10163 | 1.5 Red Wire Gauge Tube 1.5mm² | 15 | 15 | 0 | free_stock | PR-SEP-0023387-[171] | PR |  | LV | Automated: Replaced AE2000-1865-14 by SEP10163. Automated: Replaced AE2000-1865-14 by SEP10163. | - | 2025-11-08 | 2025-10-25 | 0
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40143 | 1250x1.5mm Aluzinc Coil, 150 gsm, Minimum Spangle (Matte Surface) | 9.154 | 9.154 | 0 | free_stock | PO-SEP-6249-[3] | PO | 2025-11-30 | Mechanical | Automated: Replaced VM 2440 1220-15 by SEP40143. Automated: Replaced VM 2440 1220-15 by SEP40143. | - | 2025-11-08 | 2025-10-25 | 36 | Ningbo Atlas Steel Trading Company Limited | 1250x2.8mm G. I. Coil, 275 gsm, Zero Spangle (Matte Surface) | 5390 | 06-10-2025
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40123 | Coil, Aluzinc, Minimum spangle, 1220 x 2 mm, 150 gsm | 3565.442 | 3565.442 | 0 | free_stock | PO-SEP-8732-[1] | PO | 2025-11-30 | Mechanical | Automated: Replaced VM 2440 1220-20 by SEP40123. Automated: Replaced VM 2440 1220-20 by SEP40123. | - | 2025-11-08 | 2025-10-25 | 36 | Ningbo Atlas Steel Trading Company Limited | Coil, Aluzinc, Minimum spangle, 1220 x 2 mm, 150 gsm Received from Local
6100K019 | PP12 : SWITCHGEAR - PP12 | SWGR | ROH | SEP40146 | 1500x2.0mm Aluzinc Coil, 150 gsm, Minimum Spangle (Matte Surface) | 117.75 | 117.75 | 0 | free_stock | PO-SEP-5866-[3] | PO | 2025-12-30 | Mechanical | Automated: Replaced VM 2500 1500-20 by SEP40146. Automated: Replaced VM 2500 1500-20 by SEP40146. | - | 2025-11-08 | 2025-10-25 | 66 | Ningbo Atlas Steel Trading Company Limited | 1250x1.0mm Aluzinc Coil, 150 gsm, Minimum Spangle (Matte Surface) | 24720 | 07-07-2025 | 07-07-2025 |  |  | PO-5866/YYD2025100
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0815.0109 | CCC Side Plate | 300 | 0 | 300 | PR Required | - | PR |  | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1046 | Lock Tongue | 330 | 0 | 330 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 8DF.0818.1115 | left support plate (5mmT B.I Sheet) | 304 | 0 | 304 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | 8DF.0818.1115 | left support plate (5mmT B.I Sheet) | 396 | 0 | 396 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Leter | CM0000001949 | Sprit for cleaning | 75 | 0 | 75 | PR Required | - | PR |  | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | CM0000001950 | Desiccant | 150 | 150 | 0 | 6100KDP02 | PO-SEP-7352-[62] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | g | CM0000001951 | Vacuum Silicone Grease | 7500 | 7500 | 0 | free_stock | PO-SEP-8286-[2] | PO | 2025-11-10 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | Consumables for RMU Factory
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | CM0000001952 | Dust-free Paper | 3000 | 500 | 2500 | free_stock | PO-SEP-8286-[1] | PO | 2025-11-10 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | Consumables for RMU Factory
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | CM0000001952 | Dust-free Paper | 2500 | 2500 | 0 | 6100KDP02 | PO-SEP-7352-[61] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF240110385 | M24 Gran head nylon | 96 | 96 | 0 | 6100KDP02 | PO-SEP-6237-[27] | PO | 2025-11-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L1T & 2L2T SRMU Outer Enclosure (DFE Updated Design) M1 Material & Fastners for 677 Units | 531 | 24-06-2025 | 24-06-2025 |  |  | CSD25060201-SEA
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF240110385 | M24 Gran head nylon | 172 | 172 | 0 | 6100KDP02 | PO-SEP-6237-[27] | PO | 2025-11-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L1T & 2L2T SRMU Outer Enclosure (DFE Updated Design) M1 Material & Fastners for 677 Units | 531 | 24-06-2025 | 24-06-2025 |  |  | CSD25060201-SEA
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | mL | DF240424022 | Threadlocker | 15 | 0 | 15 | PR Required | - | PR |  | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | mL | DF240603043 | Glass glue | 7500 | 0 | 7500 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | mL | DF240603043 | Glass glue | 7600 | 0 | 7600 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | g | DF240603044 | Varnish (Epoxy anti-corrosion clear topcoat) | 1500 | 0 | 1500 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | g | DF240603044 | Varnish (Epoxy anti-corrosion clear topcoat) | 1520 | 0 | 1520 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF240612021 | UK2.5B Center Connection Bar (7connections)FBI 10-7(0203250) | 150 | 0 | 150 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF240612021 | UK2.5B Center Connection Bar (7connections)FBI 10-7(0203250) | 152 | 0 | 152 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | g | DF240612026 | Styrofoam | 7500 | 0 | 7500 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | g | DF240612026 | Styrofoam | 7600 | 0 | 7600 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF250318010 | Cross groove large pan head screw Stainless steel | 288 | 0 | 288 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF250318010 | Cross groove large pan head screw Stainless steel | 900 | 0 | 900 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF250318010 | Cross groove large pan head screw Stainless steel | 912 | 0 | 912 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF250616001 | Cross recessed pan head screw M6*20 | 3600 | 0 | 3600 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF250616001 | Cross recessed pan head screw M6*20 | 3648 | 0 | 3648 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF250719001 | Rubber pad 165*175*3 | 300 | 0 | 300 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF250719001 | Rubber pad 165*175*3 | 304 | 0 | 304 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF250802001 | φ3*8 Waterproof blind rivets Stainless steel | 300 | 0 | 300 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF250802001 | φ3*8 Waterproof blind rivets Stainless steel | 400 | 0 | 400 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF250820003 | Hydraulic Rod 1000N;L=450;One side flat, one side ball head | 96 | 0 | 96 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF250820003 | Hydraulic Rod 1000N;L=450;One side flat, one side ball head | 300 | 0 | 300 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | DF250820003 | Hydraulic Rod 1000N;L=450;One side flat, one side ball head | 304 | 0 | 304 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | LV0000000493 | Relay (RXM4AB2BD) Including base and buckle | 150 | 0 | 150 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | LV0000000493 | Relay (RXM4AB2BD) Including base and buckle | 152 | 0 | 152 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | HALB | RMU000000157 | Gas Tank, SF6 Insulated, Completed, 3L, 3 Way, 17.5kV/400, SKD Model, DEF E5312 | 152 | 152 | 0 | 6100KDP02 | PO-SEP-7353-[1] | PO | 2025-11-17 | Gas Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02 // 3L DFE Complete SRMU (QTY 48), Ready Gas Tank (QTY 152)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | HALB | RMU000000158 | SRMU Inner Cabinet, SF6 Insulated, 3L, 3 Way, 17.5kV/400, SKD Model, DEF E5312 | 48 | 48 | 0 | 6100KDP02 | PO-SEP-7353-[2] | PO | 2025-11-17 | RMU |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02 // 3L DFE Complete SRMU (QTY 48), Ready Gas Tank (QTY 152)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000172 | MCB-NDB1-63 C4/2(DFST) | 150 | 0 | 150 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000172 | MCB-NDB1-63 C4/2(DFST) | 152 | 0 | 152 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000176 | Common Enclosure Roof Bar | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[17] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000177 | Grounding Bar 1 | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[16] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000179 | Side Plate Transverse Tar | 300 | 300 | 0 | 6100KDP02 | PO-SEP-7352-[26] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000180 | 198 Bushing | 1800 | 1800 | 0 | 6100KDP02 | PO-SEP-7352-[14] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000181 | 220 Bushing | 1350 | 1350 | 0 | 6100KDP02 | PO-SEP-7352-[15] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000186 | Pressure Gauge Pad | 300 | 300 | 0 | 6100KDP02 | PO-SEP-7352-[24] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000187 | Front Reinforcing Rib | 300 | 300 | 0 | 6100KDP02 | PO-SEP-7352-[31] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000189 | Stator | 300 | 300 | 0 | 6100KDP02 | PO-SEP-7352-[30] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000196 | Three-station Load Switch Sealing Assembly | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[11] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | SET | RMU000000198 | UK2.5B Center Connection Bar (2 connections)FBI 2-6(0203438) | 750 | 0 | 750 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | SET | RMU000000198 | UK2.5B Center Connection Bar (2 connections)FBI 2-6(0203438) | 760 | 0 | 760 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000199 | UK2.5B Center Connection Bar (3 connections)FBI 10-3(0203250) | 150 | 0 | 150 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000199 | UK2.5B Center Connection Bar (3 connections)FBI 10-3(0203250) | 152 | 0 | 152 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000201 | UK2.5B Center Connection Bar (5 connections)FBI 10-5(0203250) | 150 | 0 | 150 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000201 | UK2.5B Center Connection Bar (5 connections)FBI 10-5(0203250) | 152 | 0 | 152 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000204 | Secondary grounding bar | 150 | 0 | 150 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000204 | Secondary grounding bar | 152 | 0 | 152 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000205 | Lead crystal battery (6-CNFJ-24) | 300 | 300 | 0 | 6100KDP02 | PO-SEP-8114-[1] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | AMMARTECH Contracting & Smart Solutions | 6100KDP02 // 3L 355 Units Amar tech Scope Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000205 | Lead crystal battery (6-CNFJ-24) | 304 | 304 | 0 | 6100KDP02 | PO-SEP-8114-[1] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | AMMARTECH Contracting & Smart Solutions | 6100KDP02 // 3L 355 Units Amar tech Scope Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000207 | C-A Phase Bus | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[37] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000208 | C-B Phase Bus | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[39] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000209 | C-C Phase Bus | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[41] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000210 | C-A Phase Grounding Bar | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[38] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000211 | C-B Phase Grounding Bar | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[40] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000212 | C-C Phase Grounding Bar | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[42] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | RMU000000216 | Wiring Channel 80 * 40 | 528 | 0 | 528 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | RMU000000216 | Wiring Channel 80 * 40 | 535.04 | 0 | 535.04 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000218 | Door lock (MS705 GH-18) | 300 | 300 | 0 | 6100KDP02 | PO-SEP-7697-[19] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000218 | Door lock (MS705 GH-18) | 304 | 304 | 0 | 6100KDP02 | PO-SEP-7697-[19] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000219 | ECT (400A/225mV) | 900 | 900 | 0 | 6100KDP02 | PO-SEP-8114-[3] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | AMMARTECH Contracting & Smart Solutions | 6100KDP02 // 3L 355 Units Amar tech Scope Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000219 | ECT (400A/225mV) | 912 | 912 | 0 | 6100KDP02 | PO-SEP-8114-[3] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | AMMARTECH Contracting & Smart Solutions | 6100KDP02 // 3L 355 Units Amar tech Scope Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000222 | Door stop guide sleeve | 300 | 0 | 300 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000222 | Door stop guide sleeve | 304 | 0 | 304 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000223 | Hinge (CL230-HL017) | 600 | 600 | 0 | 6100KDP02 | PO-SEP-7697-[20] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000223 | Hinge (CL230-HL017) | 608 | 608 | 0 | 6100KDP02 | PO-SEP-7697-[20] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000224 | Close button indicator light | 450 | 0 | 450 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000224 | Close button indicator light | 456 | 0 | 456 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000225 | Low pressure lockout indicator light;Red | 150 | 0 | 150 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000225 | Low pressure lockout indicator light;Red | 152 | 0 | 152 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000226 | Low pressure warning indicator light;Yellow | 600 | 0 | 600 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000226 | Low pressure warning indicator light;Yellow | 608 | 0 | 608 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | ROH | RMU000000227 | Open button indicator light | 450 | 0 | 450 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | ROH | RMU000000227 | Open button indicator light | 456 | 0 | 456 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000229 | Isolation Indicator | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[36] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | RMU000000231 | SEC Logo Board Print + Outdoor Protection | 96 | 96 | 0 | 6100KDP02 | PO-SEP-8868-[11] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | RMU000000231 | SEC Logo Board Print + Outdoor Protection | 300 | 300 | 0 | 6100KDP02 | PO-SEP-8868-[11] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | RMU000000231 | SEC Logo Board Print + Outdoor Protection | 304 | 304 | 0 | 6100KDP02 | PO-SEP-8868-[11] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000232 | Terminal strip label | 600 | 0 | 600 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000232 | Terminal strip label | 608 | 0 | 608 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | RMU000000233 | Warning Sign (Print + Outdoor Protection) | 96 | 96 | 0 | 6100KDP02 | PO-SEP-8868-[10] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | RMU000000233 | Warning Sign (Print + Outdoor Protection) | 300 | 300 | 0 | 6100KDP02 | PO-SEP-8868-[10] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | RMU000000233 | Warning Sign (Print + Outdoor Protection) | 304 | 304 | 0 | 6100KDP02 | PO-SEP-8868-[10] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000234 | Limit switch (YBLX-ME/8112) | 300 | 67 | 233 | 6100K011A | PO-SEP-7830-[2] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | CHINT ELECTRIC SAUDI ARABIA CO LTD | OVR // K006/K011A/K012A (DOOR LIMIT SWITCHES)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000234 | Limit switch (YBLX-ME/8112) | 233 | 15 | 218 | 6100K012A | PO-SEP-7830-[3] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | CHINT ELECTRIC SAUDI ARABIA CO LTD | OVR // K006/K011A/K012A (DOOR LIMIT SWITCHES)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000234 | Limit switch (YBLX-ME/8112) | 218 | 14 | 204 | 6100K006 | PO-SEP-7830-[1] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | CHINT ELECTRIC SAUDI ARABIA CO LTD | OVR // K006/K011A/K012A (DOOR LIMIT SWITCHES)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000234 | Limit switch (YBLX-ME/8112) | 204 | 204 | 0 | 6100K013 | PO-SEP-8253-[1] | PO | 2025-12-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 13 | CHINT ELECTRIC SAUDI ARABIA CO LTD
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000234 | Limit switch (YBLX-ME/8112) | 304 | 304 | 0 | 6100K013 | PO-SEP-8253-[1] | PO | 2025-12-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 13 | CHINT ELECTRIC SAUDI ARABIA CO LTD
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | SET | RMU000000236 | UK-2.5B marking strip (1-10) | 900 | 0 | 900 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | SET | RMU000000236 | UK-2.5B marking strip (1-10) | 912 | 0 | 912 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | SET | RMU000000240 | UK-2.5B marking strip (1-5) | 300 | 0 | 300 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | SET | RMU000000240 | UK-2.5B marking strip (1-5) | 304 | 0 | 304 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000247 | Load Switching Mechanism | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[10] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | SET | RMU000000248 | Load Switch Mechanism Mechanical Interlocking | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[48] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | SET | RMU000000249 | Load Switch Mechanism Mounting Assembly | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[49] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | SET | RMU000000250 | SF6 Gas Density Meter | 150 | 150 | 0 | 6100KDP02 | PO-SEP-7352-[46] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000252 | MCB-NDB1Z-63 C16/2+OF1(DFST) | 150 | 150 | 0 | 6100K013 | PO-SEP-8099-[4] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Shanghai Quisure Info-Tech Co. Ltd
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000252 | MCB-NDB1Z-63 C16/2+OF1(DFST) | 152 | 152 | 0 | 6100K013 | PO-SEP-8099-[8] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Shanghai Quisure Info-Tech Co. Ltd
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000253 | MCB-NDB1Z-63 C6/2(DFST) | 300 | 300 | 0 | 6100K013 | PO-SEP-8099-[3] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Shanghai Quisure Info-Tech Co. Ltd
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000253 | MCB-NDB1Z-63 C6/2(DFST) | 304 | 304 | 0 | 6100K013 | PO-SEP-8099-[3] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Shanghai Quisure Info-Tech Co. Ltd
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000254 | MCB-NDB1Z-63 C6/2+FS1(DFST) | 150 | 150 | 0 | 6100K013 | PO-SEP-8099-[2] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Shanghai Quisure Info-Tech Co. Ltd
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000254 | MCB-NDB1Z-63 C6/2+FS1(DFST) | 152 | 152 | 0 | 6100K013 | PO-SEP-8099-[6] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Shanghai Quisure Info-Tech Co. Ltd
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000256 | Data acquisition module (LP-204) | 150 | 0 | 150 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000256 | Data acquisition module (LP-204) | 152 | 0 | 152 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000257 | Power module (DFE500A-AC220D24-ST-X) | 150 | 150 | 0 | 6100KDP02 | PO-SEP-8114-[5] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | AMMARTECH Contracting & Smart Solutions | 6100KDP02 // 3L 355 Units Amar tech Scope Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000257 | Power module (DFE500A-AC220D24-ST-X) | 152 | 152 | 0 | 6100KDP02 | PO-SEP-8114-[5] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | AMMARTECH Contracting & Smart Solutions | 6100KDP02 // 3L 355 Units Amar tech Scope Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000259 | UK-2.5B voltage terminal partition (D-UK2.5) | 950 | 950 | 0 | 6100K013 | PO-SEP-8571-[2] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Phoenix Contact Trading LLC | RMU PHOENIX ITEMS-NOT UNDER SECRECY AGREEMENT
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000259 | UK-2.5B voltage terminal partition (D-UK2.5) | 1216 | 1216 | 0 | 6100K013 | PO-SEP-8571-[2] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Phoenix Contact Trading LLC | RMU PHOENIX ITEMS-NOT UNDER SECRECY AGREEMENT
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000267 | Socket (13A/60HZ) | 150 | 0 | 150 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000267 | Socket (13A/60HZ) | 152 | 0 | 152 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000268 | Soft connection (YTZ-(X)-35/8-12) | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[65] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000269 | V Strut Welding | 300 | 300 | 0 | 6100KDP02 | PO-SEP-7352-[12] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000272 | Three-station Load Switch | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[9] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | RMU000000273 | Waterproof Adhesive Tape (Large) UC-15 EPDM | 1056 | 116.28 | 939.72 | 6100KDP02 | PO-SEP-8869-[1] | PO | 2025-10-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | MESAN KİLİT A.Ş. | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | RMU000000273 | Waterproof Adhesive Tape (Large) UC-15 EPDM | 939.72 | 939.72 | 0 | free_stock | PO-SEP-8850-[6] | PO | 2025-10-27 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Etjahat Alrabt Est | Sealing strip (2018EVA)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | RMU000000273 | Waterproof Adhesive Tape (Large) UC-15 EPDM | 1408 | 1360.28 | 47.72 | free_stock | PO-SEP-8850-[6] | PO | 2025-10-27 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Etjahat Alrabt Est | Sealing strip (2018EVA)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | RMU000000273 | Waterproof Adhesive Tape (Large) UC-15 EPDM | 47.72 | 47.72 | 0 | free_stock | PO-SEP-8850-[4] | PO | 2025-10-27 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Etjahat Alrabt Est | Sealing strip (2018EVA)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | RMU000000274 | Waterproof Adhesive Tape (Large) UD-07 EPDM | 195 | 195 | 0 | 6100KDP02 | PO-SEP-8869-[2] | PO | 2025-10-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | MESAN KİLİT A.Ş. | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | RMU000000274 | Waterproof Adhesive Tape (Large) UD-07 EPDM | 260 | 260 | 0 | 6100KDP02 | PO-SEP-8869-[2] | PO | 2025-10-25 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | MESAN KİLİT A.Ş. | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000278 | Phoenix voltage terminal (UK-2.5B) | 4050 | 4050 | 0 | 6100K013 | PO-SEP-8571-[1] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Phoenix Contact Trading LLC | RMU PHOENIX ITEMS-NOT UNDER SECRECY AGREEMENT
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000278 | Phoenix voltage terminal (UK-2.5B) | 4104 | 4104 | 0 | 6100K013 | PO-SEP-8571-[1] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Phoenix Contact Trading LLC | RMU PHOENIX ITEMS-NOT UNDER SECRECY AGREEMENT
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000279 | Test Socket NTC1-332AS6h/250V | 150 | 150 | 0 | 6100K013 | PO-SEP-8102-[1] | PO | 2025-11-27 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | CHINT ELECTRIC SAUDI ARABIA CO LTD
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000279 | Test Socket NTC1-332AS6h/250V | 152 | 152 | 0 | 6100K013 | PO-SEP-8102-[2] | PO | 2025-11-27 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | CHINT ELECTRIC SAUDI ARABIA CO LTD
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000280 | Tie strap (black) 4*150 | 112500 | 0 | 112500 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000280 | Tie strap (black) 4*150 | 114000 | 0 | 114000 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000281 | Tie strap (black) 5*200 | 3750 | 0 | 3750 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000281 | Tie strap (black) 5*200 | 3800 | 0 | 3800 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000285 | Self-sealing Valve | 300 | 300 | 0 | 6100KDP02 | PO-SEP-7352-[47] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000286 | Button protection cover | 900 | 0 | 900 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000286 | Button protection cover | 912 | 0 | 912 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000287 | Door lock (MS310 Hengzhu) | 450 | 0 | 450 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000287 | Door lock (MS310 Hengzhu) | 456 | 0 | 456 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000288 | Grounding identification 1 φ12 | 150 | 0 | 150 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000288 | Grounding identification 1 φ12 | 152 | 0 | 152 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000289 | Grounding identification 2 φ10 | 600 | 600 | 0 | 6100KDP02 | PO-SEP-7352-[27] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000289 | Grounding identification 2 φ10 | 906 | 20 | 886 | 6100KDP02 | PO-SEP-7352-[27] | PO | 2025-11-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000289 | Grounding identification 2 φ10 | 886 | 0 | 886 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000291 | Cable door guide sleeve | 1812 | 0 | 1812 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000292 | Hinge (F45) | 900 | 0 | 900 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000292 | Hinge (F45) | 912 | 0 | 912 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000293 | Charge indicator (DXN-T-FD/17.5) | 450 | 0 | 450 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000293 | Charge indicator (DXN-T-FD/17.5) | 456 | 0 | 456 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000294 | Cable room insulation board 1 | 900 | 0 | 900 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000294 | Cable room insulation board 1 | 912 | 0 | 912 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000295 | Grounding box twist lock (38*27) | 450 | 0 | 450 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000295 | Grounding box twist lock (38*27) | 456 | 0 | 456 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | ROH | RMU000000303 | RTU_DF1725IED (3Way-3L)_Subrack 2/3 19" +48DI+8CO+9ECT+3EVT ¦ DF250723003 | 48 | 48 | 0 | 6100KDP02 | PO-SEP-7894-[1] | PO | 2025-11-26 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | AMMARTECH Contracting & Smart Solutions | 6100KDP02 // 3L SRMU (350 Units RTU)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10160 | TRAFFOLYTE, BLACK/WHITE/WHITE - BLACK/TRAFFOLYTE | 75 | 0 | 75 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10160 | TRAFFOLYTE, BLACK/WHITE/WHITE - BLACK/TRAFFOLYTE | 76 | 0 | 76 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10162 | FERRULE TUBE, WHITE , INNER DIA 3.5MM (1.5 WIRE),200 MTRS,KSS | 1600 | 20 | 1580 | 6100K024 | PO-SEP-8879-[5] | PO | 2025-12-21 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 4 | Sana For Electric And Telephone Co | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10162 | FERRULE TUBE, WHITE , INNER DIA 3.5MM (1.5 WIRE),200 MTRS,KSS | 1580 | 450 | 1130 | free_stock | PO-SEP-6620-[1] | PO | 2025-08-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Sana For Electric And Telephone Co | EBM-BULK/FERRULE TUBE - PLANT-A | 774 | 17-07-2025
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10162 | FERRULE TUBE, WHITE , INNER DIA 3.5MM (1.5 WIRE),200 MTRS,KSS | 1130 | 165 | 965 | free_stock | PO-SEP-7636-[4] | PO | 2025-09-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Sana For Electric And Telephone Co | LV-BULK ITEMS
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10162 | FERRULE TUBE, WHITE , INNER DIA 3.5MM (1.5 WIRE),200 MTRS,KSS | 965 | 747 | 218 | free_stock | PO-SEP-8356-[3] | PO | 2025-10-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Sana For Electric And Telephone Co | EBM-BULK FAST MOVING
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10162 | FERRULE TUBE, WHITE , INNER DIA 3.5MM (1.5 WIRE),200 MTRS,KSS | 218 | 64 | 154 | 6100K021 | PO-SEP-8881-[11] | PO | 2025-12-21 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 4 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10162 | FERRULE TUBE, WHITE , INNER DIA 3.5MM (1.5 WIRE),200 MTRS,KSS | 154 | 64 | 90 | 6100K025 | PO-SEP-8884-[11] | PO | 2025-12-21 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 4 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10162 | FERRULE TUBE, WHITE , INNER DIA 3.5MM (1.5 WIRE),200 MTRS,KSS | 90 | 64 | 26 | 6100K020 | PO-SEP-8830-[5] | PO | 2025-12-31 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 14 | Sana For Electric And Telephone Co | 6100K020 Mahar SS SWGR Electrical components order.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10162 | FERRULE TUBE, WHITE , INNER DIA 3.5MM (1.5 WIRE),200 MTRS,KSS | 26 | 26 | 0 | free_stock | PO-SEP-8502-[31] | PO | 2025-12-31 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 14 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10162 | 1.5 White Wire Gauge Tube 1.5mm² | 1672 | 25 | 1647 | free_stock | PO-SEP-8502-[31] | PO | 2025-12-31 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 14 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10162 | 1.5 White Wire Gauge Tube 1.5mm² | 1647 | 1647 | 0 | free_stock | PR-SEP-0023387-[172] | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10163 | FERRULE TUBE, RED , INNER DIA. 3.5MM (1.5 WIRE),200 MTRS,KSS | 22.5 | 3 | 19.5 | free_stock | PO-SEP-8906-[3] | PO | 2026-01-04 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 18 | Sana For Electric And Telephone Co | EBM-BULK/ PETTY CASH/ Lugs, Terminal Ring, 1.5 Sq.mm ¦ CEM-RF-M4 ¦ Cembre
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10163 | FERRULE TUBE, RED , INNER DIA. 3.5MM (1.5 WIRE),200 MTRS,KSS | 19.5 | 19.5 | 0 | free_stock | PR-SEP-0023387-[171] | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10163 | 1.5 Red Wire Gauge Tube 1.5mm² | 22.8 | 22.8 | 0 | free_stock | PR-SEP-0023387-[171] | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10298 | FERRULE TUBE, RED , INNER DIA. 4.5MM (2,5 WIRE),200 MTRS,KSS | 15 | 1 | 14 | 6100K024 | PO-SEP-8879-[2] | PO | 2025-12-21 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 4 | Sana For Electric And Telephone Co | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10298 | FERRULE TUBE, RED , INNER DIA. 4.5MM (2,5 WIRE),200 MTRS,KSS | 14 | 7 | 7 | free_stock | PO-SEP-7302-[2] | PO | 2025-09-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Sana For Electric And Telephone Co | PLANT -A BULK MATERIAL | 67 | 25-08-2025
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10298 | FERRULE TUBE, RED , INNER DIA. 4.5MM (2,5 WIRE),200 MTRS,KSS | 7 | 3 | 4 | 6100K021 | PO-SEP-8881-[2] | PO | 2025-12-21 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 4 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10298 | FERRULE TUBE, RED , INNER DIA. 4.5MM (2,5 WIRE),200 MTRS,KSS | 4 | 3 | 1 | 6100K025 | PO-SEP-8884-[2] | PO | 2025-12-21 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 4 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10298 | FERRULE TUBE, RED , INNER DIA. 4.5MM (2,5 WIRE),200 MTRS,KSS | 1 | 1 | 0 | 6100K020 | PO-SEP-8830-[2] | PO | 2025-12-31 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 14 | Sana For Electric And Telephone Co | 6100K020 Mahar SS SWGR Electrical components order.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10298 | 4.0 Red Wire Gauge Tube 4.0mm² | 15.2 | 2 | 13.2 | 6100K020 | PO-SEP-8830-[2] | PO | 2025-12-31 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 14 | Sana For Electric And Telephone Co | 6100K020 Mahar SS SWGR Electrical components order.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10298 | 4.0 Red Wire Gauge Tube 4.0mm² | 13.2 | 13.2 | 0 | free_stock | PR-SEP-0023387-[167] | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10298 | FERRULE TUBE, RED , INNER DIA. 4.5MM (2,5 WIRE),200 MTRS,KSS | 52.5 | 52.5 | 0 | free_stock | PR-SEP-0023387-[167] | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10298 | 2.5 Red Wire Gauge Tube 2.5mm² | 53.2 | 53.2 | 0 | free_stock | PR-SEP-0024130-[143] | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10526 | Wrapped tube (black) φ8 | 1200 | 0 | 1200 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10526 | Wrapped tube (black) φ8 | 1216 | 0 | 1216 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10650 | FERRULE TUBE, WHITE , INNER DIA 4.0MM (2.5 WIRE),200 MTRS,KSS | 52.5 | 52.5 | 0 | free_stock | PR-SEP-0023387-[173] | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10650 | 4.0 White Wire Gauge Tube 4.0mm² | 53.2 | 53.2 | 0 | free_stock | PR-SEP-0023387-[173] | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10650 | FERRULE TUBE, WHITE , INNER DIA 4.0MM (2.5 WIRE),200 MTRS,KSS | 225 | 225 | 0 | free_stock | PR-SEP-0023387-[173] | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10650 | 2.5 White Wire Gauge Tube 2.5mm² | 228 | 228 | 0 | free_stock | PR-SEP-0024130-[176] | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10848 | Cross recessed self-tapping locking screw M4*12 | 150 | 150 | 0 | 6100K024 | PO-SEP-8871-[1] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10848 | Cross recessed self-tapping locking screw M4*12 | 200 | 200 | 0 | 6100K024 | PO-SEP-8871-[1] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10848 | Cross recessed self-tapping locking screw M4*12 | 300 | 300 | 0 | 6100K024 | PO-SEP-8871-[1] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10848 | Cross recessed self-tapping locking screw M4*12 | 400 | 400 | 0 | 6100K024 | PO-SEP-8871-[1] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10848 | Cross recessed self-tapping locking screw M4*12 | 4050 | 4050 | 0 | 6100K024 | PO-SEP-8871-[1] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10848 | Cross recessed self-tapping locking screw M4*12 | 4104 | 3270 | 834 | 6100K024 | PO-SEP-8871-[1] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10848 | Cross recessed self-tapping locking screw M4*12 | 834 | 0 | 834 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10849 | Hex Nut M10 | 6300 | 6300 | 0 | 6100K024 | PO-SEP-8871-[2] | PO | 2025-10-23 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10849 | Hex Nut M10 | 12080 | 6100 | 5980 | 6100K024 | PO-SEP-8871-[2] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10849 | Hex Nut M10 | 5980 | 5980 | 0 | 6100KDP02 | PO-SEP-7352-[5] | PO | 2025-11-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10850 | Hex Nut M12 | 150 | 150 | 0 | 6100K024 | PO-SEP-8871-[3] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10850 | Hex Nut M12 | 152 | 152 | 0 | 6100K024 | PO-SEP-8871-[3] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10852 | Hex Nut M8 | 3450 | 3450 | 0 | 6100K024 | PO-SEP-8871-[4] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10852 | Hex Nut M8 | 3496 | 3496 | 0 | 6100K024 | PO-SEP-8871-[4] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10852 | Hex Nut M8 | 14400 | 184 | 14216 | 6100K024 | PO-SEP-8871-[4] | PO | 2025-10-23 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10852 | Hex Nut M8 | 14216 | 14216 | 0 | 6100KDP02 | PO-SEP-7352-[6] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10853 | Flat Washer φ10 | 2250 | 2250 | 0 | 6100KDP02 | PO-SEP-7352-[3] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10853 | Flat Washer φ10 | 10200 | 540 | 9660 | 6100KDP02 | PO-SEP-7352-[3] | PO | 2025-11-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10853 | Flat Washer φ10 | 9660 | 0 | 9660 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10853 | Flat Washer φ10 | 10336 | 0 | 10336 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10854 | Flat Washer φ6 | 8700 | 8700 | 0 | 6100K024 | PO-SEP-8871-[6] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10854 | Flat Washer φ6 | 8816 | 8816 | 0 | 6100K024 | PO-SEP-8871-[6] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10854 | Flat Washer φ6 | 11200 | 464 | 10736 | 6100K024 | PO-SEP-8871-[6] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10854 | Flat Washer φ6 | 10736 | 4340 | 6396 | 6100KDP02 | PO-SEP-7697-[9] | PO | 2025-11-30 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10854 | Flat Washer φ6 | 6396 | 6396 | 0 | 6100KDP02 | PO-SEP-8868-[29] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10855 | Flat Washer φ8 | 1650 | 1650 | 0 | 6100K024 | PO-SEP-8871-[7] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10855 | Flat Washer φ8 | 1672 | 1672 | 0 | 6100K024 | PO-SEP-8871-[7] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10855 | Flat Washer φ8 | 12000 | 88 | 11912 | 6100K024 | PO-SEP-8871-[7] | PO | 2025-10-23 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10855 | Flat Washer φ8 | 11912 | 11912 | 0 | 6100KDP02 | PO-SEP-7352-[4] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10856 | Spring Washer φ10 | 5100 | 5100 | 0 | 6100K024 | PO-SEP-8871-[8] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10856 | Spring Washer φ10 | 5168 | 5168 | 0 | 6100K024 | PO-SEP-8871-[8] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10856 | Spring Washer φ10 | 7650 | 272 | 7378 | 6100K024 | PO-SEP-8871-[8] | PO | 2025-10-23 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10856 | Spring Washer φ10 | 7378 | 7378 | 0 | 6100KDP02 | PO-SEP-7352-[1] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10857 | Spring Washer φ4 | 300 | 300 | 0 | 6100K024 | PO-SEP-8871-[9] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10857 | Spring Washer φ4 | 304 | 304 | 0 | 6100K024 | PO-SEP-8871-[9] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10857 | Spring Washer φ4 | 4200 | 16 | 4184 | 6100K024 | PO-SEP-8871-[9] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10857 | Spring Washer φ4 | 4184 | 620 | 3564 | 6100KDP02 | PO-SEP-7697-[25] | PO | 2025-11-30 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10857 | Spring Washer φ4 | 3564 | 0 | 3564 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10858 | Spring Washer φ6 | 11400 | 11400 | 0 | 6100K024 | PO-SEP-8871-[10] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10858 | Spring Washer φ6 | 11552 | 11552 | 0 | 6100K024 | PO-SEP-8871-[10] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10858 | Spring Washer φ6 | 12300 | 608 | 11692 | 6100K024 | PO-SEP-8871-[10] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10858 | Spring Washer φ6 | 11692 | 8990 | 2702 | 6100KDP02 | PO-SEP-7697-[10] | PO | 2025-11-30 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10858 | Spring Washer φ6 | 2702 | 2702 | 0 | 6100KDP02 | PO-SEP-8868-[9] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10858 | Spring Washer φ6 | 16400 | 16400 | 0 | 6100KDP02 | PO-SEP-8868-[9] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10859 | Spring Washer φ8 | 5250 | 5250 | 0 | 6100K024 | PO-SEP-8871-[11] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10859 | Spring Washer φ8 | 5320 | 5320 | 0 | 6100K024 | PO-SEP-8871-[11] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10859 | Spring Washer φ8 | 14400 | 280 | 14120 | 6100K024 | PO-SEP-8871-[11] | PO | 2025-10-23 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10859 | Spring Washer φ8 | 14120 | 14120 | 0 | 6100KDP02 | PO-SEP-7352-[2] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10861 | M12*110 Expansion bolt hot dip galvanized | 1200 | 1200 | 0 | 6100KDP02 | PO-SEP-8868-[5] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10861 | M12*110 Expansion bolt hot dip galvanized | 1600 | 900 | 700 | 6100KDP02 | PO-SEP-8868-[5] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10861 | M12*110 Expansion bolt hot dip galvanized | 700 | 0 | 700 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10862 | Half round head hexagon socket bolt M6*40 | 900 | 900 | 0 | 6100K024 | PO-SEP-8871-[12] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10862 | Half round head hexagon socket bolt M6*40 | 912 | 912 | 0 | 6100K024 | PO-SEP-8871-[12] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10863 | Hex Bolt M10*110 | 900 | 900 | 0 | 6100K024 | PO-SEP-8871-[13] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10863 | Hex Bolt M10*110 | 912 | 912 | 0 | 6100K024 | PO-SEP-8871-[13] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10864 | Hex Bolt M10*25 | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[69] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10865 | Hexagonal head combination bolt M10*25 | 1350 | 1350 | 0 | 6100KDP02 | PO-SEP-7352-[68] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10866 | M10*30 Hex bolts Stainless steel | 1200 | 1200 | 0 | 6100KDP02 | PO-SEP-8868-[2] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10866 | M10*30 Hex bolts Stainless steel | 1600 | 1600 | 0 | 6100KDP02 | PO-SEP-8868-[2] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10867 | Hex Bolt M10*35 | 3300 | 3300 | 0 | 6100K024 | PO-SEP-8871-[14] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10867 | Hex Bolt M10*35 | 3344 | 3344 | 0 | 6100K024 | PO-SEP-8871-[14] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10869 | Hex Bolt M12*30 | 150 | 150 | 0 | 6100K024 | PO-SEP-8871-[15] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10869 | Hex Bolt M12*30 | 152 | 152 | 0 | 6100K024 | PO-SEP-8871-[15] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10870 | Hex Bolt M6*16 | 3600 | 1240 | 2360 | 6100KDP02 | PO-SEP-7697-[6] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10870 | Hex Bolt M6*16 | 2360 | 0 | 2360 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10870 | Hex Bolt M6*16 | 3648 | 0 | 3648 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10871 | Hex Bolt M6*20 | 1950 | 1950 | 0 | 6100K024 | PO-SEP-8871-[17] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10871 | Hex Bolt M6*20 | 1976 | 1976 | 0 | 6100K024 | PO-SEP-8871-[17] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10871 | Hex Bolt M6*20 | 11700 | 104 | 11596 | 6100K024 | PO-SEP-8871-[17] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10871 | Hex Bolt M6*20 | 11596 | 4030 | 7566 | 6100KDP02 | PO-SEP-7697-[7] | PO | 2025-11-30 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10871 | Hex Bolt M6*20 | 7566 | 7566 | 0 | 6100KDP02 | PO-SEP-8868-[7] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10871 | Hex Bolt M6*20 | 15600 | 15600 | 0 | 6100KDP02 | PO-SEP-8868-[7] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10872 | Hex Bolt M8*20 | 900 | 900 | 0 | 6100K024 | PO-SEP-8871-[18] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10872 | Hex Bolt M8*20 | 912 | 912 | 0 | 6100K024 | PO-SEP-8871-[18] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10873 | Hex Bolt M8*25 | 600 | 600 | 0 | 6100K024 | PO-SEP-8871-[19] | PO | 2025-10-23 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10873 | Hex Bolt M8*25 | 1650 | 1650 | 0 | 6100K024 | PO-SEP-8871-[19] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10873 | Hex Bolt M8*25 | 1672 | 1160 | 512 | 6100K024 | PO-SEP-8871-[19] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10873 | Hex Bolt M8*25 | 512 | 512 | 0 | 6100KDP02 | PO-SEP-7352-[7] | PO | 2025-11-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10874 | Half round head hexagon combination screw M6 * 12 | 5436 | 5436 | 0 | 6100K024 | PO-SEP-8871-[20] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10875 | Hex Bolt M6*25 | 906 | 906 | 0 | 6100K024 | PO-SEP-8871-[21] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10876 | Plastic buckle M4.5*10 | 2718 | 2718 | 0 | 6100K024 | PO-SEP-8871-[22] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10876 | Plastic buckle M4.5*10 | 3150 | 72 | 3078 | 6100K024 | PO-SEP-8871-[22] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10876 | Plastic buckle M4.5*10 | 3078 | 3078 | 0 | 6100KDP02 | PO-SEP-8868-[15] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10878 | Round plastic buckle φ23 | 1812 | 1812 | 0 | 6100K024 | PO-SEP-8871-[23] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10879 | Round plastic buckle 40° | 906 | 906 | 0 | 6100K024 | PO-SEP-8871-[24] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10883 | Black rubber gasket (φ6-12 2mm) | 3624 | 3624 | 0 | 6100K024 | PO-SEP-8871-[25] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10884 | Gland M30*1.5 | 1812 | 1812 | 0 | 6100K024 | PO-SEP-8871-[26] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10885 | Gland M40*1.5 | 1208 | 1208 | 0 | 6100K024 | PO-SEP-8871-[27] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10889 | Grub Screw M6*16 | 3624 | 3624 | 0 | 6100K024 | PO-SEP-8871-[28] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10895 | Flange Nut M8 | 1812 | 1248 | 564 | 6100K024 | PO-SEP-8871-[29] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10895 | Flange Nut M8 | 564 | 0 | 564 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10896 | Hex Nut M4 | 604 | 604 | 0 | 6100K024 | PO-SEP-8871-[30] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10897 | Hex Nut M8 | 302 | 302 | 0 | 6100K024 | PO-SEP-8871-[31] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10897 | Hex Nut M8 | 700 | 8 | 692 | 6100K024 | PO-SEP-8871-[31] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10897 | Hex Nut M8 | 692 | 692 | 0 | 6100KDP02 | PO-SEP-8868-[17] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10898 | Hexagonal thin nut M3*1.65 | 7248 | 7248 | 0 | 6100K024 | PO-SEP-8871-[32] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10899 | Self-locking Nut M3 | 1400 | 1400 | 0 | 6100K024 | PO-SEP-8871-[33] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10899 | Self-locking Nut M3 | 2416 | 1080 | 1336 | 6100K024 | PO-SEP-8871-[33] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10899 | Self-locking Nut M3 | 1336 | 1336 | 0 | 6100KDP02 | PO-SEP-7697-[15] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10900 | Self-locking Nut M4 | 3624 | 3624 | 0 | 6100K024 | PO-SEP-8871-[34] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10900 | Self-locking Nut M4 | 6300 | 96 | 6204 | 6100K024 | PO-SEP-8871-[34] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10900 | Self-locking Nut M4 | 6204 | 3720 | 2484 | 6100KDP02 | PO-SEP-7697-[4] | PO | 2025-11-30 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10900 | Self-locking Nut M4 | 2484 | 0 | 2484 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10901 | Self-locking Nut M6 | 3624 | 3624 | 0 | 6100K024 | PO-SEP-8871-[35] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10901 | Self-locking Nut M6 | 7000 | 96 | 6904 | 6100K024 | PO-SEP-8871-[35] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10901 | Self-locking Nut M6 | 6904 | 930 | 5974 | 6100KDP02 | PO-SEP-7697-[23] | PO | 2025-11-30 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10901 | Self-locking Nut M6 | 5974 | 5974 | 0 | 6100KDP02 | PO-SEP-8868-[35] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10902 | Self-locking Nut M8 | 1400 | 1400 | 0 | 6100K024 | PO-SEP-8871-[36] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10902 | Self-locking Nut M8 | 1950 | 1950 | 0 | 6100K024 | PO-SEP-8871-[36] | PO | 2025-10-23 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10902 | Self-locking Nut M8 | 3322 | 60 | 3262 | 6100K024 | PO-SEP-8871-[36] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10902 | Self-locking Nut M8 | 3262 | 2015 | 1247 | 6100KDP02 | PO-SEP-7352-[67] | PO | 2025-11-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10902 | Self-locking Nut M8 | 1247 | 1247 | 0 | 6100KDP02 | PO-SEP-8868-[18] | PO | 2025-12-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10904 | Paw pad φ6 | 1510 | 1510 | 0 | 6100K024 | PO-SEP-8871-[37] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10906 | Tower seal ring φ115 | 906 | 0 | 906 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | (blank) | SEP10907 | Rivet Nut M6*15 | 1208 | 1208 | 0 | 6100K024 | PO-SEP-8871-[38] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10907 | Rivet Nut M6*15 | 10570 | 10570 | 0 | 6100K024 | PO-SEP-8871-[38] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10907 | Rivet Nut M6*15 | 27300 | 312 | 26988 | 6100K024 | PO-SEP-8871-[38] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10907 | Rivet Nut M6*15 | 26988 | 3100 | 23888 | 6100KDP02 | PO-SEP-7697-[18] | PO | 2025-11-30 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10907 | Rivet Nut M6*15 | 23888 | 0 | 23888 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10908 | Rivet Nut M8*18 | 3926 | 3926 | 0 | 6100K024 | PO-SEP-8871-[39] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10909 | Blind Rivet (φ3.2*7) | 604 | 604 | 0 | 6100K024 | PO-SEP-8871-[40] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10911 | Seahorse countersunk rivets φ6.4*10.5 | 4228 | 4228 | 0 | 6100K024 | PO-SEP-8871-[41] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10913 | Seahorse rivet (φ6.4*10.5) | 18900 | 18900 | 0 | 6100K024 | PO-SEP-8871-[42] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10913 | Seahorse rivet (φ6.4*10.5) | 43186 | 25430 | 17756 | 6100K024 | PO-SEP-8871-[42] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10913 | Seahorse rivet (φ6.4*10.5) | 17756 | 17756 | 0 | 6100KDP02 | PO-SEP-8916-[1] | PO | 2025-11-04 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Sea house Rivet updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10914 | Seahorse rivet φ6.4*12.5 | 4530 | 4530 | 0 | 6100K024 | PO-SEP-8871-[43] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10915 | Seahorse rivet φ6.4*16.5 | 1400 | 0 | 1400 | PR Required | - | PR |  | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10915 | Seahorse rivet φ6.4*16.5 | 3624 | 0 | 3624 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10916 | Round plastic buckle φ54 | 302 | 302 | 0 | 6100K024 | PO-SEP-8871-[45] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10917 | Hexagon Socket Head Cap Screw M10*35 | 1350 | 1350 | 0 | 6100KDP02 | PO-SEP-7352-[58] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10918 | Hexagon Socket Countersunk Head Screw M8*25 | 1800 | 1800 | 0 | 6100KDP02 | PO-SEP-7352-[52] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10919 | Cross groove pan head combination screw M4*10 | 1800 | 1800 | 0 | 6100K024 | PO-SEP-8871-[46] | PO | 2025-10-23 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10919 | Cross groove pan head combination screw M4*10 | 1812 | 60 | 1752 | 6100K024 | PO-SEP-8871-[46] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10919 | Cross groove pan head combination screw M4*10 | 1752 | 1752 | 0 | 6100KDP02 | PO-SEP-7352-[51] | PO | 2025-11-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10920 | Cross groove pan head combination screw M4*20 | 1350 | 1350 | 0 | 6100KDP02 | PO-SEP-7352-[71] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10922 | Cross recessed pan head screw M3*12 | 1400 | 1400 | 0 | 6100K024 | PO-SEP-8871-[47] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10922 | Cross recessed pan head screw M3*12 | 4228 | 2230 | 1998 | 6100K024 | PO-SEP-8871-[47] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10922 | Cross recessed pan head screw M3*12 | 1998 | 1860 | 138 | 6100KDP02 | PO-SEP-7697-[13] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10922 | Cross recessed pan head screw M3*12 | 138 | 0 | 138 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10923 | Cross recessed pan head screw M4 * 12 | 4832 | 4832 | 0 | 6100K024 | PO-SEP-8871-[48] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10924 | Cross recessed pan head screw M4*16 | 1812 | 1812 | 0 | 6100K024 | PO-SEP-8871-[49] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10925 | Cross recessed pan head screw M4*30 | 1208 | 1208 | 0 | 6100K024 | PO-SEP-8871-[50] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10926 | Cross recessed self-tapping screw M5*12 | 1400 | 1400 | 0 | 6100K024 | PO-SEP-8871-[51] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10926 | Cross recessed self-tapping screw M5*12 | 11778 | 10690 | 1088 | 6100K024 | PO-SEP-8871-[51] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10926 | Cross recessed self-tapping screw M5*12 | 1088 | 1088 | 0 | 6100KDP02 | PO-SEP-8868-[40] | PO | 2025-12-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10927 | External hexagonal flange triangular thread self-tapping locking screw M6*12 | 9450 | 9450 | 0 | 6100K024 | PO-SEP-8871-[52] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10927 | External hexagonal flange triangular thread self-tapping locking screw M6*12 | 19026 | 10080 | 8946 | 6100K024 | PO-SEP-8871-[52] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10927 | External hexagonal flange triangular thread self-tapping locking screw M6*12 | 8946 | 8946 | 0 | free_stock | PO-SEP-8856-[2] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | REPLACEMENT ORDER FOR PO-SEP-8416 &PO-SEP-8449
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10928 | Cross groove countersunk head screw M3*6 | 7248 | 7248 | 0 | 6100K024 | PO-SEP-8871-[53] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10929 | Hexagon Socket Head Cap Screw M10*30 | 1800 | 1800 | 0 | 6100KDP02 | PO-SEP-7352-[56] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10930 | Hexagonal half round head combination screw M6 * 25 | 8100 | 8100 | 0 | 6100KDP02 | PO-SEP-7352-[50] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10931 | Hexagon Socket Head Cap Screw M12*35 | 1350 | 1350 | 0 | 6100KDP02 | PO-SEP-7352-[53] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10932 | Hexagonal Flange Triangular Thread Self-Tapping Screw M6*16 | 6040 | 6040 | 0 | 6100K024 | PO-SEP-8871-[54] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10933 | M4*16 Phillips countersunk head screw Stainless steel | 4200 | 4200 | 0 | 6100KDP02 | PO-SEP-8868-[19] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10934 | Sealing strip (2018EVA) | 4564 | 4564 | 0 | free_stock | PO-SEP-8850-[1] | PO | 2025-10-27 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Etjahat Alrabt Est | Sealing strip (2018EVA)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10934 | Sealing strip (2018EVA) | 6462.8 | 6462.8 | 0 | free_stock | PO-SEP-8850-[2] | PO | 2025-10-27 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Etjahat Alrabt Est | Sealing strip (2018EVA)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10935 | Square Nut M6 | 3624 | 3624 | 0 | 6100K024 | PO-SEP-8871-[55] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10936 | Welded stud M6*16 | 6040 | 6040 | 0 | 6100K024 | PO-SEP-8871-[56] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10937 | Welded Stud M8*20 | 11850 | 11850 | 0 | 6100KDP02 | PO-SEP-7352-[8] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10938 | Welded Stud M8*35 | 7200 | 7200 | 0 | 6100KDP02 | PO-SEP-7352-[45] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10939 | Welded Stud M8*25 | 900 | 900 | 0 | 6100KDP02 | PO-SEP-7352-[70] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10940 | Large Flat Washer φ6-18 | 11778 | 11778 | 0 | 6100K024 | PO-SEP-8871-[57] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10940 | Large Flat Washer φ6-18 | 17500 | 312 | 17188 | 6100K024 | PO-SEP-8871-[57] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10940 | Large Flat Washer φ6-18 | 17188 | 6510 | 10678 | 6100KDP02 | PO-SEP-7697-[8] | PO | 2025-11-30 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10940 | Large Flat Washer φ6-18 | 10678 | 10678 | 0 | 6100KDP02 | PO-SEP-8868-[8] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10941 | Large flat washer φ8-24 | 700 | 700 | 0 | 6100K024 | PO-SEP-8871-[58] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10941 | Large flat washer φ8-24 | 3000 | 3000 | 0 | 6100K024 | PO-SEP-8871-[58] | PO | 2025-10-23 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10941 | Large flat washer φ8-24 | 12080 | 8700 | 3380 | 6100K024 | PO-SEP-8871-[58] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10941 | Large flat washer φ8-24 | 3380 | 465 | 2915 | 6100KDP02 | PO-SEP-7352-[44] | PO | 2025-11-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10941 | Large flat washer φ8-24 | 2915 | 700 | 2215 | 6100KDP02 | PO-SEP-8868-[27] | PO | 2025-12-15 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10941 | Large flat washer φ8-24 | 2215 | 0 | 2215 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10942 | Flat Washer φ12 | 604 | 604 | 0 | 6100K024 | PO-SEP-8871-[59] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10943 | Flat Washer φ4 | 4200 | 4200 | 0 | 6100K024 | PO-SEP-8871-[60] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10943 | Flat Washer φ4 | 4228 | 140 | 4088 | 6100K024 | PO-SEP-8871-[60] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10943 | Flat Washer φ4 | 4088 | 4088 | 0 | 6100KDP02 | PO-SEP-7697-[3] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10944 | Flat Washer φ3 | 1400 | 1400 | 0 | 6100K024 | PO-SEP-8871-[61] | PO | 2025-10-23 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10944 | Flat Washer φ3 | 2416 | 1080 | 1336 | 6100K024 | PO-SEP-8871-[61] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10944 | Flat Washer φ3 | 1336 | 1336 | 0 | 6100KDP02 | PO-SEP-7697-[14] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP02 // 3L (310 Unit LV compartment Fasteners)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10945 | Thickened Plain Washer φ10 | 7650 | 7650 | 0 | 6100KDP02 | PO-SEP-7352-[57] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10946 | Thickened Plain Washer φ12 | 1350 | 1350 | 0 | 6100KDP02 | PO-SEP-7352-[54] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP10947 | φ10 spring washer Stainless steel | 2800 | 2800 | 0 | 6100KDP02 | PO-SEP-8868-[3] | PO | 2025-12-15 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100KDP02 // 3L SRMU Outer Enclosure updated item code parts
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10948 | White nylon washer (φ6-12 1.3mm) | 5436 | 5436 | 0 | 6100K024 | PO-SEP-8871-[62] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10956 | Wrapped mesh (black) φ25 | 2416 | 0 | 2416 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10957 | Wrapped mesh (black) φ30 | 211.4 | 211.4 | 0 | 6100K013 | PO-SEP-8087-[5] | PO | 2025-12-10 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Sana For Electric And Telephone Co | SRMU Electrical consumables
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP10958 | Hex Bolt M6*12 | 3624 | 3624 | 0 | 6100K024 | PO-SEP-8871-[63] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10975 | FERRULE TUBE, WHITE , INNER DIA. 2.5MM (1.0 WIRE),200 MTRS,KSS | 75 | 0 | 75 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP10975 | 1.0 White Wire Gauge Tube 1.0mm² | 76 | 0 | 76 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11135 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Red, 105°, 600/1000V , 1 x 91.4 m | 1238 | 50 | 1188 | 6100K024 | PO-SEP-8915-[31] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | Cable Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11135 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Red, 105°, 600/1000V , 1 x 91.4 m | 1188 | 38 | 1150 | 6100KDP02 | PO-SEP-7781-[2] | PO | 2025-10-10 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV -BULK MATERIAL | 12 | 30-10-2025
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11135 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Red, 105°, 600/1000V , 1 x 91.4 m | 1150 | 0 | 1150 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11135 | Wire harness (Red)BVR-1.5mm² | 1368 | 0 | 1368 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11136 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Yellow, 105°, 600/1000V, 1 x 91.4 m | 1200 | 50 | 1150 | 6100K024 | PO-SEP-8915-[32] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | Cable Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11136 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Yellow, 105°, 600/1000V, 1 x 91.4 m | 1150 | 0 | 1150 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11136 | Wire harness (Yellow)BVR-1.5mm² | 1368 | 0 | 1368 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11137 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Blue, 105°, 600/1000V , 1 x 91.4 m | 12997 | 300 | 12697 | 6100K024 | PO-SEP-8915-[33] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | Cable Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11137 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Blue, 105°, 600/1000V , 1 x 91.4 m | 12697 | 0 | 12697 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11137 | Wire harness (Blue)BVR-1.5mm² | 13680 | 0 | 13680 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 3900 | 50 | 3850 | 6100K024 | PO-SEP-8915-[34] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | Cable Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 3850 | 123 | 3727 | 6100K008 | PO-SEP-7860-[21] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 3727 | 119 | 3608 | 6100K017 | PO-SEP-7860-[45] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 3608 | 57 | 3551 | 6100K006 | PO-SEP-7860-[9] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 3551 | 42 | 3509 | 6100K007 | PO-SEP-7860-[13] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 3509 | 30 | 3479 | 6100K010 | PO-SEP-7860-[25] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 3479 | 30 | 3449 | 6100K012A | PO-SEP-7860-[37] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 3449 | 11 | 3438 | 6100K006 | PO-SEP-7860-[1] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs) | 208 | 30-10-2025
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 3438 | 1 | 3437 | 6100K007 | PO-SEP-7860-[17] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 3437 | 50 | 3387 | 6100K006 | PO-SEP-7858-[1] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/SEC/OVR (1.5 sq mm wires black)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 3387 | 520 | 2867 | free_stock | PO-SEP-8294-[2] | PO | 2025-12-29 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 12 | Al-Fanar Company Limited | EBM-BULK CABLE ITEMS
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 2867 | 407 | 2460 | free_stock | PO-SEP-8891-[2] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | EBM-BULK/ KANBAN MATERIALS/ Lugs, Terminal Ring, 1.5 Sq.mm ¦ R1-4A ¦ Jeesoon
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 2460 | 0 | 2460 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11138 | Wire harness (black)BVR-1.5mm² | 3952 | 0 | 3952 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11142 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 21462 | 483 | 20979 | 6100K024 | PO-SEP-8915-[35] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | Cable Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11142 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 20979 | 5100 | 15879 | free_stock | PO-SEP-8294-[3] | PO | 2025-12-29 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 12 | Al-Fanar Company Limited | EBM-BULK CABLE ITEMS | 1175 | 30-10-2025
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11142 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 15879 | 6701 | 9178 | free_stock | PO-SEP-8891-[1] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | EBM-BULK/ KANBAN MATERIALS/ Lugs, Terminal Ring, 1.5 Sq.mm ¦ R1-4A ¦ Jeesoon
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11142 | Cable, Control, 1 CORE CU/PVC, 1.5 Sq.mm, Grey, 105°, 600/1000V , 1 x 91.4 m | 9178 | 0 | 9178 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11142 | Wire harness (grey)BVR-1.5mm² | 23560 | 0 | 23560 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11143 | Wire harness (Red)BVR-2.5mm² | 90.4 | 50 | 40.4 | 6100K024 | PO-SEP-8915-[36] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | Cable Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11143 | Wire harness (Red)BVR-2.5mm² | 40.4 | 40.4 | 0 | 6100K011B | PO-SEP-7860-[36] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11150 | Wire harness (grey)BVR-2.5mm² | 183 | 50 | 133 | 6100K024 | PO-SEP-8915-[38] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | Cable Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11150 | Wire harness (grey)BVR-2.5mm² | 133 | 6 | 127 | free_stock | PO-SEP-7289-[2] | PO | 2025-09-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | EBM - PLANT A Electrical_Cables&Wires | 994 | 10-09-2025
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11150 | Wire harness (grey)BVR-2.5mm² | 127 | 127 | 0 | free_stock | PO-SEP-8891-[4] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | EBM-BULK/ KANBAN MATERIALS/ Lugs, Terminal Ring, 1.5 Sq.mm ¦ R1-4A ¦ Jeesoon
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 2475 | 50 | 2425 | 6100K024 | PO-SEP-8915-[39] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | Cable Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 2425 | 102 | 2323 | 6100K012B | PO-SEP-7860-[43] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 2323 | 91 | 2232 | 6100K007 | PO-SEP-7860-[19] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 2232 | 88.7 | 2143.3 | 6100K017 | PO-SEP-7860-[47] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 2143.3 | 69.9 | 2073.4 | 6100K011B | PO-SEP-7860-[35] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 2073.4 | 47 | 2026.4 | 6100K011A | PO-SEP-7860-[31] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 2026.4 | 30 | 1996.4 | 6100K006 | PO-SEP-7860-[7] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 1996.4 | 22 | 1974.4 | 6100K006 | PO-SEP-7860-[3] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 1974.4 | 13 | 1961.4 | 6100K008 | PO-SEP-7860-[23] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 1961.4 | 6 | 1955.4 | 6100K006 | PO-SEP-7860-[11] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 1955.4 | 5 | 1950.4 | 6100K007 | PO-SEP-7860-[15] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 1950.4 | 5 | 1945.4 | 6100K012A | PO-SEP-7860-[39] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 1945.4 | 3 | 1942.4 | 6100K010 | PO-SEP-7860-[27] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | MV- BULK LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 1942.4 | 100 | 1842.4 | free_stock | PO-SEP-8294-[5] | PO | 2025-12-29 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 12 | Al-Fanar Company Limited | EBM-BULK CABLE ITEMS | 130 | 30-10-2025
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 1842.4 | 719 | 1123.4 | free_stock | PO-SEP-8891-[3] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | EBM-BULK/ KANBAN MATERIALS/ Lugs, Terminal Ring, 1.5 Sq.mm ¦ R1-4A ¦ Jeesoon
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Cable, Control, 1 CORE CU/PVC, 2.5 Sq.mm Yellow/Green, 105°, 600/1000V , 1 x 91.4 m | 1123.4 | 0 | 1123.4 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11151 | Grounding wire (yellow green) BVR-2.5mm² | 2508 | 0 | 2508 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11152 | Cable, Power, 1 CORE CU/PVC, 4.0 Sq.mm, Red, 105°, 600/1000V , 1 x 91.4 m | 750 | 50 | 700 | 6100K024 | PO-SEP-8915-[40] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | Cable Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11152 | Cable, Power, 1 CORE CU/PVC, 4.0 Sq.mm, Red, 105°, 600/1000V , 1 x 91.4 m | 700 | 0 | 700 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11152 | Wire harness (Red)BVR-4.0mm² | 912 | 0 | 912 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11155 | Cable, Power, 1 CORE CU/PVC, 4.0 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 721 | 2 | 719 | free_stock | PO-SEP-7591-[7] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | LV-BULK/ Z85, Z98, Z99 PLUS REMAINING PANELS/ Cable, Power, 1 CORE CU/PVC, 6.0 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 48 | 09-10-2025
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11155 | Cable, Power, 1 CORE CU/PVC, 4.0 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 719 | 0 | 719 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11155 | Wire harness (black)BVR-4.0mm² | 912 | 0 | 912 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11161 | Cable, Power, 1 CORE CU/PVC, 6.0 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 900 | 2 | 898 | 6100K024 | PO-SEP-8915-[42] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | Cable Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11161 | Cable, Power, 1 CORE CU/PVC, 6.0 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 898 | 5 | 893 | free_stock | PO-SEP-7326-[35] | PO | 2025-07-01 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Raja Procuremnet Local Purchases
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11161 | Cable, Power, 1 CORE CU/PVC, 6.0 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 893 | 10 | 883 | free_stock | PO-SEP-7944-[1] | PO | 2025-08-13 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Raja Procuremnet Local Purchases | LV BULK/ PC/ Cable, Power, 1 CORE CU/PVC, 6.0 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11161 | Cable, Power, 1 CORE CU/PVC, 6.0 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 883 | 6 | 877 | free_stock | PO-SEP-7591-[1] | PO | 2025-10-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Al-Fanar Company Limited | LV-BULK/ Z85, Z98, Z99 PLUS REMAINING PANELS/ Cable, Power, 1 CORE CU/PVC, 6.0 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 184 | 09-10-2025
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11161 | Cable, Power, 1 CORE CU/PVC, 6.0 Sq.mm, Black, 105°, 600/1000V , 1 x 91.4 m | 877 | 0 | 877 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11161 | Wire harness (black)BVR-6.0mm² | 912 | 0 | 912 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11245 | Wire, Grounding, Yellow/Green, 1.5 Sq.mm, BVR, 450/750V, 105°C | 360 | 0 | 360 | PR Required | - | PR |  | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11249 | Communication line | 453 | 453 | 0 | free_stock | PO-SEP-8044-[2] | PO | 2025-08-26 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Raja Procuremnet Local Purchases
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11251 | Cable, Power, 1 CORE CU/PVC, 6.0 Sq.mm, 600/1000V, Yellow/Green, 105°, 1 x 91.4 m | 675 | 1 | 674 | 6100K024 | PO-SEP-8915-[43] | PO | 2026-01-11 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 25 | Al-Fanar Company Limited | Cable Items
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11251 | Cable, Power, 1 CORE CU/PVC, 6.0 Sq.mm, 600/1000V, Yellow/Green, 105°, 1 x 91.4 m | 674 | 0 | 674 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | M | SEP11251 | Grounding wire (yellow green) BVR-6mm² | 684 | 0 | 684 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12003 | Lugs, Terminal Blade, 1.5 Sq.mm ¦ RF-PP16/23 ¦ Jeesoon | 15100 | 15100 | 0 | free_stock | PO-SEP-8918-[4] | PO | 2025-11-01 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12013 | Lugs, Terminal Fork, 1.5 Sq.mm ¦ S1-4A ¦ Jeesoon | 31408 | 8665 | 22743 | 6100K017 | PO-SEP-7847-[48] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12013 | Lugs, Terminal Fork, 1.5 Sq.mm ¦ S1-4A ¦ Jeesoon | 22743 | 8000 | 14743 | 6100K006 | PO-SEP-7847-[8] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12013 | Lugs, Terminal Fork, 1.5 Sq.mm ¦ S1-4A ¦ Jeesoon | 14743 | 6660 | 8083 | 6100K011A | PO-SEP-7847-[32] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12013 | Lugs, Terminal Fork, 1.5 Sq.mm ¦ S1-4A ¦ Jeesoon | 8083 | 5000 | 3083 | 6100K006 | PO-SEP-7847-[4] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12013 | Lugs, Terminal Fork, 1.5 Sq.mm ¦ S1-4A ¦ Jeesoon | 3083 | 3083 | 0 | 6100K012B | PO-SEP-7847-[44] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12017 | Lugs, Terminal Ring, 1.5 Sq.mm ¦ R1-4A ¦ Jeesoon | 3926 | 3926 | 0 | free_stock | PO-SEP-8918-[1] | PO | 2025-11-01 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12021 | Lugs, Terminal Ring, 1.5 Sq.mm ¦ R1-6A ¦ Jeesoon | 4832 | 4200 | 632 | 6100K024 | PO-SEP-8895-[2] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12021 | Lugs, Terminal Ring, 1.5 Sq.mm ¦ R1-6A ¦ Jeesoon | 632 | 0 | 632 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12045 | Lugs, Terminal PIN, 1.5 Sq.mm ¦ PT1-12A ¦ Jeesoon | 72782 | 22000 | 50782 | 6100K006 | PO-SEP-7847-[1] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12045 | Lugs, Terminal PIN, 1.5 Sq.mm ¦ PT1-12A ¦ Jeesoon | 50782 | 16400 | 34382 | 6100K011B | PO-SEP-7847-[33] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12045 | Lugs, Terminal PIN, 1.5 Sq.mm ¦ PT1-12A ¦ Jeesoon | 34382 | 12300 | 22082 | 6100K008 | PO-SEP-7847-[21] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12045 | Lugs, Terminal PIN, 1.5 Sq.mm ¦ PT1-12A ¦ Jeesoon | 22082 | 5700 | 16382 | 6100K006 | PO-SEP-7847-[9] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12045 | Lugs, Terminal PIN, 1.5 Sq.mm ¦ PT1-12A ¦ Jeesoon | 16382 | 4500 | 11882 | 6100K012A | PO-SEP-7847-[37] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12045 | Lugs, Terminal PIN, 1.5 Sq.mm ¦ PT1-12A ¦ Jeesoon | 11882 | 4200 | 7682 | 6100K007 | PO-SEP-7847-[13] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12045 | Lugs, Terminal PIN, 1.5 Sq.mm ¦ PT1-12A ¦ Jeesoon | 7682 | 3000 | 4682 | 6100K010 | PO-SEP-7847-[25] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12045 | Lugs, Terminal PIN, 1.5 Sq.mm ¦ PT1-12A ¦ Jeesoon | 4682 | 4682 | 0 | 6100K013 | PO-SEP-8053-[11] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12070 | Lugs, Terminal PIN, 2.5 Sq.mm ¦ PT2-12A ¦ Jeesoon | 10872 | 6800 | 4072 | 6100K006 | PO-SEP-7847-[6] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12070 | Lugs, Terminal PIN, 2.5 Sq.mm ¦ PT2-12A ¦ Jeesoon | 4072 | 4072 | 0 | 6100K008 | PO-SEP-7847-[22] | PO | 2025-11-20 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | LBS/OVR (Cables and Lugs)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12074 | Lugs, Terminal Fork, 2.5 Sq.mm ¦ S2-4SA ¦ Jeesoon | 12382 | 12382 | 0 | 6100K013 | PO-SEP-8053-[8] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12082 | Lugs, Terminal Ring, 2.5 Sq.mm ¦ R2-4SA ¦ Jeesoon | 1812 | 1812 | 0 | free_stock | PO-SEP-8918-[3] | PO | 2025-11-01 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12084 | Lugs, Terminal Ring, 2.5 Sq.mm ¦ R2-5SA ¦ Jeesoon | 3020 | 3000 | 20 | 6100K013 | PO-SEP-8053-[3] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12084 | Lugs, Terminal Ring, 2.5 Sq.mm ¦ R2-5SA ¦ Jeesoon | 20 | 20 | 0 | 6100K013 | PO-SEP-8053-[18] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12090 | Lugs, Terminal Ring, 2.5 Sq.mm ¦ R2-10A ¦ Jeesoon | 2416 | 2416 | 0 | 6100K013 | PO-SEP-8053-[5] | PO | 2025-11-30 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12102 | Lugs, Terminal End Sleeve, 2.5 Sq.mm, Blue Insulated ¦ PKE/E2512 ¦ Jeesoon | 25972 | 10000 | 15972 | free_stock | PO-SEP-7935-[1] | PO | 2025-08-31 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Raja Procuremnet Local Purchases | Lugs, Terminal End Sleeve, 2.5 Sq.mm, Blue Insulated ¦ PKE/E2512 ¦ Jeesoon
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12102 | Lugs, Terminal End Sleeve, 2.5 Sq.mm, Blue Insulated ¦ PKE/E2512 ¦ Jeesoon | 15972 | 15972 | 0 | free_stock | PO-SEP-8281-[1] | PO | 2025-09-17 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Raja Procuremnet Local Purchases | Lugs, Terminal End Sleeve, 2.5 Sq.mm, Blue Insulated ¦ PKE/E2512 ¦ Jeesoon
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12122 | Lugs, Terminal Ring, 4.0 Sq.mm ¦ R5-6A ¦ Jeesoon | 7248 | 4900 | 2348 | 6100K024 | PO-SEP-8895-[7] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Jeesoon Terminals Co., Ltd. | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12122 | Lugs, Terminal Ring, 4.0 Sq.mm ¦ R5-6A ¦ Jeesoon | 2348 | 0 | 2348 | PR Required | - | PR |  | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12204 | Pre insulated terminal O-type red HRV1.25-5 (Red) | 1800 | 1800 | 0 | 6100KDP02 | PO-SEP-7352-[66] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12216 | Pre insulated terminal O-type HRV1.25-8 (RED) | 1800 | 1800 | 0 | 6100KDP02 | PO-SEP-7352-[64] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP12227 | Lugs, Terminal End Sleeve, 4.0 Sq.mm, Insulated, Grey ¦ CE040010 ¦ Jeesoon | 3926 | 3926 | 0 | free_stock | PO-SEP-8583-[2] | PO | 2025-10-25 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Raja Procuremnet Local Purchases | Lugs, Terminal Ring, 2.5 Sq.mm ¦ R2-6A ¦ Jeesoon
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | KG | SEP30124 | WIREMESH(30X1X20) gauze Stainless steel | 24.5 | 24.5 | 0 | free_stock | PO-SEP-8599-[7] | PO | 2026-03-30 | Outer-enclosure |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 103 | Dalian Jinda Industry Co.,Ltd | REPLACEMENT ORDER FOR PO-SEP-8120
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP30166 | Spring Washer φ12 | 302 | 302 | 0 | 6100K024 | PO-SEP-8871-[64] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP30166 | Spring Washer φ12 | 1350 | 8 | 1342 | 6100K024 | PO-SEP-8871-[64] | PO | 2025-10-23 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dalian Jinda Industry Co.,Ltd | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP30166 | Spring Washer φ12 | 1342 | 1342 | 0 | 6100KDP02 | PO-SEP-7352-[55] | PO | 2025-11-15 | Gas-Tank |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | KGs | SEP40171 | Flat Copper 25x5mm/FRE (Bare Copper) | 2416 | 2416 | 0 | 6100K024 | PO-SEP-8845-[1] | PO | 2025-10-23 | Others |  | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Innovation Solutions Factory | 6100K024 SMRU 3L Mechanistical Componentes.
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000307 | Power Transformer, PT ¦ JDZ12A-17.5R | 150 | 0 | 150 | PR Required | - | PR |  | Others | Automated: Replaced 206024196 by RMU000000307. Automated: Replaced 206024196 by RMU000000307. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000307 | Power Transformer, PT ¦ JDZ12A-17.5R | 152 | 0 | 152 | PR Required | - | PR |  | Others | Automated: Replaced 206024196 by RMU000000307. Automated: Replaced 206024196 by RMU000000307. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000160 | Bar, Ground, 6, CCC ¦ 8DF.0815.2086 ¦ DFE | 150 | 150 | 0 | 6100KDP02 | PO-SEP-7352-[19] | PO | 2025-11-15 | Gas-Tank | Automated: Replaced 8DF.0815.2086 by RMU000000160. Automated: Replaced 8DF.0815.2086 by RMU000000160. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000162 | Front Box, Reinforcement Ribs, CCC ¦ 8DF.0815.3106 ¦ DFE | 300 | 300 | 0 | 6100KDP02 | PO-SEP-7352-[21] | PO | 2025-11-15 | Gas-Tank | Automated: Replaced 8DF.0815.3106 by RMU000000162. Automated: Replaced 8DF.0815.3106 by RMU000000162. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000163 | Plate, Rear, CCC ¦ 8DF.0815.3110 ¦ DFE | 150 | 150 | 0 | 6100KDP02 | PO-SEP-7352-[22] | PO | 2025-11-15 | Gas-Tank | Automated: Replaced 8DF.0815.3110 by RMU000000163. Automated: Replaced 8DF.0815.3110 by RMU000000163. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000164 | Mother Row, Main, CCC ¦ 8DF.0815.3131 ¦ DFE | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[23] | PO | 2025-11-15 | Gas-Tank | Automated: Replaced 8DF.0815.3131 by RMU000000164. Automated: Replaced 8DF.0815.3131 by RMU000000164. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000166 | Plate, Front, CCC ¦ 8DF.0818.0070 ¦ DFE | 150 | 150 | 0 | 6100KDP02 | PO-SEP-7352-[32] | PO | 2025-11-15 | Gas-Tank | Automated: Replaced 8DF.0818.0070 by RMU000000166. Automated: Replaced 8DF.0818.0070 by RMU000000166. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000167 | Plate, Top, CCC ¦ 8DF.0818.0071 ¦ DFE | 150 | 150 | 0 | 6100KDP02 | PO-SEP-7352-[33] | PO | 2025-11-15 | Gas-Tank | Automated: Replaced 8DF.0818.0071 by RMU000000167. Automated: Replaced 8DF.0818.0071 by RMU000000167. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000165 | Soft Connection, C Unit Side ¦ 8DF.0816.0167 ¦ DFE | 450 | 450 | 0 | 6100KDP02 | PO-SEP-7352-[25] | PO | 2025-11-15 | Gas-Tank | Automated: Replaced 8DF.0818.0081 by RMU000000165. Automated: Replaced 8DF.0818.0081 by RMU000000165. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000168 | Rib, Front Reinforcing, CCC ¦ 8DF.0818.0103 ¦ DFE | 150 | 150 | 0 | 6100KDP02 | PO-SEP-7352-[34] | PO | 2025-11-15 | Gas-Tank | Automated: Replaced 8DF.0818.0103 by RMU000000168. Automated: Replaced 8DF.0818.0103 by RMU000000168. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000169 | Bracket, PT Installation ¦ 8DF.0818.1069 ¦ DFE | 150 | 150 | 0 | 6100KDP02 | PO-SEP-7352-[35] | PO | 2025-11-15 | Gas-Tank | Automated: Replaced 8DF.0818.1069 by RMU000000169. Automated: Replaced 8DF.0818.1069 by RMU000000169. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | Dongfang Electronics International Engineering Co. Ltd | 6100KDP02//3L SRMU Loose Gas Tank (QTY 155)
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1034A | Lower sealing plate | 150 | 0 | 150 | PR Required | - | PR |  | Others | Automated: Replaced 8DF.0818.1346A by 8DF.0818.1034A. Automated: Replaced 8DF.0818.1346A by 8DF.0818.1034A. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | 8DF.0818.1034A | Lower sealing plate | 152 | 0 | 152 | PR Required | - | PR |  | Others | Automated: Replaced 8DF.0818.1346A by 8DF.0818.1034A. Automated: Replaced 8DF.0818.1346A by 8DF.0818.1034A. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | HOSAS55415 | HOSE ASSEMBLY~TYPE: FLEXIBLE~CONNECTION TYPE: MH14~CONNECTION TYPE2: MH14 | 300 | 0 | 300 | PR Required | - | PR |  | Others | Automated: Replaced DF250714001 by HOSAS55415. Automated: Replaced DF250714001 by HOSAS55415. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | HOSAS55415 | HOSE ASSEMBLY~TYPE: FLEXIBLE~CONNECTION TYPE: MH14~CONNECTION TYPE2: MH14 | 304 | 0 | 304 | PR Required | - | PR |  | Others | Automated: Replaced DF250714001 by HOSAS55415. Automated: Replaced DF250714001 by HOSAS55415. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF240510052 | RTU (DF1725IED) | 150 | 0 | 150 | PR Required | - | PR |  | Others | Automated: Replaced DF250723003 by DF240510052. Automated: Replaced DF250723003 by DF240510052. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | DF240510052 | RTU (DF1725IED) | 152 | 0 | 152 | PR Required | - | PR |  | Others | Automated: Replaced DF250723003 by DF240510052. Automated: Replaced DF250723003 by DF240510052. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000191 | Module, Control ¦ ISCU-01E-3L | 450 | 0 | 450 | PR Required | - | PR |  | Others | Automated: Replaced RMU000000255 by RMU000000191. Automated: Replaced RMU000000255 by RMU000000191. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | RMU000000191 | Module, Control ¦ ISCU-01E-3L | 456 | 0 | 456 | PR Required | - | PR |  | Others | Automated: Replaced RMU000000255 by RMU000000191. Automated: Replaced RMU000000255 by RMU000000191. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP30183 | Nut, G.I, M6 | 600 | 600 | 0 | free_stock | PO-SEP-7717-[39] | PO | 2025-10-20 | Outer-enclosure | Automated: Replaced SEP10851 by SEP30183. Automated: Replaced SEP10851 by SEP30183. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | ALAM AL NIMA TRADING EST | LV BULK MATERIALS
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | PC | SEP30183 | Nut, G.I, M6 | 800 | 800 | 0 | free_stock | PO-SEP-7717-[39] | PO | 2025-10-20 | Outer-enclosure | Automated: Replaced SEP10851 by SEP30183. Automated: Replaced SEP10851 by SEP30183. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | ALAM AL NIMA TRADING EST | LV BULK MATERIALS
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP30183 | Nut, G.I, M6 | 6300 | 6300 | 0 | free_stock | PO-SEP-7717-[39] | PO | 2025-10-20 | Others | Automated: Replaced SEP10851 by SEP30183. Automated: Replaced SEP10851 by SEP30183. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | ALAM AL NIMA TRADING EST | LV BULK MATERIALS
6100K024 | 3L - 908321124 : SWGR,SMART RMU OD,3LBS,13.8 KV,400 | sRMU | Pcs | SEP30183 | Nut, G.I, M6 | 6384 | 6384 | 0 | free_stock | PO-SEP-7717-[39] | PO | 2025-10-20 | Others | Automated: Replaced SEP10851 by SEP30183. Automated: Replaced SEP10851 by SEP30183. | JB01-Jubail Industrial Warehouse | 2025-12-31 | 2025-12-17 | 0 | ALAM AL NIMA TRADING EST | LV BULK MATERIALS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-6812-[48] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 2079 | 1200 | 879 | 6100KDP01 | PO-SEP-6812-[40] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 879 | 8 | 871 | 606PD013 | PO-SEP-8168-[216] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 871 | 4 | 867 | 606PD013 | PO-SEP-8834-[24] | PO | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Dalian Jinda Industry Co.,Ltd
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 867 | 867 | 0 | 6100KDP01 | PO-SEP-8378-[227] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 03366 | STEEL RIVETS T22205/4.8 TS | 148 | 148 | 0 | 6100KDP01 | PO-SEP-8378-[228] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 30 | 30 | 0 | 6100KDP01 | PO-SEP-6812-[56] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08017 | TOMMY HEAD SCREW ACC T21010/M4x22 | 36 | 26 | 10 | 6100KDP01 | PO-SEP-6812-[32] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08017 | TOMMY HEAD SCREW ACC T21010/M4x22 | 10 | 10 | 0 | 6100K023 | PO-SEP-8647-[14] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Mattssons Fasteners AB
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08448 | SQUARE FASTENING NUT TS ACC T21597/5 | 60 | 28 | 32 | 6100KDP01 | PO-SEP-6812-[42] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08448 | SQUARE FASTENING NUT TS ACC T21597/5 | 32 | 32 | 0 | 6100KDP01 | PO-SEP-8378-[338] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8629-[18] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | FLY METALTECH TRADING CO.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08856 | WASHER STEEL T22100/ 6.4 | 60 | 28 | 32 | 6100KDP01 | PO-SEP-6812-[16] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 08856 | WASHER STEEL T22100/ 6.4 | 32 | 32 | 0 | 6100KDP01 | PO-SEP-8378-[280] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 09021 | SELF-LOCKING HEX. NUT,T21192/M10 (LOCAL) | 120 | 120 | 0 | 6100KDP01 | PO-SEP-8680-[18] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | ALAM AL NIMA TRADING EST
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 09601 | WASHER, FLAT ACC T22000/3.2X7 | 84 | 36 | 48 | 6100KDP01 | PO-SEP-6812-[8] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 09601 | WASHER, FLAT ACC T22000/3.2X7 | 48 | 48 | 0 | 6100KDP01 | PO-SEP-8378-[275] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 09947 | SPRING WASHER ACC T22104/6 | 10 | 10 | 0 | 6100KDP01 | PO-SEP-8378-[270] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1000057457 | WASHER CU AL M10 | 15 | 6 | 9 | 6100KDP01 | PO-SEP-6812-[30] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1000057457 | WASHER CU AL M10 | 9 | 9 | 0 | 6100K023 | PO-SEP-8385-[290] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 12989 | COUNTERSUNK STEEL SCREW T21065/M8X30 | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8646-[1] | PO | 2025-10-20 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 13.8-VT-ZS1-3WDG-25VA | Incomer, BRM and BEM VTs ¦ 13.8-VT-ZS1-3WDG-25VA ¦ RITZ | 18 | 18 | 0 | 6100K025 | PO-SEP-8756-[11] | PO | 2025-10-23 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16301 | RIVET T22213/4 | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8645-[4] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Saeed Aziz Alsomali Trading Est
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8379-[52] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 33 | 33 | 0 | 6100KDP01 | PO-SEP-8379-[43] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611400R1005 | PILOT LIGHT#ML1-100W | 16 | 16 | 0 | 6100KDP01 | PO-SEP-8041-[68] | PO | 2025-12-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611605R1100 | HOLDER#MCBH-00 | 13 | 13 | 0 | 6100KDP01 | PO-SEP-8041-[69] | PO | 2025-12-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611621R1055 | LAMP BLOCK#MLBL-05W | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8041-[73] | PO | 2025-12-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8041-[74] | PO | 2025-12-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8041-[75] | PO | 2025-12-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SNA206394R0200 | *** USE MV-1SNA206394R0200 *** | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8386-[29] | PO | 2025-11-10 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SNK900654R0000 | SC-JB8-4 Short circuit bridges - Yellow | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8386-[17] | PO | 2025-11-10 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR000490F0001 | SHEET PROFILE | 20 | 16 | 4 | 6100KDP01 | PO-SEP-8402-[66] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR000490F0001 | SHEET PROFILE | 4 | 4 | 0 | 6100K023 | PO-SEP-8402-[17] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR000491F0001 | SHEET PROFILE | 20 | 16 | 4 | 6100KDP01 | PO-SEP-8402-[61] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR000491F0001 | SHEET PROFILE | 4 | 4 | 0 | 6100K023 | PO-SEP-8402-[32] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR002047G0001 | COMPLETE ASSEMBLY KIT FOR DIRAK LOCKUP | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8446-[3] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Ningbo Shengjiu Technology CO., LTD. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VCR002428G0001 | LOCKUP ROD ASSEMBLY | 7 | 7 | 0 | 6100KDP01 | PO-SEP-8387-[24] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7600732P0101 | SPACER TUBE | 18 | 18 | 0 | 6100K023 | PO-SEP-8403-[2] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7605506P0101 | ABB LOGO UNIGEAR ZS1 | 5 | 4 | 1 | 6100KDP01 | PO-SEP-8379-[53] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7605506P0101 | ABB LOGO UNIGEAR ZS1 | 1 | 1 | 0 | 6100K023 | PO-SEP-8379-[55] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7605506P0102 | ABB LOGO UNIGEAR ZS1 | 46 | 38 | 8 | 6100K023 | PO-SEP-8379-[24] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7605506P0102 | ABB LOGO UNIGEAR ZS1 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8379-[45] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7607280R0101 | HINGE WITHOUT FASTENERS | 176 | 87 | 89 | 6100KDP01 | PO-SEP-6832-[3] | PO | 2025-08-20 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | (Mechanical Parts) PP-12
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7607280R0101 | HINGE WITHOUT FASTENERS | 89 | 89 | 0 | 6100KDP01 | PO-SEP-8397-[4] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7623184R0101 | COMPLETE HANDLE | 49 | 46 | 3 | 6100KDP01 | PO-SEP-5621-[1] | PO | 2025-11-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | SHAMS ALRIYADH INDUSTRIAL FACTORY | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "C&D" Material (Supplier-SHAMS ALRIYADH INDUSTRIAL FACTORY)
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1VL7623184R0101 | COMPLETE HANDLE | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8552-[1] | PO | 2025-11-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | SHAMS ALRIYADH INDUSTRIAL FACTORY | AL Azyziyah DMM Project under Dummy 6100KDP01 2nd Lot of Mechanical Componentes for SEC a/c Dammam Aziziya Fast track project 13.8kV MV SWGR.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB000003-FDX | MIMIC , OUTGOING WITH EARTHING | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8379-[48] | PO | 2025-10-30 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 12 | 12 | 0 | 6100K023 | PO-SEP-8629-[13] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | FLY METALTECH TRADING CO.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010025P0101 | HINGE COMPONENT #2 | 48 | 48 | 0 | 6100K023 | PO-SEP-8403-[3] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010029P0122 | CVI DIVIDER, 12-17.5kV, Set 1B (11425) | 7 | 7 | 0 | 6100KDP01 | PO-SEP-8445-[2] | PO | 2025-12-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Ritz Instrument Transformers GMBH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010037P0101 | STRENGHTENING SHEET 13.8KV/24KV | 6 | 6 | 0 | free_stock | PO-SEP-6816-[8] | PO | 2025-09-18 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010037P0102 | STRENGTHENING SHEET FOR 40KA PANEL | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8402-[64] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010075P0101 | PARTITION PLATE UPPER CT W800 SS STL | 10 | 10 | 0 | 6100KDP01 | PO-SEP-8402-[58] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010076P0101 | COVER FOR PARTITION PLATE | 10 | 10 | 0 | 6100KDP01 | PO-SEP-8402-[56] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010138P0102 | PROTECTIVE COVER W800 | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8396-[31] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010145P0102 | DOOR STOPPER ROD 8 MM DIA. | 9 | 9 | 0 | 6100KDP01 | PO-SEP-8523-[7] | PO | 2025-10-23 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0101 | HEX. BOLT M10X20 POLYAMIDE | 36 | 36 | 0 | 6100KDP01 | PO-SEP-8378-[208] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010241P0103 | HEX. BOLT M10X30 POLYAMIDE | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8378-[160] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8379-[40] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010301P0111 | Label printed in Trafolite 200 x 100 | 9 | 9 | 0 | 6100KDP01 | PO-SEP-8379-[39] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8379-[29] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010402R0103 | LABELS FOR SHUTTERS BUSBAR-CABLE -FEEDER | 13 | 13 | 0 | 6100KDP01 | PO-SEP-8379-[37] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010489P0101 | FLAT BRAIDED, 16SQMM. TIN(13.8kV)6mmdia | 54 | 54 | 0 | 6100KDP01 | PO-SEP-8378-[211] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB010489P0102 | FLAT BRAIDED CONNECTOR, 16 SQMM. TINNED | 8 | 8 | 0 | 6100K023 | PO-SEP-8403-[4] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 24 | 24 | 0 | 6100K025 | PO-SEP-8773-[1] | PO | 2025-10-23 | A |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB52333VW6CN00 | VD4/P 171240-p210-125VDC (1VCD400222) | 1 | 1 | 0 | 6100K025 | PO-SEP-8773-[3] | PO | 2025-10-23 | A |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5320XHI1XN00 | POWER QUALITY ANALYZER, ISKRA iMC784 | 3 | 3 | 0 | 6100K025 | PO-SEP-8547-[2] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Enerziff Solutions FZCO | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXCX0100 | BREAKER CONTROL SWITCH (Comelectric)Breaker Control Switch3-Pole, 3-Position & spring returnDim: 51 X 51 mm Padlockable handle:Colour : Red YellowFront plate:Text Engrave : OPEN- NORMAL-CLOSELettering plate:Text Engrave : BREAKER CONTROL SWITCH Ordering Code: R601 SAM303 011 01-L078+48-30309T133 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8398-[10] | PO | 2025-12-31 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXCX0210 | CBMODE6P,4Pos.Off-Emer-Local-Rem-Padlock(COMELECTRIC), Breaker Mode Selector Switch 6-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH COMELETRIC Part No. R601 SA412 067 27-L071+48-40513T134 SAP Part no: 1YAB5331XXCX0210 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8398-[11] | PO | 2025-12-31 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXCX0300 | SPACE HEATER SEL. SWITCH ( COMELECTRIC )R601 SA302 112-W051+48-31090T124 20A, 3Positions without internal links 2pole,3position Engraving (OFF/Auto/Manual) OFF-zero contacts AUTO-2 contacts MANUAL-2contacts TOP PLATE (SPACE HEATER) Single hole mounting FT6 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8398-[13] | PO | 2025-12-31 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC )R601 SAM201 071-W051+48-20547T123 20A SPRING RETAIN WITHOUT INTERNAL LINKS 2 POSITION,1POLE Engraving (OFF-TEST) TOP PLATE Engraving (LAMP TEST) | 1 | 1 | 0 | 6100K020 | PO-SEP-8785-[17] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Aman Engineering FZC
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5331XXKX0700 | Auto Re-close IN-OUT Selector Switch(COMELECTRIC),"Auto Re-close IN-OUT Selector Switch 4-Pole, 2-Positions Dim: 51 X 51 mm Padlockable handle: Colour : Black Front plate: Text Engrave : IN-OUT Lettering plate Text Engrave : A/R IN-OUT SWITCH" CA10-A723-SA0030-E 1YAB5331XXKX0700 | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8398-[9] | PO | 2025-12-31 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5332XXAXB000 | PB Black 1NO+1NC-22 dia-1SFA611100R4076 | 40 | 40 | 0 | 6100KDP01 | PO-SEP-8041-[76] | PO | 2025-12-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXAA2G00 | MCB S 202-K6 6A AC -2P - 2CDS252001R0377 | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8041-[78] | PO | 2025-12-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXAB2G00 | MCB 6A DC 2P S202M-K6UC -2CDS272061R0377 | 14 | 14 | 0 | 6100KDP01 | PO-SEP-8041-[88] | PO | 2025-12-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5336XXACG000 | Aux contact 2NC, S2C-HO2L-for MCB Order # 2CDS200936R0003 | 9 | 9 | 0 | 6100KDP01 | PO-SEP-8041-[89] | PO | 2025-12-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XAJXXN00 | RF-4R_125Vdc_4 C/O_LED | 6 | 6 | 0 | 6100K023 | PO-SEP-8407-[1] | PO | 2025-09-18 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Innovative Systems Co. Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XAJXXN01 | BJ-8RP_Bistable_125Vdc_8 C/O | 2 | 2 | 0 | 6100K023 | PO-SEP-8407-[2] | PO | 2025-09-18 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Innovative Systems Co. Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XJAXXN00 | THREE PHASE FUSE SUPERVISION RELAY Type : RXBA4 (ABB) ORDER NO. : RK 428 004-AA CONTACTS : 2 CHANGE OVER SELF RESET | 5 | 4 | 1 | 6100K023 | PO-SEP-8751-[34] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XJAXXN00 | THREE PHASE FUSE SUPERVISION RELAY Type : RXBA4 (ABB) ORDER NO. : RK 428 004-AA CONTACTS : 2 CHANGE OVER SELF RESET | 1 | 1 | 0 | 6100K021 | PO-SEP-8751-[2] | PO | 2025-12-31 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 250 | 250 | 0 | 6100K023 | PO-SEP-8417-[2] | PO | 2025-11-30 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Phoenix Contact Trading LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355AMC0001 | Feed-through terminal block,ZT 4/4AN/2 .Base Terminal Plug AC-DC-4mm 1848350000 | 10 | 10 | 0 | 6100KDP01 | PO-SEP-8518-[1] | PO | 2025-12-31 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355DXC0000 | 460660001 DEK 5 FSZ 1-10 Z-Terminal 1-10 | 600 | 600 | 0 | 6100KDP01 | PO-SEP-8518-[7] | PO | 2025-12-31 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 129 | 129 | 0 | 6100KDP01 | PO-SEP-8378-[271] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 28627 | Rivet NUT ACC T21098/M6 (countersunk) | 155 | 91 | 64 | 6100KDP01 | PO-SEP-6812-[54] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 28627 | Rivet NUT ACC T21098/M6 (countersunk) | 64 | 64 | 0 | 6100KDP01 | PO-SEP-8645-[3] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Saeed Aziz Alsomali Trading Est
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 2CSM258163R0721 | MV MATERIAL MV-AC-SOCKET-WOA 1YAB53305XAX0000 M1363-L | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8388-[28] | PO | 2025-10-30 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 4CE7000583P0101 | PIN | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8680-[5] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | ALAM AL NIMA TRADING EST
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 500673075 | PIN T22681/8X54,5-5 | 40 | 40 | 0 | 6100KDP01 | PO-SEP-8387-[34] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 593503001 | ROLLER | 10 | 10 | 0 | 6100KDP01 | PO-SEP-8387-[35] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 593509/001 | COMPRESSION SPRING | 17 | 17 | 0 | 6100KDP01 | PO-SEP-8483-[4] | PO | 2025-12-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AB KOMPONENTY s.r.o. | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 9ABA450060P0004 | NUT_ISO7040_M6-8/A3K | 14 | 14 | 0 | 6100KDP01 | PO-SEP-8680-[6] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | ALAM AL NIMA TRADING EST
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 9ABA450060P0005 | NUT_ISO7040_M8-8/A3K | 4 | 4 | 0 | 6100KDP01 | PO-SEP-6812-[62] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-1865-04 | BLACK TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 340 | 340 | 0 | 6100K023 | PO-SEP-8404-[1] | PO | 2025-09-18 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-1865-05 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 450 | 0 | 450 | PR Required | - | PR |  | LV |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-1865-13 | BLACK TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 340 | 340 | 0 | 6100K023 | PO-SEP-8404-[2] | PO | 2025-09-18 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 140 | 140 | 0 | 6100KDP01 | PO-SEP-6812-[138] | PO | 2025-08-31 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE2632-2000-33 | Spring for Door Combiflex | 0.04 | 0.04 | 0 | 6100KDP01 | PO-SEP-8388-[22] | PO | 2025-10-30 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AE5295-2000-08 | POST INSULATOR h=50mm (2035679) | 9 | 9 | 0 | 6100KDP01 | PO-SEP-8389-[6] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 47 | 47 | 0 | 6100KDP01 | PO-SEP-8379-[44] | PO | 2025-10-30 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | CDX7005632R1A | EARTHING CONTACT COMPLETE | 16 | 16 | 0 | 6100KDP01 | PO-SEP-8387-[27] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | CDXN010061R1103 | HANDLE COMPLETE | 7 | 7 | 0 | 6100KDP01 | PO-SEP-8387-[31] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DM0000000058 | Relay, Auxiliary, 2 Coils, Self Reset Contacts, Hand Reset Flag, 110-125V, DC, 2NO, 1NC, Coil ¦ RXSF1 RK 271 007-AN | 8 | 8 | 0 | 6100K019 | PO-SEP-8305-[1] | PO | 2025-12-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Hitachi Energy Ltd | PP-12 additional relays
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 16 | 16 | 0 | 6100KDP01 | PO-SEP-8378-[212] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-6812-[120] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 21 | 15 | 6 | 6100KDP01 | PO-SEP-6812-[124] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8378-[169] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2017-659 | BOLT HEX HEAD H D M20X45 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8680-[7] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | ALAM AL NIMA TRADING EST
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2452-293 | SCREW CROSS REC.HEAD M4X16 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-6812-[52] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 343 | 76 | 267 | 606PD013 | PO-SEP-6812-[148] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 267 | 21 | 246 | 606PD013 | PO-SEP-8924-[4] | PO | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | ALAM AL NIMA TRADING EST
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 246 | 246 | 0 | 6100KDP01 | PO-SEP-8680-[9] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | ALAM AL NIMA TRADING EST
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 24 | 24 | 0 | 6100KDP01 | PO-SEP-6812-[50] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-371 | BOLT SOCKET CAP M6X20 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8378-[246] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-372 | BOLT SOCKET CAP M6X25 | 1 | 1 | 0 | 6100KDP01 | PO-SEP-6812-[94] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 24 | 24 | 0 | 6100KDP01 | PO-SEP-8378-[252] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 428 | 428 | 0 | 6100KDP01 | PO-SEP-8378-[164] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 271 | 238 | 33 | 6100KDP01 | PO-SEP-6812-[104] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 33 | 33 | 0 | 6100KDP01 | PO-SEP-8378-[178] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-457 | BOLT SOCKET CAP M8X35 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-6812-[92] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 12 | 12 | 0 | 6100KDP01 | PO-SEP-6812-[102] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8378-[214] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 42 | 42 | 0 | 6100KDP01 | PO-SEP-8378-[215] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 90 | 90 | 0 | 6100KDP01 | PO-SEP-6812-[100] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 86 | 86 | 0 | 6100KDP01 | PO-SEP-8378-[173] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-531 | BOLT SOCKET CAP M12X16 (C.H.) | 11 | 11 | 0 | 6100KDP01 | PO-SEP-8378-[251] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 348 | 155 | 193 | 6100KDP01 | PO-SEP-6812-[112] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 193 | 193 | 0 | 6100KDP01 | PO-SEP-8378-[174] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 48 | 48 | 0 | 6100KDP01 | PO-SEP-8378-[210] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 132 | 90 | 42 | 6100KDP01 | PO-SEP-6812-[110] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 42 | 42 | 0 | 6100KDP01 | PO-SEP-8378-[157] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2519-628 | BOLT SOCKET CAP HEAD M16X40 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8378-[243] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 80 | 2 | 78 | 606PD013 | PO-SEP-8924-[5] | PO | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | ALAM AL NIMA TRADING EST
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 78 | 78 | 0 | 6100KDP01 | PO-SEP-8680-[10] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | ALAM AL NIMA TRADING EST
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 61 | 61 | 0 | 6100KDP01 | PO-SEP-8680-[3] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | ALAM AL NIMA TRADING EST
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2151 2062-136 | WASHER FLAT BRIR 4.3X8X0.8 | 96 | 96 | 0 | 6100KDP01 | PO-SEP-8680-[20] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | ALAM AL NIMA TRADING EST
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 147 | 147 | 0 | 6100KDP01 | PO-SEP-6812-[26] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 24 | 24 | 0 | free_stock | PO-SEP-8044-[11] | PO | 2025-07-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Raja Procuremnet Local Purchases
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 48 | 48 | 0 | 6100KDP01 | PO-SEP-6812-[24] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 415 | 333 | 82 | 6100KDP01 | PO-SEP-6812-[12] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 82 | 82 | 0 | 6100KDP01 | PO-SEP-8378-[170] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 240 | 240 | 0 | 6100KDP01 | PO-SEP-8378-[257] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 45 | 45 | 0 | 6100KDP01 | PO-SEP-6812-[10] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 414 | 414 | 0 | 606PD013 | PO-SEP-6812-[142] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 2400 | 2400 | 0 | 6100KDP01 | PO-SEP-8378-[234] | PO | 2025-11-17 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 6 | 6 | 0 | 6100K025 | PO-SEP-8757-[1] | PO | 2025-12-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Shanghai Feili Xuncheng Electrical Technology Co.,Ltd | Snap action Switch
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0007249P0100 | GREASE ISOPLEX TOPAS,NB52,1kg | 0.109 | 0.109 | 0 | 6100KDP01 | PO-SEP-8908-[4] | PO | 2025-10-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Quality Bearing Online Limited
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0068009P0100 | BUSHING D8/3 PVC | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8755-[2] | PO | 2025-12-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | MESAN KİLİT A.Ş.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0305871P0100 | HEX BOLT M8X16 DIN 933-POLY | 110 | 43 | 67 | 6100KDP01 | PO-SEP-6812-[84] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0305871P0100 | HEX BOLT M8X16 DIN 933-POLY | 67 | 67 | 0 | 6100KDP01 | PO-SEP-8378-[290] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 91 | 37 | 54 | 6100KDP01 | PO-SEP-6812-[86] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 54 | 17 | 37 | 606PD013 | PO-SEP-6812-[146] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 37 | 7 | 30 | 606PD013 | PO-SEP-8834-[19] | PO | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Dalian Jinda Industry Co.,Ltd
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 30 | 30 | 0 | 6100KDP01 | PO-SEP-8378-[198] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0316044P0100 | HEAD SCREW M8X50, DIN 603-4.3 | 26 | 26 | 0 | 6100KDP01 | PO-SEP-8629-[7] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | FLY METALTECH TRADING CO.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 12 | 12 | 0 | 6100KDP01 | PO-SEP-6812-[46] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0336985P0100 | TAPPING SCREW M6X16/6KTHEAD | 9 | 9 | 0 | 6100KDP01 | PO-SEP-8378-[177] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0367309P0100 | HEX. NUT M6, DIN 985-6 ( LOCK NUT ) | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8378-[291] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 236 | 236 | 0 | 6100KDP01 | PO-SEP-8378-[168] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 540 | 108 | 432 | 6100KDP01 | PO-SEP-6812-[76] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 432 | 280 | 152 | 6100KDP01 | PO-SEP-8168-[200] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 152 | 152 | 0 | 6100KDP01 | PO-SEP-8378-[255] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0402911P0100 | WASHER POLYAMID, A8.4, DIN 125 | 166 | 166 | 0 | 6100KDP01 | PO-SEP-8378-[172] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0402912P0100 | WASHER POLYAMID, A10.5, DIN 125 | 72 | 48 | 24 | 6100KDP01 | PO-SEP-6812-[20] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0402912P0100 | WASHER POLYAMID, A10.5, DIN 125 | 24 | 24 | 0 | 6100KDP01 | PO-SEP-8378-[293] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0410004P0100 | SPRING RING A3, DIN 127-FST | 6 | 6 | 0 | 6100K023 | PO-SEP-8385-[231] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0413160P0100 | RETAINING WASHER VS5 | 14 | 14 | 0 | 6100K023 | PO-SEP-8385-[300] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418203P0100 | WASHER,RETAINING 6, WN418-FST | 48 | 48 | 0 | 6100KDP01 | PO-SEP-8378-[292] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418204P0100 | WASHER RETAINING 8/WN 418-FST | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8680-[14] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | ALAM AL NIMA TRADING EST
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418205P0100 | WASHER RETAINING 10, WN418-FST | 52 | 20 | 32 | 6100KDP01 | PO-SEP-6812-[18] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0418205P0100 | WASHER RETAINING 10, WN418-FST | 32 | 32 | 0 | 6100KDP01 | PO-SEP-8378-[197] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0457035P0100 | BLIND RIVET 5X10 AL | 58 | 58 | 0 | 6100KDP01 | PO-SEP-8378-[331] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0457038P0100 | BLIND RIVET 5X16, CIECO, WN457-ALU | 32 | 24 | 8 | 6100KDP01 | PO-SEP-6812-[132] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0457038P0100 | BLIND RIVET 5X16, CIECO, WN457-ALU | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8378-[334] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0909123P0100 | PLUG-IN CONNECTION - 645060000 | 7 | 3 | 4 | free_stock | PR-SEP-0024114-[185] | PR |  | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0909123P0100 | PLUG-IN CONNECTION - 645060000 | 4 | 0 | 4 | PR Required | - | PR |  | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0909124P0100 | BUSH STV2/10 ORDER.NO. 0645160000 | 10 | 8 | 2 | free_stock | PR-SEP-0024114-[186] | PR |  | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0909124P0100 | BUSH STV2/10 ORDER.NO. 0645160000 | 2 | 0 | 2 | PR Required | - | PR |  | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 53 | 53 | 0 | 6100KDP01 | PO-SEP-8409-[4] | PO | 2025-12-15 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990162P0102 | PANEL HEATER 240V,100W-Boxin-5MetCable | 7 | 7 | 0 | 6100KDP01 | PO-SEP-8409-[6] | PO | 2025-12-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990403P0100 | VENTILATOR QK08A-2EM.50.CH WITH CAPACITO | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8748-[7] | PO | 2025-12-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | ZIEHL ABEGG Middle East FZE | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0990404P0100 | RADIAL FLOW FAN QK08A-2EM.35.CF | 4 | 4 | 0 | 6100K021 | PO-SEP-8748-[2] | PO | 2025-12-31 | B |  | - | 2026-02-15 | 2026-02-01 | 0 | ZIEHL ABEGG Middle East FZE | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0996027P0100 | PROTECTION CAP M10NR.610 | 84 | 84 | 0 | 6100KDP01 | PO-SEP-8629-[2] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | FLY METALTECH TRADING CO.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0998134P0100 | SEALING RUBBER | 211.08 | 150 | 61.08 | 6100KDP01 | PO-SEP-6997-[1] | PO | 2025-11-20 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Suzhou Dirak Co. Ltd | Sealing rubber 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0998134P0100 | SEALING RUBBER | 61.08 | 61.08 | 0 | 6100KDP01 | PO-SEP-8394-[2] | PO | 2025-12-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Suzhou Dirak Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE0998162P0100 | REDUCING RING PVC | 152 | 152 | 0 | 6100K023 | PO-SEP-8385-[10] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4395592P0100 | WASHER FLAT 8 X 11 X 0.5 MM | 54 | 54 | 0 | 6100KDP01 | PO-SEP-8378-[258] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4530250P0100 | DESIGNATION LABEL L1 (RED) | 7 | 7 | 0 | 6100KDP01 | PO-SEP-8379-[31] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4530251P0100 | DESIGNATION LABEL L2 (YELLOW) | 7 | 7 | 0 | 6100KDP01 | PO-SEP-8379-[32] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4530252P0100 | DESIGNATION LABEL L3 (BLUE) | 7 | 7 | 0 | 6100KDP01 | PO-SEP-8379-[33] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8379-[36] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000496P0102 | TORSION SPRING | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8387-[20] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000497R0101 | BEARING HOUSING COMPLETE | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8387-[30] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000507P0101 | ACTUATING LEVEL | 48 | 29 | 19 | free_stock | PO-SEP-6816-[1] | PO | 2025-09-18 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000507P0101 | ACTUATING LEVEL | 19 | 19 | 0 | 6100KDP01 | PO-SEP-8509-[10] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000508P0101 | GROOVED PIN | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8523-[11] | PO | 2025-10-23 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000525P0101 | WASHER,STOP | 14 | 6 | 8 | 6100KDP01 | PO-SEP-6812-[1] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000525P0101 | WASHER,STOP | 8 | 8 | 0 | 6100K023 | PO-SEP-8385-[301] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000552P0101 | STOP WASHER | 28 | 12 | 16 | 6100KDP01 | PO-SEP-6812-[38] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000552P0101 | STOP WASHER | 16 | 16 | 0 | 6100KDP01 | PO-SEP-8378-[241] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000654P0102 | Slide | 48 | 29 | 19 | free_stock | PO-SEP-6816-[2] | PO | 2025-09-18 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000654P0102 | Slide | 19 | 19 | 0 | 6100KDP01 | PO-SEP-8509-[5] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000663R0101 | BEVEL GEAR DRIVE FOR EK6 ZS1 | 14 | 6 | 8 | 6100KDP01 | PO-SEP-6832-[1] | PO | 2025-08-20 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | (Mechanical Parts) PP-12
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7000663R0101 | BEVEL GEAR DRIVE FOR EK6 ZS1 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8397-[5] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7001732R0106 | EARTHING SWITCH: EK6-ZS1-1710-210 | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8382-[4] | PO | 2026-01-22 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | Earthing Switch/6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7003008P0101 | RING | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8387-[21] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7003579P0101 | TENSION SPRING 6.5/.9/30/16 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8396-[38] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7003694P0102 | CARRIER | 14 | 6 | 8 | 6100KDP01 | PO-SEP-6832-[2] | PO | 2025-08-20 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | (Mechanical Parts) PP-12
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7003694P0102 | CARRIER | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8397-[6] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7109399R0101 | AUXILIARY SWITCH 5NO | 16 | 16 | 0 | 6100KDP01 | PO-SEP-8409-[7] | PO | 2025-12-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7192037R0100 | INSULATOR SGB 24N A1 POT 24kV 2040742 | 15 | 15 | 0 | 6100KDP01 | PO-SEP-8389-[5] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7208367P0100 | DESIGNATION LABEL | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8379-[34] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7208368P0100 | DESIGNATION LABEL | 49 | 40 | 9 | 6100K023 | PO-SEP-8379-[10] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE7208368P0100 | DESIGNATION LABEL | 9 | 9 | 0 | 6100KDP01 | PO-SEP-8379-[35] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8000336P0101 | K- INTERMEDIATE PIECE 40x6x9(ZINC CHR.) | 14 | 14 | 0 | 6100KDP01 | PO-SEP-8402-[48] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8000801P0101P | CONTACT PIN, RD.79MM L=107MM | 6 | 6 | 0 | 6100K023 | PO-SEP-8385-[118] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8000881P0102 | INTERMEDITE PLATE 80x15x125 CU SILVERPLA | 6 | 6 | 0 | 6100K023 | PO-SEP-8385-[72] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8002757P0107 | COVER | 6 | 6 | 0 | 6100K023 | PO-SEP-8385-[73] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8002866R0102P | PADLOCK ES - NORMAL | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8396-[37] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003638P0103P | INTER LOCKING AGLE LEFT | 7 | 7 | 0 | 6100KDP01 | PO-SEP-8396-[33] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003638P0104P | INTERLOCKING ANGLE RIGHT | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8396-[42] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003671P0102 | SPECIAL SCREW M12 X 50/20 | 2 | 2 | 0 | 6100K023 | PO-SEP-8403-[13] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003671P0116 | SPCEIAL SCREW M12X34/45 | 42 | 42 | 0 | 6100KDP01 | PO-SEP-8523-[9] | PO | 2025-10-23 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003824P0101 | K- SUPPORT PLATE YELLOW CHROMATION. | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8402-[47] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003899R0101 | SPOUT 12KV, >2500A | 24 | 18 | 6 | 6100KDP01 | PO-SEP-8381-[6] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Europroxy FZCO | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003899R0101 | SPOUT 12KV, >2500A | 6 | 6 | 0 | 6100K023 | PO-SEP-8381-[4] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Europroxy FZCO | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003900P0101 | COVER FOR SPOUT | 24 | 12 | 12 | 6100K023 | PO-SEP-8385-[77] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003900P0101 | COVER FOR SPOUT | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8385-[202] | PO | 2025-10-05 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8003900P0102 | COVER FOR SPOUT | 18 | 18 | 0 | 6100K023 | PO-SEP-8385-[47] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 65 | 7 | 58 | 6100KDP01 | PO-SEP-6812-[130] | PO | 2025-08-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 58 | 51 | 7 | 6100KDP01 | PO-SEP-8387-[26] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 7 | 7 | 0 | 6100K023 | PO-SEP-8387-[8] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004437P0103P | SHROUD (EARTHING CONTACT)GCE8004437P0103 | 66 | 66 | 0 | 6100K023 | PO-SEP-8385-[78] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004471R0101P | ELECTRODE, ZS1 95kV BIL | 21 | 15 | 6 | 6100K023 | PO-SEP-8385-[49] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004471R0101P | ELECTRODE, ZS1 95kV BIL | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8385-[135] | PO | 2025-10-05 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8004944R0101 | SPOUT ZS1 (4000A) | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8381-[7] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Europroxy FZCO | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005041P0101P | CONTACT PIN 109mm,3150A(GCE8005041P0101) | 18 | 18 | 0 | 6100K023 | PO-SEP-8385-[115] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005042P0101 | CONNECTION PIECE 3150A ZS1 | 9 | 9 | 0 | 6100K023 | PO-SEP-8385-[116] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005112P0103P | OPERATING BOLT | 8 | 6 | 2 | 6100K023 | PO-SEP-8385-[51] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005112P0103P | OPERATING BOLT | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[190] | PO | 2025-10-05 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005117P0101 | CARRIER | 16 | 16 | 0 | 6100KDP01 | PO-SEP-8505-[2] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | WORKSTEEL s.r.o. | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005136P0101 | SUPPORT (POLY) | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8396-[45] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005164P0101 | SCREENING | 54 | 54 | 0 | 6100K023 | PO-SEP-8385-[52] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005250P0101 | K- LIFTING HOOK (ZINC CHROM) | 216 | 204 | 12 | 6100KDP01 | PO-SEP-8402-[41] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005250P0101 | K- LIFTING HOOK (ZINC CHROM) | 12 | 12 | 0 | 6100K023 | PO-SEP-8402-[9] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8005595R0102P | BUSBAR ZS D100, 12THICK,800/800, L=795 | 24 | 24 | 0 | 6100K023 | PO-SEP-8385-[122] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8006587P0101 | LOCK SCREW M6X25 ( ROUND FLAT HEAD ) | 416 | 296 | 120 | 6100K023 | PO-SEP-8403-[12] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8006587P0101 | LOCK SCREW M6X25 ( ROUND FLAT HEAD ) | 120 | 120 | 0 | 6100KDP01 | PO-SEP-8403-[5] | PO | 2025-10-05 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8008881P0103 | BRACKET BOTTOM | 106 | 96 | 10 | 6100KDP01 | PO-SEP-8402-[67] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8008881P0103 | BRACKET BOTTOM | 10 | 10 | 0 | 6100K023 | PO-SEP-8402-[22] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8008881P0104 | SHUTTER BRACKET | 110 | 102 | 8 | 6100KDP01 | PO-SEP-8402-[43] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8008881P0104 | SHUTTER BRACKET | 8 | 8 | 0 | 6100K023 | PO-SEP-8402-[23] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 58 | 51 | 7 | 6100KDP01 | PO-SEP-8387-[28] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 7 | 7 | 0 | 6100K023 | PO-SEP-8387-[9] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010004P0102 | GUIDE RAIL RIGHT 12kV | 60 | 51 | 9 | 6100KDP01 | PO-SEP-8387-[29] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010004P0102 | GUIDE RAIL RIGHT 12kV | 9 | 9 | 0 | 6100K023 | PO-SEP-8387-[10] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010008P0101 | BUSHING PLATE (STAINLESS STEEL) | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8402-[77] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010022P0111R | SHUTTER UPPER W800 (GCE8010022P0111) | 57 | 46 | 11 | 6100KDP01 | PO-SEP-8396-[32] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010022P0111R | SHUTTER UPPER W800 (GCE8010022P0111) | 11 | 11 | 0 | 6100K023 | PO-SEP-8396-[10] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010022P0112Y | SHUTTER LOWER W800 (GCE8010022P0112) | 52 | 43 | 9 | 6100KDP01 | PO-SEP-8396-[39] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010022P0112Y | SHUTTER LOWER W800 (GCE8010022P0112) | 9 | 9 | 0 | 6100K023 | PO-SEP-8396-[11] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010022P0113R | SHUTTER UPPER (DWG.GCE8010022P0113) | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8396-[34] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010022P0114Y | SHUTTER LOWER (DWG.GCE8010022P0114) | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8396-[35] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010023P0101 | PIN (ZINC COATED) | 224 | 224 | 0 | 6100KDP01 | PO-SEP-8523-[14] | PO | 2025-10-23 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 110 | 2 | 108 | 6100KDP01 | PO-SEP-8920-[4] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 108 | 92 | 16 | 6100KDP01 | PO-SEP-8396-[29] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 16 | 16 | 0 | 6100K023 | PO-SEP-8396-[18] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0103 | PRESSURE RELIEF FLAP W1000 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8396-[27] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0105 | PRESSURE RELIEF FLAP, REAR | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8396-[25] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0105A | Pressure Relief Flap, Rear BB Comp, W800, 238mm (OG FDR) | 40 | 40 | 0 | 6100KDP01 | PO-SEP-8920-[3] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0106 | PRESSURE RELIEF FLAP W1000 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8396-[26] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010028R0106A | Pessure Relief Flap, Rear BB Comp, W800, 290mm (BRM) | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8920-[2] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010073P0102 | PARTITION WALL | 52 | 46 | 6 | 6100KDP01 | PO-SEP-8402-[63] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010073P0102 | PARTITION WALL | 6 | 6 | 0 | 6100K023 | PO-SEP-8402-[24] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010073P0103 | BB/CB.PARTITION WALL W1000(PaintRAL7035) | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8402-[40] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010096P0101P | PIN 12DIA(ZINC COAT)DWG:GCE8010096P0101 | 2 | 2 | 0 | 6100K023 | PO-SEP-8523-[5] | PO | 2025-10-23 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010097P0101 | MOUNTING PLATE W800, S=310 | 4 | 3 | 1 | 6100KDP01 | PO-SEP-8402-[79] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010097P0101 | MOUNTING PLATE W800, S=310 | 1 | 1 | 0 | 6100K023 | PO-SEP-8402-[25] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010097P0102 | MOUNTING PLATE S=310 W1000 | 7 | 5 | 2 | 6100KDP01 | PO-SEP-8402-[49] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010097P0102 | MOUNTING PLATE S=310 W1000 | 2 | 2 | 0 | 6100K023 | PO-SEP-8402-[11] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010104P0103P | BUSHING D60/49X25 | 18 | 18 | 0 | 6100K023 | PO-SEP-8385-[53] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010104P0104P | BUSHING D58/47X25 | 24 | 18 | 6 | 6100KDP01 | PO-SEP-8387-[25] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010104P0104P | BUSHING D58/47X25 | 6 | 6 | 0 | 6100K023 | PO-SEP-8387-[12] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010178P0102 | SUPPORT ANGLE | 57 | 46 | 11 | 6100KDP01 | PO-SEP-8402-[55] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010178P0102 | SUPPORT ANGLE | 11 | 11 | 0 | 6100K023 | PO-SEP-8402-[26] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8010178P0103 | SUPPORT ANGLE W1000 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8402-[50] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011408P0101 | MOUNTING PLATE W800, METERING | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8402-[81] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011549P0101 | CT-COOLER(HEAT SINK) | 30 | 21 | 9 | 6100KDP01 | PO-SEP-5542-[56] | PO | 2025-12-05 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | MV Switchgear component ABB Supply
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011549P0101 | CT-COOLER(HEAT SINK) | 9 | 9 | 0 | free_stock | PO-SEP-8340-[1] | PO | 2025-12-20 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AB KOMPONENTY s.r.o. | CT Cooler
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011552P0102 | FLAT SCREEN FOR CB.MIDDLE PLATE W800 | 8 | 1 | 7 | 606PD013 | PO-SEP-8920-[1] | PO | 2025-11-03 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011552P0102 | FLAT SCREEN FOR CB.MIDDLE PLATE W800 | 7 | 7 | 0 | 6100KDP01 | PO-SEP-8396-[43] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011642P0101 | SPACER | 148 | 148 | 0 | 6100K023 | PO-SEP-8385-[54] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011650P0101 | SUPPORT REINFORCEMENT | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8402-[46] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011673P0101 | PARTITION WALL W800 | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8402-[82] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011710P0103 | RIB | 120 | 48 | 72 | 6100KDP01 | PO-SEP-8402-[62] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011710P0103 | RIB | 72 | 24 | 48 | 6100K023 | PO-SEP-8402-[27] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8011710P0103 | RIB | 48 | 48 | 0 | 6100KDP01 | PO-SEP-5654-[37] | PO | 2025-12-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries)
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8012119P0101 | STRENGTHENING STRIP (5mmx30x2005mm) W800 | 12 | 6 | 6 | 6100KDP01 | PO-SEP-8402-[65] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8012119P0101 | STRENGTHENING STRIP (5mmx30x2005mm) W800 | 6 | 4 | 2 | 6100K023 | PO-SEP-8402-[28] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8012119P0101 | STRENGTHENING STRIP (5mmx30x2005mm) W800 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-5654-[38] | PO | 2025-12-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries)
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8012119P0102 | STRENGTHENING STRIP (5mmx30x710mm)W800 | 6 | 3 | 3 | 6100KDP01 | PO-SEP-8402-[68] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8012119P0102 | STRENGTHENING STRIP (5mmx30x710mm)W800 | 3 | 2 | 1 | 6100K023 | PO-SEP-8402-[29] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8012119P0102 | STRENGTHENING STRIP (5mmx30x710mm)W800 | 1 | 1 | 0 | 6100KDP01 | PO-SEP-5654-[39] | PO | 2025-12-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries)
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8012228P0101 | SUPPORTING SHEET | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8402-[44] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013214P0101 | PARTITION WALL BOTTOM W800 (SS STL)BARE | 53 | 43 | 10 | 6100KDP01 | PO-SEP-8402-[57] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013214P0101 | PARTITION WALL BOTTOM W800 (SS STL)BARE | 10 | 10 | 0 | 6100K023 | PO-SEP-8402-[30] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013244P0101 | TRANSFORMER PLATE W800mm | 53 | 43 | 10 | 6100KDP01 | PO-SEP-8402-[60] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013244P0101 | TRANSFORMER PLATE W800mm | 10 | 10 | 0 | 6100K023 | PO-SEP-8402-[31] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013412R0101 | PRESSURE RELIEF FLAP FOR W1000 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8396-[28] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013414P0101 | FIXING PLATE FOR DUCT | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8402-[52] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013419R0101 | FRAME FOR FLAT SCREEN COMPLETE | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8396-[30] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013423P0101 | PARTITION WALL W1000 (PAINTED RAL7035) | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8402-[53] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013427P0101 | GAIN CT PLATE | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8402-[54] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013430P0101 | COOLING PLATE 1 ( small ) | 9 | 9 | 0 | 6100K023 | PO-SEP-8385-[55] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013431P0101 | COOLING PLATE 2 ( Big ) | 9 | 9 | 0 | 6100K023 | PO-SEP-8385-[117] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013433P0101P | SHROUD (DWG NO. GCE8013433P0101) | 6 | 6 | 0 | 6100K023 | PO-SEP-8385-[56] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013434P0101P | SHROUD (DWG NO. GCE8013434P0101) | 6 | 6 | 0 | 6100K023 | PO-SEP-8385-[57] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013434P0102P | SHROUD (DWG NO. GCE8013434P0102) | 6 | 6 | 0 | 6100K023 | PO-SEP-8385-[58] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013435P0101P | SPACER DISC (GCE8013435P0101) | 48 | 48 | 0 | 6100KDP01 | PO-SEP-8483-[5] | PO | 2025-12-31 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AB KOMPONENTY s.r.o. | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8013444R0101 | PRESSURE RELIEF FLAP(W1000) | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8396-[24] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8487370R0100 | EARTHING CONTACT | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8387-[38] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 56 | 56 | 0 | 6100KDP01 | PO-SEP-8379-[38] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8684080P0101 | EARTHING STRIP | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8403-[9] | PO | 2025-10-05 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE8685778P0121P | CONTACT PIN 800/1200A SIL.COAT = 72L | 3 | 3 | 0 | 6100K023 | PO-SEP-8385-[121] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9401556P0100 | STOP WASHER | 126 | 98 | 28 | 6100KDP01 | PO-SEP-8378-[327] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9401556P0100 | STOP WASHER | 28 | 28 | 0 | 6100K023 | PO-SEP-8378-[326] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9401766P0107 | LOCKING MAGNET DC125 V | 33 | 33 | 0 | 6100KDP01 | PO-SEP-8501-[3] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Xiamen Leelen High Voltage Electric Co. Ltd | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9476775R0100 | IND.CONTACT/ VAN FLOW SWITCH | 6 | 4 | 2 | 6100K023 | PO-SEP-8385-[62] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9476775R0100 | IND.CONTACT/ VAN FLOW SWITCH | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[209] | PO | 2025-10-05 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | GCE9477367P0102 | FORK D11x20 | 11 | 11 | 0 | 6100KDP01 | PO-SEP-8523-[8] | PO | 2025-10-23 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | K031-BS3600-13.8-LCT | Bus-Tie Lower CTs ¦ K031-BS3600-13.8-LCT ¦ ABB | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8580-[10] | PO | 2026-01-24 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | AL Aziyziyah Project SWGR KDP01 CTs
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | K031-BS3600-13.8-UCT | Bus-Tie Upper CTs ¦ K031-BS3600-13.8-UCT ¦ ABB | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8580-[9] | PO | 2026-01-24 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | AL Aziyziyah Project SWGR KDP01 CTs
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | K031-CAP1250-13.8-LCT | Capacitor O/G Feeder Lower CTs ¦ K031-CAP1250-13.8-LCT ¦ ABB | 9 | 9 | 0 | 6100KDP01 | PO-SEP-8580-[4] | PO | 2026-01-24 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | AL Aziyziyah Project SWGR KDP01 CTs
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | K031-CAP1250-13.8-UCT | Capacitor O/G Feeder Upper CTs ¦ K031-CAP1250-13.8-UCT ¦ ABB | 9 | 9 | 0 | 6100KDP01 | PO-SEP-8580-[3] | PO | 2026-01-24 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | AL Aziyziyah Project SWGR KDP01 CTs
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | K031-INC3600-13.8-LCT | Incomer Lower CTs ¦ K031-INC3600-13.8-LCT ¦ ABB | 9 | 9 | 0 | 6100KDP01 | PO-SEP-8580-[2] | PO | 2026-01-24 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | AL Aziyziyah Project SWGR KDP01 CTs
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | K031-OG1250-13.8-LCT | OUTGOING PLAIN Lower CT ¦ K031-OG1250-13.8-LCT ¦ ABB | 114 | 114 | 0 | 6100KDP01 | PO-SEP-8580-[8] | PO | 2026-02-07 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 6 | Abb Electrical Industriesco | AL Aziyziyah Project SWGR KDP01 CTs
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | K031-OG1250-13.8-UCT | OUTGOING PLAIN Upper CTs ¦ K031-OG1250-13.8-UCT ¦ ABB | 114 | 114 | 0 | 6100KDP01 | PO-SEP-8580-[7] | PO | 2026-02-07 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 6 | Abb Electrical Industriesco | AL Aziyziyah Project SWGR KDP01 CTs
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | K031-SST630-13.8-LCT | Station AUX Lower CTs ¦ K031-SST630-13.8-LCT ¦ ABB | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8580-[6] | PO | 2026-01-24 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | AL Aziyziyah Project SWGR KDP01 CTs
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | K031-SST630-13.8-UCT | Station Aux. Upper CTs ¦ K031-SST630-13.8-UCT ¦ ABB | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8580-[5] | PO | 2026-01-24 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Abb Electrical Industriesco | AL Aziyziyah Project SWGR KDP01 CTs
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 102 | 102 | 0 | 6100KDP01 | PO-SEP-8446-[4] | PO | 2025-11-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Ningbo Shengjiu Technology CO., LTD. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 96 | 96 | 0 | 6100KDP01 | PO-SEP-8388-[23] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV2000-1685-06-W | WHITE TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 1190 | 1190 | 0 | free_stock | PO-SEP-7852-[1] | PO | 2025-08-20 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Raja Procuremnet Local Purchases | Tube, Ferrule, White, Inner Diameter 3.5 mm, 1.5 Wire
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV2000-1685-06-W | WHITE TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 12750 | 810 | 11940 | free_stock | PO-SEP-7852-[1] | PO | 2025-08-20 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Raja Procuremnet Local Purchases | Tube, Ferrule, White, Inner Diameter 3.5 mm, 1.5 Wire
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MV2000-1685-06-W | WHITE TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 11940 | 0 | 11940 | PR Required | - | PR |  | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | RMU000000339 | PLATE -FOR PANEL FIXING | 176 | 176 | 0 | 6100KDP01 | PO-SEP-8402-[75] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000022P0001 | K-SLIDING PART | 96 | 29 | 67 | free_stock | PO-SEP-6816-[7] | PO | 2025-09-18 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000022P0001 | K-SLIDING PART | 67 | 48 | 19 | 6100KDP01 | PO-SEP-8509-[3] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000022P0001 | K-SLIDING PART | 19 | 19 | 0 | 6100K023 | PO-SEP-8509-[4] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000024P0001P | BUSHING (LOCAL PUR) | 57 | 49 | 8 | 6100KDP01 | PO-SEP-8484-[7] | PO | 2025-12-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000024P0001P | BUSHING (LOCAL PUR) | 8 | 8 | 0 | 6100K023 | PO-SEP-8484-[8] | PO | 2025-12-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000026P0001P | BUSHING (LOCAL PUR) | 180 | 153 | 27 | 6100KDP01 | PO-SEP-8403-[6] | PO | 2025-10-05 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000026P0001P | BUSHING (LOCAL PUR) | 27 | 27 | 0 | 6100K023 | PO-SEP-8484-[2] | PO | 2025-12-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000037P0001 | K-LEVER | 100 | 50 | 50 | 6100KDP01 | PO-SEP-8523-[12] | PO | 2025-10-23 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000037P0001 | K-LEVER | 50 | 41 | 9 | 6100K023 | PO-SEP-8523-[10] | PO | 2025-10-23 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000037P0001 | K-LEVER | 9 | 9 | 0 | free_stock | PO-SEP-8659-[1] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Laser Company for Metal Industries Ltd | K-Lever ¦ SCB1000037P0001 ¦ ABB
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000047P0001 | INTERLOCKING SCOTCH | 60 | 51 | 9 | 6100KDP01 | PO-SEP-8523-[6] | PO | 2025-10-23 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1000047P0001 | INTERLOCKING SCOTCH | 9 | 9 | 0 | 6100K023 | PO-SEP-8523-[2] | PO | 2025-10-23 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1001476P0001 | PROTECTION NET/ T11180 / 2.5T4 | 107 | 107 | 0 | 6100KDP01 | PO-SEP-8385-[303] | PO | 2025-10-12 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1001678P0001 | HOOKING LEVER (ZINC PLATED) | 1 | 1 | 0 | 6100K023 | PO-SEP-8402-[39] | PO | 2025-11-17 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1001813R0802P | MECHANICAL OFF BUTTON FOR VD4 - HOR | 11 | 11 | 0 | 6100K023 | PO-SEP-8385-[67] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1001915P0001P | PIN | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8484-[6] | PO | 2025-12-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1001916P0001P | INTERLOCK LEVER (LOCAL PUR) | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8484-[5] | PO | 2025-12-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1001982P0001 | ROLLER | 8 | 6 | 2 | 6100K023 | PO-SEP-8385-[68] | PO | 2025-09-21 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SCB1001982P0001 | ROLLER | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[198] | PO | 2025-10-05 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP10038 | Humidistat, 250V, AC, MFR 012 ¦ 01220.0-00 | 51 | 50 | 1 | free_stock | PO-SEP-7749-[2] | PO | 2025-09-30 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | STEGO Elektrotechnik GmbH | CY-BULK/ NEW PROJECTS/ HEATER, 120/240V AC, 100W/14007.0-00/HG 140
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP10038 | Humidistat, 250V, AC, MFR 012 ¦ 01220.0-00 | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8198-[3] | PO | 2025-10-05 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | STEGO Elektrotechnik GmbH | PP-12 additional components
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP10038 | Humidistat, 250V, AC, MFR 012 ¦ 01220.0-00 | 51 | 50 | 1 | 6100KDP01 | PO-SEP-8198-[3] | PO | 2025-10-05 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | STEGO Elektrotechnik GmbH | PP-12 additional components
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP10038 | Humidistat, 250V, AC, MFR 012 ¦ 01220.0-00 | 1 | 1 | 0 | 6100KDP02 | PO-SEP-8198-[1] | PO | 2025-10-09 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | STEGO Elektrotechnik GmbH | PP-12 additional components
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11257 | FLEX. CABLE,70MM.SQ, PVC 85 YEL/GRN,85°C | 0.86313 | 0.86313 | 0 | free_stock | PR-SEP-0023556-[73] | PR |  | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11258 | Cable, Control, 1 Core,CU/PVC, 1.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 1.116 | 1.116 | 0 | 6100K020 | PO-SEP-8915-[44] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11258 | FLEX.CABLE,1/C,1.5MM BLUE ATC,105 Deg C | 111.5974 | 106 | 5.5974 | 6100K021 | PO-SEP-8915-[16] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11258 | FLEX.CABLE,1/C,1.5MM BLUE ATC,105 Deg C | 5.5974 | 5.5974 | 0 | 6100K025 | PO-SEP-8915-[1] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11259 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 0.36105 | 0.36105 | 0 | 6100K020 | PO-SEP-8915-[45] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11259 | FLEX.CABLE,1/C,1.5MM BLACK ATC,105 Deg C | 36.2691 | 35.6389 | 0.6302 | 6100K020 | PO-SEP-8915-[45] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11259 | FLEX.CABLE,1/C,1.5MM BLACK ATC,105 Deg C | 0.6302 | 0.6302 | 0 | 6100K021 | PO-SEP-8915-[17] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11260 | FLEX.CABLE,1/C,1.5MM GREY ATC,105 Deg C | 0.010941 | 0.010941 | 0 | 6100K021 | PO-SEP-8915-[18] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11260 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 8.3807 | 8.3807 | 0 | 6100K025 | PO-SEP-8915-[3] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11260 | FLEX.CABLE,1/C,1.5MM GREY ATC,105 Deg C | 838.0744 | 838 | 0.074398 | 6100K020 | PO-SEP-8915-[46] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11260 | FLEX.CABLE,1/C,1.5MM GREY ATC,105 Deg C | 0.074398 | 0.074398 | 0 | 6100K021 | PO-SEP-8915-[18] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11261 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 0.36105 | 0.36105 | 0 | 6100K020 | PO-SEP-8915-[47] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11261 | FLEX.CABLE,1/C,1.5MM RED C,105 Deg C | 36.2691 | 33.6389 | 2.6302 | 6100K020 | PO-SEP-8915-[47] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11261 | FLEX.CABLE,1/C,1.5MM RED C,105 Deg C | 2.6302 | 2.6302 | 0 | 6100K021 | PO-SEP-8915-[19] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11262 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 1.5098 | 1.5098 | 0 | 6100K020 | PO-SEP-8915-[48] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11262 | FLEX.CABLE,1/C,2.5MM BLUE ATC,105 Deg C | 150.6565 | 148 | 2.6565 | 6100K021 | PO-SEP-8915-[20] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11262 | FLEX.CABLE,1/C,2.5MM BLUE ATC,105 Deg C | 2.6565 | 2.6565 | 0 | 6100K025 | PO-SEP-8915-[5] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11263 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 0.95186 | 0.95186 | 0 | 6100K021 | PO-SEP-8915-[21] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11263 | FLEX.CABLE,1/C,2.5MM BLACK ATC,105 Deg C | 94.8578 | 94.8578 | 0 | 6100K020 | PO-SEP-8915-[49] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11264 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 0.28446 | 0.28446 | 0 | 6100K021 | PO-SEP-8915-[22] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11264 | FLEX.CABLE,1/C,2.5MM GREY ATC,105 Deg C | 27.8993 | 27.8993 | 0 | 6100K020 | PO-SEP-8915-[50] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11265 | FLEX.CABLE,1/C,2.5MM YE/GN ATC,105 Deg C | 0.010941 | 0.010941 | 0 | 6100K020 | PO-SEP-8915-[51] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11265 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm Yellow/Green, ATC, 105°, 600/1000V , 1 x 100 m | 0.28446 | 0.28446 | 0 | 6100K020 | PO-SEP-8915-[51] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11265 | FLEX.CABLE,1/C,2.5MM YE/GN ATC,105 Deg C | 28.0088 | 17.7046 | 10.3042 | 6100K020 | PO-SEP-8915-[51] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11265 | FLEX.CABLE,1/C,2.5MM YE/GN ATC,105 Deg C | 10.3042 | 10.3042 | 0 | 6100K021 | PO-SEP-8915-[23] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11266 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 1.5098 | 1.5098 | 0 | 6100K021 | PO-SEP-8915-[24] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11266 | FLEX.CABLE,1/C,2.5MM RED ATC,105 Deg C | 150.6565 | 150.6565 | 0 | 6100K020 | PO-SEP-8915-[52] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11267 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Yellow, ATC,105°, 600/1000V , 1 x 100 m | 1.5098 | 1.5098 | 0 | 6100K020 | PO-SEP-8915-[53] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11267 | FLEX.CABLE,1/C,2.5MM YELLOW ATC,90 Deg C | 150.6565 | 148 | 2.6565 | 6100K025 | PO-SEP-8915-[10] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11267 | FLEX.CABLE,1/C,2.5MM YELLOW ATC,90 Deg C | 2.6565 | 2.6565 | 0 | 6100K021 | PO-SEP-8915-[25] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11268 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 0.087527 | 0.087527 | 0 | 6100K021 | PO-SEP-8915-[26] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11268 | FLEX.CABLE,1/C,4MM BLUE ATC,105 Deg C | 8.3698 | 8.3698 | 0 | 6100K020 | PO-SEP-8915-[54] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11269 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 0.10941 | 0.10941 | 0 | 6100K025 | PO-SEP-8915-[12] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11269 | FLEX.CABLE,1/C,4MM BLACK ATC,105 Deg C | 11.1597 | 11.1597 | 0 | 6100K021 | PO-SEP-8915-[27] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11270 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 0.087527 | 0.087527 | 0 | 6100K025 | PO-SEP-8915-[14] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR |  | SEP11270 | FLEX.CABLE,1/C,4MM RED ATC,105 Deg C | 8.3698 | 8.3698 | 0 | 6100K020 | PO-SEP-8915-[57] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11271 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Yellow, ATC, 105°, 600/1000V , 1 x 100 m | 0.087527 | 0.087527 | 0 | 6100K021 | PO-SEP-8915-[30] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11271 | FLEX.CABLE,1/C,4MM YELLOW ATC,105 Deg C | 8.3698 | 8.3698 | 0 | 6100K020 | PO-SEP-8915-[58] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11272 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Grey, ATC, 105°, 600/1000V, 1 x 100 m | 0.10941 | 0.10941 | 0 | 6100K025 | PO-SEP-8915-[13] | PO | 2026-01-11 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP11272 | FLEX.CABLE,1/C,4MM GREY ATC,105 Deg C | 11.1597 | 11.1597 | 0 | 6100K021 | PO-SEP-8915-[28] | PO | 2026-01-11 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12004 | TERM.LUGS BLADE RF-PP 12/23 | 15300 | 15300 | 0 | 6100K020 | PO-SEP-8894-[10] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12012 | TERM.LUGS SPADE RF-U4 1.5/M4 | 6375 | 6375 | 0 | 6100K020 | PO-SEP-8894-[11] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12016 | TERM.LUGS RING RF-M4 1.5/M4 | 5100 | 5100 | 0 | 6100K020 | PO-SEP-8894-[13] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12026 | BENT LUGS TYPE RF-PPL30 | 35700 | 35700 | 0 | 6100K020 | PO-SEP-8894-[1] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12048 | END SLEEVES PKE 1508 (1x1.5sqmm , Black) | 765 | 765 | 0 | 6100K020 | PO-SEP-8894-[17] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12050 | UN-INSUL SLeve Lugs KE1510ST (1.5mm) | 1020 | 1020 | 0 | 6100K020 | PO-SEP-8894-[2] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12052 | END SLEEVES PKT 1508 (2x1.5sqmm , Black) | 765 | 765 | 0 | 6100K020 | PO-SEP-8894-[18] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12063 | TERM.LUGS BLADE BF-PP12/25 2.5MM | 5100 | 5100 | 0 | 6100K025 | PO-SEP-8894-[46] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12083 | TERM.LUGS BF-M5 (RING) | 6120 | 6120 | 0 | 6100K020 | PO-SEP-8894-[15] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12085 | WIRE LUGS RING TYPE BF-M6 2.5/M6 | 408 | 408 | 0 | 6100K020 | PO-SEP-8894-[16] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12087 | RING TYPE LUGS BF-M 8 | 408 | 408 | 0 | 6100K020 | PO-SEP-8894-[3] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12091 | BENT LUGS TYPE BF-PPL30 | 15300 | 15300 | 0 | 6100K025 | PO-SEP-8894-[41] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12103 | UN-INSUL SLEEVE Lugs for 2.5mm KE2510ST | 2550 | 2550 | 0 | 6100K025 | PO-SEP-8894-[44] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12105 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 1020 | 1020 | 0 | 6100K020 | PO-SEP-8894-[19] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12117 | TERM.LUGS RING BF-M4 | 10200 | 10200 | 0 | 6100K020 | PO-SEP-8894-[14] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12119 | RING TYPE LUGS GF-M 5 | 1020 | 1020 | 0 | 6100K020 | PO-SEP-8894-[12] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12127 | BENT LUGS TYPE BF-PPL46 | 7650 | 7650 | 0 | 6100K025 | PO-SEP-8894-[40] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12129 | Un-Insul Sleeve Lugs 4.0 mm KE410ST | 2550 | 2550 | 0 | 6100K025 | PO-SEP-8894-[45] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12131 | Lugs, Sleeve 4.0/9mm ( W/O Ins.) 3200302 | 2550 | 2550 | 0 | 6100K025 | PO-SEP-8894-[42] | PO | 2025-10-23 | LV |  | - | 2026-02-15 | 2026-02-01 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40173 | Busbar, Copper, 30 x 5 mm, R=1, 5.5m | 375.486 | 155.522 | 219.964 | free_stock | PO-SEP-7505-[4] | PO | 2025-09-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al Shatara Electricals
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40173 | Busbar, Copper, 30 x 5 mm, R=1, 5.5m | 219.964 | 60 | 159.964 | free_stock | PO-SEP-7505-[3] | PO | 2025-10-10 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Al Shatara Electricals
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40173 | Busbar, Copper, 30 x 5 mm, R=1, 5.5m | 159.964 | 159.964 | 0 | free_stock | PO-SEP-8142-[1] | PO | 2025-10-30 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Innovation Solutions Factory | EBM-BULK / FAST MOVING | 352.84 | 27-10-2025
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40181 | Busbar, Copper, 32 x 8 mm, R=1, 5.5m | 103.69 | 103.69 | 0 | 6100KDP01 | PO-SEP-8566-[4] | PO | 2025-11-27 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Innovation Solutions Factory
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40202 | Busbar, Copper, 80 x 10 mm, R=5, 5.5m | 6819.93 | 4358.88 | 2461.05 | 6100KDP01 | PO-SEP-8566-[2] | PO | 2025-11-27 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Innovation Solutions Factory
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40202 | Busbar, Copper, 80 x 10 mm, R=5, 5.5m | 2461.05 | 2420.52 | 40.53 | 6100K023 | PO-SEP-8566-[10] | PO | 2025-11-27 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Innovation Solutions Factory
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40202 | Busbar, Copper, 80 x 10 mm, R=5, 5.5m | 40.53 | 40.53 | 0 | free_stock | PO-SEP-8672-[5] | PO | 2025-12-15 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Innovation Solutions Factory | Copper Busbar for ACDC
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40210 | Busbar, Copper, 120 x 10 mm, R=5, 5.5m | 1147.706 | 1147.706 | 0 | 6100KDP01 | PO-SEP-8566-[14] | PO | 2025-11-27 | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0 | Innovation Solutions Factory
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP40223 | Copper earthing bar 12.5 x 4.0 mm | 51 | 0 | 51 | PR Required | - | PR |  | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | XM 2000 1000-22 | POLYCARBONATE 2000X1000X2.0 MM | 40 | 0 | 40 | PR Required | - | PR |  | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | XM 2050 1500-30 | POLYCARBONATE 2050X1500X3.0 MM | 374.52 | 0 | 374.52 | PR Required | - | PR |  | Mechanical |  | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1SNA234000R0200 | Marker, RC810, 1 ¦ 10/1SNA234041R2600 ¦ ENTRELEC | 90 | 90 | 0 | 6100KDP01 | PO-SEP-8386-[16] | PO | 2025-11-10 | LV | Automated: Replaced 1SNA234000R0200 by SEP20333. | - | 2026-02-15 | 2026-02-01 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5340XIAXXN01 | Relay, Auxiliary, 2 Coils, Self Reset Contacts, Hand Reset Flag, 110-125V, DC, 2NO, 1NC, Coil ¦ RXSF1 RK 271 007-AN | 51 | 51 | 0 | 6100K021 | PO-SEP-8751-[1] | PO | 2025-12-31 | LV | Automated: Replaced 1YAB5340XIAXXN01 by DM0000000058. | - | 2026-02-15 | 2026-02-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CAB0000 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 428 | 100 | 328 | 6100KDP01 | PO-SEP-6702-[3] | QC | 2025-06-30 | LV | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-02-15 | 2026-02-01 | 0 | Phoenix Contact Middle East Fzllc | 13.8KV SWGR PP-12 SS#9077 ELEC COMPONENTS (2x I/C, 2xSST, 1xBRM, 1xBS & 1x BME) | 100 | 11-06-2025 | 11-06-2025 |  |  | PO-6050/6702/347252
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 1YAB5355CAB0000 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 328 | 328 | 0 | 6100KDP01 | PO-SEP-8572-[3] | PO | 2025-12-15 | LV | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-02-15 | 2026-02-01 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | MARWI60236 | Marker, Numbering, Blank, UCT-TM 10 ¦ 0829142 ¦ PHOENIX | 14 | 14 | 0 | 6100K020 | PO-SEP-8792-[26] | PO | 2025-12-20 | LV | Automated: Replaced 1YAB5355HAB0000 by MARWI60236. Automated: Replaced 1YAB5355HAB0000 by MARWI60236. | - | 2026-02-15 | 2026-02-01 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | 25541 | HEX.RIVET NUT M10X24 ( 25541 ) | 98 | 98 | 0 | 6100KDP01 | PO-SEP-8645-[2] | PO | 2025-10-30 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-02-15 | 2026-02-01 | 0 | Saeed Aziz Alsomali Trading Est
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP10163 | 1.5 Red Wire Gauge Tube 1.5mm² | 510 | 470 | 40 | free_stock | PR-SEP-0024130-[145] | PR |  | LV | Automated: Replaced AE2000-1865-14 by SEP10163. Automated: Replaced AE2000-1865-14 by SEP10163. | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP10163 | 1.5 Red Wire Gauge Tube 1.5mm² | 40 | 40 | 0 | free_stock | PR-SEP-0023387-[171] | PR |  | LV | Automated: Replaced AE2000-1865-14 by SEP10163. Automated: Replaced AE2000-1865-14 by SEP10163. | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2126 2011-113 | Nut, Hexagonal Head, M4, Stainless Steel | 6 | 6 | 0 | 606PD013 | PO-SEP-6812-[156] | PO | 2025-08-31 | Mechanical | Automated: Replaced DMS 2126 2011-113 by DF240510018. Automated: Replaced DF240510018 by SEP10896. | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | DMS 2641 0087-19 | Lugs, Terminal Ring, 70 Sq.mm, Copper Tube Crimping ¦ China star | 16 | 12 | 4 | 6100KDP01 | PO-SEP-6812-[136] | PO | 2025-08-31 | Mechanical | Automated: Replaced DMS 2641 0087-19 by SEP12186. | - | 2026-02-15 | 2026-02-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP12186 | Lugs, Terminal Ring, 70 Sq.mm, Copper Tube Crimping ¦ China star | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8834-[17] | PO | 2025-10-05 | Mechanical | Automated: Replaced DMS 2641 0087-19 by SEP12186. Automated: Replaced DMS 2641 0087-19 by SEP12186. | - | 2026-02-15 | 2026-02-01 | 0 | Dalian Jinda Industry Co.,Ltd
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP10650 | 2.5 White Wire Gauge Tube 2.5mm² | 2040 | 1709.3 | 330.7 | free_stock | PR-SEP-0023387-[173] | PR |  | LV | Automated: Replaced MV2000-1865-01-W by SEP10650. Automated: Replaced MV2000-1865-01-W by SEP10650. | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP10650 | 2.5 White Wire Gauge Tube 2.5mm² | 330.7 | 330.7 | 0 | free_stock | PR-SEP-0024130-[176] | PR |  | LV | Automated: Replaced MV2000-1865-01-W by SEP10650. Automated: Replaced MV2000-1865-01-W by SEP10650. | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP10650 | 2.5 White Wire Gauge Tube 2.5mm² | 2040 | 1652 | 388 | free_stock | PR-SEP-0024130-[176] | PR |  | Mechanical | Automated: Replaced MV2000-1865-01-W by SEP10650. Automated: Replaced MV2000-1865-01-W by SEP10650. | - | 2026-02-15 | 2026-02-01 | 0
6100K031 | Aziziyah (Fast Track) : SWITCHGEAR - Aziziyah | SWGR | ROH | SEP10650 | 2.5 White Wire Gauge Tube 2.5mm² | 388 | 388 | 0 | free_stock | PR-SEP-0023081-[172] | PR |  | Mechanical | Automated: Replaced MV2000-1865-01-W by SEP10650. Automated: Replaced MV2000-1865-01-W by SEP10650. | - | 2026-02-15 | 2026-02-01 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 14 | 10 | 4 | 6100KDP01 | PO-SEP-6812-[48] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8378-[225] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 4096 | 4096 | 0 | 6100KDP01 | PO-SEP-8378-[227] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 03366 | STEEL RIVETS T22205/4.8 TS | 705 | 705 | 0 | 6100KDP01 | PO-SEP-8378-[228] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 356 | 40 | 316 | 6100KDP01 | PO-SEP-6812-[56] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 316 | 316 | 0 | 6100KDP01 | PO-SEP-8378-[272] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 07959 | TOMMY HEAD SCREW FULL THREAD T21010/4X25 | 238 | 238 | 0 | 6100KDP01 | PO-SEP-8680-[19] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 08017 | TOMMY HEAD SCREW ACC T21010/M4x22 | 104 | 104 | 0 | 6100KDP01 | PO-SEP-8647-[6] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Mattssons Fasteners AB
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 08448 | SQUARE FASTENING NUT TS ACC T21597/5 | 92 | 92 | 0 | 6100KDP01 | PO-SEP-8378-[338] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 134 | 134 | 0 | 6100KDP01 | PO-SEP-8629-[18] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | FLY METALTECH TRADING CO.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 08856 | WASHER STEEL T22100/ 6.4 | 92 | 92 | 0 | 6100KDP01 | PO-SEP-8378-[280] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 09021 | SELF-LOCKING HEX. NUT,T21192/M10 (LOCAL) | 184 | 184 | 0 | 6100K023 | PO-SEP-8680-[32] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 09601 | WASHER, FLAT ACC T22000/3.2X7 | 132 | 132 | 0 | 6100KDP01 | PO-SEP-8378-[275] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 09929 | STEEL SPRING WASHER ACC T22104/10 | 72 | 72 | 0 | 6100KDP01 | PO-SEP-8378-[278] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 09947 | SPRING WASHER ACC T22104/6 | 10 | 10 | 0 | 6100K023 | PO-SEP-8378-[230] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1000057457 | WASHER CU AL M10 | 21 | 21 | 0 | 6100K023 | PO-SEP-8385-[290] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1020178 | COMBINATION SPANNER SETS | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 12980 | COUNTERSUNK STEEL SCREW T21065/M6X14 | 64 | 64 | 0 | 6100KDP01 | PO-SEP-8646-[2] | PO | 2025-10-20 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 12989 | COUNTERSUNK STEEL SCREW T21065/M8X30 | 46 | 46 | 0 | 6100KDP01 | PO-SEP-8646-[1] | PO | 2025-10-20 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1366 1062-804 | 3/4"XSCHED.40X6M BI PIPE | 19.36 | 0 | 19.36 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 16301 | RIVET T22213/4 | 154 | 154 | 0 | 6100KDP01 | PO-SEP-8645-[4] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Saeed Aziz Alsomali Trading Est
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 16304 | RIVET TT ALUMINUM T22213/5 | 33 | 33 | 0 | 6100KDP01 | PO-SEP-8378-[288] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 46 | 46 | 0 | 6100KDP01 | PO-SEP-8379-[52] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 163 | 163 | 0 | 6100KDP01 | PO-SEP-8379-[43] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611400R1001 | PILOT LIGHT#ML1-100R | 13 | 13 | 0 | 6100KDP01 | PO-SEP-8041-[65] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611400R1002 | PILOT LIGHT#ML1-100G | 13 | 13 | 0 | 6100KDP01 | PO-SEP-8041-[66] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611400R1003 | PILOT LIGHT#ML1-100Y | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8041-[67] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611400R1005 | PILOT LIGHT#ML1-100W | 42 | 42 | 0 | 6100KDP01 | PO-SEP-8041-[68] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611605R1100 | HOLDER#MCBH-00 | 108 | 108 | 0 | 6100KDP01 | PO-SEP-8041-[69] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611621R1051 | LAMP BLOCK#MLBL-05R | 11 | 11 | 0 | 6100KDP01 | PO-SEP-8041-[70] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611621R1052 | LAMP BLOCK#MLBL-05G | 13 | 13 | 0 | 6100KDP01 | PO-SEP-8041-[71] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611621R1053 | LAMP BLOCK#MLBL-05Y | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8041-[72] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611621R1055 | LAMP BLOCK#MLBL-05W | 42 | 42 | 0 | 6100KDP01 | PO-SEP-8041-[73] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 108 | 108 | 0 | 6100KDP01 | PO-SEP-8041-[74] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 108 | 108 | 0 | 6100KDP01 | PO-SEP-8041-[75] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SNK900654R0000 | SC-JB8-4 Short circuit bridges - Yellow | 69 | 69 | 0 | 6100KDP01 | PO-SEP-8386-[17] | PO | 2025-11-10 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR002047G0001 | COMPLETE ASSEMBLY KIT FOR DIRAK LOCKUP | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8446-[3] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Ningbo Shengjiu Technology CO., LTD. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR002416G0001 | LOCKUP ROD ASSEMBLY | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8387-[23] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR002428G0001 | LOCKUP ROD ASSEMBLY | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8387-[24] | PO | 2025-11-30 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR003760G0001 | CRANK FOR EARTHING SWITCH EK6 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8387-[39] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VCR008770F0001 | BLOCK PIN | 96 | 96 | 0 | 6100K023 | PO-SEP-8385-[31] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7600732P0101 | SPACER TUBE | 46 | 46 | 0 | 6100K023 | PO-SEP-8403-[2] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7602006R0101 | TIE ROD W800 CABLE COMPT. | 26 | 26 | 0 | 6100K023 | PO-SEP-8385-[34] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7605506P0101 | ABB LOGO UNIGEAR ZS1 | 6 | 2 | 4 | 6100K023 | PO-SEP-8379-[55] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7605506P0101 | ABB LOGO UNIGEAR ZS1 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-6543-[73] | PO | 2025-12-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | Labels for outdoor
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7605506P0102 | ABB LOGO UNIGEAR ZS1 | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8379-[45] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7607280R0101 | HINGE WITHOUT FASTENERS | 253 | 253 | 0 | 6100KDP01 | PO-SEP-8397-[4] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7608266P0101 | CONNECTION PIECE tublar GCE8005046R0101 | 18 | 18 | 0 | 6100K023 | PO-SEP-8385-[35] | PO | 2025-09-21 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1VL7623184R0101 | COMPLETE HANDLE | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8552-[1] | PO | 2025-11-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | SHAMS ALRIYADH INDUSTRIAL FACTORY | AL Azyziyah DMM Project under Dummy 6100KDP01 2nd Lot of Mechanical Componentes for SEC a/c Dammam Aziziya Fast track project 13.8kV MV SWGR.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB000003-FDX | MIMIC , OUTGOING WITH EARTHING | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8379-[48] | PO | 2025-10-30 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB000004-BTE | MIMIC BUS SEC WITH EARTHG ON RIGHT SIDE | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8379-[49] | PO | 2025-10-30 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010005P0102 | SHROUD, LEFT W1000 | 3 | 3 | 0 | 6100K023 | PO-SEP-8385-[36] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010005P0103 | SHROUD, LEFT W800 | 37 | 37 | 0 | 6100K023 | PO-SEP-8385-[69] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010006P0102 | SHROUD, RIGHT W1000 | 3 | 3 | 0 | 6100K023 | PO-SEP-8385-[37] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010006P0103 | SHROUD, RIGHT W800 | 37 | 37 | 0 | 6100K023 | PO-SEP-8385-[70] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 63 | 63 | 0 | 6100K023 | PO-SEP-8629-[13] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | FLY METALTECH TRADING CO.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010025P0101 | HINGE COMPONENT #2 | 126 | 126 | 0 | 6100K023 | PO-SEP-8403-[3] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010029P0122 | CVI DIVIDER, 12-17.5kV, Set 1B (11425) | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8445-[2] | PO | 2025-12-31 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Ritz Instrument Transformers GMBH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010138P0102 | PROTECTIVE COVER W800 | 16 | 16 | 0 | 6100KDP01 | PO-SEP-8396-[31] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010138P0103 | PROTECTIVE COVER W1000 | 3 | 3 | 0 | 6100K023 | PO-SEP-8385-[38] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010145P0102 | DOOR STOPPER ROD 8 MM DIA. | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8523-[7] | PO | 2025-10-23 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010241P0101 | HEX. BOLT M10X20 POLYAMIDE | 144 | 144 | 0 | 6100KDP01 | PO-SEP-8378-[208] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 72 | 12 | 60 | 6100KDP01 | PO-SEP-6812-[80] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 60 | 60 | 0 | 6100K023 | PO-SEP-8629-[21] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | FLY METALTECH TRADING CO.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010241P0103 | HEX. BOLT M10X30 POLYAMIDE | 72 | 72 | 0 | 6100KDP01 | PO-SEP-8378-[160] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010241P0104 | HEX. BOLT M10X40 POLYAMIDE | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8378-[300] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8379-[40] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010301P0111 | Label printed in Trafolite 200 x 100 | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8379-[39] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010378P0110 | SEC.FEMALE CONTACTS 1.5,W.SLEEVES 50X | 950 | 950 | 0 | 6100K023 | PO-SEP-8385-[40] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010378P0112 | SEC. FEMALE CONTACT PIN 2.5MM | 800 | 800 | 0 | 6100K023 | PO-SEP-8385-[71] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 44 | 44 | 0 | 6100KDP01 | PO-SEP-8379-[29] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010402R0103 | LABELS FOR SHUTTERS BUSBAR-CABLE -FEEDER | 21 | 21 | 0 | 6100K023 | PO-SEP-8379-[22] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010489P0101 | FLAT BRAIDED, 16SQMM. TIN(13.8kV)6mmdia | 73 | 73 | 0 | 6100K023 | PO-SEP-8378-[111] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB010489P0102 | FLAT BRAIDED CONNECTOR, 16 SQMM. TINNED | 21 | 21 | 0 | 6100K023 | PO-SEP-8403-[4] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB51342VA6T1XX | Voltage Transformer (RITZ / VES 17,5-14) | 18 | 0 | 18 | PR Required | - | PR |  | C |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 2 | 2 | 0 | 6100K020 | PO-SEP-8776-[1] | PO | 2025-10-23 | A |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | 6100K020 Mahar SS SWGR Electrical components order.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB52333VW6CN00 | VD4/P 171240-p210-125VDC (1VCD400222) | 2 | 2 | 0 | 6100K020 | PO-SEP-8776-[3] | PO | 2025-10-23 | A |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | 6100K020 Mahar SS SWGR Electrical components order.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB52371V06CN00 | VD4/P 173225-p275-125VDC (1VCD400222) | 2 | 2 | 0 | 6100K025 | PO-SEP-8773-[4] | PO | 2025-10-23 | A |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 22 | 22 | 0 | 6100K025 | PO-SEP-8775-[1] | PO | 2025-10-23 | A |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5320XDB1XN01 | CEWE Elite 440-448 | 14 | 0 | 14 | PR Required | - | PR |  | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 3 | 3 | 0 | 6100K025 | PO-SEP-8829-[2] | PO | 2025-10-23 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abdullah AbuNayyan Trading Corp
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5331XXCX0000 | CAPACITOR PARKING KEY_COMELECTRIC ITALY | 2 | 2 | 0 | free_stock | PR-SEP-0023081-[32] | PR |  | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5331XXCX0100 | BREAKER CONTROL SWITCH (Comelectric) | 21 | 21 | 0 | 6100K020 | PO-SEP-8785-[13] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Aman Engineering FZC
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5331XXCX0210 | CBMODE6P,4Pos.Off-Emer-Local-Rem-Padlock | 5 | 5 | 0 | 6100K020 | PO-SEP-8785-[14] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Aman Engineering FZC
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5331XXCX0220 | OFF-EMER-LOCAL-REMOTE 4P4P, PADLCK (COM) | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8398-[17] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5331XXCX0300 | SPACE HEATER SEL. SWITCH ( COMELECTRIC ) | 23 | 23 | 0 | 6100K021 | PO-SEP-8785-[10] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Aman Engineering FZC
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC ) | 23 | 23 | 0 | 6100K020 | PO-SEP-8785-[17] | PO | 2025-10-23 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Aman Engineering FZC
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5331XXKX0700 | Auto Re-close IN-OUT Selector Switch(K&N | 16 | 16 | 0 | 6100K021 | PO-SEP-8785-[12] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Aman Engineering FZC
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5332XXAXB000 | PB Black 1NO+1NC-22 dia-1SFA611100R4076 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8041-[76] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXAA2E00 | MCB 3A AC -2P,2CDS252001R0317 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8041-[77] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXAA2G00 | MCB S 202-K6 6A AC -2P - 2CDS252001R0377 | 43 | 43 | 0 | 6100KDP01 | PO-SEP-8041-[78] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXAA2L00 | MCB 16A AC -2P - 2CDS252001R0467 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8041-[79] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXAB2G00 | MCB 6A DC 2P S202M-K6UC -2CDS272061R0377 | 134 | 134 | 0 | 6100KDP01 | PO-SEP-8041-[88] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXACG000 | Aux contact 2NC, S2C-HO2L-for MCB Order # 2CDS200936R0003 | 109 | 109 | 0 | 6100KDP01 | PO-SEP-8041-[89] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXACH000 | Aux contact 1NO+1NC MCB -2CDS200936R0001 | 128 | 128 | 0 | 6100KDP01 | PO-SEP-8041-[82] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5336XXACJ000 | S2C-H01 - 1NC- Bottom Auxiliary Contact 2CDS200970R0031 | 10 | 10 | 0 | 6100KDP01 | PO-SEP-8041-[83] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XAJXXN00 | RF-4R_125Vdc_4 C/O_LED | 35 | 35 | 0 | 6100K023 | PO-SEP-8407-[1] | PO | 2025-09-18 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Innovative Systems Co. Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XAJXXN01 | BJ-8RP_Bistable_125Vdc_8 C/O | 16 | 16 | 0 | 6100K023 | PO-SEP-8407-[2] | PO | 2025-09-18 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Innovative Systems Co. Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XCLXXN00 | MVAJ105 RA 0802_125VDC (8 NO + 2 NC) | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8376-[6] | PO | 2026-01-30 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Grid Solution Middle-East Fze | MV
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XDAXXN00 | RXMVB 4, RK 251 401-AP | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8366-[6] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XEAXXN00 | RXMB1 6NO_110-125VDC-1MRK 000 863-AN | 8 | 8 | 0 | 6100K020 | PO-SEP-8751-[37] | PO | 2025-10-23 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XFAXXN00 | DIN Timer (RXKL1, TYPE: 1MRK 000 066-AB) | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8366-[9] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XIAXXN00 | RXSF1_DC110-125V-MV RK 271 019-AN | 21 | 21 | 0 | 6100K020 | PO-SEP-8751-[39] | PO | 2025-10-23 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5340XNHXXN00 | TRIP LOR/ER 7840FD 20NO+20NC, 125VDC | 6 | 6 | 0 | free_stock | PR-SEP-0024130-[18] | PR |  | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 2760 | 2760 | 0 | 6100K023 | PO-SEP-8417-[2] | PO | 2025-11-30 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Phoenix Contact Trading LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 618 | 618 | 0 | 6100KDP01 | PO-SEP-8386-[26] | PO | 2025-11-10 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AEA0001 | M 6/8.RS (SpringLoaded) 1SNA115685R1200 | 869 | 869 | 0 | 6100KDP01 | PO-SEP-8386-[18] | PO | 2025-11-10 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AFA0001 | M4/6.SNTS Spring Loaded 1SNA115229R2000 | 790 | 790 | 0 | 6100KDP01 | PO-SEP-8386-[20] | PO | 2025-11-10 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355AMC0001 | Feed-through terminal block,ZT 4/4AN/2 .Base Terminal Plug AC-DC-4mm 1848350000 | 690 | 690 | 0 | 6100K025 | PO-SEP-8750-[12] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 236 | 236 | 0 | 6100K025 | PO-SEP-8750-[13] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 298 | 298 | 0 | 6100KDP01 | PO-SEP-8518-[3] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CBA0000 | FEM8T6 End Sections Grey 1SNA215266R0100 | 180 | 180 | 0 | 6100KDP01 | PO-SEP-8386-[23] | PO | 2025-11-10 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CEA0000 | FEMR8 End Sections Grey 1SNA116987R0200 | 340 | 340 | 0 | 6100KDP01 | PO-SEP-8386-[24] | PO | 2025-11-10 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CFA0000 | FEM6 End Sections Grey - 1SNA118368R1600 | 110 | 110 | 0 | 6100KDP01 | PO-SEP-8386-[25] | PO | 2025-11-10 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CMC0000 | Terminal End Plate 1848360000-Wiedmuller | 70 | 70 | 0 | 6100KDP01 | PO-SEP-8518-[4] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355DFA0000 | RC610-VerticalMarking 1SNA233060R0400 | 158 | 158 | 0 | 6100KDP01 | PO-SEP-8386-[28] | PO | 2025-11-10 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355DXC0000 | 460660001 DEK 5 FSZ 1-10 Z-Terminal 1-10 | 9300 | 9300 | 0 | 6100K025 | PO-SEP-8750-[10] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355EEA0000 | JUMPER BAR "BJS8" 20 Poles | 34 | 34 | 0 | 6100KDP01 | PO-SEP-8386-[21] | PO | 2025-11-10 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355EFA0000 | PC61-CombTypeJumprBar10 1SNA163311R2200 | 68 | 68 | 0 | 6100KDP01 | PO-SEP-8386-[22] | PO | 2025-11-10 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 124 | 124 | 0 | 6100KDP01 | PO-SEP-8518-[8] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB60050819P0103 | Braided HARNESS TUBE (D40) | 200 | 200 | 0 | 6100K020 | PO-SEP-8834-[12] | PO | 2025-10-23 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Dalian Jinda Industry Co.,Ltd
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB60050819P0106 | Braided HARNESS TUBE (D30) | 400 | 400 | 0 | 6100K020 | PO-SEP-8834-[2] | PO | 2025-10-23 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Dalian Jinda Industry Co.,Ltd
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB60050819P0107 | Braided HARNESS TUBE (D20) | 200 | 200 | 0 | 6100K025 | PO-SEP-8834-[11] | PO | 2025-10-23 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Dalian Jinda Industry Co.,Ltd
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAZ21500101 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8388-[35] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 210 | 210 | 0 | 6100K023 | PO-SEP-8378-[1] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 28452 | FLEXIBLE SPIROID PINS T22513/3X26 | 8 | 6 | 2 | 6100K023 | PO-SEP-8385-[224] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 28452 | FLEXIBLE SPIROID PINS T22513/3X26 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[223] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 28627 | Rivet NUT ACC T21098/M6 (countersunk) | 318 | 318 | 0 | 6100KDP01 | PO-SEP-8645-[3] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Saeed Aziz Alsomali Trading Est
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 2CSM258163R0721 | M1363-L | 1 | 1 | 0 | 6100K023 | PO-SEP-8388-[3] | PO | 2025-10-30 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 2TRE123451P0001 | 3 PIN SOCKET SWITCH,13A,250V,BSRDP-I | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8388-[29] | PO | 2025-10-30 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014480P0004 | RETAINING_WASHER_DIN6799_6-SPST/A3K | 36 | 6 | 30 | 6100KDP01 | PO-SEP-6812-[58] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014480P0004 | RETAINING_WASHER_DIN6799_6-SPST/A3K | 30 | 30 | 0 | 6100K023 | PO-SEP-8385-[291] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 56 | 56 | 0 | 6100KDP01 | PO-SEP-8378-[355] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 4CE7000583P0101 | PIN | 32 | 32 | 0 | 6100K023 | PO-SEP-8680-[33] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 500214111 | WASHER T22001/6.8X18 | 39 | 39 | 0 | 6100KDP01 | PO-SEP-8378-[277] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 500673075 | PIN T22681/8X54,5-5 | 72 | 72 | 0 | 6100K023 | PO-SEP-8387-[18] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 5022 643 | COVER PROFILE, AP3 | 30 | 30 | 0 | 6100K023 | PO-SEP-8417-[9] | PO | 2025-11-30 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Phoenix Contact Trading LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 550 | 550 | 0 | 6100K023 | PO-SEP-8417-[10] | PO | 2025-11-30 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Phoenix Contact Trading LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 5217 708-3 | M.CONTACT/HAN-E16M/09330162601 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8368-[12] | PO | 2025-12-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 5217 708-7 | F.CONTACT/HAN-E16F/09330162701 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8368-[8] | PO | 2025-12-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 593503001 | ROLLER | 26 | 26 | 0 | 6100K023 | PO-SEP-8387-[19] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 593509/001 | COMPRESSION SPRING | 62 | 62 | 0 | 6100K023 | PO-SEP-8483-[6] | PO | 2025-12-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AB KOMPONENTY s.r.o. | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 9ABA450060P0004 | NUT_ISO7040_M6-8/A3K | 22 | 22 | 0 | 6100K023 | PO-SEP-8680-[34] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 9ABA450060P0005 | NUT_ISO7040_M8-8/A3K | 70 | 10 | 60 | 6100KDP01 | PO-SEP-6812-[62] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 9ABA450060P0005 | NUT_ISO7040_M8-8/A3K | 60 | 60 | 0 | 6100KDP01 | PO-SEP-8378-[183] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 9ADJ100023P0357 | BLIND_RIVET_ISO15979_6,4x16-ST/ST | 156 | 156 | 0 | 6100KDP01 | PO-SEP-8378-[204] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 11342 2100-10 | ANCHOR NUT M10X65 (DOWEL) | 140 | 140 | 0 | 6100KDP01 | PO-SEP-8680-[51] | PO | 2025-11-17 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2093 7000-6N | RAYCHEM SHRINKABLE TUBE, BPTM 120/50-A/U | 8.94 | 8.94 | 0 | 6100KDP01 | PO-SEP-8393-[4] | PO | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Saudi Electrical Supply Co Sesco | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 315 | 30 | 285 | 6100K023 | PO-SEP-8925-[6] | PO | 2025-09-21 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Sana For Electric And Telephone Co
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 285 | 285 | 0 | 6100KDP01 | PO-SEP-8925-[4] | PO | 2025-10-05 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Sana For Electric And Telephone Co
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 155 | 155 | 0 | 6100KDP01 | PO-SEP-8388-[31] | PO | 2025-10-30 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8379-[46] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8379-[27] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 42 | 42 | 0 | 6100KDP01 | PO-SEP-8379-[26] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-1865-02 | YELLOW TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 190 | 0 | 190 | PR Required | - | PR |  | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-1865-04 | BLACK TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 230 | 70 | 160 | 6100K023 | PO-SEP-8404-[1] | PO | 2025-09-18 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-1865-04 | BLACK TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 160 | 0 | 160 | PR Required | - | PR |  | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-1865-05 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 230 | 0 | 230 | PR Required | - | PR |  | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-1865-13 | BLACK TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 230 | 70 | 160 | 6100K023 | PO-SEP-8404-[2] | PO | 2025-09-18 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-1865-13 | BLACK TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 160 | 0 | 160 | PR Required | - | PR |  | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 460 | 460 | 0 | 6100KDP01 | PO-SEP-8378-[232] | PO | 2025-11-17 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 80 | 80 | 0 | 6100K025 | PO-SEP-8834-[15] | PO | 2025-10-23 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Dalian Jinda Industry Co.,Ltd
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 15.26 | 15.26 | 0 | 6100K023 | PO-SEP-8384-[1] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | DIRAK MIDDLE EAST FZE | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2522-2000-01 | HOOD HAN-E16,09300161520 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8368-[11] | PO | 2025-12-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 3 | 3 | 0 | 6100K021 | PO-SEP-8754-[1] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301,HAN-E16 (standard) | 4 | 4 | 0 | 6100K025 | PO-SEP-8754-[2] | PO | 2025-12-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 22 | 22 | 0 | 6100K023 | PO-SEP-8403-[1] | PO | 2025-09-18 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 22 | 22 | 0 | 6100K025 | PO-SEP-8831-[1] | PO | 2025-11-12 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | First Telecom Industries
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE5295-2000-08 | POST INSULATOR h=50mm (2035679) | 6 | 6 | 0 | 6100K023 | PO-SEP-8389-[4] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 710 | 710 | 0 | 6100K023 | PO-SEP-8417-[11] | PO | 2025-11-30 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Phoenix Contact Trading LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS | 500 | 25-10-2025
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE5849-2100-013 | CASTER WHEEL 100X30-50 (LOCKABLE) | 16 | 0 | 16 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE8004633P0101 | ANGLE LEFT ( POLY )(GCE8004633P0101) | 4 | 0 | 4 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE8004633P0102 | ANGLE RIGHT ( POLY ) (GCE8004633P0102) | 4 | 0 | 4 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE8004633P0111 | ANGLE LEFT ( POLY ) (GCE8004633P0111) | 4 | 0 | 4 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE8004633P0112 | ANGLE RIGHT ( POLY ) (GCE8004633P0112) | 4 | 0 | 4 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 23 | 23 | 0 | 6100K023 | PO-SEP-8379-[16] | PO | 2025-10-30 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | BM0145-1373-ASY | STEP LADDER SCECO CENTRAL (STANDARD) | 1 | 0 | 1 | PR Required | - | PR |  | LAX-COM |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | CDX7005632R1A | EARTHING CONTACT COMPLETE | 42 | 42 | 0 | 6100KDP01 | PO-SEP-8387-[27] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | CDXN010061R1103 | HANDLE COMPLETE | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8387-[31] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-233 | BOLT HEX HEAD M5X30 | 16 | 0 | 16 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 46 | 46 | 0 | 6100KDP01 | PO-SEP-8378-[212] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8378-[185] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-419 | BOLT HEX HEAD M8X45 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8378-[305] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-494 | BOLT HEX HEAD M10X35 | 18 | 6 | 12 | 6100KDP01 | PO-SEP-6812-[126] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-494 | BOLT HEX HEAD M10X35 | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8378-[247] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-508 | BOLT HEX HEAD M10X130 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-6812-[128] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 63 | 63 | 0 | 6100KDP01 | PO-SEP-8378-[169] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-659 | BOLT HEX HEAD M20X45 | 30 | 30 | 0 | 6100KDP01 | PO-SEP-8378-[205] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-660 | BOLT HEX HEAD M20X50 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-6812-[122] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2016-666 | BOLT HEX HEAD M20X90 | 36 | 36 | 0 | 6100KDP01 | PO-SEP-8378-[201] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2017-659 | BOLT HEX HEAD H D M20X45 | 6 | 6 | 0 | 6100K023 | PO-SEP-8680-[22] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2452-293 | SCREW CROSS REC.HEAD M4X16 | 16 | 4 | 12 | 6100KDP01 | PO-SEP-6812-[52] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2452-293 | SCREW CROSS REC.HEAD M4X16 | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8680-[13] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 1299 | 1299 | 0 | 6100KDP01 | PO-SEP-8680-[9] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 108 | 12 | 96 | 6100KDP01 | PO-SEP-6812-[50] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 96 | 96 | 0 | 6100KDP01 | PO-SEP-8378-[194] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-291 | BOLT SOCKET CAP HEAD M4X12 | 20 | 8 | 12 | 6100KDP01 | PO-SEP-8168-[202] | PO | 2025-09-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-291 | BOLT SOCKET CAP HEAD M4X12 | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8378-[343] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-325 | BOLT SOCKET CAP M5X10 | 18 | 8 | 10 | 6100KDP01 | PO-SEP-6812-[96] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-325 | BOLT SOCKET CAP M5X10 | 10 | 4 | 6 | 6100KDP01 | PO-SEP-8168-[210] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-325 | BOLT SOCKET CAP M5X10 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8378-[186] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-371 | BOLT SOCKET CAP M6X20 | 10 | 10 | 0 | 6100KDP01 | PO-SEP-8378-[246] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-372 | BOLT SOCKET CAP M6X25 | 4 | 1 | 3 | 6100KDP01 | PO-SEP-6812-[94] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-372 | BOLT SOCKET CAP M6X25 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8378-[187] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-430 | BOLT SOCKET CAP HEAD M6X50 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8168-[212] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 156 | 156 | 0 | 6100KDP01 | PO-SEP-8378-[252] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 1797 | 1797 | 0 | 6100KDP01 | PO-SEP-8378-[164] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 940 | 940 | 0 | 6100KDP01 | PO-SEP-8378-[178] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 256 | 20 | 236 | 606PD013 | PO-SEP-8168-[213] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 236 | 236 | 0 | 6100K023 | PO-SEP-8378-[114] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-457 | BOLT SOCKET CAP M8X35 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-6812-[92] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 44 | 44 | 0 | 6100KDP01 | PO-SEP-8680-[17] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 63 | 63 | 0 | 6100KDP01 | PO-SEP-8378-[214] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 138 | 138 | 0 | 6100KDP01 | PO-SEP-8378-[215] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 949 | 230 | 719 | 6100KDP01 | PO-SEP-6812-[100] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 719 | 719 | 0 | 6100KDP01 | PO-SEP-8378-[182] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 224 | 28 | 196 | 6100KDP01 | PO-SEP-6812-[116] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 196 | 196 | 0 | 6100KDP01 | PO-SEP-8378-[167] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 385 | 385 | 0 | 6100KDP01 | PO-SEP-8378-[173] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-499 | BOLT SOCKET CAP HEAD M10X40 | 27 | 27 | 0 | 6100KDP01 | PO-SEP-6812-[114] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-500 | BOLT SOCKET CAP HEAD M10X45 | 378 | 378 | 0 | 6100KDP01 | PO-SEP-8378-[203] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-531 | BOLT SOCKET CAP M12X16 (C.H.) | 21 | 21 | 0 | 6100K023 | PO-SEP-8378-[32] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 33 | 15 | 18 | 6100KDP01 | PO-SEP-6812-[98] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8378-[245] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 15 | 13 | 2 | 6100K023 | PO-SEP-8378-[123] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8378-[248] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 541 | 541 | 0 | 6100KDP01 | PO-SEP-8378-[174] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-540 | BOLT SOCKET CAP HEAD M12X40 | 13 | 13 | 0 | 6100KDP01 | PO-SEP-8680-[46] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 240 | 240 | 0 | 6100KDP01 | PO-SEP-8378-[210] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-542 | BOLT SOCKET CAP HEAD M12X50 | 42 | 42 | 0 | 6100KDP01 | PO-SEP-8378-[179] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-544 | BOLT SOCKET CAP HEAD M12X60 | 60 | 60 | 0 | 6100KDP01 | PO-SEP-8680-[16] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 318 | 318 | 0 | 6100KDP01 | PO-SEP-8378-[157] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-628 | BOLT SOCKET CAP HEAD M16X40 | 24 | 21 | 3 | 6100KDP01 | PO-SEP-8378-[243] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2519-628 | BOLT SOCKET CAP HEAD M16X40 | 3 | 3 | 0 | 6100K023 | PO-SEP-8378-[37] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 128 | 128 | 0 | 6100K023 | PO-SEP-8680-[38] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 626 | 626 | 0 | 6100KDP01 | PO-SEP-8680-[3] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 265 | 265 | 0 | 6100KDP01 | PO-SEP-8378-[254] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 843-1 | RIVET NUT M6 (HEXAGONAL) | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8378-[329] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2151 2062-136 | WASHER FLAT BRIR 4.3X8X0.8 | 153 | 153 | 0 | 6100K023 | PO-SEP-8680-[42] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 721 | 69 | 652 | 6100KDP01 | PO-SEP-6812-[26] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 652 | 34 | 618 | 606PD013 | PO-SEP-6812-[152] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 618 | 618 | 0 | 6100KDP01 | PO-SEP-8378-[249] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 90 | 90 | 0 | free_stock | PO-SEP-8044-[11] | PO | 2025-07-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Raja Procuremnet Local Purchases
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 184 | 8 | 176 | 6100KDP01 | PO-SEP-6812-[24] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 176 | 176 | 0 | 6100KDP01 | PO-SEP-8378-[213] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2151 2063-177 | WASHER FLAT H D GALV 13X29X2 | 32 | 0 | 32 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 1519 | 1519 | 0 | 6100K023 | PO-SEP-8378-[49] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 1380 | 1380 | 0 | 6100KDP01 | PO-SEP-8378-[170] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 618 | 618 | 0 | 6100KDP01 | PO-SEP-8378-[257] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 129 | 27 | 102 | 6100KDP01 | PO-SEP-6812-[2] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 102 | 102 | 0 | 6100KDP01 | PO-SEP-8378-[202] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 360 | 65 | 295 | 6100KDP01 | PO-SEP-6812-[10] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 295 | 16 | 279 | 606PD013 | PO-SEP-6812-[150] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 279 | 8 | 271 | 606PD013 | PO-SEP-8834-[22] | PO | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Dalian Jinda Industry Co.,Ltd
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 271 | 271 | 0 | 6100KDP01 | PO-SEP-8378-[175] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 3735 | 318 | 3417 | 606PD013 | PO-SEP-6812-[142] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 3417 | 20 | 3397 | 606PD013 | PO-SEP-8168-[214] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 3397 | 4 | 3393 | 606PD013 | PO-SEP-8834-[23] | PO | 2025-11-03 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Dalian Jinda Industry Co.,Ltd
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 3393 | 3393 | 0 | 6100KDP01 | PO-SEP-8378-[163] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 9200 | 9200 | 0 | 6100KDP01 | PO-SEP-8378-[234] | PO | 2025-11-17 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 996 | 996 | 0 | 6100K025 | PO-SEP-8925-[1] | PO | 2025-10-23 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Sana For Electric And Telephone Co
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 924 0010 | Combiflex wire Socket 1.5mm 1MRK002136-B | 3800 | 3800 | 0 | 6100KDP01 | PO-SEP-8366-[16] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 924 0020 | Combiflex wire Socket 2.5mm 1MRK002136-E | 2600 | 2600 | 0 | 6100K025 | PO-SEP-8751-[16] | PO | 2025-12-31 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 6 | 6 | 0 | 6100K021 | PO-SEP-8757-[2] | PO | 2025-12-15 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Shanghai Feili Xuncheng Electrical Technology Co.,Ltd | Snap action Switch
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0068009P0100 | BUSHING D8/3 PVC | 18 | 18 | 0 | 6100K023 | PO-SEP-8755-[4] | PO | 2025-12-31 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | MESAN KİLİT A.Ş.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0305850P0100 | POLYAMID BOLT M6X20 | 57 | 57 | 0 | 6100KDP01 | PO-SEP-8378-[235] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0305871P0100 | HEX BOLT M8X16 DIN 933-POLY | 142 | 142 | 0 | 6100K023 | PO-SEP-8378-[297] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 154 | 154 | 0 | 6100KDP01 | PO-SEP-8378-[198] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0316044P0100 | HEAD SCREW M8X50, DIN 603-4.3 | 40 | 40 | 0 | 6100K023 | PO-SEP-8629-[14] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | FLY METALTECH TRADING CO.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 44 | 44 | 0 | 6100KDP01 | PO-SEP-8629-[5] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | FLY METALTECH TRADING CO.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0336970P0100 | BOLT,TAPTITE HEX BOLT M5X12 | 6 | 6 | 0 | 6100K023 | PO-SEP-8385-[230] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0336985P0100 | TAPPING SCREW M6X16/6KTHEAD | 9 | 7 | 2 | 6100K023 | PO-SEP-8378-[57] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0336985P0100 | TAPPING SCREW M6X16/6KTHEAD | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8378-[177] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0352913P0100 | NUT M10 DIN 555-Polyamide | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8680-[8] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0365304P0100 | NUT,HEX.NUT MPG 16 | 4 | 2 | 2 | 6100KDP01 | PO-SEP-6812-[64] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0365304P0100 | NUT,HEX.NUT MPG 16 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8378-[219] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0367309P0100 | HEX. NUT M6, DIN 985-6 ( LOCK NUT ) | 10 | 10 | 0 | 6100K023 | PO-SEP-8378-[294] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0367402P0100 | HEX. NUT M4, DIN 6925-13 ( LOCK NUT ) | 4 | 4 | 0 | 6100KDP01 | PO-SEP-6812-[78] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0367406P0100 | HEX. NUT M10, (LOCK NUT ) | 16 | 0 | 16 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369010P0100 | RIVET NUT M6X16 WITH GROOVE | 57 | 57 | 0 | 6100KDP01 | PO-SEP-8378-[330] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 1063 | 1063 | 0 | 6100KDP01 | PO-SEP-8378-[168] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 358 | 358 | 0 | 6100K023 | PO-SEP-8378-[61] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369215P0100 | RIVET NUT , M12 | 32 | 0 | 32 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 849 | 285 | 564 | 6100KDP01 | PO-SEP-6812-[82] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 564 | 46 | 518 | 606PD013 | PO-SEP-6812-[144] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 518 | 16 | 502 | 606PD013 | PO-SEP-8168-[217] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 502 | 502 | 0 | 6100KDP01 | PO-SEP-8378-[162] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 235 | 235 | 0 | 6100KDP01 | PO-SEP-8378-[165] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0401027P0100 | WASHER FLAT 10.5,DIN433-ST | 136 | 136 | 0 | 6100KDP01 | PO-SEP-8378-[196] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0402008P0100 | WASHER, A5., DIN 125-ST | 16 | 0 | 16 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0402909P0100 | WASHER POLYAMID, A6.4, DIN 125 | 57 | 57 | 0 | 6100KDP01 | PO-SEP-8629-[1] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | FLY METALTECH TRADING CO.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0402911P0100 | WASHER POLYAMID, A8.4, DIN 125 | 394 | 394 | 0 | 6100K023 | PO-SEP-8378-[65] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0402912P0100 | WASHER POLYAMID, A10.5, DIN 125 | 312 | 312 | 0 | 6100KDP01 | PO-SEP-8378-[293] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0410004P0100 | SPRING RING A3, DIN 127-FST | 20 | 10 | 10 | 6100K023 | PO-SEP-8385-[231] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0410004P0100 | SPRING RING A3, DIN 127-FST | 10 | 8 | 2 | 6100KDP01 | PO-SEP-8877-[8] | PO | 2025-09-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0410004P0100 | SPRING RING A3, DIN 127-FST | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[149] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0412007P0100 | SPRING RING 10 DIN 7980-FST | 72 | 72 | 0 | 6100KDP01 | PO-SEP-8378-[244] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0413160P0100 | RETAINING WASHER VS5 | 22 | 22 | 0 | 6100K023 | PO-SEP-8385-[300] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0413167P0100 | WASHER VS12 - FST | 4 | 4 | 0 | 6100KDP01 | PO-SEP-6812-[14] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0413307P0100 | CONTACT WASHER 12 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8378-[350] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 89 | 12 | 77 | 6100KDP01 | PO-SEP-6812-[4] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 77 | 77 | 0 | 6100KDP01 | PO-SEP-8629-[10] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | FLY METALTECH TRADING CO.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0418203P0100 | WASHER,RETAINING 6, WN418-FST | 96 | 96 | 0 | 6100K023 | PO-SEP-8378-[295] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0418204P0100 | WASHER RETAINING 8/WN 418-FST | 27 | 27 | 0 | 6100K023 | PO-SEP-8680-[43] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0418205P0100 | WASHER RETAINING 10, WN418-FST | 84 | 84 | 0 | 6100KDP01 | PO-SEP-8378-[197] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0422013P0100 | WASHER,RETAINING 16X1 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8378-[323] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0438423P0100 | SPRING PIN 3X16 | 12 | 8 | 4 | 6100KDP01 | PO-SEP-6812-[44] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0438423P0100 | SPRING PIN 3X16 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8629-[6] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | FLY METALTECH TRADING CO.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0438425P0100 | SPRING PIN SLOTTED 3X20 (EQUIV.=28272) | 24 | 18 | 6 | 6100K023 | PO-SEP-8385-[3] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0438425P0100 | SPRING PIN SLOTTED 3X20 (EQUIV.=28272) | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8385-[199] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0457035P0100 | BLIND RIVET 5X10 AL | 238 | 238 | 0 | 6100KDP01 | PO-SEP-8378-[331] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0457038P0100 | BLIND RIVET 5X16, CIECO, WN457-ALU | 112 | 112 | 0 | 6100KDP01 | PO-SEP-8378-[334] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0457040P0100 | BLIND RIVET 6.4X12 STEEL | 201 | 201 | 0 | 6100KDP01 | PO-SEP-8378-[335] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0518520P0101 | ATTENTION SIGN (SEGNALE DI PERICOLO) | 3 | 2 | 1 | 6100KDP01 | PO-SEP-6543-[63] | PO | 2025-12-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | Labels for outdoor
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0518520P0101 | ATTENTION SIGN (SEGNALE DI PERICOLO) | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[425] | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0909121P0100 | STRAIN RELIEF TYPE ZE2/10 | 8 | 6 | 2 | 6100K023 | PO-SEP-8385-[5] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0909121P0100 | STRAIN RELIEF TYPE ZE2/10 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[150] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0909123P0100 | PLUG-IN CONNECTION - 645060000 | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0909124P0100 | BUSH STV2/10 ORDER.NO. 0645160000 | 10 | 0 | 10 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0931008P0100 | POST TYPE INSULATOR 12kV SIZE B 2040384 | 27 | 21 | 6 | 6100KDP01 | PO-SEP-8389-[9] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0931008P0100 | POST TYPE INSULATOR 12kV SIZE B 2040384 | 6 | 6 | 0 | 606PD013 | PO-SEP-8389-[7] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0990014P0100 | THREADED PLATE M10 | 8 | 8 | 0 | 6100K023 | PO-SEP-8403-[14] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 23 | 23 | 0 | 6100K023 | PO-SEP-8409-[3] | PO | 2025-12-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 23 | 23 | 0 | 6100K023 | PO-SEP-8409-[3] | PO | 2025-12-15 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0990162P0102 | PANEL HEATER 240V,100W-Boxin-5MetCable | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8409-[6] | PO | 2025-12-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0990403P0100 | VENTILATOR QK08A-2EM.50.CH WITH CAPACITO | 3 | 3 | 0 | 6100K021 | PO-SEP-8748-[1] | PO | 2025-12-31 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | ZIEHL ABEGG Middle East FZE | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0990404P0100 | RADIAL FLOW FAN QK08A-2EM.35.CF | 1 | 1 | 0 | 6100K025 | PO-SEP-8748-[4] | PO | 2025-12-31 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | ZIEHL ABEGG Middle East FZE | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0996027P0100 | PROTECTION CAP M10NR.610 | 96 | 96 | 0 | 6100K023 | PO-SEP-8629-[3] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | FLY METALTECH TRADING CO.
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0998134P0100 | SEALING RUBBER | 314.61 | 314.61 | 0 | 6100KDP01 | PO-SEP-8394-[2] | PO | 2025-12-15 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Suzhou Dirak Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0998162P0100 | REDUCING RING PVC | 401 | 401 | 0 | 6100K023 | PO-SEP-8385-[10] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE0998168P0100 | PLASTIC BUSHING EK/G36 | 3 | 3 | 0 | 6100K023 | PO-SEP-8385-[11] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4395060P0100 | WASHER,PLAIN , LARGE 6.1/18X1 | 40 | 24 | 16 | 6100KDP01 | PO-SEP-6812-[6] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4395060P0100 | WASHER,PLAIN , LARGE 6.1/18X1 | 16 | 16 | 0 | 6100KDP01 | PO-SEP-8378-[351] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4395592P0100 | WASHER FLAT 8 X 11 X 0.5 MM | 150 | 150 | 0 | 6100K023 | PO-SEP-8378-[70] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4395856P0100 | PLAIN WASHER, LARGE 6.2x12x0.2 | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8378-[218] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4396016P0100 | PLAIN WASSHER 9/33X2.5 | 8 | 8 | 0 | 6100K023 | PO-SEP-8378-[156] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4396073P0100 | WASHER LARG PLN (12.1/23.5X2.5 | 20 | 12 | 8 | 6100KDP01 | PO-SEP-8378-[191] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4396073P0100 | WASHER LARG PLN (12.1/23.5X2.5 | 8 | 8 | 0 | 6100K023 | PO-SEP-8378-[72] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4530250P0100 | DESIGNATION LABEL L1 (RED) | 25 | 25 | 0 | 6100KDP01 | PO-SEP-8379-[31] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4530251P0100 | DESIGNATION LABEL L2 (YELLOW) | 25 | 25 | 0 | 6100KDP01 | PO-SEP-8379-[32] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4530252P0100 | DESIGNATION LABEL L3 (BLUE) | 25 | 25 | 0 | 6100KDP01 | PO-SEP-8379-[33] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8379-[36] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4539452P0100 | INDICATION LABEL Mech.Operation STICKER | 29 | 29 | 0 | 6100KDP01 | PO-SEP-8379-[28] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4539457P0101A | INFORMATION PLATE ( LOCAL ) | 12 | 0 | 12 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE4539458P0101A | INFORMATION PLATE ( LOCAL ) | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000496P0102 | TORSION SPRING | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8387-[20] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000497R0101 | BEARING HOUSING COMPLETE | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8387-[30] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000508P0101 | GROOVED PIN | 44 | 41 | 3 | 6100KDP01 | PO-SEP-8523-[11] | PO | 2025-10-23 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000508P0101 | GROOVED PIN | 3 | 3 | 0 | 6100K023 | PO-SEP-8704-[2] | PO | 2025-11-12 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000525P0101 | WASHER,STOP | 22 | 22 | 0 | 6100K023 | PO-SEP-8385-[301] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000541P0101P | ADJUSTING RING | 8 | 0 | 8 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000542P0101 | BUSH D10/6.2X15 | 16 | 0 | 16 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000552P0101 | STOP WASHER | 88 | 82 | 6 | 6100KDP01 | PO-SEP-8378-[241] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000552P0101 | STOP WASHER | 6 | 6 | 0 | 6100K023 | PO-SEP-8378-[74] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000663R0101 | BEVEL GEAR DRIVE FOR EK6 ZS1 | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8397-[5] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000847P0101P | K - STUD | 8 | 4 | 4 | 6100K023 | PO-SEP-8385-[87] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000847P0101P | K - STUD | 4 | 2 | 2 | 6100KDP01 | PO-SEP-8877-[3] | PO | 2025-09-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7000847P0101P | K - STUD | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[281] | PO | 2025-10-19 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7001732R0105 | EARTHING SWITCH: EK6/ZS1-1710-275 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8382-[5] | PO | 2026-01-22 | A |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | Earthing Switch/6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7001732R0106 | EARTHING SWITCH: EK6-ZS1-1710-210 | 2 | 2 | 0 | 6100K023 | PO-SEP-8382-[2] | PO | 2026-01-22 | A |  | - | 2026-03-07 | 2026-02-21 | 0 | Abb Electrical Industriesco | Earthing Switch/6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003008P0101 | RING | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8387-[21] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003012P0101P | TUBE 8X5.1X25 | 8 | 4 | 4 | 6100K023 | PO-SEP-8385-[88] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003012P0101P | TUBE 8X5.1X25 | 4 | 2 | 2 | 6100KDP01 | PO-SEP-8877-[4] | PO | 2025-09-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003012P0101P | TUBE 8X5.1X25 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[282] | PO | 2025-10-19 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003536P0101 | DETENT | 8 | 0 | 8 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003544P0101 | SPINDLE | 7 | 0 | 7 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003553P0101P | HEXAGON BOLT | 16 | 6 | 10 | 6100KDP01 | PO-SEP-8680-[49] | PO | 2025-10-19 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003553P0101P | HEXAGON BOLT | 10 | 2 | 8 | 6100KDP01 | PO-SEP-8168-[207] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003553P0101P | HEXAGON BOLT | 8 | 4 | 4 | 6100K023 | PO-SEP-8680-[26] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003553P0101P | HEXAGON BOLT | 4 | 0 | 4 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003556P0101 | SLIDE | 17 | 0 | 17 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003557P0101 | SLIDE | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003568P0101 | NUT SPECIAL | 8 | 0 | 8 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003578P0101 | SQUARE BOLT 4KT8/20 | 16 | 2 | 14 | 6100KDP01 | PO-SEP-8057-[1] | PO | 2025-09-20 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003578P0101 | SQUARE BOLT 4KT8/20 | 14 | 3 | 11 | 6100KDP01 | PO-SEP-8396-[46] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003578P0101 | SQUARE BOLT 4KT8/20 | 11 | 2 | 9 | 6100K023 | PO-SEP-8396-[17] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003578P0101 | SQUARE BOLT 4KT8/20 | 9 | 0 | 9 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003579P0101 | TENSION SPRING 6.5/.9/30/16 | 33 | 33 | 0 | 6100KDP01 | PO-SEP-8396-[38] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003579P0102 | TENSION SPRING 6.5/.9/30/16 | 8 | 0 | 8 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003581P0101 | COMPRESSION SPRING 7.5/0,8/9/25 | 16 | 0 | 16 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003582P0101 | NUT | 16 | 0 | 16 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003694P0102 | CARRIER | 42 | 41 | 1 | 6100KDP01 | PO-SEP-8397-[6] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7003694P0102 | CARRIER | 1 | 1 | 0 | 6100K023 | PO-SEP-8397-[2] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7107642P0100 | TENSION SPRING 8.9/0.7/35/10 | 8 | 0 | 8 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7109399R0101 | AUXILIARY SWITCH 5NO | 44 | 44 | 0 | 6100KDP01 | PO-SEP-8409-[7] | PO | 2025-12-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7109399R0106 | AUXILIARY SWITCH 5NC | 16 | 16 | 0 | 6100K023 | PO-SEP-8385-[25] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7109399R0118 | SLIDE F.AUX.SWICH 5NC | 3 | 3 | 0 | 6100K023 | PO-SEP-8385-[26] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7192037R0100 | INSULATOR SGB 24N A1 POT 24kV 2040742 | 15 | 13 | 2 | 6100K023 | PO-SEP-8389-[1] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7192037R0100 | INSULATOR SGB 24N A1 POT 24kV 2040742 | 2 | 1 | 1 | 6100KDP01 | PO-SEP-8389-[5] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7192037R0100 | INSULATOR SGB 24N A1 POT 24kV 2040742 | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[234] | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7204654P0101 | BOLT 7/4X15 | 22 | 16 | 6 | 6100K023 | PO-SEP-8385-[233] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7204654P0101 | BOLT 7/4X15 | 6 | 4 | 2 | 6100KDP01 | PO-SEP-8877-[7] | PO | 2025-09-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7204654P0101 | BOLT 7/4X15 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[191] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7208367P0100 | DESIGNATION LABEL | 45 | 40 | 5 | 6100K023 | PO-SEP-8379-[9] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7208367P0100 | DESIGNATION LABEL | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8379-[34] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE7208368P0100 | DESIGNATION LABEL | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8379-[35] | PO | 2025-10-30 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8000633P0113P | MOUNTING CHANNEL 760mm (GCE8000633P0113) | 8 | 8 | 0 | 6100K023 | PO-SEP-8385-[42] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8000801P0101P | CONTACT PIN, RD.79MM L=107MM | 12 | 6 | 6 | 6100K023 | PO-SEP-8385-[118] | PO | 2025-09-21 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8000801P0101P | CONTACT PIN, RD.79MM L=107MM | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8385-[176] | PO | 2025-10-05 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8000881P0102 | INTERMEDITE PLATE 80x15x125 CU SILVERPLA | 12 | 6 | 6 | 6100K023 | PO-SEP-8385-[72] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8000881P0102 | INTERMEDITE PLATE 80x15x125 CU SILVERPLA | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8385-[204] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8001698R0107P | LEVER MECHANISM LEFT-SX 2X R250/55(w1000 | 3 | 3 | 0 | 6100K023 | PO-SEP-8385-[113] | PO | 2025-09-21 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8001698R0108P | LEVER MECHANISM RIGHT,DX2X R250/55(w1000 | 3 | 3 | 0 | 6100K023 | PO-SEP-8385-[114] | PO | 2025-09-21 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8001710P0101 | SPECIAL BOLT | 8 | 6 | 2 | 6100K023 | PO-SEP-8403-[11] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8001710P0101 | SPECIAL BOLT | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8403-[15] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8001975P0101 | WASHER 40X21X10 (LOCAL PUR) | 18 | 12 | 6 | 6100K023 | PO-SEP-8924-[2] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | ALAM AL NIMA TRADING EST
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8001975P0101 | WASHER 40X21X10 (LOCAL PUR) | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8378-[363] | PO | 2025-11-17 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8001976P0101 | WASHER 40X21X2 | 15 | 15 | 0 | 6100KDP01 | PO-SEP-6812-[28] | PO | 2025-08-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8002371P0101 | BOLT GUIDE | 4 | 2 | 2 | 6100K023 | PO-SEP-8385-[105] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8002371P0101 | BOLT GUIDE | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[246] | PO | 2025-10-12 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8002757P0107 | COVER | 12 | 6 | 6 | 6100K023 | PO-SEP-8385-[73] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8002757P0107 | COVER | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8385-[203] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8002866R0102P | PADLOCK ES - NORMAL | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8396-[37] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003638P0103P | INTER LOCKING AGLE LEFT | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8396-[33] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003638P0104P | INTERLOCKING ANGLE RIGHT | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8396-[42] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003671P0102 | SPECIAL SCREW M12 X 50/20 | 4 | 2 | 2 | 6100K023 | PO-SEP-8403-[13] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003671P0102 | SPECIAL SCREW M12 X 50/20 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8403-[16] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003671P0116 | SPCEIAL SCREW M12X34/45 | 68 | 68 | 0 | 6100K023 | PO-SEP-8523-[3] | PO | 2025-10-23 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003899R0101 | SPOUT 12KV, >2500A | 12 | 6 | 6 | 6100K023 | PO-SEP-8381-[4] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Europroxy FZCO | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003899R0101 | SPOUT 12KV, >2500A | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[370] | PR |  | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003900P0101 | COVER FOR SPOUT | 12 | 6 | 6 | 6100KDP01 | PO-SEP-8385-[202] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003900P0101 | COVER FOR SPOUT | 6 | 6 | 0 | 606PD013 | PO-SEP-8385-[234] | PO | 2025-10-14 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8003900P0102 | COVER FOR SPOUT | 30 | 30 | 0 | 6100KDP01 | PO-SEP-8385-[133] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 23 | 23 | 0 | 6100K023 | PO-SEP-8387-[8] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004437P0103P | SHROUD (EARTHING CONTACT)GCE8004437P0103 | 32 | 6 | 26 | 6100K023 | PO-SEP-8385-[78] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004437P0103P | SHROUD (EARTHING CONTACT)GCE8004437P0103 | 26 | 26 | 0 | 6100KDP01 | PO-SEP-8385-[206] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004471R0101P | ELECTRODE, ZS1 95kV BIL | 21 | 18 | 3 | 6100KDP01 | PO-SEP-8385-[135] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004471R0101P | ELECTRODE, ZS1 95kV BIL | 3 | 3 | 0 | free_stock | PR-SEP-0024114-[254] | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004626P0101 | SPACER 40 X 20 X 92 | 4 | 0 | 4 | PR Required | - | PR |  | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004633P0111 | ANGLE LEFT ( POLY ) | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004633P0112 | ANGLE RIGHT ( POLY ) | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004944R0101 | SPOUT ZS1 (4000A) | 30 | 18 | 12 | 6100K023 | PO-SEP-8381-[3] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Europroxy FZCO | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004944R0101 | SPOUT ZS1 (4000A) | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8381-[7] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Europroxy FZCO | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8004990P0101 | CARRIER FOR BUSBAR SHROUD | 3 | 0 | 3 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005041P0101P | CONTACT PIN 109mm,3150A(GCE8005041P0101) | 30 | 30 | 0 | 6100KDP01 | PO-SEP-8385-[177] | PO | 2025-10-05 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005042P0101 | CONNECTION PIECE 3150A ZS1 | 15 | 15 | 0 | 6100KDP01 | PO-SEP-8385-[178] | PO | 2025-10-05 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005049P0101 | SUPPORT (POLY ) T = SHAPE | 12 | 9 | 3 | 6100KDP01 | PO-SEP-8396-[36] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005049P0101 | SUPPORT (POLY ) T = SHAPE | 3 | 3 | 0 | 6100K023 | PO-SEP-8396-[5] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005112P0103P | OPERATING BOLT | 10 | 8 | 2 | 6100KDP01 | PO-SEP-8385-[190] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005112P0103P | OPERATING BOLT | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[260] | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005117P0101 | CARRIER | 20 | 12 | 8 | 6100K023 | PO-SEP-8505-[1] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | WORKSTEEL s.r.o. | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005117P0101 | CARRIER | 8 | 4 | 4 | 6100KDP01 | PO-SEP-8505-[2] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | WORKSTEEL s.r.o. | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005117P0101 | CARRIER | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[261] | PR |  | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005136P0101 | SUPPORT (POLY) | 6 | 6 | 0 | 6100K023 | PO-SEP-8396-[14] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005164P0101 | SCREENING | 90 | 90 | 0 | 6100KDP01 | PO-SEP-8385-[208] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005595R0102P | BUSBAR ZS D100, 12THICK,800/800, L=795 | 84 | 84 | 0 | 6100K023 | PO-SEP-8385-[122] | PO | 2025-09-21 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005595R0109P | Busbar D100,12mm Thick 800/1000,L=830 | 14 | 12 | 2 | 6100K023 | PO-SEP-8385-[123] | PO | 2025-09-21 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005595R0109P | Busbar D100,12mm Thick 800/1000,L=830 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[250] | PO | 2025-10-12 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005595R0110P | Busbar D100,12mm Thick 800/1000,L=895 | 14 | 12 | 2 | 6100K023 | PO-SEP-8385-[124] | PO | 2025-09-21 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005595R0110P | Busbar D100,12mm Thick 800/1000,L=895 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[251] | PO | 2025-10-12 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005595R0111P | Busbar D100,12mm Thick 800/1000,L=960 | 14 | 12 | 2 | 6100K023 | PO-SEP-8385-[125] | PO | 2025-09-21 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8005595R0111P | Busbar D100,12mm Thick 800/1000,L=960 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[252] | PO | 2025-10-12 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8006587P0101 | LOCK SCREW M6X25 ( ROUND FLAT HEAD ) | 152 | 152 | 0 | 6100KDP01 | PO-SEP-8403-[5] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8007213P0101 | SHROUD ZS3.2, Middle | 15 | 15 | 0 | 6100K023 | PO-SEP-8385-[109] | PO | 2025-09-21 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8007214P0101 | COVER FOR SHROUD ZS3.2, end side | 30 | 30 | 0 | 6100K023 | PO-SEP-8385-[110] | PO | 2025-09-21 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 23 | 23 | 0 | 6100K023 | PO-SEP-8387-[9] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010004P0102 | GUIDE RAIL RIGHT 12kV | 23 | 23 | 0 | 6100K023 | PO-SEP-8387-[10] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010022P0111R | SHUTTER UPPER W800 (GCE8010022P0111) | 18 | 18 | 0 | 6100K023 | PO-SEP-8396-[10] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010022P0112Y | SHUTTER LOWER W800 (GCE8010022P0112) | 16 | 16 | 0 | 6100K023 | PO-SEP-8396-[11] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010022P0113R | SHUTTER UPPER (DWG.GCE8010022P0113) | 5 | 3 | 2 | 6100K023 | PO-SEP-8396-[6] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010022P0113R | SHUTTER UPPER (DWG.GCE8010022P0113) | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8396-[34] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010022P0114Y | SHUTTER LOWER (DWG.GCE8010022P0114) | 5 | 3 | 2 | 6100K023 | PO-SEP-8396-[7] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010022P0114Y | SHUTTER LOWER (DWG.GCE8010022P0114) | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8396-[35] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | HALB | GCE8010023P0101 | PIN (ZINC COATED) | 84 | 84 | 0 | 6100KDP01 | PO-SEP-8523-[14] | PO | 2025-10-23 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 37 | 37 | 0 | 6100K023 | PO-SEP-8396-[18] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010028R0103 | PRESSURE RELIEF FLAP W1000 | 9 | 5 | 4 | 6100K023 | PO-SEP-8396-[19] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010028R0103 | PRESSURE RELIEF FLAP W1000 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8396-[27] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010028R0105 | PRESSURE RELIEF FLAP, REAR | 5 | 3 | 2 | 6100K023 | PO-SEP-8396-[20] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010028R0105 | PRESSURE RELIEF FLAP, REAR | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8396-[25] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010028R0106 | PRESSURE RELIEF FLAP W1000 | 14 | 3 | 11 | 6100K023 | PO-SEP-8396-[21] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010028R0106 | PRESSURE RELIEF FLAP W1000 | 11 | 2 | 9 | 6100KDP01 | PO-SEP-8396-[26] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010028R0106 | PRESSURE RELIEF FLAP W1000 | 9 | 5 | 4 | free_stock | PR-SEP-0024114-[275] | PR |  | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010028R0106 | PRESSURE RELIEF FLAP W1000 | 4 | 0 | 4 | PR Required | - | PR |  | B |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010096P0101P | PIN 12DIA(ZINC COAT)DWG:GCE8010096P0101 | 4 | 2 | 2 | 6100K023 | PO-SEP-8523-[5] | PO | 2025-10-23 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010096P0101P | PIN 12DIA(ZINC COAT)DWG:GCE8010096P0101 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8704-[4] | PO | 2025-11-12 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010104P0103P | BUSHING D60/49X25 | 30 | 30 | 0 | 6100KDP01 | PO-SEP-8385-[210] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010104P0104P | BUSHING D58/47X25 | 12 | 6 | 6 | 6100K023 | PO-SEP-8387-[12] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8010104P0104P | BUSHING D58/47X25 | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[377] | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8011549P0101 | CT-COOLER (HEAT SINK) | 15 | 9 | 6 | 6100K023 | PO-SEP-8340-[2] | PO | 2025-12-20 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | AB KOMPONENTY s.r.o. | CT Cooler
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8011549P0101 | CT-COOLER (HEAT SINK) | 6 | 6 | 0 | free_stock | PO-SEP-8340-[1] | PO | 2025-12-20 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | AB KOMPONENTY s.r.o. | CT Cooler
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8011552P0102 | FLAT SCREEN FOR CB.MIDDLE PLATE W800 | 14 | 14 | 0 | 6100K023 | PO-SEP-8396-[12] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8011642P0101 | SPACER | 156 | 95 | 61 | 6100K023 | PO-SEP-8385-[54] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8011642P0101 | SPACER | 61 | 61 | 0 | 6100KDP01 | PO-SEP-8385-[154] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013263P0101 | SHROUD | 28 | 28 | 0 | 6100KDP01 | PO-SEP-8396-[44] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013412R0101 | PRESSURE RELIEF FLAP FOR W1000 | 5 | 3 | 2 | 6100K023 | PO-SEP-8396-[22] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013412R0101 | PRESSURE RELIEF FLAP FOR W1000 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8396-[28] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013419R0101 | FRAME FOR FLAT SCREEN COMPLETE | 5 | 4 | 1 | 6100KDP01 | PO-SEP-8396-[30] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013419R0101 | FRAME FOR FLAT SCREEN COMPLETE | 1 | 1 | 0 | 6100K023 | PO-SEP-8396-[8] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013430P0101 | COOLING PLATE 1 ( small ) | 15 | 15 | 0 | 6100KDP01 | PO-SEP-8385-[192] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013431P0101 | COOLING PLATE 2 ( Big ) | 15 | 15 | 0 | 6100KDP01 | PO-SEP-8385-[175] | PO | 2025-10-05 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013433P0101P | SHROUD (DWG NO. GCE8013433P0101) | 10 | 10 | 0 | 6100KDP01 | PO-SEP-8385-[167] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013434P0101P | SHROUD (DWG NO. GCE8013434P0101) | 10 | 10 | 0 | 6100KDP01 | PO-SEP-8385-[168] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013434P0102P | SHROUD (DWG NO. GCE8013434P0102) | 10 | 10 | 0 | 6100KDP01 | PO-SEP-8385-[169] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013435P0101P | SPACER DISC (GCE8013435P0101) | 80 | 48 | 32 | 6100K023 | PO-SEP-8483-[1] | PO | 2025-12-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AB KOMPONENTY s.r.o. | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013435P0101P | SPACER DISC (GCE8013435P0101) | 32 | 32 | 0 | 6100KDP01 | PO-SEP-8483-[5] | PO | 2025-12-31 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AB KOMPONENTY s.r.o. | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013444R0101 | PRESSURE RELIEF FLAP(W1000) | 5 | 3 | 2 | 6100K023 | PO-SEP-8396-[23] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8013444R0101 | PRESSURE RELIEF FLAP(W1000) | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8396-[24] | PO | 2025-11-30 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8487370R0100 | EARTHING CONTACT | 4 | 2 | 2 | 6100K023 | PO-SEP-8387-[11] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8487370R0100 | EARTHING CONTACT | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8387-[38] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 31 | 31 | 0 | 6100K023 | PO-SEP-8379-[41] | PO | 2025-10-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8684080P0101 | EARTHING STRIP | 4 | 2 | 2 | 6100KDP01 | PO-SEP-8403-[9] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8684080P0101 | EARTHING STRIP | 2 | 2 | 0 | 6100K023 | PO-SEP-8484-[1] | PO | 2025-12-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8685778P0121P | CONTACT PIN 800/1200A SIL.COAT = 72L | 6 | 3 | 3 | 6100K023 | PO-SEP-8385-[121] | PO | 2025-09-21 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE8685778P0121P | CONTACT PIN 800/1200A SIL.COAT = 72L | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8385-[278] | PO | 2025-10-19 | B |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9401556P0100 | STOP WASHER | 44 | 44 | 0 | 6100K023 | PO-SEP-8378-[326] | PO | 2025-11-17 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9401766P0107 | LOCKING MAGNET DC125 V | 22 | 22 | 0 | 6100K023 | PO-SEP-8501-[1] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Xiamen Leelen High Voltage Electric Co. Ltd | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9476775R0100 | IND.CONTACT/ VAN FLOW SWITCH | 6 | 5 | 1 | 6100KDP01 | PO-SEP-8385-[209] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9476775R0100 | IND.CONTACT/ VAN FLOW SWITCH | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[304] | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9477367P0102 | FORK D11x20 | 15 | 9 | 6 | 6100K023 | PO-SEP-8523-[1] | PO | 2025-10-23 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9477367P0102 | FORK D11x20 | 6 | 4 | 2 | 6100KDP01 | PO-SEP-8523-[8] | PO | 2025-10-23 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9477367P0102 | FORK D11x20 | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[305] | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9477394R0101 | CHARGING LEVER COMPLETE | 4 | 0 | 4 | PR Required | - | PR |  | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | GCE9478476P0101 | FIXING RING | 8 | 0 | 8 | PR Required | - | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | K016-BS3600-13.8-UCT | Bus-Tie Upper CTs | 3 | 3 | 0 | 6100k016 | PO-SEP-8248-[11] | PO | 2026-01-19 | A |  | - | 2026-03-07 | 2026-02-21 | 0 | Ritz Instrument Transformers GMBH | K016_UNITED CEMENT S/S (CT&VT)
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | K016-BS3600-13.8-UCT | Bus-Tie Upper CTs ¦ K016-BS3600-13.8-UCT ¦ Ritz | 3 | 0 | 3 | PR Required | - | PR |  | C |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | K016-CAP1250-13.8-LCT | Capacitor O/G Feeder Lower CTs ¦ K016-CAP1250-13.8-LCT ¦ Ritz | 42 | 6 | 36 | 6100k016 | PO-SEP-8248-[2] | PO | 2026-02-05 | C |  | - | 2026-03-07 | 2026-02-21 | 0 | Ritz Instrument Transformers GMBH | K016_UNITED CEMENT S/S (CT&VT)
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | K016-CAP1250-13.8-LCT | Capacitor O/G Feeder Lower CTs ¦ K016-CAP1250-13.8-LCT ¦ Ritz | 36 | 0 | 36 | PR Required | - | PR |  | C |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | K016-CAP1250-13.8-UCT | Capacitor O/G Feeder Upper CTs | 42 | 6 | 36 | 6100k016 | PO-SEP-8248-[1] | PO | 2026-02-18 | A |  | - | 2026-03-07 | 2026-02-21 | 0 | Ritz Instrument Transformers GMBH | K016_UNITED CEMENT S/S (CT&VT)
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | K016-CAP1250-13.8-UCT | Capacitor O/G Feeder Upper CTs | 36 | 0 | 36 | PR Required | - | PR |  | A |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | K016-INC3600-13.8-UCT | Incomer Upper CTs | 12 | 6 | 6 | 6100k016 | PO-SEP-8248-[5] | PO | 2026-01-19 | A |  | - | 2026-03-07 | 2026-02-21 | 0 | Ritz Instrument Transformers GMBH | K016_UNITED CEMENT S/S (CT&VT)
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | K016-INC3600-13.8-UCT | Incomer Upper CTs | 6 | 0 | 6 | PR Required | - | PR |  | A |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | K016-INC3600-13.8-UCT | Incomer Upper CTs ¦ K016-INC3600-13.8-UCT ¦ Ritz | 12 | 0 | 12 | PR Required | - | PR |  | C |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | K016-MET-13.8-VT | Incomer, BRM and BEM VTs | 66 | 12 | 54 | 6100k016 | PO-SEP-8248-[13] | PO | 2026-02-18 | A |  | - | 2026-03-07 | 2026-02-21 | 0 | Ritz Instrument Transformers GMBH | K016_UNITED CEMENT S/S (CT&VT)
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | K016-MET-13.8-VT | Incomer, BRM and BEM VTs | 54 | 0 | 54 | PR Required | - | PR |  | A |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | K016-SST630-13.8-LCT | Station AUX O/G Feeder Lower CTs ¦ K016-SST630-13.8-LCT ¦ Ritz | 6 | 6 | 0 | 6100k016 | PO-SEP-8248-[10] | PO | 2026-02-05 | C |  | - | 2026-03-07 | 2026-02-21 | 0 | Ritz Instrument Transformers GMBH | K016_UNITED CEMENT S/S (CT&VT)
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | K016-SST630-13.8-UCT | Station Aux. O/G Feeder Upper CTs | 6 | 6 | 0 | 6100k016 | PO-SEP-8248-[9] | PO | 2026-02-18 | A |  | - | 2026-03-07 | 2026-02-21 | 0 | Ritz Instrument Transformers GMBH | K016_UNITED CEMENT S/S (CT&VT)
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 46 | 46 | 0 | 6100K023 | PO-SEP-8446-[2] | PO | 2025-11-30 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Ningbo Shengjiu Technology CO., LTD. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | MV-600-A/S3/I/802 | Metrosil for Triple Pole Relay for 1A CT | 2 | 0 | 2 | PR Required | - | PR |  | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 42 | 42 | 0 | free_stock | PO-SEP-8388-[7] | PO | 2025-10-30 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | MV-ZB9016765 | resistor(0-820ohms) | 6 | 6 | 0 | 6100k016 | PO-SEP-8376-[2] | PO | 2026-01-30 | LV |  | - | 2026-03-07 | 2026-02-21 | 0 | Grid Solution Middle-East Fze | MV
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | MV2000-1685-06 | YELLOW TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 5750 | 0 | 5750 | PR Required | - | PR |  | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | MV2000-1865-01 | YELLOW TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 920 | 0 | 920 | PR Required | - | PR |  | LV |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | C&D | NO CODE | CB trolley with raise lower function | 1 | 0 | 1 | PR Required | - | PR |  | LAX-COM |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1000024P0001P | BUSHING (LOCAL PUR) | 22 | 22 | 0 | 6100K023 | PO-SEP-8484-[8] | PO | 2025-12-15 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1000026P0001P | BUSHING (LOCAL PUR) | 157 | 96 | 61 | 6100K023 | PO-SEP-8484-[2] | PO | 2025-12-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1000026P0001P | BUSHING (LOCAL PUR) | 61 | 61 | 0 | free_stock | PR-SEP-0024114-[312] | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1000047P0001 | INTERLOCKING SCOTCH | 23 | 23 | 0 | 6100K023 | PO-SEP-8523-[2] | PO | 2025-10-23 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1001813R0802P | MECHANICAL OFF BUTTON FOR VD4 - HOR | 21 | 21 | 0 | 6100K023 | PO-SEP-8385-[67] | PO | 2025-09-21 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1001915P0001P | PIN | 10 | 6 | 4 | 6100K023 | PO-SEP-8484-[9] | PO | 2025-12-15 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1001915P0001P | PIN | 4 | 2 | 2 | 6100KDP01 | PO-SEP-8484-[6] | PO | 2025-12-15 | LAX |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1001915P0001P | PIN | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[318] | PR |  | LAX |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1001916P0001P | INTERLOCK LEVER (LOCAL PUR) | 10 | 6 | 4 | 6100K023 | PO-SEP-8484-[3] | PO | 2025-12-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1001916P0001P | INTERLOCK LEVER (LOCAL PUR) | 4 | 2 | 2 | 6100KDP01 | PO-SEP-8484-[5] | PO | 2025-12-15 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1001916P0001P | INTERLOCK LEVER (LOCAL PUR) | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[319] | PR |  | C&D |  | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SCB1001982P0001 | ROLLER | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[198] | PO | 2025-10-05 | C&D |  | - | 2026-03-07 | 2026-02-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SNA234000R0200 | Marker, RC810, 1 ¦ 10/1SNA234041R2600 ¦ ENTRELEC | 230 | 230 | 0 | 6100KDP01 | PO-SEP-8386-[16] | PO | 2025-11-10 | LV | Automated: Replaced 1SNA234000R0200 by SEP20333. | - | 2026-03-07 | 2026-02-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CAB0000 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 230 | 126 | 104 | 6100KDP01 | PO-SEP-8572-[3] | PO | 2025-12-15 | LV | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-03-07 | 2026-02-21 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1YAB5355CAB0000 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 104 | 104 | 0 | 6100K020 | PO-SEP-8792-[23] | PO | 2025-12-20 | LV | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-03-07 | 2026-02-21 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | MARWI60236 | Marker, Numbering, Blank, UCT-TM 10 ¦ 0829142 ¦ PHOENIX | 276 | 276 | 0 | 6100K021 | PO-SEP-8792-[16] | PO | 2025-12-20 | LV | Automated: Replaced 1YAB5355HAB0000 by MARWI60236. Automated: Replaced 1YAB5355HAB0000 by MARWI60236. | - | 2026-03-07 | 2026-02-21 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 1SNA206394R0200 | Screw, EV6I_Screw+PstWasherIP20_M6/8.RS_M4/6.RS Type: EV6I Order no: 1SNA 206 394 R0200 Color: Grey ¦ 1SNA206394R0200 ¦ ABB | 184 | 184 | 0 | 6100KDP01 | PO-SEP-8386-[29] | PO | 2025-11-10 | LV | Automated: Replaced 1YAB5355HEA0000 by 1SNA206394R0200. Automated: Replaced 1YAB5355HEA0000 by 1SNA206394R0200. | - | 2026-03-07 | 2026-02-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | 25541 | HEX.RIVET NUT M10X24 ( 25541 ) | 837 | 837 | 0 | 6100KDP01 | PO-SEP-8645-[2] | PO | 2025-10-30 | C&D | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-03-07 | 2026-02-21 | 0 | Saeed Aziz Alsomali Trading Est
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SEP10163 | 1.5 Red Wire Gauge Tube 1.5mm² | 230 | 230 | 0 | free_stock | PR-SEP-0023081-[170] | PR |  | LV | Automated: Replaced AE2000-1865-14 by SEP10163. Automated: Replaced AE2000-1865-14 by SEP10163. | - | 2026-03-07 | 2026-02-21 | 0
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | AE2000-2150-01 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 50 | 50 | 0 | 6100KDP01 | PO-SEP-8388-[17] | PO | 2025-10-30 | C&D | Automated: Replaced AE2000-2150-01 by 1YAZ21500101. | - | 2026-03-07 | 2026-02-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2011-113 | Nut, Hexagonal Head, M4, Stainless Steel | 70 | 12 | 58 | 606PD013 | PO-SEP-6812-[156] | PO | 2025-08-31 | C&D | Automated: Replaced DMS 2126 2011-113 by DF240510018. Automated: Replaced DF240510018 by SEP10896. | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2011-113 | Nut, Hexagonal Head, M4, Stainless Steel | 58 | 4 | 54 | 6100KDP01 | PO-SEP-8168-[204] | PO | 2025-10-30 | C&D | Automated: Replaced DMS 2126 2011-113 by DF240510018. Automated: Replaced DF240510018 by SEP10896. | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | DMS 2126 2011-113 | Nut, Hexagonal Head, M4, Stainless Steel | 54 | 54 | 0 | 6100KDP01 | PO-SEP-8378-[354] | PO | 2025-11-17 | C&D | Automated: Replaced DMS 2126 2011-113 by DF240510018. Automated: Replaced DF240510018 by SEP10896. | - | 2026-03-07 | 2026-02-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SEP12186 | Lugs, Terminal Ring, 70 Sq.mm, Copper Tube Crimping ¦ China star | 44 | 44 | 0 | 6100KDP01 | PO-SEP-8834-[17] | PO | 2025-10-05 | C&D | Automated: Replaced DMS 2641 0087-19 by SEP12186. Automated: Replaced DMS 2641 0087-19 by SEP12186. | - | 2026-03-07 | 2026-02-21 | 0 | Dalian Jinda Industry Co.,Ltd
6100K016 | United_Cement : SWITCHGEAR - UNITED CEMENT | SWGR | ROH | SEP12105 | Lugs, Terminal End Sleeve, 2 x 2.5 Sq.mm, Blue Insulated ¦ CEM-PKT2512 / CT225013 ¦ Cembre | 100 | 100 | 0 | 6100K025 | PO-SEP-8894-[57] | PO | 2025-10-23 | LV | Automated: Replaced PKT 2512 by SEP12105. Automated: Replaced PKT 2512 by SEP12105. | - | 2026-03-07 | 2026-02-21 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 14 | 14 | 0 | 6100K023 | PO-SEP-8378-[229] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 20 | 20 | 0 | 6100K023 | PO-SEP-8385-[41] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 266 | 266 | 0 | 6100K023 | PO-SEP-8378-[82] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 6922 | 6922 | 0 | 6100K023 | PO-SEP-8378-[82] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 03366 | STEEL RIVETS T22205/4.8 TS | 929 | 929 | 0 | 6100K023 | PO-SEP-8378-[83] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 8 | 8 | 0 | 6100K023 | PO-SEP-8378-[84] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 420 | 420 | 0 | 6100K023 | PO-SEP-8378-[84] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 07959 | TOMMY HEAD SCREW FULL THREAD T21010/4X25 | 180 | 180 | 0 | 6100K023 | PO-SEP-8680-[31] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 08017 | TOMMY HEAD SCREW ACC T21010/M4x22 | 156 | 156 | 0 | 6100K023 | PO-SEP-8647-[14] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Mattssons Fasteners AB
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 08448 | SQUARE FASTENING NUT TS ACC T21597/5 | 164 | 164 | 0 | 6100K023 | PO-SEP-8378-[337] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 200 | 200 | 0 | 6100K023 | PO-SEP-8629-[20] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | FLY METALTECH TRADING CO.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 08856 | WASHER STEEL T22100/ 6.4 | 164 | 164 | 0 | 6100K023 | PO-SEP-8378-[92] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 09021 | SELF-LOCKING HEX. NUT,T21192/M10 (LOCAL) | 328 | 144 | 184 | 6100K023 | PO-SEP-8680-[32] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 09021 | SELF-LOCKING HEX. NUT,T21192/M10 (LOCAL) | 184 | 184 | 0 | 6100KDP01 | PO-SEP-8680-[18] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 09601 | WASHER, FLAT ACC T22000/3.2X7 | 240 | 240 | 0 | 6100K023 | PO-SEP-8378-[95] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 09929 | STEEL SPRING WASHER ACC T22104/10 | 48 | 48 | 0 | 6100K023 | PO-SEP-8378-[96] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 09947 | SPRING WASHER ACC T22104/6 | 10 | 6 | 4 | 6100KDP01 | PO-SEP-8378-[270] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 09947 | SPRING WASHER ACC T22104/6 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-6812-[43] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1000057457 | WASHER CU AL M10 | 41 | 11 | 30 | 6100K023 | PO-SEP-8385-[290] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1000057457 | WASHER CU AL M10 | 30 | 30 | 0 | 6100KDP01 | PO-SEP-8385-[227] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 12980 | COUNTERSUNK STEEL SCREW T21065/M6X14 | 82 | 82 | 0 | 6100K023 | PO-SEP-8646-[3] | PO | 2025-10-20 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 12989 | COUNTERSUNK STEEL SCREW T21065/M8X30 | 82 | 82 | 0 | 6100K023 | PO-SEP-8646-[4] | PO | 2025-10-20 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 129A539G01 | ‭FT SWITCH, (T T T T T T T T T T)/129A539G01/FT-1‬ | 51 | 51 | 0 | 6100K023 | PO-SEP-8747-[15] | PO | 2025-12-31 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 13.8-VT-ZS1-3WDG-25VA | Voltage Transformer (RITZ) | 12 | 12 | 0 | 6100K023 | PO-SEP-8758-[11] | PO | 2025-10-23 | VT |  | - | 2026-04-04 | 2026-03-21 | 0 |  | 6100K023 Halfmoon SS SWGR CT/Order
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 16301 | RIVET T22213/4 | 172 | 172 | 0 | 6100K023 | PO-SEP-8645-[6] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 16304 | RIVET TT ALUMINUM T22213/5 | 27 | 27 | 0 | 6100K023 | PO-SEP-8378-[101] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 80 | 80 | 0 | 6100K023 | PO-SEP-8379-[17] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 287 | 287 | 0 | 6100K023 | PO-SEP-8379-[18] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA611400R1001 | PILOT LIGHT#ML1-100R | 39 | 39 | 0 | 6100K023 | PO-SEP-8041-[41] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA611400R1002 | PILOT LIGHT#ML1-100G | 39 | 39 | 0 | 6100K023 | PO-SEP-8041-[42] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA611400R1003 | PILOT LIGHT#ML1-100Y | 42 | 42 | 0 | 6100K023 | PO-SEP-8041-[43] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA611400R1005 | PILOT LIGHT#ML1-100W | 90 | 82 | 8 | 6100K023 | PO-SEP-8041-[44] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA611400R1005 | PILOT LIGHT#ML1-100W | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8041-[68] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA611605R1100 | HOLDER#MCBH-00 | 210 | 206 | 4 | 6100K023 | PO-SEP-8041-[45] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA611605R1100 | HOLDER#MCBH-00 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8041-[69] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA611621R1051 | LAMP BLOCK#MLBL-05R | 39 | 39 | 0 | 6100K023 | PO-SEP-8041-[46] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA611621R1052 | LAMP BLOCK#MLBL-05G | 39 | 39 | 0 | 6100K023 | PO-SEP-8041-[47] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA611621R1053 | LAMP BLOCK#MLBL-05Y | 42 | 42 | 0 | 6100K023 | PO-SEP-8041-[48] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA611621R1055 | LAMP BLOCK#MLBL-05W | 86 | 86 | 0 | 6100K023 | PO-SEP-8041-[49] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 206 | 204 | 2 | 6100K023 | PO-SEP-8041-[50] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8041-[74] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 206 | 202 | 4 | 6100K023 | PO-SEP-8041-[51] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8041-[75] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SNA206394R0200 | Screw, EV6I_Screw+PstWasherIP20_M6/8.RS_M4/6.RS Type: EV6I Order no: 1SNA 206 394 R0200 Color: Grey ¦ 1SNA206394R0200 ¦ ABB | 328 | 328 | 0 | 6100K023 | PO-SEP-8386-[13] | PO | 2025-11-10 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SNK900654R0000 | SC-JB8-4 Short circuit bridges - Yellow | 123 | 123 | 0 | 6100K023 | PO-SEP-8386-[14] | PO | 2025-11-10 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VCR000490F0001 | SHEET PROFILE | 12 | 8 | 4 | 6100K023 | PO-SEP-8402-[17] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VCR000490F0001 | SHEET PROFILE | 4 | 4 | 0 | 6100KDP01 | PO-SEP-5654-[34] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries)
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VCR000491F0001 | SHEET PROFILE | 4 | 4 | 0 | 6100KDP01 | PO-SEP-5654-[40] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries)
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VCR002047G0001 | COMPLETE ASSEMBLY KIT FOR DIRAK LOCKUP | 41 | 41 | 0 | 6100K023 | PO-SEP-8446-[1] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Ningbo Shengjiu Technology CO., LTD. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VCR002416G0001 | LOCKUP ROD ASSEMBLY | 41 | 41 | 0 | 6100K023 | PO-SEP-8387-[6] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VCR002428G0001 | LOCKUP ROD ASSEMBLY | 41 | 41 | 0 | 6100K023 | PO-SEP-8387-[7] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VCR003760G0001 | EK6- Earthing Switch (Crank) | 2 | 2 | 0 | 6100K023 | PO-SEP-8387-[13] | PO | 2025-11-30 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VCR008770F0001 | BLOCK PIN | 328 | 232 | 96 | 6100K023 | PO-SEP-8385-[31] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VCR008770F0001 | BLOCK PIN | 96 | 96 | 0 | 6100KDP01 | PO-SEP-8385-[161] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7600732P0101 | SPACER TUBE | 82 | 18 | 64 | 6100K023 | PO-SEP-8403-[2] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7600732P0101 | SPACER TUBE | 64 | 64 | 0 | 6100KDP01 | PO-SEP-8403-[7] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7601387P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Short | 29 | 29 | 0 | 6100K023 | PO-SEP-8385-[32] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7601389P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Long | 30 | 30 | 0 | 6100K023 | PO-SEP-8385-[33] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7602006R0101 | TIE ROD W800 CABLE COMPT. | 82 | 56 | 26 | 6100K023 | PO-SEP-8385-[34] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7602006R0101 | TIE ROD W800 CABLE COMPT. | 26 | 26 | 0 | 6100KDP01 | PO-SEP-8385-[162] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7605506P0101 | ABB LOGO UNIGEAR ZS1 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-6543-[73] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | Labels for outdoor
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7605506P0102 | ABB LOGO UNIGEAR ZS1 | 38 | 8 | 30 | 6100KDP01 | PO-SEP-8379-[45] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7605506P0102 | ABB LOGO UNIGEAR ZS1 | 30 | 30 | 0 | 6100KDP01 | PO-SEP-6543-[74] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | Labels for outdoor
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7607280R0101 | HINGE WITHOUT FASTENERS | 451 | 451 | 0 | 6100K023 | PO-SEP-8397-[3] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7608266P0101 | CONNECTION PIECE tublar GCE8005046R0101 | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8385-[151] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1VL7623184R0101 | COMPLETE HANDLE | 40 | 40 | 0 | 6100K023 | PO-SEP-8552-[2] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | SHAMS ALRIYADH INDUSTRIAL FACTORY | AL Azyziyah DMM Project under Dummy 6100KDP01 2nd Lot of Mechanical Componentes for SEC a/c Dammam Aziziya Fast track project 13.8kV MV SWGR.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB000002-FDV | MIMIC DIAGRAM, INCOMER-2W,VT | 1 | 1 | 0 | 6100K023 | PO-SEP-8379-[11] | PO | 2025-10-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB000003-FDX | MIMIC , OUTGOING WITH EARTHING | 36 | 36 | 0 | 6100K023 | PO-SEP-8379-[12] | PO | 2025-10-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB000004-BTE | MIMIC BUS SEC WITH EARTHG ON RIGHT SIDE | 1 | 1 | 0 | 6100K023 | PO-SEP-8379-[13] | PO | 2025-10-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB000007-BME | MIMIC, BUS MET. & EARTHING-2W,VT | 1 | 1 | 0 | 6100K023 | PO-SEP-8379-[14] | PO | 2025-10-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB000009-BRM | MIMIC , BUS RISER & MET.-2W,VT | 1 | 1 | 0 | 6100K023 | PO-SEP-8379-[15] | PO | 2025-10-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010005P0102 | SHROUD, LEFT W1000 | 6 | 3 | 3 | 6100K023 | PO-SEP-8385-[36] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010005P0102 | SHROUD, LEFT W1000 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8385-[152] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010005P0103 | SHROUD, LEFT W800 | 108 | 71 | 37 | 6100K023 | PO-SEP-8385-[69] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010005P0103 | SHROUD, LEFT W800 | 37 | 37 | 0 | 6100KDP01 | PO-SEP-8385-[126] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010006P0102 | SHROUD, RIGHT W1000 | 6 | 3 | 3 | 6100K023 | PO-SEP-8385-[37] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010006P0102 | SHROUD, RIGHT W1000 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8385-[153] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010006P0103 | SHROUD, RIGHT W800 | 108 | 71 | 37 | 6100K023 | PO-SEP-8385-[70] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010006P0103 | SHROUD, RIGHT W800 | 37 | 37 | 0 | 6100KDP01 | PO-SEP-8385-[127] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 18 | 0 | 18 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 117 | 42 | 75 | 6100K023 | PO-SEP-8629-[13] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | FLY METALTECH TRADING CO.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 75 | 75 | 0 | 6100KDP01 | PO-SEP-8549-[1] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | FLY METALTECH TRADING CO. | 6100KDP01- AZYZIYAH DMM for SEC a/c Fast track project 13.8kV MV SWGR 1st Lot Mechanical Componentes.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010025P0101 | HINGE COMPONENT #2 | 234 | 60 | 174 | 6100K023 | PO-SEP-8403-[3] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010025P0101 | HINGE COMPONENT #2 | 174 | 174 | 0 | 6100KDP01 | PO-SEP-8403-[10] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010029P0122 | CVI DIVIDER, 12-17.5kV, Set 1B (11425) | 38 | 38 | 0 | 6100K023 | PO-SEP-8445-[1] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Ritz Instrument Transformers GMBH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010032P0101 | CT PLATE,UPPER,W1000 (PAINT RAL7035-STD) | 1 | 1 | 0 | 6100K023 | PO-SEP-8402-[5] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010033P0101 | CT MOUNTING PLATE, LOWER, W1000, 3150A | 1 | 1 | 0 | 6100K023 | PO-SEP-8402-[6] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010037P0101 | STRENGHTENING SHEET 13.8KV/24KV | 74 | 74 | 0 | 6100K023 | PO-SEP-8509-[2] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010037P0102 | STRENGTHENING SHEET FOR 40KA PANEL | 4 | 4 | 0 | 6100K023 | PO-SEP-8402-[18] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010072P0101P | CONTACT PIN 35 DIA, 90L | 102 | 102 | 0 | 6100K023 | PO-SEP-8385-[119] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010075P0101 | PARTITION PLATE UPPER CT W800 SS STL | 36 | 36 | 0 | 6100K023 | PO-SEP-8402-[19] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010076P0101 | COVER FOR PARTITION PLATE | 36 | 36 | 0 | 6100K023 | PO-SEP-8402-[20] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 61.26 | 61.26 | 0 | 6100K023 | PO-SEP-8384-[5] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | DIRAK MIDDLE EAST FZE | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010138P0102 | PROTECTIVE COVER W800 | 36 | 36 | 0 | 6100K023 | PO-SEP-8396-[9] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010138P0103 | PROTECTIVE COVER W1000 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8385-[207] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010145P0102 | DOOR STOPPER ROD 8 MM DIA. | 41 | 41 | 0 | 6100K023 | PO-SEP-8704-[1] | PO | 2025-11-13 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010241P0101 | HEX. BOLT M10X20 POLYAMIDE | 240 | 240 | 0 | 6100K023 | PO-SEP-8378-[102] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 120 | 60 | 60 | 6100K023 | PO-SEP-8629-[21] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | FLY METALTECH TRADING CO.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 60 | 60 | 0 | 6100KDP01 | PO-SEP-8378-[299] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010241P0103 | HEX. BOLT M10X30 POLYAMIDE | 108 | 108 | 0 | 6100K023 | PO-SEP-8378-[118] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010241P0104 | HEX. BOLT M10X40 POLYAMIDE | 12 | 12 | 0 | 6100K023 | PO-SEP-8378-[104] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 38 | 38 | 0 | 6100K023 | PO-SEP-8379-[19] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010301P0111 | Label printed in Trafolite 200 x 100 | 41 | 41 | 0 | 6100K023 | PO-SEP-8379-[20] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010378P0110 | SEC.FEMALE CONTACTS 1.5,W.SLEEVES 50X | 50 | 50 | 0 | 6100K023 | PO-SEP-8385-[40] | PO | 2025-09-21 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010378P0110 | SEC.FEMALE CONTACTS 1.5,W.SLEEVES 50X | 2050 | 1100 | 950 | 6100K023 | PO-SEP-8385-[40] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010378P0110 | SEC.FEMALE CONTACTS 1.5,W.SLEEVES 50X | 950 | 950 | 0 | 6100KDP01 | PO-SEP-8385-[216] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010378P0112 | SEC. FEMALE CONTACT PIN 2.5MM | 1900 | 1100 | 800 | 6100K023 | PO-SEP-8385-[71] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010378P0112 | SEC. FEMALE CONTACT PIN 2.5MM | 800 | 800 | 0 | 6100KDP01 | PO-SEP-8385-[129] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 80 | 80 | 0 | 6100K023 | PO-SEP-8379-[21] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010402R0103 | LABELS FOR SHUTTERS BUSBAR-CABLE -FEEDER | 39 | 18 | 21 | 6100K023 | PO-SEP-8379-[22] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010402R0103 | LABELS FOR SHUTTERS BUSBAR-CABLE -FEEDER | 21 | 21 | 0 | 6100KDP01 | PO-SEP-8379-[37] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010402R0104 | LABELS FOR SHUTTERS BUSBAR-1,2,3-B/S,B/R | 1 | 1 | 0 | 6100K023 | PO-SEP-8379-[54] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010489P0101 | FLAT BRAIDED, 16SQMM. TIN(13.8kV)6mmdia | 127 | 54 | 73 | 6100K023 | PO-SEP-8378-[111] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010489P0101 | FLAT BRAIDED, 16SQMM. TIN(13.8kV)6mmdia | 73 | 73 | 0 | 6100KDP01 | PO-SEP-8378-[211] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010489P0102 | FLAT BRAIDED CONNECTOR, 16 SQMM. TINNED | 39 | 10 | 29 | 6100K023 | PO-SEP-8403-[4] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB010489P0102 | FLAT BRAIDED CONNECTOR, 16 SQMM. TINNED | 29 | 29 | 0 | 6100KDP01 | PO-SEP-8403-[8] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5112XFS00000 | VT 3Nos PRIMARY FUSE 17.5kV, 3A, SIBA.VT PRIMARY FUSE FOR 17.5kV UG ZS1 Fuse length : 192 mm Fuse dia : 53 mm Rated Voltage: 17.5kV Rated Current: 3A Rated breaking current : 31.5 kA Frequency: 60 Hz Fuse make : SIBA Type: 30 179 11.3 | 12 | 12 | 0 | 6100K023 | PO-SEP-8408-[1] | PO | 2026-01-15 | VT fuse |  | - | 2026-04-04 | 2026-03-21 | 0 | SABANA TRADERS LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 30 | 30 | 0 | 6100K023 | PO-SEP-8359-[1] | PO | 2026-01-20 | A |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | CBs / 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB52333VW6CN00 | VD4/P 171240-p210-125VDC (1VCD400222) | 2 | 2 | 0 | 6100K023 | PO-SEP-8359-[3] | PO | 2026-01-20 | A |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | CBs / 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB52371V06CN00 | VD4/P 173225-p275-125VDC (1VCD400222) | 3 | 3 | 0 | 6100K023 | PO-SEP-8359-[4] | PO | 2026-01-20 | A |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | CBs / 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 39 | 39 | 0 | 6100K023 | PO-SEP-8360-[1] | PO | 2025-12-07 | A |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | Relay /Aziziyah & 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5320XHI1XN00 | POWER QUALITY ANALYZER, ISKRA iMC784 | 2 | 2 | 0 | 6100K020 | PO-SEP-8547-[3] | PO | 2025-10-23 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Enerziff Solutions FZCO | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 41 | 41 | 0 | 6100K023 | PO-SEP-8829-[1] | PO | 2025-10-23 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Abdullah AbuNayyan Trading Corp
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5331XXCX0000 | CAPACITOR PARKING KEY_COMELECTRIC ITALY.ELECTROMECHANICAL TRAPPED KEY INTERLOCK SWITCH Model: SR 102 R20 2/4 Key Trapped Solenoid Release Switch with IP20 Contacts. Key Free Position: 0 Degree, 4 Contacts. Key Trapped Position: 90 Degree, 4 Contacts. Label: Capacitor Bank Gate Interlock. Make: Comeletric, Italy. Door Interlock lock : KD1 SAP PART NO: 1YAB5331XXCX0000 ------------------ CAPACITOR PARKING KEY_COMELECTRIC ITALY | 2 | 0 | 2 | PR Required | - | PR |  | Customer to supply |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5331XXCX0100 | BREAKER CONTROL SWITCH (Comelectric)Breaker Control Switch3-Pole, 3-Position & spring returnDim: 51 X 51 mm Padlockable handle:Colour : Red YellowFront plate:Text Engrave : OPEN- NORMAL-CLOSELettering plate:Text Engrave : BREAKER CONTROL SWITCH Ordering Code: R601 SAM303 011 01-L078+48-30309T133 | 39 | 39 | 0 | 6100K023 | PO-SEP-8398-[2] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5331XXCX0210 | CBMODE6P,4Pos.Off-Emer-Local-Rem-Padlock(COMELECTRIC), Breaker Mode Selector Switch 6-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH COMELETRIC Part No. R601 SA412 067 27-L071+48-40513T134 SAP Part no: 1YAB5331XXCX0210 | 5 | 5 | 0 | 6100K023 | PO-SEP-8398-[3] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5331XXCX0220 | OFF-EMER-LOCAL-REMOTE 4P4P, PADLCK (COMELECTRIC), Breaker Mode Selector Switch 4-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH Ordering Code: R601 SA408 067 27-L071+48-40513T134 20A, 4 pos Stayput 4 contacts in each Pos, TYPE 1: Engraving: OFF-EMERGENCY-LOCAL-REMOTE TOP PLATE: BREAKER MODE PADLOCK SAP PART NO: 1YAB5331XXCX0220 | 34 | 34 | 0 | 6100K023 | PO-SEP-8398-[18] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5331XXCX0300 | SPACE HEATER SEL. SWITCH ( COMELECTRIC )R601 SA302 112-W051+48-31090T124 20A, 3Positions without internal links 2pole,3position Engraving (OFF/Auto/Manual) OFF-zero contacts AUTO-2 contacts MANUAL-2contacts TOP PLATE (SPACE HEATER) Single hole mounting FT6 | 41 | 41 | 0 | 6100K023 | PO-SEP-8398-[5] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC )R601 SAM201 071-W051+48-20547T123 20A SPRING RETAIN WITHOUT INTERNAL LINKS 2 POSITION,1POLE Engraving (OFF-TEST) TOP PLATE Engraving (LAMP TEST) | 41 | 41 | 0 | 6100K023 | PO-SEP-8398-[6] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5331XXKX0700 | Auto Re-close IN-OUT Selector Switch(COMELECTRIC),"Auto Re-close IN-OUT Selector Switch 4-Pole, 2-Positions Dim: 51 X 51 mm Padlockable handle: Colour : Black Front plate: Text Engrave : IN-OUT Lettering plate Text Engrave : A/R IN-OUT SWITCH" CA10-A723-SA0030-E 1YAB5331XXKX0700 | 32 | 32 | 0 | 6100K023 | PO-SEP-8398-[7] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5332XXAXB000 | PB Black 1NO+1NC-22 dia-1SFA611100R4076 | 86 | 10 | 76 | 6100K023 | PO-SEP-8041-[52] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5332XXAXB000 | PB Black 1NO+1NC-22 dia-1SFA611100R4076 | 76 | 12 | 64 | 6100KDP01 | PO-SEP-8041-[76] | PO | 2025-12-15 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5332XXAXB000 | PB Black 1NO+1NC-22 dia-1SFA611100R4076 | 64 | 64 | 0 | 6100K025 | PO-SEP-8753-[76] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5336XXAA2E00 | MCB 3A AC -2P,2CDS252001R0317 | 3 | 3 | 0 | 6100K023 | PO-SEP-8753-[47] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5336XXAA2G00 | MCB S 202-K6 6A AC -2P - 2CDS252001R0377 | 83 | 83 | 0 | 6100K023 | PO-SEP-8753-[48] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5336XXAA2L00 | MCB 16A AC -2P - 2CDS252001R0467 | 3 | 3 | 0 | 6100K023 | PO-SEP-8753-[49] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5336XXAA3F00 | MCB S203-K 4 MC -3P 2CDS253001R0337 | 24 | 24 | 0 | free_stock | PR-SEP-0024130-[50] | PR |  | LVB |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5336XXAB2G00 | MCB 6A DC 2P S202M-K6UC -2CDS272061R0377 | 242 | 242 | 0 | 6100K023 | PO-SEP-8753-[51] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5336XXACG000 | Aux contact 2NC, S2C-HO2L-for MCB Order # 2CDS200936R0003 | 199 | 199 | 0 | 6100K023 | PO-SEP-8753-[52] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5336XXACH000 | Aux contact 1NO+1NC MCB -2CDS200936R0001 | 259 | 259 | 0 | 6100K023 | PO-SEP-8753-[53] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5336XXACJ000 | S2C-H01 - 1NC- Bottom Auxiliary Contact 2CDS200970R0031 | 50 | 50 | 0 | 6100K023 | PO-SEP-8753-[54] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XAJXXN00 | RF-4R_125Vdc_4 C/O_LED | 71 | 30 | 41 | 6100K023 | PO-SEP-8407-[1] | PO | 2025-09-18 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Innovative Systems Co. Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XAJXXN00 | RF-4R_125Vdc_4 C/O_LED | 41 | 41 | 0 | 6100KDP01 | PO-SEP-8407-[3] | PO | 2025-10-05 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Innovative Systems Co. Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XAJXXN01 | BJ-8RP_Bistable_125Vdc_8 C/O | 34 | 16 | 18 | 6100K023 | PO-SEP-8407-[2] | PO | 2025-09-18 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Innovative Systems Co. Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XAJXXN01 | BJ-8RP_Bistable_125Vdc_8 C/O | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8407-[4] | PO | 2025-10-05 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Innovative Systems Co. Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XCHXXN01 | LOCKOUT RELAY (86) TYPE 7835FD, HIGH SPEED TRIP 8ms, TRIP COIL (70-280VDC),10NO+10NC ELECTRICAL RESET COIL (100-150VDC) | 39 | 39 | 0 | 6100KDP01 | PO-SEP-8556-[1] | PO | 2025-12-30 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Electroswitch | AL Azyziyah Khobar SWGR Project to SEC Under Dummy 6100KDP01 (3rd Lot of Electrical Componentes).
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XCLXXN00 | MVAJ205 ,125VDC ) CAT No. MVAJ205TB0808A | 1 | 1 | 0 | 6100K023 | PO-SEP-8841-[2] | PO | 2026-02-28 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Grid Solution Middle-East Fze | MV
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XDAXXN00 | RXMVB 4, RK 251 401-AP | 5 | 5 | 0 | 6100K023 | PO-SEP-8751-[27] | PO | 2025-12-31 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XDAXXN01 | RXMVB2, RK 251 204-AP | 6 | 6 | 0 | 6100K023 | PO-SEP-8751-[28] | PO | 2025-12-31 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XEAXXN00 | RXMB1 6NO_110-125VDC-1MRK 000 863-AN | 10 | 10 | 0 | 6100K023 | PO-SEP-8751-[29] | PO | 2025-12-31 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XFAXXN00 | RXKL1, TYPE: 1MRK 000 066-AB | 3 | 3 | 0 | 6100K023 | PO-SEP-8751-[30] | PO | 2025-12-31 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XIAXXN00 | RXSF1_DC110-125V-MV RK 271 019-AN No volt flag relay | 121 | 121 | 0 | 6100K023 | PO-SEP-8751-[31] | PO | 2025-12-31 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XJAXXN00 | THREE PHASE FUSE SUPERVISION RELAY Type : RXBA4 (ABB) ORDER NO. : RK 428 004-AA CONTACTS : 2 CHANGE OVER SELF RESET | 4 | 4 | 0 | 6100K025 | PO-SEP-8751-[4] | PO | 2025-12-31 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XNHXXN00 | TRIP LOR/ER 7840FD 20NO+20NC, 125VDC HIGH SPEED TRIP 8ms, TRIP COIL (70-280VDC), ELECTRICAL RESET COIL (100-150VDC) | 6 | 3 | 3 | free_stock | PR-SEP-0024130-[18] | PR |  | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XNHXXN00 | TRIP LOR/ER 7840FD 20NO+20NC, 125VDC HIGH SPEED TRIP 8ms, TRIP COIL (70-280VDC), ELECTRICAL RESET COIL (100-150VDC) | 3 | 0 | 3 | PR Required | - | PR |  | LVA |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 5460 | 2490 | 2970 | 6100K023 | PO-SEP-8417-[2] | PO | 2025-11-30 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Phoenix Contact Trading LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 2970 | 2970 | 0 | 6100KDP01 | PO-SEP-8572-[2] | PO | 2025-12-15 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 1845 | 1845 | 0 | 6100K023 | PO-SEP-8386-[2] | PO | 2025-11-10 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AEA0001 | M 6/8.RS (SpringLoaded) 1SNA115685R1200 | 1811 | 1811 | 0 | 6100K023 | PO-SEP-8386-[3] | PO | 2025-11-10 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 9625 | 9625 | 0 | 6100K023 | PO-SEP-8386-[4] | PO | 2025-11-10 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AFA0001 | M4/6.SNTS Spring Loaded 1SNA115229R2000 | 1845 | 1845 | 0 | 6100K023 | PO-SEP-8386-[5] | PO | 2025-11-10 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 371 | 371 | 0 | 6100K023 | PO-SEP-8386-[6] | PO | 2025-11-10 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AMC0001 | Base Terminal Plug AC-DC-4mm 1848350000.Feed-through terminal block,ZT 4/4AN/2 . | 1230 | 1230 | 0 | 6100K023 | PO-SEP-8518-[22] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 492 | 492 | 0 | 6100K023 | PO-SEP-8518-[23] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 588 | 588 | 0 | 6100K023 | PO-SEP-8518-[24] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355CBA0000 | FEM8T6 End Sections Grey 1SNA215266R0100 | 615 | 615 | 0 | 6100K023 | PO-SEP-8386-[7] | PO | 2025-11-10 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355CEA0000 | FEMR8 End Sections Grey 1SNA116987R0200 | 820 | 820 | 0 | 6100K023 | PO-SEP-8386-[8] | PO | 2025-11-10 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355CFA0000 | FEM6 End Sections Grey - 1SNA118368R1600 | 410 | 410 | 0 | 6100K023 | PO-SEP-8386-[9] | PO | 2025-11-10 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355CMC0000 | Terminal End Plate 1848360000-Wiedmuller | 164 | 164 | 0 | 6100K023 | PO-SEP-8518-[25] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355CPC0000 | Terminal End Plate 1816110000-Wiedmuller | 67 | 67 | 0 | 6100K023 | PO-SEP-8518-[26] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355CTC0000 | Terminal End Plate 1816070000-Wiedmuller | 20 | 20 | 0 | 6100K023 | PO-SEP-8518-[27] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 1600 | 1600 | 0 | 6100KDP01 | PO-SEP-8572-[4] | PO | 2025-12-15 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355DFA0000 | RC610-VerticalMarking 1SNA233060R0400 | 369 | 369 | 0 | 6100K023 | PO-SEP-8386-[10] | PO | 2025-11-10 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355DXC0000 | 460660001 DEK 5 FSZ 1-10 Z-Terminal 1-10 | 16500 | 16500 | 0 | 6100K023 | PO-SEP-8518-[28] | PO | 2025-12-31 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355EEA0000 | JUMPER BAR "BJS8" 20 Poles | 82 | 82 | 0 | 6100K023 | PO-SEP-8386-[11] | PO | 2025-11-10 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355EFA0000 | PC61-CombTypeJumprBar10 1SNA163311R2200 | 164 | 164 | 0 | 6100K023 | PO-SEP-8386-[12] | PO | 2025-11-10 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 328 | 328 | 0 | 6100K023 | PO-SEP-8518-[29] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355HAB0001 | Zack Strip-Vertical(11-20)- 1053027:0011 | 210 | 0 | 210 | PR Required | - | PR |  | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 136 | 136 | 0 | 6100K023 | PO-SEP-8518-[31] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355JPC0000 | 6Pole Plug 2.5mm-1815240000-Cont-loop | 66 | 66 | 0 | 6100K023 | PO-SEP-8518-[32] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355JTC0000 | 10Pole Plug 2.5mm-1815280000-Cont-loop | 100 | 100 | 0 | 6100K023 | PO-SEP-8518-[33] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 240 | 240 | 0 | 6100K023 | PO-SEP-8518-[34] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355KPC0000 | Locking ele. 1816130000 for ZT2.5/4AN/2 | 130 | 130 | 0 | 6100K023 | PO-SEP-8518-[35] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355LMC0000 | Coding element 1856860000 - ZT4/4AN/2 | 132 | 132 | 0 | 6100K023 | PO-SEP-8518-[36] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355LPC0000 | Coding element 1816150000 | 148 | 148 | 0 | 6100K023 | PO-SEP-8518-[37] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355MPC0000 | Strain Relief Wied mulpart # 1816140000 | 130 | 130 | 0 | 6100K023 | PO-SEP-8518-[38] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-04 | 2026-03-21 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB539500002004 | Adjustable Trolley (Haydraulic type) | 1 | 1 | 0 | 6100K023 | PO-SEP-8497-[1] | PO | 2025-12-21 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Leistung Energie Limited | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB60050819P0103 | Braided HARNESS TUBE (D40) | 615 | 615 | 0 | 6100K023 | PO-SEP-8378-[75] | PO | 2025-11-17 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB60050819P0106 | Braided HARNESS TUBE (D30) | 820 | 820 | 0 | 6100K023 | PO-SEP-8378-[77] | PO | 2025-11-17 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB60050819P0107 | Braided HARNESS TUBE (D20) | 410 | 410 | 0 | 6100K023 | PO-SEP-8378-[78] | PO | 2025-11-17 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAZ21500101 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 172 | 172 | 0 | 6100K023 | PO-SEP-8388-[21] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 372 | 162 | 210 | 6100K023 | PO-SEP-8378-[1] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 210 | 210 | 0 | 6100KDP01 | PO-SEP-8378-[271] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 28373 | LOCK NUT ACC TO T21192/M2.5x0.45 | 56 | 56 | 0 | 6100K023 | PO-SEP-8647-[17] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Mattssons Fasteners AB
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 28452 | FLEXIBLE SPIROID PINS T22513/3X26 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8385-[223] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 28627 | Rivet NUT ACC T21098/M6 (countersunk) | 512 | 512 | 0 | 6100K023 | PO-SEP-8645-[8] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 29823 | TOMMY HEAD SCREW ACC. T21010/M2.5x20 | 54 | 54 | 0 | 6100K023 | PO-SEP-8647-[18] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Mattssons Fasteners AB
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 2CDS254001R0337 | MCB S204-K 4 MC -4P 2CDS254001R0337 | 106 | 106 | 0 | 6100K023 | PO-SEP-8753-[50] | PO | 2025-12-31 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 2TRE123451P0001 | 3 PIN SOCKET SWITCH,13A,250V,BSRDP-I | 3 | 2 | 1 | 6100K023 | PO-SEP-8388-[4] | PO | 2025-10-30 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 2TRE123451P0001 | 3 PIN SOCKET SWITCH,13A,250V,BSRDP-I | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8388-[29] | PO | 2025-10-30 | LVB |  | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 3WKA014480P0004 | RETAINING_WASHER_DIN6799_6-SPST/A3K | 40 | 10 | 30 | 6100K023 | PO-SEP-8385-[291] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 3WKA014480P0004 | RETAINING_WASHER_DIN6799_6-SPST/A3K | 30 | 30 | 0 | 6100KDP01 | PO-SEP-8385-[289] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 80 | 80 | 0 | 6100K023 | PO-SEP-8378-[356] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 3WKA014538P0012 | SPIRAL_PIN_ISO8748_4X20-ST/BK | 52 | 52 | 0 | 6100K023 | PO-SEP-8385-[1] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 4CE7000583P0101 | PIN | 40 | 8 | 32 | 6100K023 | PO-SEP-8680-[33] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 4CE7000583P0101 | PIN | 32 | 32 | 0 | 6100KDP01 | PO-SEP-8680-[5] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 500214111 | WASHER T22001/6.8X18 | 41 | 41 | 0 | 6100K023 | PO-SEP-8378-[9] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 500673075 | PIN T22681/8X54,5-5 | 152 | 80 | 72 | 6100K023 | PO-SEP-8387-[18] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 500673075 | PIN T22681/8X54,5-5 | 72 | 72 | 0 | 6100KDP01 | PO-SEP-8387-[34] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 5022 643 | COVER PROFILE, AP3 | 65.6 | 40 | 25.6 | 6100K023 | PO-SEP-8417-[9] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Phoenix Contact Trading LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 5022 643 | COVER PROFILE, AP3 | 25.6 | 25.6 | 0 | 6100KDP01 | PO-SEP-8572-[9] | PO | 2025-12-15 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 1025 | 500 | 525 | 6100K023 | PO-SEP-8417-[10] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Phoenix Contact Trading LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 525 | 525 | 0 | 6100KDP01 | PO-SEP-8572-[10] | PO | 2025-12-15 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 5217 708-3 | M.CONTACT/HAN-E16M/09330162601 | 2 | 2 | 0 | 6100K023 | PO-SEP-8368-[2] | PO | 2025-12-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 5217 708-7 | F.CONTACT/HAN-E16F/09330162701 | 2 | 2 | 0 | 6100K023 | PO-SEP-8368-[3] | PO | 2025-12-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 561762/001 | PLATE -FOR PANEL FIXING | 164 | 0 | 164 | PR Required | - | PR |  | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 564093/001 | BLOCK FOUNDATION - ZINK COATED | 116 | 116 | 0 | 6100K023 | PO-SEP-8629-[19] | PO | 2025-10-30 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | FLY METALTECH TRADING CO.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 565937/001 | LEAF SPRING 499355009 | 6 | 6 | 0 | 6100K023 | PO-SEP-8483-[2] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AB KOMPONENTY s.r.o. | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 593503001 | ROLLER | 38 | 12 | 26 | 6100K023 | PO-SEP-8387-[19] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 593503001 | ROLLER | 26 | 26 | 0 | 6100KDP01 | PO-SEP-8387-[35] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 593509/001 | COMPRESSION SPRING | 78 | 16 | 62 | 6100K023 | PO-SEP-8483-[6] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AB KOMPONENTY s.r.o. | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 593509/001 | COMPRESSION SPRING | 62 | 62 | 0 | 6100KDP01 | PO-SEP-8483-[4] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AB KOMPONENTY s.r.o. | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 837A407G01 | ‭FT SWITCH, (C-C C-C C-C C-C P P)/837A407G01/FT-1‬ | 41 | 41 | 0 | 6100K023 | PO-SEP-8747-[13] | PO | 2025-12-31 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 9676A14G01 | ‭FT SWITCH, (P P P P T T T P P P)/9676A14G01/FT-1‬ | 45 | 45 | 0 | 6100K023 | PO-SEP-8747-[14] | PO | 2025-12-31 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 9ABA450060P0004 | NUT_ISO7040_M6-8/A3K | 40 | 18 | 22 | 6100K023 | PO-SEP-8680-[34] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 9ABA450060P0004 | NUT_ISO7040_M6-8/A3K | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8680-[6] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 9ABA450060P0005 | NUT_ISO7040_M8-8/A3K | 82 | 82 | 0 | 6100K023 | PO-SEP-8378-[11] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 9ADJ100023P0357 | BLIND_RIVET_ISO15979_6,4x16-ST/ST | 164 | 164 | 0 | 6100K023 | PO-SEP-8378-[12] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 2093 7000-5 | RAYCHEM SHRINKABLE TUBE, BPTM 100/40-A/U | 81.02 | 81.02 | 0 | 6100K023 | PO-SEP-8393-[2] | PO | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Saudi Electrical Supply Co Sesco | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 2093 7000-6N | RAYCHEM SHRINKABLE TUBE, BPTM 120/50-A/U | 24.43 | 24.43 | 0 | 6100K023 | PO-SEP-8393-[1] | PO | 2025-11-03 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Saudi Electrical Supply Co Sesco | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 30 | 30 | 0 | 6100K023 | PO-SEP-8502-[18] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 645 | 570 | 75 | 6100K023 | PO-SEP-8502-[18] | PO | 2025-12-31 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 75 | 75 | 0 | 6100KDP01 | PO-SEP-8925-[4] | PO | 2025-10-05 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 615 | 615 | 0 | 6100K023 | PO-SEP-8388-[5] | PO | 2025-10-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 40 | 40 | 0 | 6100K023 | PO-SEP-8379-[1] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 40 | 40 | 0 | 6100K023 | PO-SEP-8379-[2] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 82 | 82 | 0 | 6100K023 | PO-SEP-8379-[3] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 3.4 | 3.4 | 0 | 6100K023 | PO-SEP-8835-[4] | PO | 2025-09-18 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | EMKA Beschlagteile Middle East FZE
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 820 | 820 | 0 | 6100K023 | PO-SEP-8378-[79] | PO | 2025-11-17 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 246 | 246 | 0 | 6100K023 | PO-SEP-8378-[80] | PO | 2025-11-17 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 41.62 | 34.74 | 6.88 | 6100K023 | PO-SEP-8384-[1] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | DIRAK MIDDLE EAST FZE | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 6.88 | 6.88 | 0 | 6100KDP01 | PO-SEP-8384-[3] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | DIRAK MIDDLE EAST FZE | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2522-2000-01 | HOOD HAN-E16,09300161520 | 2 | 2 | 0 | 6100K023 | PO-SEP-8368-[4] | PO | 2025-12-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301,HAN-E16 | 2 | 2 | 0 | 6100K023 | PO-SEP-8368-[1] | PO | 2025-12-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 5 | 3 | 2 | 6100K023 | PO-SEP-8368-[1] | PO | 2025-12-15 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 2 | 2 | 0 | 6100K023 | PO-SEP-8368-[5] | PO | 2025-12-15 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 41 | 19 | 22 | 6100K023 | PO-SEP-8403-[1] | PO | 2025-09-18 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 22 | 22 | 0 | 6100KDP01 | PO-SEP-8484-[4] | PO | 2025-12-15 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2632-2000-33 | Spring for Door Combiflex | 0.82 | 0.82 | 0 | 6100K023 | PO-SEP-8388-[6] | PO | 2025-10-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 41 | 41 | 0 | 6100K023 | PO-SEP-8402-[70] | PO | 2025-11-17 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE5295-2000-08 | POST INSULATOR h=50mm (2035679) | 6 | 6 | 0 | 6100K023 | PO-SEP-8389-[4] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 2460 | 1290 | 1170 | 6100K023 | PO-SEP-8417-[11] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Phoenix Contact Trading LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS | 500 | 25-10-2025
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 1170 | 1170 | 0 | 6100KDP01 | PO-SEP-8572-[11] | PO | 2025-12-15 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 41 | 18 | 23 | 6100K023 | PO-SEP-8379-[16] | PO | 2025-10-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 23 | 4 | 19 | 6100KDP01 | PO-SEP-8379-[44] | PO | 2025-10-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 19 | 19 | 0 | 6100K025 | PO-SEP-8724-[3] | PO | 2025-11-16 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | CDX7005632R1A | EARTHING CONTACT COMPLETE | 82 | 82 | 0 | 6100K023 | PO-SEP-8387-[1] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | CDXN010061R1103 | HANDLE COMPLETE | 41 | 41 | 0 | 6100K023 | PO-SEP-8387-[2] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DM0000000058 | Relay, Auxiliary, 2 Coils, Self Reset Contacts, Hand Reset Flag, 110-125V, DC, 2NO, 1NC, Coil ¦ RXSF1 RK 271 007-AN | 8 | 8 | 0 | 6100K023 | PO-SEP-8751-[32] | PO | 2025-12-31 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DM0000003057 | Relay, Over Current Protection, DC, 110-250V, AC 100-230V, 19BI + 15BO, With IEC 61850-8-1, 2x Optical, Type 7SJ85 ¦ P1J198095 | 2 | 2 | 0 | 6100K023 | PO-SEP-8595-[1] | PO | 2026-01-30 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Siemens Ltd. | MV
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 82 | 82 | 0 | 6100K023 | PO-SEP-8378-[110] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 40 | 40 | 0 | 6100K023 | PO-SEP-8378-[13] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-419 | BOLT HEX HEAD M8X45 | 2 | 1 | 1 | 6100K023 | PO-SEP-8378-[148] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-419 | BOLT HEX HEAD M8X45 | 1 | 1 | 0 | 6100KDP01 | PO-SEP-6812-[119] | PO | 2025-12-31 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-494 | BOLT HEX HEAD M10X35 | 18 | 18 | 0 | 6100K023 | PO-SEP-8378-[119] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-496 | BOLT HEX HEAD M10X45 | 45 | 45 | 0 | 6100K023 | PO-SEP-8378-[125] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-508 | BOLT HEX HEAD M10X130 | 8 | 8 | 0 | 6100K023 | PO-SEP-8680-[50] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 117 | 117 | 0 | 6100K023 | PO-SEP-8378-[14] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-659 | BOLT HEX HEAD M20X45 | 30 | 30 | 0 | 6100K023 | PO-SEP-8378-[15] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-660 | BOLT HEX HEAD M20X50 | 9 | 9 | 0 | 6100K023 | PO-SEP-8378-[130] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2016-666 | BOLT HEX HEAD M20X90 | 30 | 30 | 0 | 6100K023 | PO-SEP-8378-[108] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2017-659 | BOLT HEX HEAD H D M20X45 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8680-[7] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2452-293 | SCREW CROSS REC.HEAD M4X16 | 8 | 8 | 0 | 6100K023 | PO-SEP-8680-[35] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 16 | 16 | 0 | 6100K023 | PO-SEP-8680-[36] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 2377 | 2377 | 0 | 6100K023 | PO-SEP-8680-[36] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 172 | 172 | 0 | 6100K023 | PO-SEP-8378-[19] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-291 | BOLT SOCKET CAP HEAD M4X12 | 8 | 8 | 0 | 6100K023 | PO-SEP-8378-[131] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-293 | BOLT SOCKET HEAD M4X16 | 4 | 4 | 0 | 6100K023 | PO-SEP-8378-[132] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-325 | BOLT SOCKET CAP M5X10 | 12 | 12 | 0 | 6100K023 | PO-SEP-8378-[21] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-333 | BOLT SOCKET CAP HEAD M5X25 | 1 | 1 | 0 | 6100K023 | PO-SEP-8378-[151] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-371 | BOLT SOCKET CAP M6X20 | 10 | 10 | 0 | 6100K023 | PO-SEP-8378-[121] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-372 | BOLT SOCKET CAP M6X25 | 2 | 2 | 0 | 6100K023 | PO-SEP-8378-[25] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-430 | BOLT SOCKET CAP HEAD M6X50 | 6 | 6 | 0 | 6100K023 | PO-SEP-8378-[26] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 164 | 164 | 0 | 6100K023 | PO-SEP-8378-[27] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 32 | 32 | 0 | 6100K023 | PO-SEP-8378-[112] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 3019 | 3019 | 0 | 6100K023 | PO-SEP-8378-[112] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 1700 | 1700 | 0 | 6100K023 | PO-SEP-8378-[113] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 392 | 392 | 0 | 6100K023 | PO-SEP-8378-[114] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 658 | 422 | 236 | 6100K023 | PO-SEP-8378-[114] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 236 | 236 | 0 | 6100KDP01 | PO-SEP-8378-[180] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-457 | BOLT SOCKET CAP M8X35 | 4 | 4 | 0 | 6100K023 | PO-SEP-8378-[115] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 80 | 80 | 0 | 6100K023 | PO-SEP-8680-[21] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 117 | 117 | 0 | 6100K023 | PO-SEP-8378-[117] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 246 | 246 | 0 | 6100K023 | PO-SEP-8378-[220] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 60 | 60 | 0 | 6100K023 | PO-SEP-8378-[28] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 1441 | 1441 | 0 | 6100K023 | PO-SEP-8378-[28] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 272 | 272 | 0 | 6100K023 | PO-SEP-8378-[29] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 665 | 665 | 0 | 6100K023 | PO-SEP-8378-[30] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-499 | BOLT SOCKET CAP HEAD M10X40 | 27 | 27 | 0 | 6100K023 | PO-SEP-8378-[129] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-500 | BOLT SOCKET CAP HEAD M10X45 | 558 | 558 | 0 | 6100K023 | PO-SEP-8378-[31] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-508 | BOLT SOCKET CAP HEAD M10X100 | 144 | 144 | 0 | 6100K023 | PO-SEP-8378-[126] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-531 | BOLT SOCKET CAP M12X16 (C.H.) | 39 | 18 | 21 | 6100K023 | PO-SEP-8378-[32] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-531 | BOLT SOCKET CAP M12X16 (C.H.) | 21 | 21 | 0 | 6100KDP01 | PO-SEP-8378-[251] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 46 | 46 | 0 | 6100K023 | PO-SEP-8378-[122] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8378-[248] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 9 | 6 | 3 | 6100KDP01 | PO-SEP-8378-[248] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8378-[313] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 1187 | 1187 | 0 | 6100K023 | PO-SEP-8378-[33] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-540 | BOLT SOCKET CAP HEAD M12X40 | 13 | 7 | 6 | 6100K023 | PO-SEP-8680-[27] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-540 | BOLT SOCKET CAP HEAD M12X40 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-6812-[111] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 444 | 444 | 0 | 6100K023 | PO-SEP-8378-[34] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-542 | BOLT SOCKET CAP HEAD M12X50 | 30 | 30 | 0 | 6100K023 | PO-SEP-8378-[35] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-544 | BOLT SOCKET CAP HEAD M12X60 | 66 | 66 | 0 | 6100K023 | PO-SEP-8680-[37] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 726 | 726 | 0 | 6100K023 | PO-SEP-8378-[124] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-628 | BOLT SOCKET CAP HEAD M16X40 | 18 | 15 | 3 | 6100K023 | PO-SEP-8378-[37] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2519-628 | BOLT SOCKET CAP HEAD M16X40 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-6812-[109] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 236 | 108 | 128 | 6100K023 | PO-SEP-8680-[38] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 128 | 128 | 0 | 6100KDP01 | PO-SEP-8680-[10] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2121 2852-536 | COUNTERSUNK ALLEN HEAD M12X30 | 120 | 120 | 0 | 6100K023 | PO-SEP-8378-[224] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 42 | 42 | 0 | 6100K023 | PO-SEP-8680-[41] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 784 | 784 | 0 | 6100K023 | PO-SEP-8680-[41] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 347 | 347 | 0 | 6100K023 | PO-SEP-8378-[44] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2013-122 | NUT HEX H D GALV M12 | 144 | 144 | 0 | 6100K023 | PO-SEP-8680-[24] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2013-124 | NUT HEX H D GALV M16 | 270 | 270 | 0 | 6100K023 | PO-SEP-8645-[5] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 843-1 | RIVET NUT M6 (HEXAGONAL) | 6 | 6 | 0 | 6100K023 | PO-SEP-8378-[328] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2151 2062-136 | WASHER FLAT BRIR 4.3X8X0.8 | 255 | 102 | 153 | 6100K023 | PO-SEP-8680-[42] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2151 2062-136 | WASHER FLAT BRIR 4.3X8X0.8 | 153 | 153 | 0 | 6100KDP01 | PO-SEP-8680-[20] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 1217 | 1217 | 0 | 6100K023 | PO-SEP-8378-[46] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 162 | 162 | 0 | 6100K023 | PO-SEP-8378-[47] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 328 | 328 | 0 | 6100K023 | PO-SEP-8378-[48] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 2736 | 2736 | 0 | 6100K023 | PO-SEP-8378-[49] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 4013 | 2494 | 1519 | 6100K023 | PO-SEP-8378-[49] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 1519 | 1519 | 0 | 6100KDP01 | PO-SEP-8378-[250] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 2520 | 2520 | 0 | 6100K023 | PO-SEP-8378-[50] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 1386 | 1386 | 0 | 6100K023 | PO-SEP-8378-[51] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 168 | 168 | 0 | 6100K023 | PO-SEP-8378-[52] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 4 | 4 | 0 | 6100K023 | PO-SEP-8378-[53] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 566 | 566 | 0 | 6100K023 | PO-SEP-8378-[53] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 430 | 430 | 0 | 6100K023 | PO-SEP-8378-[54] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 5857 | 5857 | 0 | 6100K023 | PO-SEP-8378-[54] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 16400 | 16400 | 0 | 6100K023 | PO-SEP-8378-[81] | PO | 2025-11-17 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 74 | 74 | 0 | 6100K023 | PO-SEP-8502-[23] | PO | 2025-12-31 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 14 | 14 | 0 | 6100K023 | PO-SEP-8502-[24] | PO | 2025-12-31 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 90 | 90 | 0 | 6100K023 | PO-SEP-8502-[25] | PO | 2025-12-31 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 88 | 88 | 0 | 6100K023 | PO-SEP-8502-[27] | PO | 2025-12-31 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 924 0010 | Combiflex wire Socket 1.5mm 1MRK002136-B | 8200 | 8200 | 0 | 6100K023 | PO-SEP-8366-[4] | PO | 2025-12-31 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 924 0020 | Combiflex wire Socket 2.5mm 1MRK002136-E | 4920 | 4920 | 0 | 6100K023 | PO-SEP-8366-[5] | PO | 2025-12-31 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 4 | 4 | 0 | 6100K023 | PO-SEP-8362-[1] | PO | 2025-12-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Shanghai Feili Xuncheng Electrical Technology Co.,Ltd | Snap action/ 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 8 | 4 | 4 | 6100K023 | PO-SEP-8362-[2] | PO | 2025-12-15 | B |  | - | 2026-04-04 | 2026-03-21 | 0 | Shanghai Feili Xuncheng Electrical Technology Co.,Ltd | Snap action/ 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 4 | 4 | 0 | 6100K020 | PO-SEP-8757-[3] | PO | 2025-12-15 | B |  | - | 2026-04-04 | 2026-03-21 | 0 | Shanghai Feili Xuncheng Electrical Technology Co.,Ltd | Snap action Switch
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0007249P0100 | GREASE ISOPLEX TOPAS,NB52,1kg | 0.462 | 0.462 | 0 | 6100K023 | PO-SEP-8908-[3] | PO | 2025-12-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Quality Bearing Online Limited
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0068009P0100 | BUSHING D8/3 PVC | 12 | 12 | 0 | 6100K023 | PO-SEP-8755-[4] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | MESAN KİLİT A.Ş.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0301012P0100 | CHEESE HEAD B0LT M3X6 | 8 | 8 | 0 | 6100K023 | PO-SEP-8378-[223] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0303179P0100 | CYLINDER HEAD BOLT M10X80 DIN 91 | 2 | 2 | 0 | 6100K023 | PO-SEP-8680-[25] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0305850P0100 | POLYAMID BOLT M6X20 | 57 | 57 | 0 | 6100K023 | PO-SEP-8378-[55] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0305871P0100 | HEX BOLT M8X16 DIN 933-POLY | 296 | 154 | 142 | 6100K023 | PO-SEP-8378-[297] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0305871P0100 | HEX BOLT M8X16 DIN 933-POLY | 142 | 142 | 0 | 6100KDP01 | PO-SEP-8378-[290] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 276 | 276 | 0 | 6100K023 | PO-SEP-8378-[56] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0316044P0100 | HEAD SCREW M8X50, DIN 603-4.3 | 76 | 36 | 40 | 6100K023 | PO-SEP-8629-[14] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | FLY METALTECH TRADING CO.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0316044P0100 | HEAD SCREW M8X50, DIN 603-4.3 | 40 | 40 | 0 | 6100KDP01 | PO-SEP-8629-[7] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | FLY METALTECH TRADING CO.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 80 | 80 | 0 | 6100K023 | PO-SEP-8629-[15] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | FLY METALTECH TRADING CO.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0336970P0100 | BOLT,TAPTITE HEX BOLT M5X12 | 8 | 2 | 6 | 6100K023 | PO-SEP-8385-[230] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0336970P0100 | BOLT,TAPTITE HEX BOLT M5X12 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8385-[193] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0336985P0100 | TAPPING SCREW M6X16/6KTHEAD | 7 | 1 | 6 | 6100KDP01 | PO-SEP-8378-[177] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0336985P0100 | TAPPING SCREW M6X16/6KTHEAD | 6 | 6 | 0 | 6100KDP01 | PO-SEP-6812-[35] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0350009P0100 | NUT M6 DIN 439-04 | 4 | 4 | 0 | 6100K023 | PO-SEP-8385-[304] | PO | 2025-09-21 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0352913P0100 | NUT M10 DIN 555-Polyamide | 12 | 12 | 0 | 6100K023 | PO-SEP-8680-[23] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0365304P0100 | NUT,HEX.NUT MPG 16 | 2 | 2 | 0 | 6100K023 | PO-SEP-8378-[58] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0367308P0100 | NUT, HEX - M5, DIN 985-6 ( LOCK NUT ) | 4 | 4 | 0 | 6100K023 | PO-SEP-8378-[296] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0367309P0100 | HEX. NUT M6, DIN 985-6 ( LOCK NUT ) | 10 | 4 | 6 | 6100KDP01 | PO-SEP-8378-[291] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0367309P0100 | HEX. NUT M6, DIN 985-6 ( LOCK NUT ) | 6 | 6 | 0 | 6100KDP01 | PO-SEP-6812-[77] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0367402P0100 | HEX. NUT M4, DIN 6925-13 ( LOCK NUT ) | 4 | 4 | 0 | 6100K023 | PO-SEP-8378-[137] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0369010P0100 | RIVET NUT M6X16 WITH GROOVE | 57 | 57 | 0 | 6100K023 | PO-SEP-8378-[59] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 1843 | 1843 | 0 | 6100K023 | PO-SEP-8378-[60] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 522 | 164 | 358 | 6100K023 | PO-SEP-8378-[61] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 358 | 358 | 0 | 6100KDP01 | PO-SEP-8378-[255] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 312 | 312 | 0 | 6100K023 | PO-SEP-8378-[62] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 1406 | 1406 | 0 | 6100K023 | PO-SEP-8378-[62] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 30 | 30 | 0 | 6100K023 | PO-SEP-8378-[63] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 340 | 340 | 0 | 6100K023 | PO-SEP-8378-[63] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0401027P0100 | WASHER FLAT 10.5,DIN433-ST | 156 | 156 | 0 | 6100K023 | PO-SEP-8378-[64] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0402909P0100 | WASHER POLYAMID, A6.4, DIN 125 | 57 | 57 | 0 | 6100K023 | PO-SEP-8629-[4] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | FLY METALTECH TRADING CO.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0402911P0100 | WASHER POLYAMID, A8.4, DIN 125 | 656 | 262 | 394 | 6100K023 | PO-SEP-8378-[65] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0402911P0100 | WASHER POLYAMID, A8.4, DIN 125 | 394 | 394 | 0 | 6100KDP01 | PO-SEP-8378-[172] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0402912P0100 | WASHER POLYAMID, A10.5, DIN 125 | 480 | 480 | 0 | 6100K023 | PO-SEP-8378-[298] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0410004P0100 | SPRING RING A3, DIN 127-FST | 16 | 16 | 0 | 6100KDP01 | PO-SEP-8385-[149] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0410006P0100 | SPRING A4, DIN 127-FST | 6 | 6 | 0 | 6100K023 | PO-SEP-8378-[138] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0410007P0100 | SPRING RING, A5, DIN 127-FST | 4 | 4 | 0 | 6100K023 | PO-SEP-8385-[171] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0412007P0100 | SPRING RING 10 DIN 7980-FST | 72 | 72 | 0 | 6100K023 | PO-SEP-8378-[66] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0413160P0100 | RETAINING WASHER VS5 | 40 | 4 | 36 | 6100K023 | PO-SEP-8385-[300] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0413160P0100 | RETAINING WASHER VS5 | 36 | 36 | 0 | 6100KDP01 | PO-SEP-8385-[298] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0413167P0100 | WASHER VS12 - FST | 4 | 4 | 0 | 6100K023 | PO-SEP-8924-[3] | PO | 2025-09-21 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0413307P0100 | CONTACT WASHER 12 | 8 | 8 | 0 | 6100K023 | PO-SEP-8378-[139] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0417501P0100 | SPLIT PIN FOR FRICK B. CHUCK | 2 | 2 | 0 | 6100K023 | PO-SEP-8385-[172] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0418011P0100 | REVTAINING RING BORE-8 | 4 | 4 | 0 | 6100K023 | PO-SEP-8385-[173] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 115 | 115 | 0 | 6100K023 | PO-SEP-8629-[16] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | FLY METALTECH TRADING CO.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0418203P0100 | WASHER,RETAINING 6, WN418-FST | 152 | 56 | 96 | 6100K023 | PO-SEP-8378-[295] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0418203P0100 | WASHER,RETAINING 6, WN418-FST | 96 | 96 | 0 | 6100KDP01 | PO-SEP-8378-[292] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0418204P0100 | WASHER RETAINING 8/WN 418-FST | 45 | 18 | 27 | 6100K023 | PO-SEP-8680-[43] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0418204P0100 | WASHER RETAINING 8/WN 418-FST | 27 | 27 | 0 | 6100KDP01 | PO-SEP-8680-[14] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | ALAM AL NIMA TRADING EST
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0418205P0100 | WASHER RETAINING 10, WN418-FST | 156 | 156 | 0 | 6100K023 | PO-SEP-8378-[69] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0422013P0100 | WASHER,RETAINING 16X1 | 8 | 4 | 4 | 6100K023 | PO-SEP-8378-[155] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0422013P0100 | WASHER,RETAINING 16X1 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-6812-[5] | PO | 2025-12-31 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0438423P0100 | SPRING PIN 3X16 | 8 | 8 | 0 | 6100K023 | PO-SEP-8629-[17] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | FLY METALTECH TRADING CO.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0438425P0100 | SPRING PIN SLOTTED 3X20 (EQUIV.=28272) | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8385-[199] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0457035P0100 | BLIND RIVET 5X10 AL | 328 | 328 | 0 | 6100K023 | PO-SEP-8378-[332] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0457038P0100 | BLIND RIVET 5X16, CIECO, WN457-ALU | 160 | 160 | 0 | 6100K023 | PO-SEP-8378-[333] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0457040P0100 | BLIND RIVET 6.4X12 STEEL | 201 | 201 | 0 | 6100K023 | PO-SEP-8378-[336] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0518520P0101 | ATTENTION SIGN (SEGNALE DI PERICOLO) | 2 | 1 | 1 | free_stock | PR-SEP-0024114-[425] | PR |  | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0518520P0101 | ATTENTION SIGN (SEGNALE DI PERICOLO) | 1 | 0 | 1 | PR Required | - | PR |  | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0909121P0100 | STRAIN RELIEF TYPE ZE2/10 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8385-[150] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0909123P0100 | PLUG-IN CONNECTION - 645060000 | 4 | 0 | 4 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0909124P0100 | BUSH STV2/10 ORDER.NO. 0645160000 | 6 | 0 | 6 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0913120P0100 | VARISTOR COMBINATION 4X610 SB | 1 | 0 | 1 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0931008P0100 | POST TYPE INSULATOR 12kV SIZE B 2040384 | 18 | 18 | 0 | 6100K023 | PO-SEP-8389-[2] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0931306P0100 | BUSHING KD20-30/115(2033335)GJ (LOWER) | 3 | 3 | 0 | 6100K023 | PO-SEP-8389-[3] | PO | 2025-11-30 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0931316P0100 | BUSBAR INSERT 2XD100 | 48 | 48 | 0 | 6100K023 | PO-SEP-8385-[101] | PO | 2025-09-21 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990014P0100 | THREADED PLATE M10 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8646-[5] | PO | 2025-10-20 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 41 | 41 | 0 | 6100K023 | PO-SEP-8409-[1] | PO | 2025-12-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 82 | 36 | 46 | 6100K023 | PO-SEP-8409-[3] | PO | 2025-12-15 | LVC |  | - | 2026-04-04 | 2026-03-21 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 46 | 46 | 0 | 6100KDP01 | PO-SEP-8409-[5] | PO | 2025-12-15 | LVC |  | - | 2026-04-04 | 2026-03-21 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990162P0102 | PANEL HEATER 240V,100W-Boxin-5MetCable | 41 | 41 | 0 | 6100K023 | PO-SEP-8409-[2] | PO | 2025-12-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990403P0100 | VENTILATOR QK08A-2EM.50.CH WITH CAPACITO | 3 | 3 | 0 | 6100K023 | PO-SEP-8361-[1] | PO | 2025-12-31 | B |  | - | 2026-04-04 | 2026-03-21 | 0 | ZIEHL ABEGG Middle East FZE | Fans / 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990404P0100 | RADIAL FLOW FAN QK08A-2EM.35.CF | 4 | 4 | 0 | 6100K023 | PO-SEP-8361-[2] | PO | 2025-12-31 | B |  | - | 2026-04-04 | 2026-03-21 | 0 | ZIEHL ABEGG Middle East FZE | Fans / 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0990431P0100 | HANDLE | 99 | 99 | 0 | 6100K023 | PO-SEP-8385-[6] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0996027P0100 | PROTECTION CAP M10NR.610 | 216 | 120 | 96 | 6100K023 | PO-SEP-8629-[3] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | FLY METALTECH TRADING CO.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0996027P0100 | PROTECTION CAP M10NR.610 | 96 | 96 | 0 | 6100KDP01 | PO-SEP-8629-[2] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | FLY METALTECH TRADING CO.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0998134P0100 | SEALING RUBBER | 552.43 | 550 | 2.43 | 6100K023 | PO-SEP-8394-[1] | PO | 2025-12-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Suzhou Dirak Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0998134P0100 | SEALING RUBBER | 2.43 | 2.43 | 0 | 6100KDP01 | PO-SEP-8394-[2] | PO | 2025-12-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Suzhou Dirak Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0998162P0100 | REDUCING RING PVC | 703 | 150 | 553 | 6100K023 | PO-SEP-8385-[10] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0998162P0100 | REDUCING RING PVC | 553 | 553 | 0 | 6100KDP01 | PO-SEP-8385-[131] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE0998168P0100 | PLASTIC BUSHING EK/G36 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8385-[164] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4117104P0117 | TUBE G16X9 | 52 | 52 | 0 | 6100K023 | PO-SEP-8385-[13] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4366010P0100 | NUT(DADO D'ANCORAGGIO) M10 WN366-ST37-2 | 264 | 264 | 0 | 6100K023 | PO-SEP-8385-[232] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4395060P0100 | WASHER,PLAIN , LARGE 6.1/18X1 | 24 | 24 | 0 | 6100K023 | PO-SEP-8378-[140] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4395592P0100 | WASHER FLAT 8 X 11 X 0.5 MM | 234 | 84 | 150 | 6100K023 | PO-SEP-8378-[70] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4395592P0100 | WASHER FLAT 8 X 11 X 0.5 MM | 150 | 150 | 0 | 6100KDP01 | PO-SEP-8378-[258] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4395856P0100 | PLAIN WASHER, LARGE 6.2x12x0.2 | 18 | 18 | 0 | 6100K023 | PO-SEP-8378-[71] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4396016P0100 | PLAIN WASSHER 9/33X2.5 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8378-[324] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4396073P0100 | WASHER LARG PLN (12.1/23.5X2.5 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-6812-[21] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4520999P0100 | INDICATION LABELS ( HOCK SYSMBLE ) | 1 | 1 | 0 | 6100K023 | PO-SEP-8379-[42] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4530250P0100 | DESIGNATION LABEL L1 (RED) | 41 | 41 | 0 | 6100K023 | PO-SEP-8379-[4] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4530251P0100 | DESIGNATION LABEL L2 (YELLOW) | 41 | 41 | 0 | 6100K023 | PO-SEP-8379-[5] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4530252P0100 | DESIGNATION LABEL L3 (BLUE) | 41 | 41 | 0 | 6100K023 | PO-SEP-8379-[6] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 40 | 40 | 0 | 6100K023 | PO-SEP-8379-[7] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE4539452P0100 | INDICATION LABEL Mech.Operation STICKER | 39 | 39 | 0 | 6100K023 | PO-SEP-8379-[8] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000495R0101 | SHAFT COMPL. | 26 | 26 | 0 | 6100K023 | PO-SEP-8385-[15] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000496P0102 | TORSION SPRING | 40 | 40 | 0 | 6100K023 | PO-SEP-8387-[3] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000497R0101 | BEARING HOUSING COMPLETE | 40 | 40 | 0 | 6100K023 | PO-SEP-8387-[4] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000507P0101 | ACTUATING LEVEL | 40 | 40 | 0 | 6100K023 | PO-SEP-8509-[11] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000508P0101 | GROOVED PIN | 40 | 37 | 3 | 6100K023 | PO-SEP-8704-[2] | PO | 2025-11-12 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000508P0101 | GROOVED PIN | 3 | 3 | 0 | free_stock | PR-SEP-0024114-[213] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000525P0101 | WASHER,STOP | 40 | 10 | 30 | 6100K023 | PO-SEP-8385-[301] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000525P0101 | WASHER,STOP | 30 | 30 | 0 | 6100KDP01 | PO-SEP-8385-[299] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000552P0101 | STOP WASHER | 80 | 74 | 6 | 6100K023 | PO-SEP-8378-[74] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000552P0101 | STOP WASHER | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[217] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000654P0102 | Slide | 40 | 40 | 0 | 6100K023 | PO-SEP-8509-[12] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000663R0101 | BEVEL GEAR DRIVE FOR EK6 ZS1 | 40 | 40 | 0 | 6100K023 | PO-SEP-8397-[1] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000847P0101P | K - STUD | 2 | 1 | 1 | 6100KDP01 | PO-SEP-8385-[281] | PO | 2025-10-19 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7000847P0101P | K - STUD | 1 | 0 | 1 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7001026P0101 | INSULATION TUBE; L=45MM. | 52 | 52 | 0 | 6100K023 | PO-SEP-8385-[20] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7001732R0105 | EARTHING SWITCH: EK6/ZS1-1710-275 | 3 | 3 | 0 | 6100K023 | PO-SEP-8382-[1] | PO | 2026-01-22 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | Earthing Switch/6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7001732R0106 | EARTHING SWITCH: EK6-ZS1-1710-210 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8382-[4] | PO | 2026-01-22 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | Earthing Switch/6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003008P0101 | RING | 40 | 40 | 0 | 6100K023 | PO-SEP-8387-[5] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003012P0101P | TUBE 8X5.1X25 | 2 | 1 | 1 | 6100KDP01 | PO-SEP-8385-[282] | PO | 2025-10-19 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003012P0101P | TUBE 8X5.1X25 | 1 | 0 | 1 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003538P0101 | COVER | 2 | 2 | 0 | 6100K023 | PO-SEP-8385-[89] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003553P0101P | HEXAGON BOLT | 4 | 0 | 4 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003561P0101 | BRACKET/SHAFT | 4 | 4 | 0 | 6100K023 | PO-SEP-8509-[7] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003563P0101 | SHAFT | 2 | 2 | 0 | 6100K023 | PO-SEP-8396-[15] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003572P0101 | TORSION SPRING | 1 | 1 | 0 | 6100K023 | PO-SEP-8396-[16] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003578P0101 | SQUARE BOLT 4KT8/20 | 2 | 0 | 2 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003579P0101 | TENSION SPRING 6.5/.9/30/16 | 41 | 41 | 0 | 6100K023 | PO-SEP-8396-[1] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003583P0101 | SUPPORT ANGLE | 2 | 2 | 0 | 6100K023 | PO-SEP-8509-[8] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003584P0101 | BRACKET | 2 | 2 | 0 | 6100K023 | PO-SEP-8509-[9] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003694P0102 | CARRIER | 40 | 39 | 1 | 6100K023 | PO-SEP-8397-[2] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7003694P0102 | CARRIER | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[228] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7004025R0102P | DRAW OUT DEVICEP210-S200 ASSY. | 2 | 0 | 2 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7004046R0101 | RECTIFIER COMPL. | 2 | 2 | 0 | 6100K023 | PO-SEP-8385-[120] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7102436P0100 | PLUG HOUSING SOCKET/GEHAUSE | 21 | 21 | 0 | 6100K023 | PO-SEP-8385-[23] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7109399R0101 | AUXILIARY SWITCH 5NO | 80 | 80 | 0 | 6100K023 | PO-SEP-8383-[1] | PO | 2025-12-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Changsha Electric Controlling Auxiliaries Factory | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7109399R0106 | AUXILIARY SWITCH 5NC | 40 | 24 | 16 | 6100K023 | PO-SEP-8385-[25] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7109399R0106 | AUXILIARY SWITCH 5NC | 16 | 16 | 0 | 6100KDP01 | PO-SEP-8385-[156] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7109399R0118 | SLIDE F.AUX.SWICH 5NC | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8385-[163] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7109399R0119 | AUX.SWITCH 5NO. (S8,S9) | 4 | 4 | 0 | 6100K023 | PO-SEP-8385-[90] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7169312R0145 | EARTHING SWITCH: EK6-ZS1-1706-210 | 19 | 19 | 0 | 6100K023 | PO-SEP-8382-[3] | PO | 2026-01-22 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | Earthing Switch/6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7192037R0100 | INSULATOR SGB 24N A1 POT 24kV 2040742 | 9 | 9 | 0 | free_stock | PR-SEP-0024114-[234] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7204654P0101 | BOLT 7/4X15 | 16 | 16 | 0 | 6100KDP01 | PO-SEP-8385-[191] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7208367P0100 | DESIGNATION LABEL | 40 | 32 | 8 | 6100KDP01 | PO-SEP-8379-[34] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7208367P0100 | DESIGNATION LABEL | 8 | 6 | 2 | 6100KDP01 | PO-SEP-6543-[58] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | Labels for outdoor
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7208367P0100 | DESIGNATION LABEL | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[236] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7208368P0100 | DESIGNATION LABEL | 40 | 7 | 33 | 6100KDP01 | PO-SEP-8379-[35] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7208368P0100 | DESIGNATION LABEL | 33 | 6 | 27 | 6100KDP01 | PO-SEP-6543-[59] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | Labels for outdoor
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE7208368P0100 | DESIGNATION LABEL | 27 | 27 | 0 | free_stock | PR-SEP-0024114-[237] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8000336P0101 | K- INTERMEDIATE PIECE 40x6x9(ZINC CHR.) | 80 | 80 | 0 | 6100K023 | PO-SEP-8402-[2] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8000633P0113P | MOUNTING CHANNEL 760mm (GCE8000633P0113) | 76 | 68 | 8 | 6100K023 | PO-SEP-8385-[42] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8000633P0113P | MOUNTING CHANNEL 760mm (GCE8000633P0113) | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8385-[130] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8000801P0101P | CONTACT PIN, RD.79MM L=107MM | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8385-[176] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8000881P0102 | INTERMEDITE PLATE 80x15x125 CU SILVERPLA | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8385-[204] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8001698R0107P | LEVER MECHANISM LEFT-SX 2X R250/55(w1000 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8385-[226] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8001698R0108P | LEVER MECHANISM RIGHT,DX2X R250/55(w1000 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8385-[225] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8001710P0101 | SPECIAL BOLT | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8403-[15] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8001975P0101 | WASHER 40X21X10 (LOCAL PUR) | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8378-[363] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8001976P0101 | WASHER 40X21X2 | 18 | 18 | 0 | 6100K023 | PO-SEP-8387-[33] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8002187P0101 | FLANGE PLATE | 105 | 105 | 0 | 6100K023 | PO-SEP-8509-[6] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8002371P0101 | BOLT GUIDE | 4 | 2 | 2 | 6100KDP01 | PO-SEP-8385-[246] | PO | 2025-10-12 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8002371P0101 | BOLT GUIDE | 2 | 2 | 0 | 6100KDP01 | PO-SEP-6812-[129] | PO | 2025-12-31 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8002757P0107 | COVER | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8385-[203] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8002866R0102P | PADLOCK ES - NORMAL | 40 | 40 | 0 | 6100K023 | PO-SEP-8396-[2] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003360R0101P | LEVER MECHANISM LEFT, 2xR250/55(W800) | 16 | 16 | 0 | 6100K023 | PO-SEP-8385-[74] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003360R0102P | LEVER MECHANISM RIGHT,2xR250/55 (W800) | 16 | 16 | 0 | 6100K023 | PO-SEP-8385-[75] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003624R0102 | MONOBLOCCO-SPOUT 1250A,ZS1 | 108 | 108 | 0 | 6100K023 | PO-SEP-8381-[5] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Europroxy FZCO | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003638P0103P | INTER LOCKING AGLE LEFT | 41 | 41 | 0 | 6100K023 | PO-SEP-8396-[3] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003638P0104P | INTERLOCKING ANGLE RIGHT | 41 | 41 | 0 | 6100K023 | PO-SEP-8396-[4] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003651P0101P | INSULATING CAP | 37 | 37 | 0 | 6100K023 | PO-SEP-8385-[76] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003671P0102 | SPECIAL SCREW M12 X 50/20 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8403-[16] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003671P0116 | SPCEIAL SCREW M12X34/45 | 148 | 80 | 68 | 6100K023 | PO-SEP-8523-[3] | PO | 2025-10-23 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003671P0116 | SPCEIAL SCREW M12X34/45 | 68 | 68 | 0 | 6100KDP01 | PO-SEP-8523-[9] | PO | 2025-10-23 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003671P0120 | SPECIAL SCREW M12X30/101 | 74 | 74 | 0 | 6100K023 | PO-SEP-8523-[4] | PO | 2025-10-23 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003824P0101 | K- SUPPORT PLATE YELLOW CHROMATION. | 37 | 37 | 0 | 6100K023 | PO-SEP-8402-[21] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003861P0101 | BEARING SHAFT (ZINC CHRM) | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8523-[13] | PO | 2025-10-23 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003899R0101 | SPOUT 12KV, >2500A | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[370] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003900P0101 | COVER FOR SPOUT | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[371] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003900P0102 | COVER FOR SPOUT | 18 | 6 | 12 | 606PD013 | PO-SEP-8385-[236] | PO | 2025-10-14 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8003900P0102 | COVER FOR SPOUT | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[251] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 41 | 11 | 30 | 6100K023 | PO-SEP-8387-[8] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 30 | 30 | 0 | free_stock | PR-SEP-0024114-[253] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8004437P0103P | SHROUD (EARTHING CONTACT)GCE8004437P0103 | 72 | 60 | 12 | 6100KDP01 | PO-SEP-8385-[206] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8004437P0103P | SHROUD (EARTHING CONTACT)GCE8004437P0103 | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[372] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8004471R0101P | ELECTRODE, ZS1 95kV BIL | 15 | 15 | 0 | free_stock | PR-SEP-0024114-[254] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8004944R0101 | SPOUT ZS1 (4000A) | 18 | 18 | 0 | free_stock | PR-SEP-0024114-[256] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005031R0101 | BUSHING ZS1/ (3 IN 1) DEACE | 28 | 28 | 0 | 6100K023 | PO-SEP-8381-[11] | PO | 2025-11-30 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Europroxy FZCO | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005041P0101P | CONTACT PIN 109mm,3150A(GCE8005041P0101) | 18 | 18 | 0 | free_stock | PR-SEP-0024114-[257] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005042P0101 | CONNECTION PIECE 3150A ZS1 | 9 | 9 | 0 | free_stock | PR-SEP-0024114-[258] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005049P0101 | SUPPORT (POLY ) T = SHAPE | 6 | 3 | 3 | 6100K023 | PO-SEP-8396-[5] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005049P0101 | SUPPORT (POLY ) T = SHAPE | 3 | 3 | 0 | free_stock | PR-SEP-0024114-[259] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005112P0103P | OPERATING BOLT | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[260] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005117P0101 | CARRIER | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[261] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005136P0101 | SUPPORT (POLY) | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8396-[45] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005164P0101 | SCREENING | 54 | 54 | 0 | free_stock | PR-SEP-0024114-[262] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005250P0101 | K- LIFTING HOOK (ZINC CHROM) | 164 | 152 | 12 | 6100K023 | PO-SEP-8402-[9] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005250P0101 | K- LIFTING HOOK (ZINC CHROM) | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[263] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005595R0102P | BUSBAR ZS D100, 12THICK,800/800, L=795 | 204 | 96 | 108 | 6100K023 | PO-SEP-8385-[122] | PO | 2025-09-21 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005595R0102P | BUSBAR ZS D100, 12THICK,800/800, L=795 | 108 | 108 | 0 | 6100KDP01 | PO-SEP-8385-[249] | PO | 2025-10-12 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005595R0109P | Busbar D100,12mm Thick 800/1000,L=830 | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8385-[250] | PO | 2025-10-12 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005595R0110P | Busbar D100,12mm Thick 800/1000,L=895 | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8385-[251] | PO | 2025-10-12 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8005595R0111P | Busbar D100,12mm Thick 800/1000,L=960 | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8385-[252] | PO | 2025-10-12 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8006587P0101 | LOCK SCREW M6X25 ( ROUND FLAT HEAD ) | 296 | 88 | 208 | 6100KDP01 | PO-SEP-8403-[5] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8006587P0101 | LOCK SCREW M6X25 ( ROUND FLAT HEAD ) | 208 | 208 | 0 | free_stock | PR-SEP-0024114-[264] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8007213P0101 | SHROUD ZS3.2, Middle | 18 | 3 | 15 | 6100K023 | PO-SEP-8385-[109] | PO | 2025-09-21 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8007213P0101 | SHROUD ZS3.2, Middle | 15 | 15 | 0 | 6100KDP01 | PO-SEP-8385-[255] | PO | 2025-10-12 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8007214P0101 | COVER FOR SHROUD ZS3.2, end side | 36 | 6 | 30 | 6100K023 | PO-SEP-8385-[110] | PO | 2025-09-21 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8007214P0101 | COVER FOR SHROUD ZS3.2, end side | 30 | 30 | 0 | 6100KDP01 | PO-SEP-8385-[259] | PO | 2025-10-12 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8008881P0103 | BRACKET BOTTOM | 74 | 64 | 10 | 6100K023 | PO-SEP-8402-[22] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8008881P0103 | BRACKET BOTTOM | 10 | 10 | 0 | free_stock | PR-SEP-0024114-[265] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8008881P0104 | SHUTTER BRACKET | 78 | 70 | 8 | 6100K023 | PO-SEP-8402-[23] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8008881P0104 | SHUTTER BRACKET | 8 | 8 | 0 | free_stock | PR-SEP-0024114-[266] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 41 | 11 | 30 | 6100K023 | PO-SEP-8387-[9] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 30 | 30 | 0 | free_stock | PR-SEP-0024114-[267] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010004P0102 | GUIDE RAIL RIGHT 12kV | 41 | 9 | 32 | 6100K023 | PO-SEP-8387-[10] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010004P0102 | GUIDE RAIL RIGHT 12kV | 32 | 32 | 0 | free_stock | PR-SEP-0024114-[268] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010008P0101 | BUSHING PLATE (STAINLESS STEEL) | 39 | 39 | 0 | 6100K023 | PO-SEP-8402-[36] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010022P0111R | SHUTTER UPPER W800 (GCE8010022P0111) | 38 | 9 | 29 | 6100K023 | PO-SEP-8396-[10] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010022P0111R | SHUTTER UPPER W800 (GCE8010022P0111) | 29 | 29 | 0 | free_stock | PR-SEP-0024114-[373] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010022P0112Y | SHUTTER LOWER W800 (GCE8010022P0112) | 36 | 11 | 25 | 6100K023 | PO-SEP-8396-[11] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010022P0112Y | SHUTTER LOWER W800 (GCE8010022P0112) | 25 | 25 | 0 | free_stock | PR-SEP-0024114-[374] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010022P0113R | SHUTTER UPPER (DWG.GCE8010022P0113) | 3 | 3 | 0 | free_stock | PR-SEP-0024114-[269] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010022P0114Y | SHUTTER LOWER (DWG.GCE8010022P0114) | 3 | 3 | 0 | free_stock | PR-SEP-0024114-[270] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 75 | 22 | 53 | 6100K023 | PO-SEP-8396-[18] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 53 | 53 | 0 | free_stock | PR-SEP-0024114-[272] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010028R0103 | PRESSURE RELIEF FLAP W1000 | 5 | 1 | 4 | 6100KDP01 | PO-SEP-8396-[27] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010028R0103 | PRESSURE RELIEF FLAP W1000 | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[273] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010028R0105 | PRESSURE RELIEF FLAP, REAR | 3 | 3 | 0 | free_stock | PR-SEP-0024114-[274] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010028R0106 | PRESSURE RELIEF FLAP W1000 | 3 | 0 | 3 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010073P0102 | PARTITION WALL | 38 | 32 | 6 | 6100K023 | PO-SEP-8402-[24] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010073P0102 | PARTITION WALL | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[375] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010073P0103 | BB/CB.PARTITION WALL W1000(PaintRAL7035) | 3 | 3 | 0 | 6100K023 | PO-SEP-8402-[10] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010096P0101P | PIN 12DIA(ZINC COAT)DWG:GCE8010096P0101 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8704-[4] | PO | 2025-11-12 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010097P0101 | MOUNTING PLATE W800, S=310 | 2 | 1 | 1 | 6100K023 | PO-SEP-8402-[25] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010097P0101 | MOUNTING PLATE W800, S=310 | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[376] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010097P0102 | MOUNTING PLATE S=310 W1000 | 3 | 1 | 2 | 6100K023 | PO-SEP-8402-[11] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010097P0102 | MOUNTING PLATE S=310 W1000 | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[333] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010104P0103P | BUSHING D60/49X25 | 18 | 18 | 0 | free_stock | PR-SEP-0024114-[277] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010104P0104P | BUSHING D58/47X25 | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[377] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010178P0102 | SUPPORT ANGLE | 38 | 27 | 11 | 6100K023 | PO-SEP-8402-[26] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010178P0102 | SUPPORT ANGLE | 11 | 11 | 0 | free_stock | PR-SEP-0024114-[378] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8010178P0103 | SUPPORT ANGLE W1000 | 3 | 3 | 0 | 6100K023 | PO-SEP-8402-[12] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011408P0101 | MOUNTING PLATE W800, METERING | 2 | 2 | 0 | 6100K023 | PO-SEP-8402-[34] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011549P0101 | CT-COOLER(HEAT SINK) | 9 | 3 | 6 | free_stock | PO-SEP-8340-[1] | PO | 2025-12-20 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AB KOMPONENTY s.r.o. | CT Cooler
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011549P0101 | CT-COOLER(HEAT SINK) | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8483-[3] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AB KOMPONENTY s.r.o. | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011552P0102 | FLAT SCREEN FOR CB.MIDDLE PLATE W800 | 34 | 20 | 14 | 6100K023 | PO-SEP-8396-[12] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011552P0102 | FLAT SCREEN FOR CB.MIDDLE PLATE W800 | 14 | 14 | 0 | 6100KDP01 | PO-SEP-8396-[43] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011642P0101 | SPACER | 243 | 236 | 7 | 6100KDP01 | PO-SEP-8385-[154] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011642P0101 | SPACER | 7 | 7 | 0 | free_stock | PR-SEP-0024114-[280] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011650P0101 | SUPPORT REINFORCEMENT | 3 | 3 | 0 | 6100K023 | PO-SEP-8402-[13] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011673P0101 | PARTITION WALL W800 | 2 | 2 | 0 | 6100K023 | PO-SEP-8402-[35] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011673P0102 | Partition Wall W1000 | 2 | 2 | 0 | 6100K023 | PO-SEP-8402-[14] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8011710P0103 | RIB | 24 | 24 | 0 | free_stock | PR-SEP-0024114-[380] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8012119P0101 | STRENGTHENING STRIP (5mmx30x2005mm) W800 | 4 | 2 | 2 | 6100KDP01 | PO-SEP-5654-[38] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries)
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8012119P0101 | STRENGTHENING STRIP (5mmx30x2005mm) W800 | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[381] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8012119P0102 | STRENGTHENING STRIP (5mmx30x710mm)W800 | 2 | 1 | 1 | 6100KDP01 | PO-SEP-5654-[39] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES | 6100KDP01 // MV SWGR (New Batha & United Cement SS) Category "LAX, LV, Outsource" Material (Supplier-First Telecom Industries)
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8012119P0102 | STRENGTHENING STRIP (5mmx30x710mm)W800 | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[382] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8012228P0101 | SUPPORTING SHEET | 18 | 18 | 0 | 6100K023 | PO-SEP-8402-[37] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013214P0101 | PARTITION WALL BOTTOM W800 (SS STL)BARE | 36 | 26 | 10 | 6100K023 | PO-SEP-8402-[30] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013214P0101 | PARTITION WALL BOTTOM W800 (SS STL)BARE | 10 | 10 | 0 | free_stock | PR-SEP-0024114-[383] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013244P0101 | TRANSFORMER PLATE W800mm | 36 | 26 | 10 | 6100K023 | PO-SEP-8402-[31] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013244P0101 | TRANSFORMER PLATE W800mm | 10 | 0 | 10 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013263P0101 | SHROUD | 68 | 68 | 0 | 6100K023 | PO-SEP-8396-[13] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013412R0101 | PRESSURE RELIEF FLAP FOR W1000 | 3 | 3 | 0 | free_stock | PR-SEP-0024114-[284] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013414P0101 | FIXING PLATE FOR DUCT | 3 | 3 | 0 | 6100K023 | PO-SEP-8402-[15] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013419R0101 | FRAME FOR FLAT SCREEN COMPLETE | 3 | 2 | 1 | 6100K023 | PO-SEP-8396-[8] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013419R0101 | FRAME FOR FLAT SCREEN COMPLETE | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[286] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013423P0101 | PARTITION WALL W1000 (PAINTED RAL7035) | 3 | 3 | 0 | 6100K023 | PO-SEP-8402-[16] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013427P0101 | GAIN CT PLATE | 3 | 3 | 0 | 6100K023 | PO-SEP-8402-[38] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013430P0101 | COOLING PLATE 1 ( small ) | 9 | 9 | 0 | free_stock | PR-SEP-0024114-[289] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013431P0101 | COOLING PLATE 2 ( Big ) | 9 | 9 | 0 | free_stock | PR-SEP-0024114-[290] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013433P0101P | SHROUD (DWG NO. GCE8013433P0101) | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[291] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013434P0101P | SHROUD (DWG NO. GCE8013434P0101) | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[292] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013434P0102P | SHROUD (DWG NO. GCE8013434P0102) | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[293] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013435P0101P | SPACER DISC (GCE8013435P0101) | 48 | 48 | 0 | free_stock | PR-SEP-0024114-[294] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8013444R0101 | PRESSURE RELIEF FLAP(W1000) | 3 | 3 | 0 | free_stock | PR-SEP-0024114-[295] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8487370R0100 | EARTHING CONTACT | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[296] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 47 | 16 | 31 | 6100K023 | PO-SEP-8379-[41] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 31 | 4 | 27 | 6100KDP01 | PO-SEP-8379-[38] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 27 | 27 | 0 | free_stock | PR-SEP-0024114-[298] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8684080P0101 | EARTHING STRIP | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[299] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE8685778P0121P | CONTACT PIN 800/1200A SIL.COAT = 72L | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8385-[278] | PO | 2025-10-19 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9401556P0100 | STOP WASHER | 80 | 8 | 72 | 6100K023 | PO-SEP-8378-[326] | PO | 2025-11-17 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9401556P0100 | STOP WASHER | 72 | 12 | 60 | 6100KDP01 | PO-SEP-6812-[39] | PO | 2025-12-31 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9401556P0100 | STOP WASHER | 60 | 60 | 0 | free_stock | PR-SEP-0024114-[301] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9401766P0107 | LOCKING MAGNET DC125 V | 40 | 18 | 22 | 6100K023 | PO-SEP-8501-[1] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Xiamen Leelen High Voltage Electric Co. Ltd | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9401766P0107 | LOCKING MAGNET DC125 V | 22 | 16 | 6 | 6100KDP01 | PO-SEP-8501-[3] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Xiamen Leelen High Voltage Electric Co. Ltd | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9401766P0107 | LOCKING MAGNET DC125 V | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[302] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9476775R0100 | IND.CONTACT/ VAN FLOW SWITCH | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[304] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCE9477367P0102 | FORK D11x20 | 9 | 9 | 0 | free_stock | PR-SEP-0024114-[305] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | GCEC830444P0101P | K-SPACER D12/4.5X8,ZS1/ZS3.2Yellow Chrom | 50 | 50 | 0 | 6100K023 | PO-SEP-8385-[65] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MARWI60236 | Zack Strip-Vertical(1-10) - 1053027:0001 | 492 | 492 | 0 | 6100K025 | PO-SEP-8792-[6] | PO | 2025-12-20 | Terminals |  | - | 2026-04-04 | 2026-03-21 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 82 | 36 | 46 | 6100K023 | PO-SEP-8446-[2] | PO | 2025-11-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Ningbo Shengjiu Technology CO., LTD. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 46 | 46 | 0 | free_stock | PR-SEP-0024114-[309] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 78 | 36 | 42 | free_stock | PO-SEP-8388-[7] | PO | 2025-10-30 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 42 | 42 | 0 | 6100K025 | PO-SEP-8836-[2] | PO | 2025-11-13 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV50001 | Incomer Upper CT, INC3600-13.8-UCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K023 | PO-SEP-8758-[1] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-04 | 2026-03-21 | 0 |  | 6100K023 Halfmoon SS SWGR CT/Order
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV50002 | Incomer Lower CT, INC3600-13.8-LCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K025 | PO-SEP-8756-[2] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-04 | 2026-03-21 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV50003 | Capacitor O/G Feeder Upper CT, CAP1250-13.8-UCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K025 | PO-SEP-8756-[3] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-04 | 2026-03-21 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV50004 | Capacitor O/G Feeder Lower CT, CAP1250-13.8-LCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K025 | PO-SEP-8756-[4] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-04 | 2026-03-21 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV50005 | Station Auxiliary Upper CT, SST630-13.8-UCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K025 | PO-SEP-8756-[5] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-04 | 2026-03-21 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV50006 | Station Auxiliary Lower CT, SST630-13.8-LCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K025 | PO-SEP-8756-[6] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-04 | 2026-03-21 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV50007 | Outgoing Plain Upper CT, OG1250-13.8-UCT ¦ ¦ RITZ | 96 | 96 | 0 | 6100K025 | PO-SEP-8756-[7] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-04 | 2026-03-21 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV50008 | Outgoing plain Lower CT, OG1250-13.8-LCT ¦ ¦ RITZ | 96 | 96 | 0 | 6100K025 | PO-SEP-8756-[8] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-04 | 2026-03-21 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV50009 | BusTie Upper CT, BS3600-13.8-UCT ¦ ¦ RITZ | 3 | 3 | 0 | 6100K025 | PO-SEP-8756-[9] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-04 | 2026-03-21 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | MV50010 | Bus-Tie Lower CT, BS3600-13.8-LCT ¦ ¦ RITZ | 3 | 3 | 0 | 6100K025 | PO-SEP-8756-[10] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-04 | 2026-03-21 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SAME CODE | UN-INSUL SLeve Lugs KE1510ST (1.5mm) | 820 | 0 | 820 | PR Required | - | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SAME CODE | UN-INSUL SLEEVE Lugs for 2.5mm KE2510ST | 2050 | 0 | 2050 | PR Required | - | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SAME CODE | Un-Insul Sleeve Lugs 4.0 mm KE410ST | 2050 | 0 | 2050 | PR Required | - | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SAME CODE | TERM.LUGS BLADE BF-PP12/25 2.5MM | 4100 | 0 | 4100 | PR Required | - | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SAME CODE | TERM.LUGS SPADE RF-U4 1.5/M4 | 5125 | 0 | 5125 | PR Required | - | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SAME CODE | TERM.LUGS BLADE RF-PP 12/23 | 12300 | 0 | 12300 | PR Required | - | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000022P0001 | K-SLIDING PART | 40 | 21 | 19 | 6100K023 | PO-SEP-8509-[4] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000022P0001 | K-SLIDING PART | 19 | 19 | 0 | free_stock | PR-SEP-0024114-[331] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000024P0001P | BUSHING (LOCAL PUR) | 40 | 10 | 30 | 6100K023 | PO-SEP-8484-[8] | PO | 2025-12-15 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000024P0001P | BUSHING (LOCAL PUR) | 30 | 30 | 0 | free_stock | PR-SEP-0024114-[310] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000025P0001P | BUSHING (LOCAL PUR) | 90 | 90 | 0 | free_stock | PR-SEP-0024114-[311] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000026P0001P | BUSHING (LOCAL PUR) | 123 | 71 | 52 | free_stock | PR-SEP-0024114-[312] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000026P0001P | BUSHING (LOCAL PUR) | 52 | 0 | 52 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000037P0001 | K-LEVER | 41 | 22 | 19 | free_stock | PO-SEP-8659-[1] | PO | 2025-10-30 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Laser Company for Metal Industries Ltd | K-Lever ¦ SCB1000037P0001 ¦ ABB
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000037P0001 | K-LEVER | 19 | 19 | 0 | free_stock | PR-SEP-0024114-[330] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000047P0001 | INTERLOCKING SCOTCH | 41 | 9 | 32 | 6100K023 | PO-SEP-8523-[2] | PO | 2025-10-23 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000047P0001 | INTERLOCKING SCOTCH | 32 | 32 | 0 | free_stock | PR-SEP-0024114-[314] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1000048P0001P | PIN (LOCAL PUR) | 16 | 16 | 0 | free_stock | PR-SEP-0024114-[315] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1001678P0001 | HOOKING LEVER (ZINC PLATED) | 2 | 1 | 1 | 6100K023 | PO-SEP-8402-[39] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1001678P0001 | HOOKING LEVER (ZINC PLATED) | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8402-[78] | PO | 2025-11-17 | Mechanical - Accessories |  | - | 2026-04-04 | 2026-03-21 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1001813R0802P | MECHANICAL OFF BUTTON FOR VD4 - HOR | 39 | 7 | 32 | 6100K023 | PO-SEP-8385-[67] | PO | 2025-09-21 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1001813R0802P | MECHANICAL OFF BUTTON FOR VD4 - HOR | 32 | 32 | 0 | 6100KDP01 | PO-SEP-8385-[136] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1001915P0001P | PIN | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[318] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1001916P0001P | INTERLOCK LEVER (LOCAL PUR) | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[319] | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SCB1001982P0001 | ROLLER | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8385-[198] | PO | 2025-10-05 | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10038 | Humidistat, 250V, AC, MFR 012 ¦ 01220.0-00 | 41 | 6 | 35 | 6100KDP02 | PO-SEP-8198-[1] | PO | 2025-10-09 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | STEGO Elektrotechnik GmbH | PP-12 additional components
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10038 | Humidistat, 250V, AC, MFR 012 ¦ 01220.0-00 | 35 | 1 | 34 | 6100K019 | PO-SEP-8198-[2] | PO | 2025-10-09 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | STEGO Elektrotechnik GmbH | PP-12 additional components
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10038 | Humidistat, 250V, AC, MFR 012 ¦ 01220.0-00 | 34 | 34 | 0 | 6100K025 | PO-SEP-8819-[1] | PO | 2025-12-31 | LVA |  | - | 2026-04-04 | 2026-03-21 | 0 | STEGO Elektrotechnik GmbH | Humidistat, 250V, AC, MFR 012
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10162 | WHITE TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 10250 | 10250 | 0 | free_stock | PR-SEP-0024130-[175] | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10163 | RED TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 410 | 180 | 230 | free_stock | PR-SEP-0023081-[170] | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10163 | RED TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 230 | 0 | 230 | PR Required | - | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 615 | 25 | 590 | free_stock | PO-SEP-7326-[26] | PO | 2025-05-18 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Raja Procuremnet Local Purchases
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 590 | 50 | 540 | free_stock | PO-SEP-7636-[5] | PO | 2025-09-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | LV-BULK ITEMS | 50 | 09-10-2025
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 540 | 4 | 536 | 6100K021 | PO-SEP-8881-[1] | PO | 2025-12-21 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 536 | 4 | 532 | 6100K025 | PO-SEP-8884-[1] | PO | 2025-12-21 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 532 | 1 | 531 | 6100K024 | PO-SEP-8879-[1] | PO | 2025-12-21 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K024 SMRU 3L Mechanistical Componentes.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 531 | 15 | 516 | free_stock | PO-SEP-8502-[33] | PO | 2025-12-31 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 516 | 4 | 512 | 6100K020 | PO-SEP-8830-[1] | PO | 2025-12-31 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K020 Mahar SS SWGR Electrical components order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 512 | 512 | 0 | free_stock | PR-SEP-0023387-[166] | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10298 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 410 | 410 | 0 | free_stock | PR-SEP-0023387-[167] | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10349 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 410 | 5 | 405 | 6100K025 | PO-SEP-8884-[3] | PO | 2025-10-23 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10349 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 405 | 5 | 400 | 6100K021 | PO-SEP-8881-[3] | PO | 2025-12-21 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10349 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 400 | 1 | 399 | 6100K024 | PO-SEP-8879-[3] | PO | 2025-12-21 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K024 SMRU 3L Mechanistical Componentes.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10349 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 399 | 5 | 394 | 6100K020 | PO-SEP-8830-[3] | PO | 2025-12-31 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K020 Mahar SS SWGR Electrical components order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10349 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 394 | 394 | 0 | free_stock | PR-SEP-0023387-[169] | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10650 | WHITE TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 1640 | 680 | 960 | free_stock | PR-SEP-0023081-[172] | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP10650 | WHITE TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 960 | 0 | 960 | PR Required | - | PR |  | LVD |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11258 | Cable, Control, 1 Core,CU/PVC, 1.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 89.7155 | 72 | 17.7155 | 6100K023 | PO-SEP-8622-[1] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11258 | Cable, Control, 1 Core,CU/PVC, 1.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 17.7155 | 17.7155 | 0 | 6100K020 | PO-SEP-8915-[44] | PO | 2026-01-11 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11259 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 29.1575 | 25 | 4.1575 | 6100K023 | PO-SEP-8622-[2] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11259 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 4.1575 | 4.1575 | 0 | 6100K025 | PO-SEP-8915-[2] | PO | 2026-01-11 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11260 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 673.9606 | 616 | 57.9606 | 6100K023 | PO-SEP-8622-[3] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11260 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 57.9606 | 1 | 56.9606 | 6100K023 | PO-SEP-8622-[35] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11260 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 56.9606 | 56.9606 | 0 | 6100K021 | PO-SEP-8915-[18] | PO | 2026-01-11 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11261 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 29.1575 | 23 | 6.1575 | 6100K023 | PO-SEP-8622-[4] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11261 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 6.1575 | 6.1575 | 0 | 6100K025 | PO-SEP-8915-[4] | PO | 2026-01-11 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11262 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 121.116 | 105 | 16.116 | 6100K023 | PO-SEP-8622-[5] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11262 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 16.116 | 16.116 | 0 | 6100K020 | PO-SEP-8915-[48] | PO | 2026-01-11 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11263 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 76.2582 | 70 | 6.2582 | 6100K023 | PO-SEP-8622-[6] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11263 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 6.2582 | 6.2582 | 0 | 6100K025 | PO-SEP-8915-[6] | PO | 2026-01-11 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11264 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 22.4289 | 22 | 0.42888 | 6100K023 | PO-SEP-8622-[7] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11264 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 0.42888 | 0.42888 | 0 | 6100K025 | PO-SEP-8915-[7] | PO | 2026-01-11 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11265 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm Yellow/Green, ATC, 105°, 600/1000V , 1 x 100 m | 22.5383 | 21 | 1.5383 | 6100K023 | PO-SEP-8622-[8] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11265 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm Yellow/Green, ATC, 105°, 600/1000V , 1 x 100 m | 1.5383 | 1 | 0.53829 | 6100K023 | PO-SEP-8622-[36] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11265 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm Yellow/Green, ATC, 105°, 600/1000V , 1 x 100 m | 0.53829 | 0.53829 | 0 | 6100K025 | PO-SEP-8915-[8] | PO | 2026-01-11 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11266 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 121.116 | 111 | 10.116 | 6100K023 | PO-SEP-8622-[9] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11266 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 10.116 | 10.116 | 0 | 6100K025 | PO-SEP-8915-[9] | PO | 2026-01-11 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11267 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Yellow, ATC,105°, 600/1000V , 1 x 100 m | 121.116 | 105 | 16.116 | 6100K023 | PO-SEP-8622-[10] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11267 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Yellow, ATC,105°, 600/1000V , 1 x 100 m | 16.116 | 16.116 | 0 | 6100K020 | PO-SEP-8915-[53] | PO | 2026-01-11 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11268 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 6.7287 | 6.7287 | 0 | 6100K023 | PO-SEP-8622-[11] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11269 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 8.9716 | 8.9716 | 0 | 6100K023 | PO-SEP-8622-[12] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11270 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 6.7287 | 6.7287 | 0 | 6100K023 | PO-SEP-8622-[13] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11271 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Yellow, ATC, 105°, 600/1000V , 1 x 100 m | 6.7287 | 6.7287 | 0 | 6100K023 | PO-SEP-8622-[14] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP11272 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 8.9716 | 8.9716 | 0 | 6100K023 | PO-SEP-8622-[15] | PO | 2026-01-30 | Wire |  | - | 2026-04-04 | 2026-03-21 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12016 | RING TYPE LUGS GF-M 5 | 820 | 820 | 0 | 6100K023 | PO-SEP-8418-[12] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12026 | BENT LUGS TYPE RF-PPL30 | 28700 | 28700 | 0 | 6100K023 | PO-SEP-8418-[2] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12048 | END SLEEVES PKE 1508 (1x1.5sqmm , Black) | 615 | 615 | 0 | 6100K023 | PO-SEP-8418-[17] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12052 | END SLEEVES PKT 1508 (2x1.5sqmm , Black) | 615 | 615 | 0 | 6100K023 | PO-SEP-8418-[19] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12083 | TERM.LUGS BF-M5 (RING) | 4920 | 4920 | 0 | 6100K023 | PO-SEP-8418-[14] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12085 | WIRE LUGS RING TYPE BF-M6 2.5/M6 | 328 | 328 | 0 | 6100K023 | PO-SEP-8418-[15] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12087 | RING TYPE LUGS BF-M 8 | 328 | 328 | 0 | 6100K023 | PO-SEP-8418-[16] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12091 | BENT LUGS TYPE BF-PPL30 | 12300 | 12300 | 0 | 6100K023 | PO-SEP-8418-[4] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12105 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 820 | 820 | 0 | 6100K023 | PO-SEP-8418-[18] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12117 | TERM.LUGS RING RF-M4 1.5/M4 | 4100 | 4100 | 0 | 6100K023 | PO-SEP-8418-[13] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12117 | TERM.LUGS RING BF-M4 | 8200 | 4100 | 4100 | 6100K023 | PO-SEP-8418-[13] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12117 | TERM.LUGS RING BF-M4 | 4100 | 4100 | 0 | 6100K025 | PO-SEP-8894-[51] | PO | 2025-10-23 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12119 | FORK SPADE BF-U4 2.5/M4 | 1968 | 900 | 1068 | 6100K023 | PO-SEP-8418-[11] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12119 | FORK SPADE BF-U4 2.5/M4 | 1068 | 1020 | 48 | 6100K025 | PO-SEP-8894-[49] | PO | 2025-10-23 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12119 | FORK SPADE BF-U4 2.5/M4 | 48 | 48 | 0 | 6100K021 | PO-SEP-8894-[30] | PO | 2025-10-27 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12127 | BENT LUGS TYPE BF-PPL46 | 6150 | 6150 | 0 | 6100K023 | PO-SEP-8418-[3] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12131 | Lugs, Sleeve 4.0/9mm ( W/O Ins.) 3200302 | 2050 | 2050 | 0 | 6100K023 | PO-SEP-8418-[1] | PO | 2025-11-30 | LVD |  | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | VT-GUARD-13.8KV | VT Guard, Anti Ferro Resonance Unit ¦ VT-GUARD-13.8KV | 1 | 1 | 0 | 6100K023 | PO-SEP-8749-[3] | PO | 2025-12-31 | RVT |  | - | 2026-04-04 | 2026-03-21 | 0 | Abb Electrical Industriesco | VT Guard/6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | XM 2000 1000-22 | POLYCARBONATE 2000X1000X2.0 MM | 12 | 0 | 12 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | XM 2050 1500-30 | POLYCARBONATE 2050X1500X3.0 MM | 128.06 | 0 | 128.06 | PR Required | - | PR |  | Mechanical |  | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP40202 | Busbar, Copper, 80 x 10 mm, R=5 | 2420.52 | 259.47 | 2161.05 | free_stock | PO-SEP-8672-[5] | PO | 2025-12-15 | Mechanical | Automated: Replaced 1535 1034-227 by SEP40202. Automated: Replaced 1535 1034-227 by SEP40202. | - | 2026-04-04 | 2026-03-21 | 0 | Innovation Solutions Factory | Copper Busbar for ACDC
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP40202 | Busbar, Copper, 80 x 10 mm, R=5 | 2161.05 | 2161.05 | 0 | free_stock | PR-SEP-0024114-[323] | PR |  | Mechanical | Automated: Replaced 1535 1034-227 by SEP40202. Automated: Replaced 1535 1034-227 by SEP40202. | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP40210 | Busbar, Copper, 120 x 10 mm, R=5 | 559.683 | 559.683 | 0 | 6100K023 | PO-SEP-8566-[15] | PO | 2025-11-27 | Mechanical | Automated: Replaced 1535 1034-495 by SEP40210. Automated: Replaced 1535 1034-495 by SEP40210. | - | 2026-04-04 | 2026-03-21 | 0 | Innovation Solutions Factory
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP40181 | Busbar, Copper, 32 x 8 mm, R=1 | 115.59 | 115.59 | 0 | 6100K023 | PO-SEP-8566-[12] | PO | 2025-11-27 | Mechanical | Automated: Replaced 1535 1044-253 by SEP40181. Automated: Replaced 1535 1044-253 by SEP40181. | - | 2026-04-04 | 2026-03-21 | 0 | Innovation Solutions Factory
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP40173 | Busbar, Copper, 30 x 5 mm, R=1 | 90.913 | 90.913 | 0 | 6100K023 | PO-SEP-8566-[13] | PO | 2025-11-27 | Mechanical | Automated: Replaced 1535 1048-217 by SEP40173. Automated: Replaced 1535 1048-217 by SEP40173. | - | 2026-04-04 | 2026-03-21 | 0 | Innovation Solutions Factory
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1SNA234000R0200 | Marker, RC810, 1 ¦ 10/1SNA234041R2600 ¦ ENTRELEC | 410 | 410 | 0 | 6100K023 | PO-SEP-8386-[1] | PO | 2025-11-10 | Terminals | Automated: Replaced 1SNA234000R0200 by SEP20333. | - | 2026-04-04 | 2026-03-21 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5340XIAXXN01 | Relay, Auxiliary, 2 Coils, Self Reset Contacts, Hand Reset Flag, 110-125V, DC, 2NO, 1NC, Coil ¦ RXSF1 RK 271 007-AN | 41 | 41 | 0 | 6100K023 | PO-SEP-8751-[33] | PO | 2025-12-31 | LVA | Automated: Replaced 1YAB5340XIAXXN01 by DM0000000058. | - | 2026-04-04 | 2026-03-21 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block, TB, Disconnecting TB for CT, OTTA 6-T, Bolt W/O Spring, 0790462 ¦ OTTA 6-T P/P ¦ PHOENIX | 1612 | 1612 | 0 | 6100KDP01 | PO-SEP-8572-[1] | PO | 2025-12-15 | Terminals | Automated: Replaced 1YAB5355AAB0001 by SEP10052. | - | 2026-04-04 | 2026-03-21 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 1YAB5355CAB0000 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 410 | 410 | 0 | 6100K021 | PO-SEP-8792-[13] | PO | 2025-12-20 | Terminals | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-04-04 | 2026-03-21 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 25541 | HEX.RIVET NUT M10X24 ( 25541 ) | 8 | 8 | 0 | 6100K023 | PO-SEP-8645-[7] | PO | 2025-10-30 | Mechanical - Accessories | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | 25541 | HEX.RIVET NUT M10X24 ( 25541 ) | 1747 | 1747 | 0 | 6100K023 | PO-SEP-8645-[7] | PO | 2025-10-30 | Mechanical | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | AE2000-2150-01 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 64 | 64 | 0 | 6100K023 | PO-SEP-8388-[9] | PO | 2025-10-30 | Mechanical | Automated: Replaced AE2000-2150-01 by 1YAZ21500101. | - | 2026-04-04 | 2026-03-21 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | DMS 2126 2011-113 | Nut, Hexagonal Head, M4, Stainless Steel | 96 | 96 | 0 | 6100K023 | PO-SEP-8378-[353] | PO | 2025-11-17 | Mechanical | Automated: Replaced DMS 2126 2011-113 by DF240510018. Automated: Replaced DF240510018 by SEP10896. | - | 2026-04-04 | 2026-03-21 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12186 | Lugs, Terminal Ring, 70 Sq.mm, Copper Tube Crimping ¦ China star | 80 | 50 | 30 | 6100KDP01 | PO-SEP-8834-[17] | PO | 2025-10-05 | Mechanical | Automated: Replaced DMS 2641 0087-19 by SEP12186. Automated: Replaced DMS 2641 0087-19 by SEP12186. | - | 2026-04-04 | 2026-03-21 | 0 | Dalian Jinda Industry Co.,Ltd
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12186 | Lugs, Terminal Ring, 70 Sq.mm, Copper Tube Crimping ¦ China star | 30 | 30 | 0 | free_stock | PR-SEP-0024114-[150] | PR |  | Mechanical | Automated: Replaced DMS 2641 0087-19 by SEP12186. Automated: Replaced DMS 2641 0087-19 by SEP12186. | - | 2026-04-04 | 2026-03-21 | 0
6100K023 | Half_Moon : SWITCHGEAR - Half_Moon | SWGR | ROH | SEP12028 | Lugs, Terminal Female, 1.5 Sq.mm ¦ CEM-RF-F608P ¦ Cembre | 36 | 36 | 0 | 6100KDP01 | PO-SEP-8502-[17] | PO | 2025-12-31 | Mechanical | Automated: Replaced DMS 2658 665-6 by SEP12028. Automated: Replaced DMS 2658 665-6 by SEP12028. | - | 2026-04-04 | 2026-03-21 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 129A539G01 | ‭FT SWITCH, (T T T T T T T T T T)/129A539G01/FT-1‬ | 66 | 66 | 0 | 6100K020 | PO-SEP-8747-[10] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 13.8-VT-ZS1-3WDG-25VA | Voltage Transformer (RITZ) | 18 | 18 | 0 | 6100K020 | PO-SEP-8759-[11] | PO | 2025-10-23 | VT |  | - | 2026-04-11 | 2026-03-28 | 0 |  | 6100K020 Mahar SS 115/13./8kv SWGR CT Order
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1815230000 | 5Pole Plug 2.5mm-1815230000-Cont-loop | 49 | 49 | 0 | 6100K020 | PO-SEP-8750-[23] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1855030000 | 6Pole Plug 4mm-1855030000-AC looping | 40 | 40 | 0 | 6100K020 | PO-SEP-8750-[24] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SFA611400R1001 | PILOT LIGHT#ML1-100R | 48 | 48 | 0 | 6100K020 | PO-SEP-8753-[66] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SFA611400R1002 | PILOT LIGHT#ML1-100G | 48 | 48 | 0 | 6100K020 | PO-SEP-8753-[67] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SFA611400R1003 | PILOT LIGHT#ML1-100Y | 52 | 52 | 0 | 6100K020 | PO-SEP-8753-[68] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SFA611400R1005 | PILOT LIGHT#ML1-100W | 114 | 114 | 0 | 6100K020 | PO-SEP-8753-[69] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SFA611605R1100 | HOLDER#MCBH-00 | 262 | 262 | 0 | 6100K020 | PO-SEP-8753-[80] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SFA611621R1051 | LAMP BLOCK#MLBL-05R | 48 | 48 | 0 | 6100K020 | PO-SEP-8753-[70] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SFA611621R1052 | LAMP BLOCK#MLBL-05G | 48 | 48 | 0 | 6100K020 | PO-SEP-8753-[71] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SFA611621R1053 | LAMP BLOCK#MLBL-05Y | 52 | 52 | 0 | 6100K020 | PO-SEP-8753-[72] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SFA611621R1055 | LAMP BLOCK#MLBL-05W | 108 | 108 | 0 | 6100K020 | PO-SEP-8753-[73] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 256 | 256 | 0 | 6100K020 | PO-SEP-8753-[74] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 256 | 256 | 0 | 6100K020 | PO-SEP-8753-[75] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SNA206394R0200 | Screw, EV6I_Screw+PstWasherIP20_M6/8.RS_M4/6.RS Type: EV6I Order no: 1SNA 206 394 R0200 Color: Grey ¦ 1SNA206394R0200 ¦ ABB | 408 | 408 | 0 | 6100K020 | PO-SEP-8833-[35] | PO | 2025-11-13 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SNK900654R0000 | SC-JB8-4 Short circuit bridges - Yellow | 153 | 153 | 0 | 6100K020 | PO-SEP-8833-[41] | PO | 2025-11-13 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB000002-FDV | MIMIC DIAGRAM, INCOMER-2W,VT | 3 | 3 | 0 | 6100K020 | PO-SEP-8724-[11] | PO | 2025-11-16 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB000003-FDX | MIMIC , OUTGOING WITH EARTHING | 43 | 43 | 0 | 6100K020 | PO-SEP-8724-[6] | PO | 2025-11-17 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB000004-BTE | MIMIC BUS SEC WITH EARTHG ON RIGHT SIDE | 2 | 2 | 0 | 6100K020 | PO-SEP-8724-[20] | PO | 2025-11-16 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB000007-BME | MIMIC, BUS MET. & EARTHING-2W,VT | 1 | 1 | 0 | 6100K020 | PO-SEP-8724-[13] | PO | 2025-11-16 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB000009-BRM | MIMIC , BUS RISER & MET.-2W,VT | 2 | 2 | 0 | 6100K020 | PO-SEP-8724-[16] | PO | 2025-11-16 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5112XFS00000 | VT 3Nos PRIMARY FUSE 17.5kV, 3A, SIBA.VT PRIMARY FUSE FOR 17.5kV UG ZS1 Fuse length : 192 mm Fuse dia : 53 mm Rated Voltage: 17.5kV Rated Current: 3A Rated breaking current : 31.5 kA Frequency: 60 Hz Fuse make : SIBA Type: 30 179 11.3 | 18 | 18 | 0 | 6100K020 | PO-SEP-8827-[2] | PO | 2026-01-25 | VT fuse |  | - | 2026-04-11 | 2026-03-28 | 0 | SABANA TRADERS LLC
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 34 | 32 | 2 | 6100K020 | PO-SEP-8776-[1] | PO | 2025-10-23 | A |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 2 | 2 | 0 | 6100K025 | PO-SEP-8773-[1] | PO | 2025-10-23 | A |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB52322VW60N00 | VD4/PW 171225-p210-125VDC-ZS1-1250A @ 60Hz, in UG ZS1- with upper CTs as per NG Stanadrad | 5 | 5 | 0 | 6100K020 | PO-SEP-8776-[2] | PO | 2025-10-23 | A |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB52333VW6CN00 | VD4/P 171240-p210-125VDC (1VCD400222) | 3 | 1 | 2 | 6100K020 | PO-SEP-8776-[3] | PO | 2025-10-23 | A |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB52333VW6CN00 | VD4/P 171240-p210-125VDC (1VCD400222) | 2 | 2 | 0 | 6100K025 | PO-SEP-8773-[3] | PO | 2025-10-23 | A |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB52371V06CN00 | VD4/P 173225-p275-125VDC (1VCD400222) | 5 | 5 | 0 | 6100K020 | PO-SEP-8776-[4] | PO | 2025-10-23 | A |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 48 | 48 | 0 | 6100K020 | PO-SEP-8775-[3] | PO | 2025-10-23 | A |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5320XDB1XN02 | DIGITAL VOLTMETER, Cl 1.0, 3PH4W, 5-500V, 60Hz, 150% Un CONT, 3 LINE DISPLAY LED, MODBUS ¦ SECURE DPM 96 V300 | 1 | 1 | 0 | 6100K020 | PO-SEP-8837-[3] | PO | 2025-12-30 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Washa Al Wisam Factory Company.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5320XHI1XN00 | POWER QUALITY ANALYZER, ISKRA iMC784 | 3 | 1 | 2 | 6100K020 | PO-SEP-8547-[3] | PO | 2025-10-23 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Enerziff Solutions FZCO | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5320XHI1XN00 | POWER QUALITY ANALYZER, ISKRA iMC784 | 2 | 2 | 0 | 6100k016 | PO-SEP-8547-[5] | PO | 2025-10-26 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Enerziff Solutions FZCO | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 51 | 51 | 0 | 6100K020 | PO-SEP-8829-[3] | PO | 2025-10-23 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Abdullah AbuNayyan Trading Corp
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5331XXCX0000 | CAPACITOR PARKING KEY_COMELECTRIC ITALY.ELECTROMECHANICAL TRAPPED KEY INTERLOCK SWITCH Model: SR 102 R20 2/4 Key Trapped Solenoid Release Switch with IP20 Contacts. Key Free Position: 0 Degree, 4 Contacts. Key Trapped Position: 90 Degree, 4 Contacts. Label: Capacitor Bank Gate Interlock. Make: Comeletric, Italy. Door Interlock lock : KD1 SAP PART NO: 1YAB5331XXCX0000 ------------------ CAPACITOR PARKING KEY_COMELECTRIC ITALY | 3 | 0 | 3 | PR Required | - | PR |  | Customer to supply |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5331XXCX0100 | BREAKER CONTROL SWITCH (Comelectric)Breaker Control Switch3-Pole, 3-Position & spring returnDim: 51 X 51 mm Padlockable handle:Colour : Red YellowFront plate:Text Engrave : OPEN- NORMAL-CLOSELettering plate:Text Engrave : BREAKER CONTROL SWITCH Ordering Code: R601 SAM303 011 01-L078+48-30309T133 | 48 | 27 | 21 | 6100K020 | PO-SEP-8785-[13] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Aman Engineering FZC
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5331XXCX0100 | BREAKER CONTROL SWITCH (Comelectric)Breaker Control Switch3-Pole, 3-Position & spring returnDim: 51 X 51 mm Padlockable handle:Colour : Red YellowFront plate:Text Engrave : OPEN- NORMAL-CLOSELettering plate:Text Engrave : BREAKER CONTROL SWITCH Ordering Code: R601 SAM303 011 01-L078+48-30309T133 | 21 | 21 | 0 | 6100K025 | PO-SEP-8785-[1] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Aman Engineering FZC
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5331XXCX0210 | CBMODE6P,4Pos.Off-Emer-Local-Rem-Padlock(COMELECTRIC), Breaker Mode Selector Switch 6-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH COMELETRIC Part No. R601 SA412 067 27-L071+48-40513T134 SAP Part no: 1YAB5331XXCX0210 | 8 | 3 | 5 | 6100K020 | PO-SEP-8785-[14] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Aman Engineering FZC
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5331XXCX0210 | CBMODE6P,4Pos.Off-Emer-Local-Rem-Padlock(COMELECTRIC), Breaker Mode Selector Switch 6-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH COMELETRIC Part No. R601 SA412 067 27-L071+48-40513T134 SAP Part no: 1YAB5331XXCX0210 | 5 | 5 | 0 | 6100K025 | PO-SEP-8785-[2] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Aman Engineering FZC
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5331XXCX0220 | OFF-EMER-LOCAL-REMOTE 4P4P, PADLCK (COMELECTRIC), Breaker Mode Selector Switch 4-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH Ordering Code: R601 SA408 067 27-L071+48-40513T134 20A, 4 pos Stayput 4 contacts in each Pos, TYPE 1: Engraving: OFF-EMERGENCY-LOCAL-REMOTE TOP PLATE: BREAKER MODE PADLOCK SAP PART NO: 1YAB5331XXCX0220 | 40 | 40 | 0 | 6100K020 | PO-SEP-8785-[15] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Aman Engineering FZC
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5331XXCX0300 | SPACE HEATER SEL. SWITCH ( COMELECTRIC )R601 SA302 112-W051+48-31090T124 20A, 3Positions without internal links 2pole,3position Engraving (OFF/Auto/Manual) OFF-zero contacts AUTO-2 contacts MANUAL-2contacts TOP PLATE (SPACE HEATER) Single hole mounting FT6 | 51 | 51 | 0 | 6100K020 | PO-SEP-8785-[16] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Aman Engineering FZC
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC )R601 SAM201 071-W051+48-20547T123 20A SPRING RETAIN WITHOUT INTERNAL LINKS 2 POSITION,1POLE Engraving (OFF-TEST) TOP PLATE Engraving (LAMP TEST) | 51 | 27 | 24 | 6100K020 | PO-SEP-8785-[17] | PO | 2025-10-23 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Aman Engineering FZC
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC )R601 SAM201 071-W051+48-20547T123 20A SPRING RETAIN WITHOUT INTERNAL LINKS 2 POSITION,1POLE Engraving (OFF-TEST) TOP PLATE Engraving (LAMP TEST) | 24 | 24 | 0 | 6100KDP01 | PO-SEP-8398-[14] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5331XXKX0700 | Auto Re-close IN-OUT Selector Switch(COMELECTRIC),"Auto Re-close IN-OUT Selector Switch 4-Pole, 2-Positions Dim: 51 X 51 mm Padlockable handle: Colour : Black Front plate: Text Engrave : IN-OUT Lettering plate Text Engrave : A/R IN-OUT SWITCH" CA10-A723-SA0030-E 1YAB5331XXKX0700 | 38 | 38 | 0 | 6100K020 | PO-SEP-8785-[18] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Aman Engineering FZC
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5332XXAXB000 | PB Black 1NO+1NC-22 dia-1SFA611100R4076 | 108 | 108 | 0 | 6100K020 | PO-SEP-8753-[79] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5336XXAA2E00 | MCB 3A AC -2P,2CDS252001R0317 | 5 | 5 | 0 | 6100K020 | PO-SEP-8753-[59] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5336XXAA2G00 | MCB S 202-K6 6A AC -2P - 2CDS252001R0377 | 103 | 103 | 0 | 6100K020 | PO-SEP-8753-[60] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5336XXAA2L00 | MCB 16A AC -2P - 2CDS252001R0467 | 5 | 5 | 0 | 6100K020 | PO-SEP-8753-[61] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5336XXAB2G00 | MCB 6A DC 2P S202M-K6UC -2CDS272061R0377 | 300 | 300 | 0 | 6100K020 | PO-SEP-8753-[62] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5336XXACG000 | Aux contact 2NC, S2C-HO2L-for MCB Order # 2CDS200936R0003 | 245 | 245 | 0 | 6100K020 | PO-SEP-8753-[63] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5336XXACH000 | Aux contact 1NO+1NC MCB -2CDS200936R0001 | 340 | 340 | 0 | 6100K020 | PO-SEP-8753-[64] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5336XXACJ000 | S2C-H01 - 1NC- Bottom Auxiliary Contact 2CDS200970R0031 | 75 | 75 | 0 | 6100K020 | PO-SEP-8753-[65] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XAJXXN00 | RF-4R_125Vdc_4 C/O_LED | 85 | 85 | 0 | 6100K020 | PO-SEP-8839-[1] | PO | 2026-02-28 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Innovative Systems Co. Ltd | Arteche MV
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XAJXXN01 | BJ-8RP_Bistable_125Vdc_8 C/O | 40 | 40 | 0 | 6100K020 | PO-SEP-8839-[2] | PO | 2026-02-28 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Innovative Systems Co. Ltd | Arteche MV
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XBLXXN00 | MVAJ101 RA 0802_ 125VDC (8 NO + 2 NC) | 2 | 2 | 0 | 6100K020 | PO-SEP-8841-[3] | PO | 2026-02-28 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Grid Solution Middle-East Fze | MV
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XCHXXN01 | LOCKOUT RELAY (86) TYPE 7835FD, HIGH SPEED TRIP 8ms, TRIP COIL (70-280VDC),10NO+10NC ELECTRICAL RESET COIL (100-150VDC) | 48 | 9 | 39 | 6100KDP01 | PO-SEP-8556-[1] | PO | 2025-12-30 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Electroswitch | AL Azyziyah Khobar SWGR Project to SEC Under Dummy 6100KDP01 (3rd Lot of Electrical Componentes).
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XCHXXN01 | LOCKOUT RELAY (86) TYPE 7835FD, HIGH SPEED TRIP 8ms, TRIP COIL (70-280VDC),10NO+10NC ELECTRICAL RESET COIL (100-150VDC) | 39 | 0 | 39 | PR Required | - | PR |  | LVA |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XCLXXN00 | MVAJ205 ,125VDC ) CAT No. MVAJ205TB0808A | 2 | 2 | 0 | 6100K020 | PO-SEP-8841-[4] | PO | 2026-02-28 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Grid Solution Middle-East Fze | MV
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XDAXXN00 | RXMVB 4, RK 251 401-AP | 8 | 8 | 0 | 6100K020 | PO-SEP-8751-[35] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XDAXXN01 | RXMVB2, RK 251 204-AP | 13 | 13 | 0 | 6100K020 | PO-SEP-8751-[36] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XEAXXN00 | RXMB1 6NO_110-125VDC-1MRK 000 863-AN | 16 | 8 | 8 | 6100K020 | PO-SEP-8751-[37] | PO | 2025-10-23 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XEAXXN00 | RXMB1 6NO_110-125VDC-1MRK 000 863-AN | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8366-[8] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XFAXXN00 | RXKL1, TYPE: 1MRK 000 066-AB | 5 | 5 | 0 | 6100K020 | PO-SEP-8751-[38] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XIAXXN00 | RXSF1_DC110-125V-MV RK 271 019-AN No volt flag relay | 150 | 129 | 21 | 6100K020 | PO-SEP-8751-[39] | PO | 2025-10-23 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XIAXXN00 | RXSF1_DC110-125V-MV RK 271 019-AN No volt flag relay | 21 | 21 | 0 | 6100KDP01 | PO-SEP-8366-[10] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XJAXXN00 | THREE PHASE FUSE SUPERVISION RELAY Type : RXBA4 (ABB) ORDER NO. : RK 428 004-AA CONTACTS : 2 CHANGE OVER SELF RESET | 6 | 6 | 0 | 6100K020 | PO-SEP-8751-[6] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XNHXXN00 | TRIP LOR/ER 7840FD 20NO+20NC, 125VDC HIGH SPEED TRIP 8ms, TRIP COIL (70-280VDC), ELECTRICAL RESET COIL (100-150VDC) | 9 | 0 | 9 | PR Required | - | PR |  | LVA |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 6550 | 6550 | 0 | 6100K020 | PO-SEP-8792-[22] | PO | 2025-12-20 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 2295 | 2295 | 0 | 6100K020 | PO-SEP-8833-[2] | PO | 2025-11-13 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355AEA0001 | M 6/8.RS (SpringLoaded) 1SNA115685R1200 | 2212 | 2212 | 0 | 6100K020 | PO-SEP-8833-[5] | PO | 2025-11-13 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 16264 | 16264 | 0 | 6100K020 | PO-SEP-8833-[8] | PO | 2025-11-13 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355AFA0001 | M4/6.SNTS Spring Loaded 1SNA115229R2000 | 2295 | 2295 | 0 | 6100K020 | PO-SEP-8833-[10] | PO | 2025-11-13 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 1617 | 1617 | 0 | 6100K020 | PO-SEP-8833-[14] | PO | 2025-11-13 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355AMC0001 | Base Terminal Plug AC-DC-4mm 1848350000.Feed-through terminal block,ZT 4/4AN/2 . | 1530 | 1530 | 0 | 6100K020 | PO-SEP-8750-[20] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 612 | 612 | 0 | 6100K020 | PO-SEP-8750-[21] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 742 | 742 | 0 | 6100K020 | PO-SEP-8750-[22] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355CBA0000 | FEM8T6 End Sections Grey 1SNA215266R0100 | 765 | 765 | 0 | 6100K020 | PO-SEP-8833-[17] | PO | 2025-11-13 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355CEA0000 | FEMR8 End Sections Grey 1SNA116987R0200 | 1020 | 1020 | 0 | 6100K020 | PO-SEP-8833-[19] | PO | 2025-11-13 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355CFA0000 | FEM6 End Sections Grey - 1SNA118368R1600 | 510 | 510 | 0 | 6100K020 | PO-SEP-8833-[24] | PO | 2025-11-13 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355CMC0000 | Terminal End Plate 1848360000-Wiedmuller | 204 | 204 | 0 | 6100K020 | PO-SEP-8750-[48] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355CPC0000 | Terminal End Plate 1816110000-Wiedmuller | 204 | 204 | 0 | 6100K020 | PO-SEP-8750-[49] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355CTC0000 | Terminal End Plate 1816070000-Wiedmuller | 106 | 106 | 0 | 6100K020 | PO-SEP-8750-[50] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 2550 | 2550 | 0 | 6100K020 | PO-SEP-8792-[24] | PO | 2025-12-20 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355DFA0000 | RC610-VerticalMarking 1SNA233060R0400 | 459 | 459 | 0 | 6100K020 | PO-SEP-8833-[26] | PO | 2025-11-13 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355DXC0000 | 460660001 DEK 5 FSZ 1-10 Z-Terminal 1-10 | 20600 | 20600 | 0 | 6100K020 | PO-SEP-8750-[18] | PO | 2025-12-31 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355EEA0000 | JUMPER BAR "BJS8" 20 Poles | 102 | 102 | 0 | 6100K020 | PO-SEP-8833-[28] | PO | 2025-11-13 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355EFA0000 | PC61-CombTypeJumprBar10 1SNA163311R2200 | 204 | 204 | 0 | 6100K020 | PO-SEP-8833-[32] | PO | 2025-11-13 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 408 | 408 | 0 | 6100K020 | PO-SEP-8750-[51] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355HAB0002 | Zack Strip-Vertical Labeled(21-30) | 368 | 368 | 0 | 6100K020 | PO-SEP-8750-[19] | PO | 2025-12-31 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 306 | 306 | 0 | 6100K020 | PO-SEP-8750-[52] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355JPC0000 | 6Pole Plug 2.5mm-1815240000-Cont-loop | 204 | 204 | 0 | 6100K020 | PO-SEP-8750-[53] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355JTC0000 | 10Pole Plug 2.5mm-1815280000-Cont-loop | 212 | 212 | 0 | 6100K020 | PO-SEP-8750-[54] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 612 | 612 | 0 | 6100K020 | PO-SEP-8750-[55] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355KPC0000 | Locking ele. 1816130000 for ZT2.5/4AN/2 | 310 | 310 | 0 | 6100K020 | PO-SEP-8750-[56] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355LMC0000 | Coding element 1856860000 - ZT4/4AN/2 | 408 | 408 | 0 | 6100K020 | PO-SEP-8750-[57] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355LPC0000 | Coding element 1816150000 | 416 | 416 | 0 | 6100K020 | PO-SEP-8750-[58] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355MPC0000 | Strain Relief Wied mulpart # 1816140000 | 310 | 310 | 0 | 6100K020 | PO-SEP-8750-[25] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 351 | 351 | 0 | 6100K020 | PO-SEP-8792-[27] | PO | 2025-12-20 | Plug socket |  | - | 2026-04-11 | 2026-03-28 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB60050819P0103 | Braided HARNESS TUBE (D40) | 765 | 565 | 200 | 6100K020 | PO-SEP-8834-[12] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Dalian Jinda Industry Co.,Ltd
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB60050819P0103 | Braided HARNESS TUBE (D40) | 200 | 200 | 0 | 6100K025 | PO-SEP-8834-[5] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Dalian Jinda Industry Co.,Ltd
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB60050819P0106 | Braided HARNESS TUBE (D30) | 1020 | 620 | 400 | 6100K020 | PO-SEP-8834-[2] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Dalian Jinda Industry Co.,Ltd
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB60050819P0106 | Braided HARNESS TUBE (D30) | 400 | 400 | 0 | 6100K025 | PO-SEP-8834-[8] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Dalian Jinda Industry Co.,Ltd
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB60050819P0107 | Braided HARNESS TUBE (D20) | 510 | 510 | 0 | 6100K020 | PO-SEP-8834-[14] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Dalian Jinda Industry Co.,Ltd
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 2CDS254001R0337 | MCB S204-K 4 MC -4P 2CDS254001R0337 | 138 | 138 | 0 | 6100K020 | PO-SEP-8753-[2] | PO | 2025-12-31 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 2TRE123451P0001 | 3 PIN SOCKET SWITCH,13A,250V,BSRDP-I | 5 | 5 | 0 | 6100K020 | PO-SEP-8836-[7] | PO | 2025-11-13 | LVB |  | - | 2026-04-11 | 2026-03-28 | 0 | Saeed Aziz Alsomali Trading Est
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 5022 643 | COVER PROFILE, AP3 | 81.6 | 81.6 | 0 | 6100K020 | PO-SEP-8792-[28] | PO | 2025-12-20 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 1275 | 1275 | 0 | 6100K020 | PO-SEP-8792-[29] | PO | 2025-12-20 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 837A407G01 | ‭FT SWITCH, (C-C C-C C-C C-C P P)/837A407G01/FT-1‬ | 51 | 51 | 0 | 6100K020 | PO-SEP-8747-[8] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 9676A14G01 | ‭FT SWITCH, (P P P P T T T P P P)/9676A14G01/FT-1‬ | 58 | 58 | 0 | 6100K020 | PO-SEP-8747-[9] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 815 | 815 | 0 | 6100K020 | PO-SEP-8836-[15] | PO | 2025-11-13 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Saeed Aziz Alsomali Trading Est
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 765 | 765 | 0 | 6100K020 | PO-SEP-8836-[16] | PO | 2025-11-13 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Saeed Aziz Alsomali Trading Est
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 66.3 | 66 | 0.3 | 6100K020 | PO-SEP-8835-[3] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | EMKA Beschlagteile Middle East FZE
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 0.3 | 0.3 | 0 | 6100K023 | PO-SEP-8835-[4] | PO | 2025-09-18 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | EMKA Beschlagteile Middle East FZE
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 1020 | 1000 | 20 | 6100K020 | PO-SEP-8830-[25] | PO | 2025-12-31 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Sana For Electric And Telephone Co | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8378-[232] | PO | 2025-11-17 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 306 | 306 | 0 | 6100K020 | PO-SEP-8834-[3] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Dalian Jinda Industry Co.,Ltd
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 8 | 8 | 0 | 6100K020 | PO-SEP-8754-[3] | PO | 2025-12-15 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 51 | 51 | 0 | 6100K020 | PO-SEP-8752-[3] | PO | 2025-12-15 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AE2632-2000-33 | Spring for Door Combiflex | 1.02 | 1 | 0.02 | 6100K020 | PO-SEP-8836-[19] | PO | 2025-11-13 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Saeed Aziz Alsomali Trading Est
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AE2632-2000-33 | Spring for Door Combiflex | 0.02 | 0.02 | 0 | 6100KDP01 | PO-SEP-8388-[22] | PO | 2025-10-30 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 51 | 51 | 0 | 6100K020 | PO-SEP-8831-[3] | PO | 2025-11-12 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | First Telecom Industries
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 3060 | 3060 | 0 | 6100K020 | PO-SEP-8792-[30] | PO | 2025-12-20 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 51 | 51 | 0 | 6100K020 | PO-SEP-8724-[4] | PO | 2025-11-16 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DM0000000058 | Relay, Auxiliary, 2 Coils, Self Reset Contacts, Hand Reset Flag, 110-125V, DC, 2NO, 1NC, Coil ¦ RXSF1 RK 271 007-AN | 8 | 8 | 0 | 6100K020 | PO-SEP-8751-[40] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DM0000000839 | COMBIFLEX TERMINAL BASE RX4 (4U 12C) | 14 | 14 | 0 | 6100K020 | PO-SEP-8751-[42] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DM0000000852 | COMBIFLEX TERMINAL BASE RX 2H -5619625-A | 243 | 243 | 0 | 6100K020 | PO-SEP-8751-[41] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DM0000003057 | Relay, Over Current Protection, DC, 110-250V, AC 100-230V, 19BI + 15BO, With IEC 61850-8-1, 2x Optical, Type 7SJ85 ¦ P1J198095 | 3 | 3 | 0 | 6100K020 | PO-SEP-8772-[3] | PO | 2026-02-28 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Siemens Ltd. | Relays, MV
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 20400 | 20400 | 0 | 6100K020 | PO-SEP-8830-[26] | PO | 2025-12-31 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Sana For Electric And Telephone Co | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 255 | 255 | 0 | 6100K020 | PO-SEP-8830-[27] | PO | 2025-12-31 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Sana For Electric And Telephone Co | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 51 | 51 | 0 | 6100K020 | PO-SEP-8830-[28] | PO | 2025-12-31 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Sana For Electric And Telephone Co | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 306 | 306 | 0 | 6100K020 | PO-SEP-8830-[29] | PO | 2025-12-31 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Sana For Electric And Telephone Co | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 2448 | 2448 | 0 | 6100K020 | PO-SEP-8925-[3] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Sana For Electric And Telephone Co
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 408 | 408 | 0 | 6100K020 | PO-SEP-8830-[30] | PO | 2025-12-31 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Sana For Electric And Telephone Co | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DMS 924 0010 | Combiflex wire Socket 1.5mm 1MRK002136-B | 10200 | 10200 | 0 | 6100K020 | PO-SEP-8751-[43] | PO | 2025-12-31 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | DMS 924 0020 | Combiflex wire Socket 2.5mm 1MRK002136-E | 6120 | 6120 | 0 | 6100K020 | PO-SEP-8751-[44] | PO | 2025-12-31 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 12 | 8 | 4 | 6100K020 | PO-SEP-8757-[3] | PO | 2025-12-15 | B |  | - | 2026-04-11 | 2026-03-28 | 0 | Shanghai Feili Xuncheng Electrical Technology Co.,Ltd | Snap action Switch
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8362-[3] | PO | 2025-12-15 | B |  | - | 2026-04-11 | 2026-03-28 | 0 | Shanghai Feili Xuncheng Electrical Technology Co.,Ltd | Snap action/ 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 102 | 102 | 0 | 6100K020 | PO-SEP-8821-[2] | PO | 2025-12-31 | LVC |  | - | 2026-04-11 | 2026-03-28 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | GCE0990403P0100 | VENTILATOR QK08A-2EM.50.CH WITH CAPACITO | 5 | 5 | 0 | 6100K020 | PO-SEP-8748-[5] | PO | 2025-12-31 | B |  | - | 2026-04-11 | 2026-03-28 | 0 | ZIEHL ABEGG Middle East FZE | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | GCE0990404P0100 | RADIAL FLOW FAN QK08A-2EM.35.CF | 7 | 7 | 0 | 6100K020 | PO-SEP-8748-[6] | PO | 2025-12-31 | B |  | - | 2026-04-11 | 2026-03-28 | 0 | ZIEHL ABEGG Middle East FZE | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MARWI60236 | Zack Strip-Vertical(1-10) - 1053027:0001 | 1224 | 1216 | 8 | 6100K020 | PO-SEP-8792-[26] | PO | 2025-12-20 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MARWI60236 | Zack Strip-Vertical(1-10) - 1053027:0001 | 8 | 8 | 0 | 6100K021 | PO-SEP-8792-[16] | PO | 2025-12-20 | Terminals |  | - | 2026-04-11 | 2026-03-28 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV-CR-U125DC3 | CR-U125DC3 - 1SVR405622R8200.CR-U125DC3 Pluggable interface relay 3c Ordering Code : 1SVR405622R8200 General: Pluggable interface relay ABB. Type : CR-U125DC3L Ordering Code: OUTPUTS: 3 C/O with LED RATED VOLTAGE: 125 VDC | 3 | 3 | 0 | 6100K020 | PO-SEP-8753-[55] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV-CR-U3S | Socket -FOR 3 C/O AND MODULE TIMER | 3 | 3 | 0 | 6100K020 | PO-SEP-8753-[56] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV-CR-UH | Holder interface relay 1SVR405669R0000 | 3 | 3 | 0 | 6100K020 | PO-SEP-8753-[57] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV-CR-UT | TIME MODULE 1SVR405667R0000 | 3 | 3 | 0 | 6100K020 | PO-SEP-8753-[58] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 96 | 96 | 0 | 6100K020 | PO-SEP-8836-[4] | PO | 2025-11-13 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | Saeed Aziz Alsomali Trading Est
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV50001 | Incomer Upper CT, INC3600-13.8-UCT ¦ ¦ RITZ | 9 | 9 | 0 | 6100K020 | PO-SEP-8759-[1] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-11 | 2026-03-28 | 0 |  | 6100K020 Mahar SS 115/13./8kv SWGR CT Order
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV50002 | Incomer Lower CT, INC3600-13.8-LCT ¦ ¦ RITZ | 9 | 9 | 0 | 6100K020 | PO-SEP-8759-[2] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-11 | 2026-03-28 | 0 |  | 6100K020 Mahar SS 115/13./8kv SWGR CT Order
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV50003 | Capacitor O/G Feeder Upper CT, CAP1250-13.8-UCT ¦ ¦ RITZ | 9 | 9 | 0 | 6100K020 | PO-SEP-8759-[3] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-11 | 2026-03-28 | 0 |  | 6100K020 Mahar SS 115/13./8kv SWGR CT Order
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV50004 | Capacitor O/G Feeder Lower CT, CAP1250-13.8-LCT ¦ ¦ RITZ | 9 | 9 | 0 | 6100K020 | PO-SEP-8759-[4] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-11 | 2026-03-28 | 0 |  | 6100K020 Mahar SS 115/13./8kv SWGR CT Order
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV50005 | Station Auxiliary Upper CT, SST630-13.8-UCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K020 | PO-SEP-8759-[5] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-11 | 2026-03-28 | 0 |  | 6100K020 Mahar SS 115/13./8kv SWGR CT Order
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV50006 | Station Auxiliary Lower CT, SST630-13.8-LCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K020 | PO-SEP-8759-[6] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-11 | 2026-03-28 | 0 |  | 6100K020 Mahar SS 115/13./8kv SWGR CT Order
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV50007 | Outgoing Plain Upper CT, OG1250-13.8-UCT ¦ ¦ RITZ | 114 | 114 | 0 | 6100K020 | PO-SEP-8759-[7] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-11 | 2026-03-28 | 0 |  | 6100K020 Mahar SS 115/13./8kv SWGR CT Order
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV50008 | Outgoing plain Lower CT, OG1250-13.8-LCT ¦ ¦ RITZ | 114 | 114 | 0 | 6100K020 | PO-SEP-8759-[8] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-11 | 2026-03-28 | 0 |  | 6100K020 Mahar SS 115/13./8kv SWGR CT Order
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV50009 | BusTie Upper CT, BS3600-13.8-UCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K020 | PO-SEP-8759-[9] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-11 | 2026-03-28 | 0 |  | 6100K020 Mahar SS 115/13./8kv SWGR CT Order
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | MV50010 | Bus-Tie Lower CT, BS3600-13.8-LCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K020 | PO-SEP-8759-[10] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-11 | 2026-03-28 | 0 |  | 6100K020 Mahar SS 115/13./8kv SWGR CT Order
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP10038 | Humidistat, 250V, AC, MFR 012 ¦ 01220.0-00 | 51 | 51 | 0 | 6100K020 | PO-SEP-8819-[3] | PO | 2025-12-31 | LVA |  | - | 2026-04-11 | 2026-03-28 | 0 | STEGO Elektrotechnik GmbH | Humidistat, 250V, AC, MFR 012
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP10162 | WHITE TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 12750 | 11103 | 1647 | free_stock | PR-SEP-0023387-[172] | PR |  | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP10162 | WHITE TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 1647 | 1647 | 0 | free_stock | PR-SEP-0023081-[171] | PR |  | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP10163 | RED TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 510 | 0 | 510 | PR Required | - | PR |  | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 765 | 705 | 60 | free_stock | PR-SEP-0024130-[142] | PR |  | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 60 | 60 | 0 | free_stock | PR-SEP-0023081-[167] | PR |  | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP10298 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 510 | 416.8 | 93.2 | free_stock | PR-SEP-0024130-[143] | PR |  | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP10298 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 93.2 | 93.2 | 0 | free_stock | PR-SEP-0023081-[168] | PR |  | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP10349 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 510 | 470 | 40 | free_stock | PR-SEP-0024130-[144] | PR |  | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP10349 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 40 | 40 | 0 | free_stock | PR-SEP-0023081-[169] | PR |  | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP10650 | WHITE TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 2040 | 0 | 2040 | PR Required | - | PR |  | LVD |  | - | 2026-04-11 | 2026-03-28 | 0
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11258 | Cable, Control, 1 Core,CU/PVC, 1.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 102 | 88.1685 | 13.8315 | 6100K020 | PO-SEP-8915-[44] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11258 | Cable, Control, 1 Core,CU/PVC, 1.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 13.8315 | 13.8315 | 0 | 6100K025 | PO-SEP-8915-[1] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11259 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 33.15 | 33.15 | 0 | 6100K021 | PO-SEP-8915-[17] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11260 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 766 | 766 | 0 | 6100K025 | PO-SEP-8915-[3] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11261 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 33.15 | 30.3698 | 2.7802 | 6100K021 | PO-SEP-8915-[19] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11261 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 2.7802 | 2.7802 | 0 | 6100K025 | PO-SEP-8915-[4] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11262 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 137.7 | 131.3742 | 6.3258 | 6100K020 | PO-SEP-8915-[48] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11262 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 6.3258 | 6.3258 | 0 | 6100K025 | PO-SEP-8915-[5] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11263 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 86.7 | 0.14223 | 86.5578 | 6100K020 | PO-SEP-8915-[49] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11263 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 86.5578 | 86.5578 | 0 | 6100K021 | PO-SEP-8915-[21] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11264 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 25.5 | 0.10066 | 25.3993 | 6100K020 | PO-SEP-8915-[50] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11264 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 25.3993 | 25.3993 | 0 | 6100K021 | PO-SEP-8915-[22] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11265 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm Yellow/Green, ATC, 105°, 600/1000V , 1 x 100 m | 25.6 | 15.4617 | 10.1383 | 6100K025 | PO-SEP-8915-[8] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11265 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm Yellow/Green, ATC, 105°, 600/1000V , 1 x 100 m | 10.1383 | 5.6958 | 4.4425 | 6100K021 | PO-SEP-8915-[23] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11265 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm Yellow/Green, ATC, 105°, 600/1000V , 1 x 100 m | 4.4425 | 4.4425 | 0 | 6100KDP01 | PO-SEP-8622-[26] | PO | 2026-01-30 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11266 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 137.7 | 0.34354 | 137.3565 | 6100K020 | PO-SEP-8915-[52] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11266 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 137.3565 | 137.3565 | 0 | 6100K021 | PO-SEP-8915-[24] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11267 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Yellow, ATC,105°, 600/1000V , 1 x 100 m | 137.7 | 131.3742 | 6.3258 | 6100K020 | PO-SEP-8915-[53] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11267 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Yellow, ATC,105°, 600/1000V , 1 x 100 m | 6.3258 | 6.3258 | 0 | 6100K021 | PO-SEP-8915-[25] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11268 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 7.65 | 7.65 | 0 | 6100K020 | PO-SEP-8915-[54] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11269 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 10.2 | 10.2 | 0 | 6100K020 | PO-SEP-8915-[55] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11270 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 7.65 | 7.65 | 0 | 6100K020 | PO-SEP-8915-[57] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11271 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Yellow, ATC, 105°, 600/1000V , 1 x 100 m | 7.65 | 7.65 | 0 | 6100K020 | PO-SEP-8915-[58] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP11272 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 10.2 | 10.2 | 0 | 6100K020 | PO-SEP-8915-[56] | PO | 2026-01-11 | Wire |  | - | 2026-04-11 | 2026-03-28 | 0 | Al-Fanar Company Limited | Cable Items
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12004 | TERM.LUGS BLADE RF-PP 12/23 | 15300 | 15300 | 0 | 6100K025 | PO-SEP-8894-[47] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12012 | TERM.LUGS SPADE RF-U4 1.5/M4 | 6375 | 6375 | 0 | 6100K025 | PO-SEP-8894-[48] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12016 | TERM.LUGS RING RF-M4 1.5/M4 | 5100 | 5100 | 0 | 6100K025 | PO-SEP-8894-[50] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12026 | BENT LUGS TYPE RF-PPL30 | 35700 | 35700 | 0 | 6100K025 | PO-SEP-8894-[39] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12048 | END SLEEVES PKE 1508 (1x1.5sqmm , Black) | 765 | 765 | 0 | 6100K025 | PO-SEP-8894-[55] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12050 | UN-INSUL SLeve Lugs KE1510ST (1.5mm) | 1020 | 1020 | 0 | 6100K025 | PO-SEP-8894-[43] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12052 | END SLEEVES PKT 1508 (2x1.5sqmm , Black) | 765 | 765 | 0 | 6100K025 | PO-SEP-8894-[56] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12063 | TERM.LUGS BLADE BF-PP12/25 2.5MM | 5100 | 5100 | 0 | 6100K020 | PO-SEP-8894-[9] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12083 | TERM.LUGS BF-M5 (RING) | 6120 | 6120 | 0 | 6100K025 | PO-SEP-8894-[52] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12085 | WIRE LUGS RING TYPE BF-M6 2.5/M6 | 408 | 408 | 0 | 6100K025 | PO-SEP-8894-[53] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12087 | RING TYPE LUGS BF-M 8 | 408 | 408 | 0 | 6100K025 | PO-SEP-8894-[54] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12091 | BENT LUGS TYPE BF-PPL30 | 15300 | 15300 | 0 | 6100K020 | PO-SEP-8894-[5] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12103 | UN-INSUL SLEEVE Lugs for 2.5mm KE2510ST | 2550 | 2550 | 0 | 6100K020 | PO-SEP-8894-[7] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12105 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 1020 | 920 | 100 | 6100K025 | PO-SEP-8894-[57] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12105 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 100 | 100 | 0 | 6100K021 | PO-SEP-8894-[38] | PO | 2025-10-27 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12117 | TERM.LUGS RING BF-M4 | 10200 | 6100 | 4100 | 6100K025 | PO-SEP-8894-[51] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12117 | TERM.LUGS RING BF-M4 | 4100 | 4100 | 0 | 6100K021 | PO-SEP-8894-[32] | PO | 2025-10-27 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12119 | RING TYPE LUGS GF-M 5 | 1020 | 972 | 48 | 6100K021 | PO-SEP-8894-[30] | PO | 2025-10-27 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12119 | RING TYPE LUGS GF-M 5 | 48 | 48 | 0 | 6100KDP01 | PO-SEP-8541-[6] | PO | 2025-10-30 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12127 | BENT LUGS TYPE BF-PPL46 | 7650 | 7650 | 0 | 6100K020 | PO-SEP-8894-[4] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12129 | Un-Insul Sleeve Lugs 4.0 mm KE410ST | 2550 | 2550 | 0 | 6100K020 | PO-SEP-8894-[8] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | SEP12131 | Lugs, Sleeve 4.0/9mm ( W/O Ins.) 3200302 | 2550 | 2550 | 0 | 6100K020 | PO-SEP-8894-[6] | PO | 2025-10-23 | LVD |  | - | 2026-04-11 | 2026-03-28 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | VT-GUARD-13.8KV | VT Guard, Anti Ferro Resonance Unit ¦ VT-GUARD-13.8KV | 6 | 6 | 0 | 6100K020 | PO-SEP-8713-[3] | PO | 2025-12-15 | RVT |  | - | 2026-04-11 | 2026-03-28 | 0 | Abb Electrical Industriesco | Al Azyziyah SS 6100KDP01. VT Guard, Anti Ferro Reso{}ce Unit ¦ VT-GUARD
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1SNA234000R0200 | Marker, RC810, 1 ¦ 10/1SNA234041R2600 ¦ ENTRELEC | 510 | 510 | 0 | 6100K020 | PO-SEP-8833-[39] | PO | 2025-11-13 | Terminals | Automated: Replaced 1SNA234000R0200 by SEP20333. | - | 2026-04-11 | 2026-03-28 | 0 | Al Suhaili Trading And Development
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5340XIAXXN01 | Relay, Auxiliary, 2 Coils, Self Reset Contacts, Hand Reset Flag, 110-125V, DC, 2NO, 1NC, Coil ¦ RXSF1 RK 271 007-AN | 51 | 51 | 0 | 6100K020 | PO-SEP-8751-[5] | PO | 2025-12-31 | LVA | Automated: Replaced 1YAB5340XIAXXN01 by DM0000000058. | - | 2026-04-11 | 2026-03-28 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block, TB, Disconnecting TB for CT, OTTA 6-T, Bolt W/O Spring, 0790462 ¦ OTTA 6-T P/P ¦ PHOENIX | 4012 | 4012 | 0 | 6100K020 | PO-SEP-8792-[21] | PO | 2025-12-20 | Terminals | Automated: Replaced 1YAB5355AAB0001 by SEP10052. | - | 2026-04-11 | 2026-03-28 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355CAB0000 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 510 | 446 | 64 | 6100K020 | PO-SEP-8792-[23] | PO | 2025-12-20 | Terminals | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-04-11 | 2026-03-28 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K020 | Mahaar : SWITCHGEAR - Mahaar | SWGR | ROH | 1YAB5355CAB0000 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 64 | 64 | 0 | 6100K025 | PO-SEP-8792-[3] | PO | 2025-12-20 | Terminals | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-04-11 | 2026-03-28 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 00046 | SCREW TS ACC T21336/M5X16 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8378-[225] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 25 | 21 | 4 | 6100K023 | PO-SEP-8385-[41] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 02030 | MICROSWITCH T36447/01 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8385-[219] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 4388 | 3656 | 732 | 6100KDP01 | PO-SEP-8378-[227] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 732 | 334 | 398 | 6100KDP01 | PO-SEP-8378-[301] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 398 | 48 | 350 | 606PD013 | PO-SEP-6812-[151] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 03363 | STEEL RIVETS, ACC T 22205/6.4 TT(13.8kV) | 350 | 0 | 350 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 03366 | STEEL RIVETS T22205/4.8 TS | 625 | 365 | 260 | 6100KDP01 | PO-SEP-8378-[228] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 03366 | STEEL RIVETS T22205/4.8 TS | 260 | 114 | 146 | 6100KDP01 | PO-SEP-6812-[41] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 03366 | STEEL RIVETS T22205/4.8 TS | 146 | 0 | 146 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 268 | 209 | 59 | 6100KDP01 | PO-SEP-8378-[272] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 59 | 8 | 51 | 6100KDP01 | PO-SEP-8378-[302] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 04472 | RIVET STAINLESS STL T22206/4.8 | 51 | 0 | 51 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 07934 | TOMMY HEAD SCREW ACC T21010/M3x6 | 84 | 84 | 0 | 6100K023 | PO-SEP-8647-[12] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Mattssons Fasteners AB
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 07959 | TOMMY HEAD SCREW FULL THREAD T21010/4X25 | 180 | 62 | 118 | 6100KDP01 | PO-SEP-8680-[19] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 07959 | TOMMY HEAD SCREW FULL THREAD T21010/4X25 | 118 | 0 | 118 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 08017 | TOMMY HEAD SCREW ACC T21010/M4x22 | 92 | 92 | 0 | 6100KDP01 | PO-SEP-8647-[6] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Mattssons Fasteners AB
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 08222 | COUNTER SUNK SCREW 6X16 ACC T21030/6X16 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-6812-[90] | PO | 2025-08-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 08448 | SQUARE FASTENING NUT TS ACC T21597/5 | 100 | 80 | 20 | 6100KDP01 | PO-SEP-8378-[338] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 08448 | SQUARE FASTENING NUT TS ACC T21597/5 | 20 | 0 | 20 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 120 | 105 | 15 | 6100KDP01 | PO-SEP-8629-[18] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | FLY METALTECH TRADING CO.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 08852 | WASHER, SRING STEEL ACC T22100/3.2 | 15 | 15 | 0 | 6100KDP01 | PO-SEP-6812-[7] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 08856 | WASHER STEEL T22100/ 6.4 | 100 | 80 | 20 | 6100KDP01 | PO-SEP-8378-[280] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 08856 | WASHER STEEL T22100/ 6.4 | 20 | 0 | 20 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 09021 | SELF-LOCKING HEX. NUT,T21192/M10 (LOCAL) | 200 | 104 | 96 | 6100KDP01 | PO-SEP-8680-[18] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 09021 | SELF-LOCKING HEX. NUT,T21192/M10 (LOCAL) | 96 | 56 | 40 | 6100KDP01 | PO-SEP-6812-[45] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 09021 | SELF-LOCKING HEX. NUT,T21192/M10 (LOCAL) | 40 | 0 | 40 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 09601 | WASHER, FLAT ACC T22000/3.2X7 | 144 | 114 | 30 | 6100KDP01 | PO-SEP-8378-[275] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 09601 | WASHER, FLAT ACC T22000/3.2X7 | 30 | 0 | 30 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 09929 | STEEL SPRING WASHER ACC T22104/10 | 48 | 0 | 48 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 09947 | SPRING WASHER ACC T22104/6 | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1000057457 | WASHER CU AL M10 | 23 | 21 | 2 | 6100KDP01 | PO-SEP-8385-[227] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1000057457 | WASHER CU AL M10 | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[18] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1020178 | COMBINATION SPANNER SETS | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 12980 | COUNTERSUNK STEEL SCREW T21065/M6X14 | 50 | 38 | 12 | 6100KDP01 | PO-SEP-8646-[2] | PO | 2025-10-20 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | AL NAKHEEL GREEN STEEL WORKS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 12980 | COUNTERSUNK STEEL SCREW T21065/M6X14 | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[19] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 12989 | COUNTERSUNK STEEL SCREW T21065/M8X30 | 50 | 38 | 12 | 6100KDP01 | PO-SEP-8646-[1] | PO | 2025-10-20 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | AL NAKHEEL GREEN STEEL WORKS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 12989 | COUNTERSUNK STEEL SCREW T21065/M8X30 | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[20] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 13441 | TORQUES WRENCH | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1366 1062-804 | 3/4"XSCHED.40X6M BI PIPE | 9.68 | 0 | 9.68 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1420601 | BI-HEXAGON DEEP SOCKET SET | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1420630 | BI HEXAGON SOCKET SET of RATCHET | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 16301 | RIVET T22213/4 | 108 | 40 | 68 | 6100KDP01 | PO-SEP-8645-[4] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 16301 | RIVET T22213/4 | 68 | 36 | 32 | 6100KDP01 | PO-SEP-6812-[55] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 16301 | RIVET T22213/4 | 32 | 32 | 0 | free_stock | PR-SEP-0024114-[22] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 16304 | RIVET TT ALUMINUM T22213/5 | 27 | 12 | 15 | 6100KDP01 | PO-SEP-8378-[288] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 16304 | RIVET TT ALUMINUM T22213/5 | 15 | 15 | 0 | free_stock | PR-SEP-0024114-[23] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 16742 | DANGER SIGN T27420/60 | 48 | 48 | 0 | 6100KDP01 | PO-SEP-8379-[52] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 175 | 161 | 14 | 6100KDP01 | PO-SEP-8379-[43] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 16743 | LABEL EARTHING (T27412/20) | 14 | 14 | 0 | free_stock | PR-SEP-0024114-[25] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1815230000 | 5Pole Plug 2.5mm-1815230000-Cont-loop | 24 | 24 | 0 | 6100KDP01 | PO-SEP-8518-[18] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1855030000 | 6Pole Plug 4mm-1855030000-AC looping | 25 | 25 | 0 | 6100KDP01 | PO-SEP-8518-[19] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SFA611400R1001 | PILOT LIGHT#ML1-100R | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8041-[65] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SFA611400R1002 | PILOT LIGHT#ML1-100G | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8041-[66] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SFA611400R1003 | PILOT LIGHT#ML1-100Y | 26 | 26 | 0 | 6100KDP01 | PO-SEP-8041-[67] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SFA611400R1005 | PILOT LIGHT#ML1-100W | 46 | 42 | 4 | 6100KDP01 | PO-SEP-8041-[68] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SFA611400R1005 | PILOT LIGHT#ML1-100W | 4 | 4 | 0 | 6100K019 | PO-SEP-8041-[57] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SFA611605R1100 | HOLDER#MCBH-00 | 118 | 118 | 0 | 6100KDP01 | PO-SEP-8041-[69] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SFA611621R1051 | LAMP BLOCK#MLBL-05R | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8041-[70] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SFA611621R1052 | LAMP BLOCK#MLBL-05G | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8041-[71] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SFA611621R1053 | LAMP BLOCK#MLBL-05Y | 26 | 26 | 0 | 6100KDP01 | PO-SEP-8041-[72] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SFA611621R1055 | LAMP BLOCK#MLBL-05W | 46 | 46 | 0 | 6100KDP01 | PO-SEP-8041-[73] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 118 | 118 | 0 | 6100KDP01 | PO-SEP-8041-[74] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 118 | 118 | 0 | 6100KDP01 | PO-SEP-8041-[75] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SNK900654R0000 | SC-JB8-4 Short circuit bridges - Yellow | 75 | 75 | 0 | 6100KDP01 | PO-SEP-8386-[17] | PO | 2025-11-10 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VCR000474F0001 | BLOCK | 5 | 5 | 0 | 6100K023 | PO-SEP-8385-[30] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VCR002047G0001 | COMPLETE ASSEMBLY KIT FOR DIRAK LOCKUP | 25 | 20 | 5 | 6100KDP01 | PO-SEP-8446-[3] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Ningbo Shengjiu Technology CO., LTD. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VCR002047G0001 | COMPLETE ASSEMBLY KIT FOR DIRAK LOCKUP | 5 | 5 | 0 | free_stock | PR-SEP-0024114-[27] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VCR002416G0001 | LOCKUP ROD ASSEMBLY | 50 | 28 | 22 | 6100KDP01 | PO-SEP-8387-[23] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VCR002416G0001 | LOCKUP ROD ASSEMBLY | 22 | 22 | 0 | free_stock | PR-SEP-0024114-[28] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VCR002428G0001 | LOCKUP ROD ASSEMBLY | 25 | 21 | 4 | 6100KDP01 | PO-SEP-8387-[24] | PO | 2025-11-30 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VCR002428G0001 | LOCKUP ROD ASSEMBLY | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[29] | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VCR003760G0001 | CRANK FOR EARTHING SWITCH EK6 | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[447] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VCR008770F0001 | BLOCK PIN | 200 | 200 | 0 | 6100KDP01 | PO-SEP-8385-[161] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7600732P0101 | SPACER TUBE | 50 | 38 | 12 | 6100KDP01 | PO-SEP-8403-[7] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7600732P0101 | SPACER TUBE | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[32] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7601387P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Short | 25 | 12 | 13 | 6100K023 | PO-SEP-8385-[32] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7601387P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Short | 13 | 13 | 0 | 6100KDP01 | PO-SEP-8385-[158] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7601389P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Long | 25 | 11 | 14 | 6100K023 | PO-SEP-8385-[33] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7601389P0101 | TIE ROD (CB COMPRTMENT DOOR,W800)Long | 14 | 14 | 0 | 6100KDP01 | PO-SEP-8385-[159] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7602006R0101 | TIE ROD W800 CABLE COMPT. | 50 | 50 | 0 | 6100KDP01 | PO-SEP-8385-[162] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7605506P0101 | ABB LOGO UNIGEAR ZS1 | 3 | 2 | 1 | 6100KDP01 | PO-SEP-6543-[73] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Labels for outdoor
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7605506P0101 | ABB LOGO UNIGEAR ZS1 | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[36] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7605506P0102 | ABB LOGO UNIGEAR ZS1 | 22 | 10 | 12 | 6100KDP01 | PO-SEP-6543-[74] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Labels for outdoor
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7605506P0102 | ABB LOGO UNIGEAR ZS1 | 12 | 7 | 5 | 6100KDP01 | PO-SEP-6543-[62] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Labels for outdoor
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7605506P0102 | ABB LOGO UNIGEAR ZS1 | 5 | 5 | 0 | free_stock | PR-SEP-0024114-[338] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7607280R0101 | HINGE WITHOUT FASTENERS | 275 | 219 | 56 | 6100KDP01 | PO-SEP-8397-[4] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7607280R0101 | HINGE WITHOUT FASTENERS | 56 | 56 | 0 | free_stock | PR-SEP-0024114-[37] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7608266P0101 | CONNECTION PIECE tublar GCE8005046R0101 | 18 | 12 | 6 | 6100KDP01 | PO-SEP-8385-[151] | PO | 2025-10-05 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7608266P0101 | CONNECTION PIECE tublar GCE8005046R0101 | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[38] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7623184R0101 | COMPLETE HANDLE | 24 | 19 | 5 | 6100KDP01 | PO-SEP-8552-[1] | PO | 2025-11-15 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | SHAMS ALRIYADH INDUSTRIAL FACTORY | AL Azyziyah DMM Project under Dummy 6100KDP01 2nd Lot of Mechanical Componentes for SEC a/c Dammam Aziziya Fast track project 13.8kV MV SWGR.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1VL7623184R0101 | COMPLETE HANDLE | 5 | 5 | 0 | free_stock | PR-SEP-0024114-[39] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB000002-FDV | MIMIC DIAGRAM, INCOMER-2W,VT | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8379-[47] | PO | 2025-10-30 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB000003-FDX | MIMIC , OUTGOING WITH EARTHING | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8379-[48] | PO | 2025-10-30 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB000004-BTE | MIMIC BUS SEC WITH EARTHG ON RIGHT SIDE | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8379-[49] | PO | 2025-10-30 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB000007-BME | MIMIC, BUS MET. & EARTHING-2W,VT | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8379-[50] | PO | 2025-10-30 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB000009-BRM | MIMIC , BUS RISER & MET.-2W,VT | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8379-[51] | PO | 2025-10-30 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010005P0102 | SHROUD, LEFT W1000 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8385-[152] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010005P0103 | SHROUD, LEFT W800 | 60 | 60 | 0 | 6100KDP01 | PO-SEP-8385-[126] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010006P0102 | SHROUD, RIGHT W1000 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8385-[153] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010006P0103 | SHROUD, RIGHT W800 | 60 | 60 | 0 | 6100KDP01 | PO-SEP-8385-[127] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010012P0102 | Copper earthing bar 12.5 x 4.0 mm | 25 | 0 | 25 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 75 | 69 | 6 | 6100KDP01 | PO-SEP-8549-[1] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | FLY METALTECH TRADING CO. | 6100KDP01- AZYZIYAH DMM for SEC a/c Fast track project 13.8kV MV SWGR 1st Lot Mechanical Componentes.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010024P0101 | HINGE BOLT COMPONENT #1 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-6812-[75] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010025P0101 | HINGE COMPONENT #2 | 150 | 114 | 36 | 6100KDP01 | PO-SEP-8403-[10] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010025P0101 | HINGE COMPONENT #2 | 36 | 36 | 0 | free_stock | PR-SEP-0024114-[43] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010029P0122 | CVI DIVIDER, 12-17.5kV, Set 1B (11425) | 22 | 19 | 3 | 6100KDP01 | PO-SEP-8445-[2] | PO | 2025-12-31 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Ritz Instrument Transformers GMBH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010029P0122 | CVI DIVIDER, 12-17.5kV, Set 1B (11425) | 3 | 1 | 2 | 606PD013 | PO-SEP-8445-[3] | PO | 2025-12-31 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Ritz Instrument Transformers GMBH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010029P0122 | CVI DIVIDER, 12-17.5kV, Set 1B (11425) | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[44] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010072P0101P | CONTACT PIN 35 DIA, 90L | 120 | 102 | 18 | 6100K023 | PO-SEP-8385-[119] | PO | 2025-09-21 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010072P0101P | CONTACT PIN 35 DIA, 90L | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8385-[267] | PO | 2025-10-19 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010137P0100 | EDGE PROTECTION (FLEXIBLE)DIRAK 209-0812 | 94.67 | 94.67 | 0 | 6100KDP01 | PO-SEP-8384-[4] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | DIRAK MIDDLE EAST FZE | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010138P0102 | PROTECTIVE COVER W800 | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8396-[31] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010138P0103 | PROTECTIVE COVER W1000 | 3 | 2 | 1 | 6100KDP01 | PO-SEP-8385-[207] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010138P0103 | PROTECTIVE COVER W1000 | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[49] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010145P0102 | DOOR STOPPER ROD 8 MM DIA. | 25 | 19 | 6 | 6100KDP01 | PO-SEP-8523-[7] | PO | 2025-10-23 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010145P0102 | DOOR STOPPER ROD 8 MM DIA. | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[51] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010241P0101 | HEX. BOLT M10X20 POLYAMIDE | 144 | 114 | 30 | 6100KDP01 | PO-SEP-8378-[208] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010241P0101 | HEX. BOLT M10X20 POLYAMIDE | 30 | 24 | 6 | 6100KDP01 | PO-SEP-6812-[81] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010241P0101 | HEX. BOLT M10X20 POLYAMIDE | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[52] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010241P0102 | HEX. BOLT M10X25 POLYAMIDE | 72 | 72 | 0 | 6100KDP01 | PO-SEP-8378-[299] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010241P0103 | HEX. BOLT M10X30 POLYAMIDE | 60 | 51 | 9 | 6100KDP01 | PO-SEP-8378-[160] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010241P0103 | HEX. BOLT M10X30 POLYAMIDE | 9 | 9 | 0 | 6100KDP01 | PO-SEP-6812-[79] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010241P0104 | HEX. BOLT M10X40 POLYAMIDE | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[54] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 24 | 23 | 1 | 6100KDP01 | PO-SEP-8379-[40] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010301P0101 | Instruction label for Pres Flap Opening | 1 | 1 | 0 | 6100KDP01 | PO-SEP-6543-[45] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Labels for outdoor | 3 | 19-08-2025
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010301P0111 | Label printed in Trafolite 200 x 100 | 25 | 19 | 6 | 6100KDP01 | PO-SEP-8379-[39] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010301P0111 | Label printed in Trafolite 200 x 100 | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[56] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010378P0110 | SEC.FEMALE CONTACTS 1.5,W.SLEEVES 50X | 1300 | 1300 | 0 | 6100KDP01 | PO-SEP-8385-[216] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010378P0112 | SEC. FEMALE CONTACT PIN 2.5MM | 1100 | 1100 | 0 | 6100KDP01 | PO-SEP-8385-[129] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010402P0101 | STICKER "operating Instruction manual" | 48 | 48 | 0 | 6100KDP01 | PO-SEP-8379-[29] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010402R0103 | LABELS FOR SHUTTERS BUSBAR-CABLE -FEEDER | 23 | 13 | 10 | 6100KDP01 | PO-SEP-8379-[37] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010402R0103 | LABELS FOR SHUTTERS BUSBAR-CABLE -FEEDER | 10 | 6 | 4 | 6100KDP01 | PO-SEP-6543-[48] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Labels for outdoor
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010402R0103 | LABELS FOR SHUTTERS BUSBAR-CABLE -FEEDER | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[59] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010402R0104 | LABELS FOR SHUTTERS BUSBAR-1,2,3-B/S,B/R | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8724-[2] | PO | 2025-11-16 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010489P0101 | FLAT BRAIDED, 16SQMM. TIN(13.8kV)6mmdia | 79 | 32 | 47 | 6100KDP01 | PO-SEP-8378-[211] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010489P0101 | FLAT BRAIDED, 16SQMM. TIN(13.8kV)6mmdia | 47 | 25 | 22 | 6100KDP01 | PO-SEP-6812-[87] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010489P0101 | FLAT BRAIDED, 16SQMM. TIN(13.8kV)6mmdia | 22 | 22 | 0 | free_stock | PR-SEP-0024114-[60] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010489P0102 | FLAT BRAIDED CONNECTOR, 16 SQMM. TINNED | 25 | 19 | 6 | 6100KDP01 | PO-SEP-8403-[8] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB010489P0102 | FLAT BRAIDED CONNECTOR, 16 SQMM. TINNED | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[61] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5112XFS00000 | VT 3Nos PRIMARY FUSE 17.5kV, 3A, SIBA | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8408-[2] | PO | 2025-01-23 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | SABANA TRADERS LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51331CA6C100 | Outgoing & Aux. UCT_TPU | 48 | 0 | 48 | PR Required | - | PR |  | A |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51331CA6C200 | Outgoing & Aux. LCT_TPU | 48 | 0 | 48 | PR Required | - | PR |  | A |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51331CA6C300 | Outgoing CAP. UCT_TPU | 12 | 0 | 12 | PR Required | - | PR |  | A |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51331CA6C400 | Outgoing CAP. LCT_TPU | 12 | 0 | 12 | PR Required | - | PR |  | A |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51331CA6T3XX | Outgoing CAP. UCT (RITZ / ASS 17,5-166) | 60 | 0 | 60 | PR Required | - | PR |  | C |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51331CA6T4XX | Outgoing CAP. LCT (RITZ / ASS 17,5-162) | 60 | 0 | 60 | PR Required | - | PR |  | C |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51341CA6C100 | Incomer UCT_KOKS A17 | 6 | 0 | 6 | PR Required | - | PR |  | A |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51341CA6C200 | Incomer LCT_KOKS A17 | 6 | 0 | 6 | PR Required | - | PR |  | A |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51341CA6T1XX | Incomer UCT (RITZ / GIS 17,5-85) | 6 | 0 | 6 | PR Required | - | PR |  | C |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51341CA6T2XX | Incomer LCT (RITZ / GIS 17,5-85) | 6 | 0 | 6 | PR Required | - | PR |  | C |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51342VA6C100 | Voltage Transformer (ABB EJF / TJP5H) | 12 | 0 | 12 | PR Required | - | PR |  | A |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51342VA6T1XX | Voltage Transformer (RITZ / VES 17,5-14) | 12 | 0 | 12 | PR Required | - | PR |  | C |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51351CA6C100 | Bus-Tie UCT_KOKS A17 | 3 | 0 | 3 | PR Required | - | PR |  | A |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51351CA6C200 | Bus-Tie LCT_KOKS A17 | 3 | 0 | 3 | PR Required | - | PR |  | A |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51351CA6T1XX | Bus-Tie UCT (RITZ / GIS 17,5-85) | 3 | 0 | 3 | PR Required | - | PR |  | C |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB51351CA6T2XX | Bus-Tie LCT (RITZ / GIS 17,5-85) | 3 | 0 | 3 | PR Required | - | PR |  | C |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 18 | 8 | 10 | 6100K025 | PO-SEP-8773-[1] | PO | 2025-10-23 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 10 | 10 | 0 | 6100K021 | PO-SEP-8770-[1] | PO | 2025-10-27 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB52322VW60N00 | VD4/PW 171225-p210-125VDC-ZS1 | 2 | 2 | 0 | 6100K025 | PO-SEP-8773-[2] | PO | 2025-10-23 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB52371V06CN00 | VD4/P 173225-p275-125VDC (1VCD400222) | 3 | 3 | 0 | 6100K025 | PO-SEP-8773-[4] | PO | 2025-10-23 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 25 | 25 | 0 | 6100K025 | PO-SEP-8775-[1] | PO | 2025-10-23 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5320XDB1XN01 | CEWE Elite 440-448 | 25 | 0 | 25 | PR Required | - | PR |  | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 25 | 25 | 0 | 6100K025 | PO-SEP-8829-[2] | PO | 2025-10-23 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abdullah AbuNayyan Trading Corp
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5331XXCX0100 | BREAKER CONTROL SWITCH (Comelectric) | 23 | 23 | 0 | 6100K021 | PO-SEP-8785-[7] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5331XXCX0210 | CBMODE6P,4Pos.Off-Emer-Local-Rem-Padlock | 3 | 3 | 0 | 6100K021 | PO-SEP-8785-[8] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5331XXCX0220 | OFF-EMER-LOCAL-REMOTE 4P4P, PADLCK (COM) | 20 | 20 | 0 | 6100K025 | PO-SEP-8785-[3] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5331XXCX0300 | SPACE HEATER SEL. SWITCH ( COMELECTRIC ) | 25 | 25 | 0 | 6100K025 | PO-SEP-8785-[4] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC ) | 25 | 25 | 0 | 6100K021 | PO-SEP-8785-[11] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5331XXKX0700 | Auto Re-close IN-OUT Selector Switch(K&N | 20 | 20 | 0 | 6100K025 | PO-SEP-8785-[6] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5332XXAXB000 | PB Black 1NO+1NC-22 dia-1SFA611100R4076 | 8 | 8 | 0 | 6100K021 | PO-SEP-8753-[78] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5334XXAX1000 | FT-1 SW-Type 129A514G01 | 20 | 20 | 0 | 6100K023 | PO-SEP-8365-[1] | PO | 2025-12-14 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | FT Switch /6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5335XXAX1100 | COMBIFLEX TERMINAL BASE RX 2H -5619625-A | 9 | 9 | 0 | 6100KDP01 | PO-SEP-8366-[14] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5336XXAA2E00 | MCB 3A AC -2P,2CDS252001R0317 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8041-[77] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5336XXAA2G00 | MCB S 202-K6 6A AC -2P - 2CDS252001R0377 | 47 | 47 | 0 | 6100KDP01 | PO-SEP-8041-[78] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5336XXAA2L00 | MCB 16A AC -2P - 2CDS252001R0467 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8041-[79] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5336XXAA3F00 | MCB S203-K 4 MC -3P 2CDS253001R0337 | 77 | 61 | 16 | free_stock | PR-SEP-0024130-[50] | PR |  | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5336XXAA3F00 | MCB S203-K 4 MC -3P 2CDS253001R0337 | 16 | 0 | 16 | PR Required | - | PR |  | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5336XXAA3I00 | MCB 10A AC -3P - 2CDS253001R0427 | 6 | 6 | 0 | free_stock | PR-SEP-0024130-[51] | PR |  | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5336XXAB2G00 | MCB 6A DC 2P S202M-K6UC -2CDS272061R0377 | 146 | 146 | 0 | 6100KDP01 | PO-SEP-8041-[88] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5336XXACG000 | Aux contact 2NC, S2C-HO2L-for MCB Order # 2CDS200936R0003 | 119 | 119 | 0 | 6100KDP01 | PO-SEP-8041-[89] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5336XXACH000 | Aux contact 1NO+1NC MCB -2CDS200936R0001 | 179 | 179 | 0 | 6100KDP01 | PO-SEP-8041-[82] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5336XXACJ000 | S2C-H01 - 1NC- Bottom Auxiliary Contact 2CDS200970R0031 | 50 | 50 | 0 | 6100KDP01 | PO-SEP-8041-[83] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | LV/ 6100K023 Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5340XAJXXN00 | RF-4R_125Vdc_4 C/O_LED | 43 | 43 | 0 | 6100KDP01 | PO-SEP-8407-[3] | PO | 2025-10-05 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Innovative Systems Co. Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5340XAJXXN01 | BJ-8RP_Bistable_125Vdc_8 C/O | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8407-[4] | PO | 2025-10-05 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Innovative Systems Co. Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5340XBLXXN00 | MVAJ101 RA 0802_ 125VDC (8 NO + 2 NC) | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8376-[5] | PO | 2026-01-30 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Grid Solution Middle-East Fze | MV
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5340XCLXXN00 | MVAJ105 RA 0802_125VDC (8 NO + 2 NC) | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8376-[6] | PO | 2026-01-30 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Grid Solution Middle-East Fze | MV
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5340XDAXXN00 | RXMVB 4, RK 251 401-AP | 3 | 3 | 0 | 6100K021 | PO-SEP-8751-[17] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5340XDAXXN01 | RXMVB2, RK 251 204-AP | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8366-[7] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5340XEAXXN00 | RXMB1 6NO_110-125VDC-1MRK 000 863-AN | 6 | 6 | 0 | 6100K021 | PO-SEP-8751-[19] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5340XFAXXN00 | RXKL1, TYPE: 1MRK 000 066-AB | 3 | 3 | 0 | 6100K025 | PO-SEP-8751-[10] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5340XIAXXN00 | RXSF1_DC110-125V-MV RK 271 019-AN | 73 | 73 | 0 | 6100K025 | PO-SEP-8751-[11] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5340XNHXXN00 | TRIP LOR/ER 7840FD 20NO+20NC, 125VDC | 6 | 0 | 6 | PR Required | - | PR |  | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 3060 | 3060 | 0 | 6100KDP01 | PO-SEP-8572-[2] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 1125 | 1125 | 0 | 6100KDP01 | PO-SEP-8386-[26] | PO | 2025-11-10 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355AEA0001 | M 6/8.RS (SpringLoaded) 1SNA115685R1200 | 1059 | 1059 | 0 | 6100KDP01 | PO-SEP-8386-[18] | PO | 2025-11-10 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 7912 | 7912 | 0 | 6100KDP01 | PO-SEP-8386-[19] | PO | 2025-11-10 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355AFA0001 | M4/6.SNTS Spring Loaded 1SNA115229R2000 | 1125 | 1125 | 0 | 6100KDP01 | PO-SEP-8386-[20] | PO | 2025-11-10 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 808 | 808 | 0 | 6100KDP01 | PO-SEP-8386-[27] | PO | 2025-11-10 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355AMC0001 | Feed-through terminal block,ZT 4/4AN/2 .Base Terminal Plug AC-DC-4mm 1848350000 | 750 | 750 | 0 | 6100K021 | PO-SEP-8750-[3] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 300 | 300 | 0 | 6100K021 | PO-SEP-8750-[4] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 364 | 364 | 0 | 6100K025 | PO-SEP-8750-[14] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355CBA0000 | FEM8T6 End Sections Grey 1SNA215266R0100 | 375 | 375 | 0 | 6100KDP01 | PO-SEP-8386-[23] | PO | 2025-11-10 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355CEA0000 | FEMR8 End Sections Grey 1SNA116987R0200 | 500 | 500 | 0 | 6100KDP01 | PO-SEP-8386-[24] | PO | 2025-11-10 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355CFA0000 | FEM6 End Sections Grey - 1SNA118368R1600 | 250 | 250 | 0 | 6100KDP01 | PO-SEP-8386-[25] | PO | 2025-11-10 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355CMC0000 | Terminal End Plate 1848360000-Wiedmuller | 100 | 100 | 0 | 6100K025 | PO-SEP-8750-[26] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355CPC0000 | Terminal End Plate 1816110000-Wiedmuller | 100 | 100 | 0 | 6100KDP01 | PO-SEP-8518-[5] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355CTC0000 | Terminal End Plate 1816070000-Wiedmuller | 52 | 52 | 0 | 6100KDP01 | PO-SEP-8518-[6] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 1250 | 950 | 300 | 6100KDP01 | PO-SEP-8572-[4] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 300 | 300 | 0 | 6100K021 | PO-SEP-8792-[14] | PO | 2025-12-20 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355DFA0000 | RC610-VerticalMarking 1SNA233060R0400 | 225 | 225 | 0 | 6100KDP01 | PO-SEP-8386-[28] | PO | 2025-11-10 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355DXC0000 | 460660001 DEK 5 FSZ 1-10 Z-Terminal 1-10 | 10100 | 10100 | 0 | 6100K021 | PO-SEP-8750-[1] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355EEA0000 | JUMPER BAR "BJS8" 20 Poles | 50 | 50 | 0 | 6100KDP01 | PO-SEP-8386-[21] | PO | 2025-11-10 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355EFA0000 | PC61-CombTypeJumprBar10 1SNA163311R2200 | 100 | 100 | 0 | 6100KDP01 | PO-SEP-8386-[22] | PO | 2025-11-10 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 200 | 200 | 0 | 6100K025 | PO-SEP-8750-[29] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355HAB0001 | Zack Strip-Vertical(11-20)- 1053027:0011 | 300 | 0 | 300 | PR Required | - | PR |  | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355HAB0002 | Zack Strip-Vertical Labeled(21-30) | 200 | 200 | 0 | 6100K023 | PO-SEP-8518-[30] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 150 | 150 | 0 | 6100KDP01 | PO-SEP-8518-[10] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355JPC0000 | 6Pole Plug 2.5mm-1815240000-Cont-loop | 100 | 100 | 0 | 6100KDP01 | PO-SEP-8518-[11] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355JTC0000 | 10Pole Plug 2.5mm-1815280000-Cont-loop | 104 | 104 | 0 | 6100KDP01 | PO-SEP-8518-[12] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 300 | 300 | 0 | 6100KDP01 | PO-SEP-8518-[13] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355KPC0000 | Locking ele. 1816130000 for ZT2.5/4AN/2 | 152 | 152 | 0 | 6100KDP01 | PO-SEP-8518-[14] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355LMC0000 | Coding element 1856860000 - ZT4/4AN/2 | 200 | 200 | 0 | 6100KDP01 | PO-SEP-8518-[15] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355LPC0000 | Coding element 1816150000 | 204 | 204 | 0 | 6100KDP01 | PO-SEP-8518-[16] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355MPC0000 | Strain Relief Wied mulpart # 1816140000 | 152 | 152 | 0 | 6100KDP01 | PO-SEP-8518-[17] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 300 | 300 | 0 | 6100KDP01 | PO-SEP-8572-[8] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB539500002004 | ZS1 CIRCUIT BREAKER TROLLEY | 2 | 2 | 0 | 606PD013 | PO-SEP-8734-[10] | PO | 2025-12-15 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | XIAMEN YUTU International Trading Co. Ltd | 606PD013 // Material for New Supplier
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB60050819P0103 | Braided HARNESS TUBE (D40) | 375 | 375 | 0 | 6100K025 | PO-SEP-8834-[5] | PO | 2025-10-23 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Dalian Jinda Industry Co.,Ltd
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB60050819P0106 | Braided HARNESS TUBE (D30) | 500 | 500 | 0 | 6100K025 | PO-SEP-8834-[8] | PO | 2025-10-23 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Dalian Jinda Industry Co.,Ltd
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB60050819P0107 | Braided HARNESS TUBE (D20) | 250 | 250 | 0 | 6100K025 | PO-SEP-8834-[11] | PO | 2025-10-23 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Dalian Jinda Industry Co.,Ltd
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAZ21500101 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 102 | 102 | 0 | 6100KDP01 | PO-SEP-8388-[35] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 228 | 123 | 105 | 6100KDP01 | PO-SEP-8378-[271] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 105 | 66 | 39 | 6100KDP01 | PO-SEP-6812-[51] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 28192 | SCREW NYLON (POLIAM T21900 / 8X25) | 39 | 39 | 0 | free_stock | PR-SEP-0024114-[65] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 28373 | LOCK NUT ACC TO T21192/M2.5x0.45 | 50 | 14 | 36 | 6100KDP01 | PO-SEP-6812-[74] | PO | 2025-08-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 28373 | LOCK NUT ACC TO T21192/M2.5x0.45 | 36 | 36 | 0 | 6100KDP01 | PO-SEP-8647-[9] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Mattssons Fasteners AB
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 28452 | FLEXIBLE SPIROID PINS T22513/3X26 | 6 | 2 | 4 | 6100KDP01 | PO-SEP-8385-[223] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 28452 | FLEXIBLE SPIROID PINS T22513/3X26 | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[67] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 28627 | Rivet NUT ACC T21098/M6 (countersunk) | 304 | 246 | 58 | 6100KDP01 | PO-SEP-8645-[3] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 28627 | Rivet NUT ACC T21098/M6 (countersunk) | 58 | 58 | 0 | free_stock | PR-SEP-0024114-[68] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 29823 | TOMMY HEAD SCREW ACC. T21010/M2.5x20 | 50 | 50 | 0 | 6100KDP01 | PO-SEP-8647-[8] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Mattssons Fasteners AB
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 2CSM258163R0721 | M1363-L | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8388-[28] | PO | 2025-10-30 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 2TRE123451P0001 | 3 PIN SOCKET SWITCH,13A,250V,BSRDP-I | 2 | 1 | 1 | 6100KDP01 | PO-SEP-8388-[29] | PO | 2025-10-30 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 2TRE123451P0001 | 3 PIN SOCKET SWITCH,13A,250V,BSRDP-I | 1 | 1 | 0 | 6100K025 | PO-SEP-8836-[5] | PO | 2025-11-13 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 3WKA014480P0004 | RETAINING_WASHER_DIN6799_6-SPST/A3K | 24 | 19 | 5 | 6100KDP01 | PO-SEP-8385-[289] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 3WKA014480P0004 | RETAINING_WASHER_DIN6799_6-SPST/A3K | 5 | 5 | 0 | free_stock | PR-SEP-0024114-[70] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 48 | 42 | 6 | 6100KDP01 | PO-SEP-8378-[355] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 3WKA014480P0007 | RETAINING_WASHER_DIN6799_9-SPST/A3K | 6 | 6 | 0 | 6100KDP01 | PO-SEP-6812-[57] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 3WKA014538P0012 | SPIRAL_PIN_ISO8748_4X20-ST/BK | 48 | 28 | 20 | 6100K023 | PO-SEP-8385-[1] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 3WKA014538P0012 | SPIRAL_PIN_ISO8748_4X20-ST/BK | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8385-[182] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 4CE7000583P0101 | PIN | 30 | 5 | 25 | 6100KDP01 | PO-SEP-8680-[5] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 4CE7000583P0101 | PIN | 25 | 6 | 19 | 6100KDP01 | PO-SEP-6812-[61] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 4CE7000583P0101 | PIN | 19 | 19 | 0 | free_stock | PR-SEP-0024114-[76] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 500214111 | WASHER T22001/6.8X18 | 25 | 12 | 13 | 6100KDP01 | PO-SEP-8378-[277] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 500214111 | WASHER T22001/6.8X18 | 13 | 7 | 6 | 6100KDP01 | PO-SEP-6812-[15] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 500214111 | WASHER T22001/6.8X18 | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[77] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 500673075 | PIN T22681/8X54,5-5 | 88 | 72 | 16 | 6100KDP01 | PO-SEP-8387-[34] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 500673075 | PIN T22681/8X54,5-5 | 16 | 16 | 0 | free_stock | PR-SEP-0024114-[347] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 5022 643 | COVER PROFILE, AP3 | 40 | 40 | 0 | 6100KDP01 | PO-SEP-8572-[9] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 625 | 625 | 0 | 6100KDP01 | PO-SEP-8572-[10] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 5217 708-3 | M.CONTACT/HAN-E16M/09330162601 | 2 | 1 | 1 | 6100KDP01 | PO-SEP-8368-[12] | PO | 2025-12-15 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 5217 708-3 | M.CONTACT/HAN-E16M/09330162601 | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[78] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 5217 708-7 | F.CONTACT/HAN-E16F/09330162701 | 2 | 1 | 1 | 6100KDP01 | PO-SEP-8368-[8] | PO | 2025-12-15 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 5217 708-7 | F.CONTACT/HAN-E16F/09330162701 | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[79] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 564093/001 | BLOCK FOUNDATION - ZINK COATED | 100 | 100 | 0 | 6100KDP01 | PO-SEP-8629-[22] | PO | 2025-10-30 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0 | FLY METALTECH TRADING CO.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 565937/001 | LEAF SPRING 499355009 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8483-[7] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | AB KOMPONENTY s.r.o. | 6100K023 – PR for Supply of
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 593502001 | BUSHING | 9 | 9 | 0 | 6100K023 | PO-SEP-8385-[28] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 593503001 | ROLLER | 30 | 10 | 20 | 6100KDP01 | PO-SEP-8387-[35] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 593503001 | ROLLER | 20 | 20 | 0 | free_stock | PR-SEP-0024114-[348] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 593509/001 | COMPRESSION SPRING | 70 | 16 | 54 | 6100KDP01 | PO-SEP-8483-[4] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | AB KOMPONENTY s.r.o. | 6100K023 – PR for Supply of
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 593509/001 | COMPRESSION SPRING | 54 | 54 | 0 | free_stock | PR-SEP-0024114-[81] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 9ABA450060P0004 | NUT_ISO7040_M6-8/A3K | 24 | 13 | 11 | 6100KDP01 | PO-SEP-8680-[6] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 9ABA450060P0004 | NUT_ISO7040_M6-8/A3K | 11 | 6 | 5 | 6100KDP01 | PO-SEP-6812-[63] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 9ABA450060P0004 | NUT_ISO7040_M6-8/A3K | 5 | 5 | 0 | free_stock | PR-SEP-0024114-[82] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 9ABA450060P0005 | NUT_ISO7040_M8-8/A3K | 50 | 42 | 8 | 6100KDP01 | PO-SEP-8378-[183] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 9ABA450060P0005 | NUT_ISO7040_M8-8/A3K | 8 | 8 | 0 | free_stock | PR-SEP-0024114-[83] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 9ADJ100023P0357 | BLIND_RIVET_ISO15979_6,4x16-ST/ST | 100 | 48 | 52 | 6100KDP01 | PO-SEP-8378-[204] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 9ADJ100023P0357 | BLIND_RIVET_ISO15979_6,4x16-ST/ST | 52 | 28 | 24 | 6100KDP01 | PO-SEP-6812-[131] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 9ADJ100023P0357 | BLIND_RIVET_ISO15979_6,4x16-ST/ST | 24 | 24 | 0 | free_stock | PR-SEP-0024114-[84] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | HALB | ACCESSORIES | Common additional accessories ( Shutter Lifting truck Parts, Extension Plug 5M) | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE 11342 2100-1 | GLASS,220X350X8.8, GCE8000436P0101 | 28 | 28 | 0 | 6100K023 | PO-SEP-8385-[81] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE 11342 2100-10 | ANCHOR NUT M10X65 (DOWEL) | 80 | 30 | 50 | 6100KDP01 | PO-SEP-8680-[51] | PO | 2025-11-17 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE 11342 2100-10 | ANCHOR NUT M10X65 (DOWEL) | 50 | 50 | 0 | free_stock | PR-SEP-0024114-[450] | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE 2093 7000-5 | RAYCHEM SHRINKABLE TUBE, BPTM 100/40-A/U | 52.84 | 52.84 | 0 | 6100KDP01 | PO-SEP-8393-[5] | PO | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Saudi Electrical Supply Co Sesco | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE 2093 7000-6N | RAYCHEM SHRINKABLE TUBE, BPTM 120/50-A/U | 24.43 | 24.43 | 0 | 6100KDP01 | PO-SEP-8393-[4] | PO | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Saudi Electrical Supply Co Sesco | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 405 | 405 | 0 | 6100KDP01 | PO-SEP-8925-[4] | PO | 2025-10-05 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 375 | 375 | 0 | 6100KDP01 | PO-SEP-8388-[31] | PO | 2025-10-30 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE 2941 2000-1 | STIKER "ON" (WHITE LETTER RED BACKGRND) | 24 | 24 | 0 | 6100KDP01 | PO-SEP-8379-[46] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE 2941 2000-2 | STICKER "OFF" (WHITE LETTER GREEN B/G) | 24 | 24 | 0 | 6100KDP01 | PO-SEP-8379-[27] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE 2941 2000-24 | STICKER "DANGER" (ENGLISH/ARABIC)) | 50 | 50 | 0 | 6100KDP01 | PO-SEP-8379-[26] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2000-1865-02 | YELLOW TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 375 | 0 | 375 | PR Required | - | PR |  | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2000-1865-04 | BLACK TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 250 | 0 | 250 | PR Required | - | PR |  | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2000-1865-05 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 250 | 0 | 250 | PR Required | - | PR |  | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2000-1865-13 | BLACK TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 250 | 0 | 250 | PR Required | - | PR |  | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 32.5 | 32.5 | 0 | 6100K023 | PO-SEP-8835-[4] | PO | 2025-09-18 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | EMKA Beschlagteile Middle East FZE
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 500 | 500 | 0 | 6100KDP01 | PO-SEP-8378-[232] | PO | 2025-11-17 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 150 | 150 | 0 | 6100K025 | PO-SEP-8834-[15] | PO | 2025-10-23 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Dalian Jinda Industry Co.,Ltd
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2001-1903-01 | EDGE PROTECTION (RUBBER) | 24.8 | 24.8 | 0 | 6100KDP01 | PO-SEP-8384-[3] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | DIRAK MIDDLE EAST FZE | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2522-2000-01 | HOOD HAN-E16,09300161520 | 2 | 1 | 1 | 6100KDP01 | PO-SEP-8368-[11] | PO | 2025-12-15 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2522-2000-01 | HOOD HAN-E16,09300161520 | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[92] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8368-[7] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 25 | 25 | 0 | 6100K021 | PO-SEP-8752-[1] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2632-2000-33 | Spring for Door Combiflex | 0.5 | 0.5 | 0 | 6100KDP01 | PO-SEP-8388-[22] | PO | 2025-10-30 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 25 | 25 | 0 | 6100K021 | PO-SEP-8831-[2] | PO | 2025-11-12 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | First Telecom Industries
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 1500 | 1500 | 0 | 6100KDP01 | PO-SEP-8572-[11] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE5849-2100-013 | CASTER WHEEL 100X30-50 (LOCKABLE) | 8 | 0 | 8 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE8004633P0101 | ANGLE LEFT ( POLY )(GCE8004633P0101) | 2 | 0 | 2 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE8004633P0102 | ANGLE RIGHT ( POLY ) (GCE8004633P0102) | 2 | 0 | 2 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE8004633P0111 | ANGLE LEFT ( POLY ) (GCE8004633P0111) | 2 | 0 | 2 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE8004633P0112 | ANGLE RIGHT ( POLY ) (GCE8004633P0112) | 2 | 0 | 2 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 25 | 25 | 0 | 6100K021 | PO-SEP-8724-[5] | PO | 2025-11-16 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | BM0145-1373-ASYP | STEP LADDER SCECO CENTRAL (STANDARD) | 1 | 1 | 0 | 6100K023 | PO-SEP-8816-[2] | PO | 2025-09-21 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0 | AL RAZIQIYAH COMPANY FOR METAL INDUSTRIES
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | CDX7005632R1A | EARTHING CONTACT COMPLETE | 46 | 44 | 2 | 6100KDP01 | PO-SEP-8387-[27] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | CDX7005632R1A | EARTHING CONTACT COMPLETE | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[95] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | CDXN010061R1103 | HANDLE COMPLETE | 25 | 21 | 4 | 6100KDP01 | PO-SEP-8387-[31] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | CDXN010061R1103 | HANDLE COMPLETE | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[96] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-233 | BOLT HEX HEAD M5X30 | 8 | 0 | 8 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 50 | 40 | 10 | 6100KDP01 | PO-SEP-8378-[212] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-256 | BOLT HEX HEAD M6X12 | 10 | 10 | 0 | 6100KDP01 | PO-SEP-6812-[121] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-263 | BOLT HEX HEAD M6X30 | 24 | 24 | 0 | 6100KDP01 | PO-SEP-8378-[185] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-419 | BOLT HEX HEAD M8X45 | 2 | 2 | 0 | 6100KDP01 | PO-SEP-6812-[119] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-493 | BOLT HEX HEAD M10X30 | 240 | 240 | 0 | 6100KDP01 | PO-SEP-8378-[306] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-494 | BOLT HEX HEAD M10X35 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8378-[247] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-496 | BOLT HEX HEAD M10X45 | 60 | 60 | 0 | 6100KDP01 | PO-SEP-8378-[339] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-508 | BOLT HEX HEAD M10X130 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-6812-[128] | PO | 2025-08-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-658 | BOLT HEX HEAD M20X40 | 69 | 69 | 0 | 6100KDP01 | PO-SEP-8378-[169] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-659 | BOLT HEX HEAD M20X45 | 30 | 18 | 12 | 6100KDP01 | PO-SEP-8378-[205] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-659 | BOLT HEX HEAD M20X45 | 12 | 6 | 6 | 6100KDP01 | PO-SEP-6812-[123] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-659 | BOLT HEX HEAD M20X45 | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[101] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-660 | BOLT HEX HEAD M20X50 | 9 | 6 | 3 | 6100KDP01 | PO-SEP-6812-[122] | PO | 2025-08-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-660 | BOLT HEX HEAD M20X50 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8378-[340] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-666 | BOLT HEX HEAD M20X90 | 18 | 12 | 6 | 6100KDP01 | PO-SEP-8378-[201] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2016-666 | BOLT HEX HEAD M20X90 | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[102] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2452-293 | SCREW CROSS REC.HEAD M4X16 | 8 | 8 | 0 | free_stock | PR-SEP-0024114-[103] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 1469 | 1399 | 70 | 6100KDP01 | PO-SEP-8680-[9] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 70 | 16 | 54 | 6100KDP01 | PO-SEP-8680-[2] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2464-364 | SCREW SELF TAPPING TORX M6X10 | 54 | 54 | 0 | 6100KDP01 | PO-SEP-6812-[49] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2467-368 | SCREW SELF TAPPING TORX M6 X 16 | 108 | 108 | 0 | 6100KDP01 | PO-SEP-8378-[194] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-291 | BOLT SOCKET CAP HEAD M4X12 | 28 | 0 | 28 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-293 | BOLT SOCKET HEAD M4X16 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8168-[208] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-299 | BOLT SOCKET CAP HEAD M4X30 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8168-[203] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-325 | BOLT SOCKET CAP M5X10 | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8378-[186] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-333 | BOLT SOCKET CAP HEAD M5X25 | 6 | 2 | 4 | 6100KDP01 | PO-SEP-8378-[308] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-333 | BOLT SOCKET CAP HEAD M5X25 | 4 | 1 | 3 | 6100K023 | PO-SEP-8378-[151] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-333 | BOLT SOCKET CAP HEAD M5X25 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-6812-[107] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-371 | BOLT SOCKET CAP M6X20 | 6 | 2 | 4 | 6100KDP01 | PO-SEP-8378-[246] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-371 | BOLT SOCKET CAP M6X20 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-6812-[95] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-372 | BOLT SOCKET CAP M6X25 | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[112] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-430 | BOLT SOCKET CAP HEAD M6X50 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8168-[212] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 132 | 24 | 108 | 6100KDP01 | PO-SEP-8378-[252] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 108 | 1 | 107 | 6100KDP01 | PO-SEP-6812-[105] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-449 | BOLT SOCKET CAP HEAD M8X16 | 107 | 107 | 0 | free_stock | PR-SEP-0024114-[114] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 1875 | 1558 | 317 | 6100KDP01 | PO-SEP-8378-[164] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 317 | 32 | 285 | 6100KDP01 | PO-SEP-8378-[309] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-451 | BOLT SOCKET CAP M8X20 | 285 | 285 | 0 | 6100KDP01 | PO-SEP-6812-[93] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-453 | BOLT SOCKET CAP HEAD M8X25 | 1012 | 1012 | 0 | 6100KDP01 | PO-SEP-8378-[310] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 628 | 567 | 61 | 6100KDP01 | PO-SEP-8378-[180] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-455 | BOLT SOCKET CAP HEAD M8X30 | 61 | 61 | 0 | 6100KDP01 | PO-SEP-8378-[311] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-457 | BOLT SOCKET CAP M8X35 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-6812-[92] | PO | 2025-08-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-461 | BOLT SOCKET CAP HEAD M8X50 | 48 | 48 | 0 | 6100KDP01 | PO-SEP-8680-[17] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 75 | 63 | 12 | 6100KDP01 | PO-SEP-8378-[214] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-465 | BOLT SOCKET CAP HEAD M8X70 | 12 | 12 | 0 | 6100KDP01 | PO-SEP-6812-[101] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 162 | 132 | 30 | 6100KDP01 | PO-SEP-8378-[215] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-491 | BOLT SOCKET CAP HEAD M10X20 | 30 | 30 | 0 | 6100KDP01 | PO-SEP-6812-[117] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-493 | BOLT SOCKET CAP M10X25 | 941 | 941 | 0 | 6100KDP01 | PO-SEP-8378-[182] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 208 | 188 | 20 | 6100KDP01 | PO-SEP-8378-[167] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-495 | BOLT SOCKET CAP HEAD M10X30 | 20 | 20 | 0 | free_stock | PR-SEP-0024114-[123] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 377 | 334 | 43 | 6100KDP01 | PO-SEP-8378-[173] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-497 | BOLT SOCKET CAP HEAD M10X35 | 43 | 43 | 0 | 6100KDP01 | PO-SEP-6812-[115] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-499 | BOLT SOCKET CAP HEAD M10X40 | 27 | 27 | 0 | 6100KDP01 | PO-SEP-6812-[114] | PO | 2025-08-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-500 | BOLT SOCKET CAP HEAD M10X45 | 378 | 342 | 36 | 6100KDP01 | PO-SEP-8378-[203] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-500 | BOLT SOCKET CAP HEAD M10X45 | 36 | 36 | 0 | free_stock | PR-SEP-0024114-[125] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-505 | CHEESE HEAD BOLT M10X70 | 24 | 24 | 0 | 6100KDP01 | PO-SEP-8680-[44] | PO | 2025-11-17 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-508 | BOLT SOCKET CAP HEAD M10X100 | 180 | 45 | 135 | 6100KDP01 | PO-SEP-6812-[118] | PO | 2025-08-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-508 | BOLT SOCKET CAP HEAD M10X100 | 135 | 135 | 0 | 6100KDP01 | PO-SEP-8378-[341] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-531 | BOLT SOCKET CAP M12X16 (C.H.) | 23 | 16 | 7 | 6100KDP01 | PO-SEP-8378-[251] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-531 | BOLT SOCKET CAP M12X16 (C.H.) | 7 | 5 | 2 | 6100KDP01 | PO-SEP-6812-[99] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-531 | BOLT SOCKET CAP M12X16 (C.H.) | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[126] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 46 | 40 | 6 | 6100KDP01 | PO-SEP-8378-[245] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-532 | BOLT SOCKET CAP M12X20 | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[354] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 23 | 1 | 22 | 6100KDP01 | PO-SEP-8378-[313] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 22 | 10 | 12 | 6100KDP01 | PO-SEP-6812-[113] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-534 | BOLT SOCKET CAP HEAD M12X25 | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[355] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-538 | BOLT SOCKET CAP HEAD M12X35 | 677 | 677 | 0 | 6100KDP01 | PO-SEP-8378-[174] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-540 | BOLT SOCKET CAP HEAD M12X40 | 13 | 13 | 0 | 6100KDP01 | PO-SEP-6812-[111] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 264 | 246 | 18 | 6100KDP01 | PO-SEP-8378-[210] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-541 | BOLT SOCKET CAP M12X45 | 18 | 18 | 0 | 6100KDP01 | PO-SEP-6812-[97] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-542 | BOLT SOCKET CAP HEAD M12X50 | 30 | 12 | 18 | 6100KDP01 | PO-SEP-8378-[179] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-542 | BOLT SOCKET CAP HEAD M12X50 | 18 | 18 | 0 | free_stock | PR-SEP-0024114-[129] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-544 | BOLT SOCKET CAP HEAD M12X60 | 66 | 45 | 21 | 6100KDP01 | PO-SEP-8680-[16] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-544 | BOLT SOCKET CAP HEAD M12X60 | 21 | 21 | 0 | free_stock | PR-SEP-0024114-[130] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-627 | BOLT SOCKET CAP HEAD M16X30 (T21216) | 426 | 426 | 0 | 6100KDP01 | PO-SEP-8378-[157] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-628 | BOLT SOCKET CAP HEAD M16X40 | 18 | 6 | 12 | 6100KDP01 | PO-SEP-6812-[109] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-628 | BOLT SOCKET CAP HEAD M16X40 | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[131] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 144 | 84 | 60 | 6100KDP01 | PO-SEP-8680-[10] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 60 | 38 | 22 | 6100KDP01 | PO-SEP-6812-[53] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 22 | 6 | 16 | 606PD013 | PO-SEP-6812-[149] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2711-366 | SCREW COUNTERSUNK HEAD M6X12 | 16 | 16 | 0 | free_stock | PR-SEP-0024114-[132] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2852-536 | COUNTERSUNK ALLEN HEAD M12X30 | 100 | 100 | 0 | 6100KDP01 | PO-SEP-8378-[314] | PO | 2025-11-17 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 2011-117 | NUT, HEX M 8 | 522 | 522 | 0 | 6100KDP01 | PO-SEP-8680-[11] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 245 | 194 | 51 | 6100KDP01 | PO-SEP-8378-[254] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 2011-122 | NUT, HEX M12 | 51 | 51 | 0 | 6100KDP01 | PO-SEP-6812-[67] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 2011-124 | NUT, HEX M16 | 9 | 9 | 0 | 6100KDP01 | PO-SEP-6812-[66] | PO | 2025-08-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 2013-122 | NUT HEX H D GALV M12 | 126 | 126 | 0 | 6100KDP01 | PO-SEP-8680-[48] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 2013-124 | NUT HEX H D GALV M16 | 360 | 72 | 288 | 6100KDP01 | PO-SEP-6812-[72] | PO | 2025-08-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 2013-124 | NUT HEX H D GALV M16 | 288 | 288 | 0 | 6100KDP01 | PO-SEP-8388-[33] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 843-1 | RIVET NUT M6 (HEXAGONAL) | 6 | 4 | 2 | 6100KDP01 | PO-SEP-8378-[329] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 843-1 | RIVET NUT M6 (HEXAGONAL) | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[139] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2151 2062-136 | WASHER FLAT BRIR 4.3X8X0.8 | 159 | 72 | 87 | 6100KDP01 | PO-SEP-8680-[20] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2151 2062-136 | WASHER FLAT BRIR 4.3X8X0.8 | 87 | 42 | 45 | 6100KDP01 | PO-SEP-6812-[23] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2151 2062-136 | WASHER FLAT BRIR 4.3X8X0.8 | 45 | 18 | 27 | 606PD013 | PO-SEP-6812-[155] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2151 2062-136 | WASHER FLAT BRIR 4.3X8X0.8 | 27 | 27 | 0 | free_stock | PR-SEP-0024114-[140] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2151 2062-153 | WASHER FLAT 6.4X12X1.5 | 745 | 745 | 0 | 6100KDP01 | PO-SEP-8378-[249] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2151 2062-165 | WASHER FLAT BRIR 8.4X16X1.5 (M8) | 98 | 98 | 0 | free_stock | PO-SEP-8044-[11] | PO | 2025-07-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Raja Procuremnet Local Purchases
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2151 2062-173 | WASHER FLAT BRIR 10.5X22X2 (M10) | 200 | 200 | 0 | 6100KDP01 | PO-SEP-8378-[213] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2151 2063-177 | WASHER FLAT H D GALV 13X29X2 | 16 | 0 | 16 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 4171 | 3425 | 746 | 6100KDP01 | PO-SEP-8378-[250] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2154 2033-10 | WASHER, CONICAL 10.5X23X2.5 | 746 | 746 | 0 | 6100KDP01 | PO-SEP-8378-[317] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2154 2033-12 | WASHER, CONICAL 13X29X3 | 1542 | 1542 | 0 | 6100KDP01 | PO-SEP-8378-[170] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 828 | 786 | 42 | 6100KDP01 | PO-SEP-8378-[257] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2154 2033-16 | WASHER, CONICAL 17X39X4 | 42 | 42 | 0 | 6100KDP01 | PO-SEP-6812-[11] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2154 2033-19 | WASHER,SPRING 21X45X5 DIN6796 | 108 | 108 | 0 | 6100KDP01 | PO-SEP-8378-[202] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2154 2033-7 | WASHER, CONICAL 6.4X14X1.5 | 382 | 382 | 0 | 6100KDP01 | PO-SEP-8378-[175] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2154 2033-9 | WASHER, CONICAL 8.4X18X2 | 3881 | 3881 | 0 | 6100KDP01 | PO-SEP-8378-[163] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 10000 | 8800 | 1200 | 6100KDP01 | PO-SEP-8378-[234] | PO | 2025-11-17 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 1200 | 1200 | 0 | 6100K021 | PO-SEP-8881-[6] | PO | 2025-12-21 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 125 | 125 | 0 | 6100K021 | PO-SEP-8881-[7] | PO | 2025-12-21 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 25 | 25 | 0 | 6100K021 | PO-SEP-8881-[8] | PO | 2025-12-21 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 150 | 150 | 0 | 6100K021 | PO-SEP-8881-[9] | PO | 2025-12-21 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 1200 | 1200 | 0 | 6100K025 | PO-SEP-8925-[1] | PO | 2025-10-23 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 200 | 200 | 0 | 6100K021 | PO-SEP-8881-[10] | PO | 2025-12-21 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 924 0010 | Combiflex wire Socket 1.5mm 1MRK002136-B | 5000 | 5000 | 0 | 6100K025 | PO-SEP-8751-[15] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 924 0020 | Combiflex wire Socket 2.5mm 1MRK002136-E | 3000 | 3000 | 0 | 6100K021 | PO-SEP-8751-[26] | PO | 2025-12-31 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8362-[4] | PO | 2025-12-15 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Shanghai Feili Xuncheng Electrical Technology Co.,Ltd | Snap action/ 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0007249P0100 | GREASE ISOPLEX TOPAS,NB52,1kg | 0.275 | 0.275 | 0 | 6100KDP01 | PO-SEP-8908-[4] | PO | 2025-10-15 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0 | Quality Bearing Online Limited
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0068009P0100 | BUSHING D8/3 PVC | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8755-[2] | PO | 2025-12-31 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | MESAN KİLİT A.Ş.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0301012P0100 | CHEESE HEAD B0LT M3X6 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8168-[199] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0303179P0100 | CYLINDER HEAD BOLT M10X80 DIN 91 | 6 | 6 | 0 | 6100KDP01 | PO-SEP-6812-[88] | PO | 2025-08-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0305850P0100 | POLYAMID BOLT M6X20 | 57 | 38 | 19 | 6100KDP01 | PO-SEP-8378-[235] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0305850P0100 | POLYAMID BOLT M6X20 | 19 | 19 | 0 | free_stock | PR-SEP-0024114-[155] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0305871P0100 | HEX BOLT M8X16 DIN 933-POLY | 172 | 147 | 25 | 6100KDP01 | PO-SEP-8378-[290] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0305871P0100 | HEX BOLT M8X16 DIN 933-POLY | 25 | 25 | 0 | free_stock | PR-SEP-0024114-[156] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 178 | 163 | 15 | 6100KDP01 | PO-SEP-8378-[198] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0316006P0100 | HEAD SCREW M6X16, DIN 603-4.6 | 15 | 15 | 0 | free_stock | PR-SEP-0024114-[157] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0316044P0100 | HEAD SCREW M8X50, DIN 603-4.3 | 48 | 28 | 20 | 6100KDP01 | PO-SEP-8629-[7] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | FLY METALTECH TRADING CO.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0316044P0100 | HEAD SCREW M8X50, DIN 603-4.3 | 20 | 2 | 18 | 606PD013 | PO-SEP-8834-[20] | PO | 2025-11-03 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Dalian Jinda Industry Co.,Ltd
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0316044P0100 | HEAD SCREW M8X50, DIN 603-4.3 | 18 | 10 | 8 | 6100KDP01 | PO-SEP-6812-[85] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0316044P0100 | HEAD SCREW M8X50, DIN 603-4.3 | 8 | 6 | 2 | 606PD013 | PO-SEP-6812-[147] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0316044P0100 | HEAD SCREW M8X50, DIN 603-4.3 | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[158] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0326219P0100 | SCREW,SET M6X10 | 48 | 48 | 0 | 6100KDP01 | PO-SEP-8629-[5] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | FLY METALTECH TRADING CO.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0336970P0100 | BOLT,TAPTITE HEX BOLT M5X12 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8385-[193] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0336985P0100 | TAPPING SCREW M6X16/6KTHEAD | 5 | 2 | 3 | 6100KDP01 | PO-SEP-6812-[35] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0336985P0100 | TAPPING SCREW M6X16/6KTHEAD | 3 | 3 | 0 | free_stock | PR-SEP-0024114-[161] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0350009P0100 | NUT M6 DIN 439-04 | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8385-[297] | PO | 2025-10-12 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0365304P0100 | NUT,HEX.NUT MPG 16 | 2 | 1 | 1 | 6100KDP01 | PO-SEP-8378-[219] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0365304P0100 | NUT,HEX.NUT MPG 16 | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[162] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0367308P0100 | NUT, HEX - M5, DIN 985-6 ( LOCK NUT ) | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8168-[211] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0367309P0100 | HEX. NUT M6, DIN 985-6 ( LOCK NUT ) | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[358] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0367402P0100 | HEX. NUT M4, DIN 6925-13 ( LOCK NUT ) | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8378-[346] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0367406P0100 | HEX. NUT M10, (LOCK NUT ) | 8 | 0 | 8 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0369010P0100 | RIVET NUT M6X16 WITH GROOVE | 57 | 38 | 19 | 6100KDP01 | PO-SEP-8378-[330] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0369010P0100 | RIVET NUT M6X16 WITH GROOVE | 19 | 19 | 0 | free_stock | PR-SEP-0024114-[163] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 1123 | 980 | 143 | 6100KDP01 | PO-SEP-8378-[168] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 143 | 102 | 41 | 6100KDP01 | PO-SEP-8378-[320] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0369213P0100 | HEX RIVET NUT M8X17, LARGE FLANGE | 41 | 41 | 0 | 606PD013 | PO-SEP-6812-[143] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 330 | 148 | 182 | 6100KDP01 | PO-SEP-8378-[255] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 182 | 8 | 174 | 6100KDP01 | PO-SEP-8378-[304] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0369214P0100 | HEX.RIVET NUT M10X24 ( 25541 ) | 174 | 174 | 0 | free_stock | PR-SEP-0024114-[165] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0369215P0100 | RIVET NUT , M12 | 16 | 0 | 16 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0369233P0100 | HEX RIVET NUT M8x18 COUNTER SUNK | 1070 | 1070 | 0 | 6100KDP01 | PO-SEP-8378-[321] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 242 | 187 | 55 | 6100KDP01 | PO-SEP-8378-[165] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 55 | 30 | 25 | 6100KDP01 | PO-SEP-8378-[322] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0369312P0100 | COUNTERSUNK RIVET NUT M10x22.9 | 25 | 25 | 0 | 6100KDP01 | PO-SEP-6812-[89] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0401027P0100 | WASHER FLAT 10.5,DIN433-ST | 92 | 56 | 36 | 6100KDP01 | PO-SEP-8378-[196] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0401027P0100 | WASHER FLAT 10.5,DIN433-ST | 36 | 20 | 16 | 6100KDP01 | PO-SEP-6812-[27] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0401027P0100 | WASHER FLAT 10.5,DIN433-ST | 16 | 16 | 0 | free_stock | PR-SEP-0024114-[168] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0402005P0100 | WASHER,SPRING A3.2 | 8 | 8 | 0 | 6100K023 | PO-SEP-8629-[11] | PO | 2025-09-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | FLY METALTECH TRADING CO.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0402008P0100 | WASHER, A5., DIN 125-ST | 12 | 0 | 12 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0402909P0100 | WASHER POLYAMID, A6.4, DIN 125 | 57 | 38 | 19 | 6100KDP01 | PO-SEP-8629-[1] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | FLY METALTECH TRADING CO.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0402909P0100 | WASHER POLYAMID, A6.4, DIN 125 | 19 | 19 | 0 | free_stock | PR-SEP-0024114-[169] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0402911P0100 | WASHER POLYAMID, A8.4, DIN 125 | 396 | 242 | 154 | 6100KDP01 | PO-SEP-8378-[172] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0402911P0100 | WASHER POLYAMID, A8.4, DIN 125 | 154 | 89 | 65 | 6100KDP01 | PO-SEP-6812-[19] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0402911P0100 | WASHER POLYAMID, A8.4, DIN 125 | 65 | 65 | 0 | free_stock | PR-SEP-0024114-[170] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0402912P0100 | WASHER POLYAMID, A10.5, DIN 125 | 288 | 252 | 36 | 6100KDP01 | PO-SEP-8378-[293] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0402912P0100 | WASHER POLYAMID, A10.5, DIN 125 | 36 | 36 | 0 | free_stock | PR-SEP-0024114-[171] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0410004P0100 | SPRING RING A3, DIN 127-FST | 16 | 16 | 0 | 6100KDP01 | PO-SEP-8385-[149] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0410006P0100 | SPRING A4, DIN 127-FST | 44 | 24 | 20 | 6100KDP01 | PO-SEP-8168-[198] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0410006P0100 | SPRING A4, DIN 127-FST | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8378-[349] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0410007P0100 | SPRING RING, A5, DIN 127-FST | 10 | 4 | 6 | 6100K023 | PO-SEP-8385-[171] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0410007P0100 | SPRING RING, A5, DIN 127-FST | 6 | 4 | 2 | 6100KDP01 | PO-SEP-8877-[10] | PO | 2025-09-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0410007P0100 | SPRING RING, A5, DIN 127-FST | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8385-[295] | PO | 2025-10-19 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0412007P0100 | SPRING RING 10 DIN 7980-FST | 72 | 48 | 24 | 6100KDP01 | PO-SEP-8378-[244] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0412007P0100 | SPRING RING 10 DIN 7980-FST | 24 | 24 | 0 | free_stock | PR-SEP-0024114-[173] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0413160P0100 | RETAINING WASHER VS5 | 24 | 13 | 11 | 6100KDP01 | PO-SEP-8385-[298] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0413160P0100 | RETAINING WASHER VS5 | 11 | 6 | 5 | 6100KDP01 | PO-SEP-6812-[59] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0413160P0100 | RETAINING WASHER VS5 | 5 | 5 | 0 | free_stock | PR-SEP-0024114-[174] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0413167P0100 | WASHER VS12 - FST | 4 | 4 | 0 | 6100KDP01 | PO-SEP-6812-[14] | PO | 2025-08-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0413307P0100 | CONTACT WASHER 12 | 24 | 4 | 20 | 6100KDP01 | PO-SEP-8378-[350] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0413307P0100 | CONTACT WASHER 12 | 20 | 8 | 12 | 6100KDP01 | PO-SEP-6812-[91] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0413307P0100 | CONTACT WASHER 12 | 12 | 0 | 12 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0417501P0100 | SPLIT PIN FOR FRICK B. CHUCK | 6 | 3 | 3 | 6100KDP01 | PO-SEP-8385-[292] | PO | 2025-10-19 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0417501P0100 | SPLIT PIN FOR FRICK B. CHUCK | 3 | 0 | 3 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0418011P0100 | REVTAINING RING BORE-8 | 4 | 4 | 0 | 6100K023 | PO-SEP-8385-[173] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 83 | 78 | 5 | 6100KDP01 | PO-SEP-8629-[10] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | FLY METALTECH TRADING CO.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0418202P0100 | WASHER,RETAINING 5/WN 418-FST | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8168-[206] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K022 // Mechanical Bulk Components,
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0418203P0100 | WASHER,RETAINING 6, WN418-FST | 88 | 40 | 48 | 6100KDP01 | PO-SEP-8378-[292] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0418203P0100 | WASHER,RETAINING 6, WN418-FST | 48 | 28 | 20 | 6100KDP01 | PO-SEP-6812-[3] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0418203P0100 | WASHER,RETAINING 6, WN418-FST | 20 | 20 | 0 | free_stock | PR-SEP-0024114-[359] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0418204P0100 | WASHER RETAINING 8/WN 418-FST | 29 | 8 | 21 | 6100KDP01 | PO-SEP-8680-[14] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | ALAM AL NIMA TRADING EST
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0418204P0100 | WASHER RETAINING 8/WN 418-FST | 21 | 11 | 10 | 6100KDP01 | PO-SEP-6812-[17] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0418204P0100 | WASHER RETAINING 8/WN 418-FST | 10 | 10 | 0 | free_stock | PR-SEP-0024114-[176] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0418205P0100 | WASHER RETAINING 10, WN418-FST | 92 | 76 | 16 | 6100KDP01 | PO-SEP-8378-[197] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0418205P0100 | WASHER RETAINING 10, WN418-FST | 16 | 16 | 0 | free_stock | PR-SEP-0024114-[177] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0422013P0100 | WASHER,RETAINING 16X1 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-6812-[5] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0422025P0100 | RETAINING RING (SHAFT)30X1.5 | 4 | 0 | 4 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0438423P0100 | SPRING PIN 3X16 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8629-[6] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | FLY METALTECH TRADING CO.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0438425P0100 | SPRING PIN SLOTTED 3X20 (EQUIV.=28272) | 18 | 6 | 12 | 6100KDP01 | PO-SEP-8385-[199] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0438425P0100 | SPRING PIN SLOTTED 3X20 (EQUIV.=28272) | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[179] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0438432P0100 | PIN,SPRING (SLOTED) 4X10 | 16 | 0 | 16 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0438453P0100 | PIN,SPRING (SLOTED) 5X26 | 22 | 0 | 22 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0438455P0100 | SPRING PIN SLOTTED 5X30 | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0457035P0100 | BLIND RIVET 5X10 AL | 200 | 112 | 88 | 6100KDP01 | PO-SEP-8378-[331] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0457035P0100 | BLIND RIVET 5X10 AL | 88 | 56 | 32 | 6100KDP01 | PO-SEP-6812-[133] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0457035P0100 | BLIND RIVET 5X10 AL | 32 | 32 | 0 | free_stock | PR-SEP-0024114-[180] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0457038P0100 | BLIND RIVET 5X16, CIECO, WN457-ALU | 96 | 78 | 18 | 6100KDP01 | PO-SEP-8378-[334] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0457038P0100 | BLIND RIVET 5X16, CIECO, WN457-ALU | 18 | 18 | 0 | free_stock | PR-SEP-0024114-[181] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0457040P0100 | BLIND RIVET 6.4X12 STEEL | 201 | 134 | 67 | 6100KDP01 | PO-SEP-8378-[335] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0457040P0100 | BLIND RIVET 6.4X12 STEEL | 67 | 67 | 0 | free_stock | PR-SEP-0024114-[182] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0518520P0101 | ATTENTION SIGN (SEGNALE DI PERICOLO) | 2 | 0 | 2 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0909121P0100 | STRAIN RELIEF TYPE ZE2/10 | 6 | 2 | 4 | 6100KDP01 | PO-SEP-8385-[150] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0909121P0100 | STRAIN RELIEF TYPE ZE2/10 | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[184] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0909123P0100 | PLUG-IN CONNECTION - 645060000 | 4 | 0 | 4 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0909124P0100 | BUSH STV2/10 ORDER.NO. 0645160000 | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0931008P0100 | POST TYPE INSULATOR 12kV SIZE B 2040384 | 12 | 12 | 0 | 606PD013 | PO-SEP-8389-[7] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0931306P0100 | BUSHING KD20-30/115(2033335)GJ (LOWER) | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8389-[8] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Georg Jordan GmbH | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0931316P0100 | BUSBAR INSERT 2XD100 | 75 | 72 | 3 | 6100K023 | PO-SEP-8385-[101] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0931316P0100 | BUSBAR INSERT 2XD100 | 3 | 3 | 0 | 606PD013 | PO-SEP-8385-[29] | PO | 2025-09-28 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0990014P0100 | THREADED PLATE M10 | 8 | 8 | 0 | free_stock | PR-SEP-0024114-[429] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 50 | 49 | 1 | 6100KDP01 | PO-SEP-8409-[4] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8409-[5] | PO | 2025-12-15 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0990162P0102 | PANEL HEATER 240V,100W-Boxin-5MetCable | 25 | 21 | 4 | 6100KDP01 | PO-SEP-8409-[6] | PO | 2025-12-15 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0990162P0102 | PANEL HEATER 240V,100W-Boxin-5MetCable | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[188] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0990403P0100 | VENTILATOR QK08A-2EM.50.CH WITH CAPACITO | 3 | 3 | 0 | 6100K025 | PO-SEP-8748-[3] | PO | 2025-12-31 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | ZIEHL ABEGG Middle East FZE | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0990404P0100 | RADIAL FLOW FAN QK08A-2EM.35.CF | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8361-[4] | PO | 2025-12-31 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | ZIEHL ABEGG Middle East FZE | Fans / 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0990431P0100 | HANDLE | 355 | 355 | 0 | 6100KDP01 | PO-SEP-8385-[132] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0996027P0100 | PROTECTION CAP M10NR.610 | 120 | 78 | 42 | 6100KDP01 | PO-SEP-8629-[2] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | FLY METALTECH TRADING CO.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0996027P0100 | PROTECTION CAP M10NR.610 | 42 | 24 | 18 | 6100KDP01 | PO-SEP-7832-[1] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | FLY METALTECH TRADING CO. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0996027P0100 | PROTECTION CAP M10NR.610 | 18 | 18 | 0 | free_stock | PR-SEP-0024114-[360] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0998134P0100 | SEALING RUBBER | 338.51 | 321.88 | 16.63 | 6100KDP01 | PO-SEP-8394-[2] | PO | 2025-12-15 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Suzhou Dirak Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0998134P0100 | SEALING RUBBER | 16.63 | 16.63 | 0 | free_stock | PR-SEP-0024114-[195] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0998162P0100 | REDUCING RING PVC | 431 | 323 | 108 | 6100KDP01 | PO-SEP-8385-[131] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0998162P0100 | REDUCING RING PVC | 108 | 108 | 0 | free_stock | PR-SEP-0024114-[196] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0998168P0100 | PLASTIC BUSHING EK/G36 | 3 | 2 | 1 | 6100KDP01 | PO-SEP-8385-[164] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE0998168P0100 | PLASTIC BUSHING EK/G36 | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[197] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4117104P0117 | TUBE G16X9 | 48 | 28 | 20 | 6100K023 | PO-SEP-8385-[13] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4117104P0117 | TUBE G16X9 | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8385-[186] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4366010P0100 | NUT(DADO D'ANCORAGGIO) M10 WN366-ST37-2 | 182 | 46 | 136 | 6100K023 | PO-SEP-8385-[232] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4366010P0100 | NUT(DADO D'ANCORAGGIO) M10 WN366-ST37-2 | 136 | 136 | 0 | 6100KDP01 | PO-SEP-8385-[134] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4395060P0100 | WASHER,PLAIN , LARGE 6.1/18X1 | 36 | 20 | 16 | 6100KDP01 | PO-SEP-8378-[351] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4395060P0100 | WASHER,PLAIN , LARGE 6.1/18X1 | 16 | 0 | 16 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4395592P0100 | WASHER FLAT 8 X 11 X 0.5 MM | 150 | 84 | 66 | 6100KDP01 | PO-SEP-8378-[258] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4395592P0100 | WASHER FLAT 8 X 11 X 0.5 MM | 66 | 42 | 24 | 6100KDP01 | PO-SEP-6812-[25] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4395592P0100 | WASHER FLAT 8 X 11 X 0.5 MM | 24 | 24 | 0 | free_stock | PR-SEP-0024114-[202] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4395856P0100 | PLAIN WASHER, LARGE 6.2x12x0.2 | 18 | 8 | 10 | 6100KDP01 | PO-SEP-8378-[218] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4395856P0100 | PLAIN WASHER, LARGE 6.2x12x0.2 | 10 | 10 | 0 | free_stock | PR-SEP-0024114-[203] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4396016P0100 | PLAIN WASSHER 9/33X2.5 | 8 | 8 | 0 | free_stock | PR-SEP-0024114-[440] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4396073P0100 | WASHER LARG PLN (12.1/23.5X2.5 | 8 | 8 | 0 | free_stock | PR-SEP-0024114-[204] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4520999P0100 | INDICATION LABELS ( HOCK SYSMBLE ) | 8 | 7 | 1 | 6100K023 | PO-SEP-8379-[42] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4520999P0100 | INDICATION LABELS ( HOCK SYSMBLE ) | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8724-[1] | PO | 2025-11-16 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4530250P0100 | DESIGNATION LABEL L1 (RED) | 25 | 19 | 6 | 6100KDP01 | PO-SEP-8379-[31] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4530250P0100 | DESIGNATION LABEL L1 (RED) | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[205] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4530251P0100 | DESIGNATION LABEL L2 (YELLOW) | 25 | 19 | 6 | 6100KDP01 | PO-SEP-8379-[32] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4530251P0100 | DESIGNATION LABEL L2 (YELLOW) | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[206] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4530252P0100 | DESIGNATION LABEL L3 (BLUE) | 25 | 19 | 6 | 6100KDP01 | PO-SEP-8379-[33] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4530252P0100 | DESIGNATION LABEL L3 (BLUE) | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[207] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4539019P0100 | INFORMATION PLATE | 24 | 24 | 0 | 6100KDP01 | PO-SEP-8379-[36] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4539452P0100 | INDICATION LABEL Mech.Operation STICKER | 23 | 19 | 4 | 6100KDP01 | PO-SEP-8379-[28] | PO | 2025-10-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4539452P0100 | INDICATION LABEL Mech.Operation STICKER | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[209] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4539457P0101A | INFORMATION PLATE ( LOCAL ) | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE4539458P0101A | INFORMATION PLATE ( LOCAL ) | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000495R0101 | SHAFT COMPL. | 24 | 14 | 10 | 6100K023 | PO-SEP-8385-[15] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000495R0101 | SHAFT COMPL. | 10 | 10 | 0 | 6100KDP01 | PO-SEP-8385-[179] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000496P0102 | TORSION SPRING | 25 | 18 | 7 | 6100KDP01 | PO-SEP-8387-[20] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000496P0102 | TORSION SPRING | 7 | 7 | 0 | free_stock | PR-SEP-0024114-[211] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000497R0101 | BEARING HOUSING COMPLETE | 24 | 19 | 5 | 6100KDP01 | PO-SEP-8387-[30] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000497R0101 | BEARING HOUSING COMPLETE | 5 | 5 | 0 | free_stock | PR-SEP-0024114-[212] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000508P0101 | GROOVED PIN | 48 | 41 | 7 | free_stock | PR-SEP-0024114-[213] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000508P0101 | GROOVED PIN | 7 | 0 | 7 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000525P0101 | WASHER,STOP | 24 | 19 | 5 | 6100KDP01 | PO-SEP-8385-[299] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000525P0101 | WASHER,STOP | 5 | 5 | 0 | free_stock | PR-SEP-0024114-[215] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000541P0101P | ADJUSTING RING | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000542P0101 | BUSH D10/6.2X15 | 12 | 0 | 12 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000545P0101 | COMPRESSION SPRING | 4 | 0 | 4 | PR Required | - | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000552P0101 | STOP WASHER | 96 | 82 | 14 | free_stock | PR-SEP-0024114-[217] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000552P0101 | STOP WASHER | 14 | 0 | 14 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000663R0101 | BEVEL GEAR DRIVE FOR EK6 ZS1 | 24 | 19 | 5 | 6100KDP01 | PO-SEP-8397-[5] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Xiamen Xingjitai Electrical Apparatus Co. Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000663R0101 | BEVEL GEAR DRIVE FOR EK6 ZS1 | 5 | 5 | 0 | free_stock | PR-SEP-0024114-[221] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7000847P0101P | K - STUD | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7001026P0101 | INSULATION TUBE; L=45MM. | 48 | 28 | 20 | 6100K023 | PO-SEP-8385-[20] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7001026P0101 | INSULATION TUBE; L=45MM. | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8385-[189] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7001732R0105 | EARTHING SWITCH: EK6/ZS1-1710-275 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8382-[5] | PO | 2026-01-22 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | Earthing Switch/6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003008P0101 | RING | 24 | 19 | 5 | 6100KDP01 | PO-SEP-8387-[21] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Fujian Sanxing Electric Co., Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003008P0101 | RING | 5 | 5 | 0 | free_stock | PR-SEP-0024114-[226] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003012P0101P | TUBE 8X5.1X25 | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003536P0101 | DETENT | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003538P0101 | COVER | 2 | 2 | 0 | 6100K023 | PO-SEP-8385-[89] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003544P0101 | SPINDLE | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003553P0101P | HEXAGON BOLT | 16 | 0 | 16 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003556P0101 | SLIDE | 12 | 0 | 12 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003557P0101 | SLIDE | 4 | 0 | 4 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003562P0101P | K - BUSH 10X60 | 2 | 0 | 2 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003563P0101 | SHAFT | 2 | 2 | 0 | 6100KDP01 | PO-SEP-8057-[2] | PO | 2025-10-20 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | XIAMEN STARLIGHTS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003568P0101 | NUT SPECIAL | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003572P0101 | TORSION SPRING | 1 | 1 | 0 | 6100KDP01 | PO-SEP-8057-[3] | PO | 2025-10-20 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | XIAMEN STARLIGHTS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003578P0101 | SQUARE BOLT 4KT8/20 | 12 | 0 | 12 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003579P0101 | TENSION SPRING 6.5/.9/30/16 | 31 | 14 | 17 | 6100KDP01 | PO-SEP-8396-[38] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003579P0101 | TENSION SPRING 6.5/.9/30/16 | 17 | 17 | 0 | free_stock | PR-SEP-0024114-[227] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003579P0102 | TENSION SPRING 6.5/.9/30/16 | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003580P0101 | CCOMPRESSION SPRING | 2 | 0 | 2 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003581P0101 | COMPRESSION SPRING 7.5/0,8/9/25 | 12 | 0 | 12 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003582P0101 | NUT | 12 | 0 | 12 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7003694P0102 | CARRIER | 36 | 36 | 0 | free_stock | PR-SEP-0024114-[228] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7004025R0102 | DRAW OUT DEVICEP210-S200 ASSY. | 2 | 2 | 0 | 6100K023 | PO-SEP-8385-[112] | PO | 2025-09-21 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7004046R0101 | RECTIFIER COMPL. | 2 | 2 | 0 | 6100K023 | PO-SEP-8385-[120] | PO | 2025-09-21 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7102436P0100 | PLUG HOUSING SOCKET/GEHAUSE | 26 | 21 | 5 | 6100K023 | PO-SEP-8385-[23] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7102436P0100 | PLUG HOUSING SOCKET/GEHAUSE | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8385-[213] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7107642P0100 | TENSION SPRING 8.9/0.7/35/10 | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7109399R0101 | AUXILIARY SWITCH 5NO | 48 | 38 | 10 | 6100KDP01 | PO-SEP-8409-[7] | PO | 2025-12-15 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7109399R0101 | AUXILIARY SWITCH 5NO | 10 | 10 | 0 | free_stock | PR-SEP-0024114-[231] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7109399R0106 | AUXILIARY SWITCH 5NC | 24 | 24 | 0 | 6100KDP01 | PO-SEP-8385-[156] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7109399R0118 | SLIDE F.AUX.SWICH 5NC | 3 | 2 | 1 | 6100KDP01 | PO-SEP-8385-[163] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7109399R0118 | SLIDE F.AUX.SWICH 5NC | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[233] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7109399R0119 | AUX.SWITCH 5NO. (S8,S9) | 4 | 4 | 0 | 6100K023 | PO-SEP-8385-[90] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7169312R0145 | EARTHING SWITCH: EK6-ZS1-1706-210 | 21 | 21 | 0 | 6100KDP01 | PO-SEP-8382-[6] | PO | 2026-01-22 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | Earthing Switch/6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7192037R0100 | INSULATOR SGB 24N A1 POT 24kV 2040742 | 9 | 5 | 4 | free_stock | PR-SEP-0024114-[234] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7192037R0100 | INSULATOR SGB 24N A1 POT 24kV 2040742 | 4 | 0 | 4 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7204654P0101 | BOLT 7/4X15 | 16 | 12 | 4 | 6100KDP01 | PO-SEP-8385-[191] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7204654P0101 | BOLT 7/4X15 | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[235] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7208367P0100 | DESIGNATION LABEL | 48 | 42 | 6 | free_stock | PR-SEP-0024114-[236] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7208367P0100 | DESIGNATION LABEL | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7208368P0100 | DESIGNATION LABEL | 24 | 17 | 7 | free_stock | PR-SEP-0024114-[237] | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE7208368P0100 | DESIGNATION LABEL | 7 | 0 | 7 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8000633P0113P | MOUNTING CHANNEL 760mm (GCE8000633P0113) | 44 | 44 | 0 | 6100KDP01 | PO-SEP-8385-[130] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8000910P0101 | PACKING PIECE 80X15 | 12 | 12 | 0 | 6100K023 | PO-SEP-8385-[104] | PO | 2025-09-21 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8001698R0107P | LEVER MECHANISM LEFT-SX 2X R250/55(w1000 | 3 | 2 | 1 | 6100KDP01 | PO-SEP-8385-[226] | PO | 2025-10-05 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8001698R0107P | LEVER MECHANISM LEFT-SX 2X R250/55(w1000 | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[242] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8001698R0108P | LEVER MECHANISM RIGHT,DX2X R250/55(w1000 | 3 | 2 | 1 | 6100KDP01 | PO-SEP-8385-[225] | PO | 2025-10-05 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8001698R0108P | LEVER MECHANISM RIGHT,DX2X R250/55(w1000 | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[243] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8001710P0101 | SPECIAL BOLT | 6 | 2 | 4 | 6100KDP01 | PO-SEP-8403-[15] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8001710P0101 | SPECIAL BOLT | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[244] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8001975P0101 | WASHER 40X21X10 (LOCAL PUR) | 12 | 6 | 6 | 6100KDP01 | PO-SEP-8378-[363] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8001975P0101 | WASHER 40X21X10 (LOCAL PUR) | 6 | 6 | 0 | 6100KDP01 | PO-SEP-6812-[29] | PO | 2025-12-31 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8001976P0101 | WASHER 40X21X2 | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8378-[361] | PO | 2025-11-17 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8002371P0101 | BOLT GUIDE | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[437] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8002866R0102P | PADLOCK ES - NORMAL | 24 | 19 | 5 | 6100KDP01 | PO-SEP-8396-[37] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8002866R0102P | PADLOCK ES - NORMAL | 5 | 5 | 0 | free_stock | PR-SEP-0024114-[246] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8002875P0101 | WINDOW PANE 350X220X16,8 (KONEX) | 8 | 8 | 0 | 6100K023 | PO-SEP-8385-[46] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003360R0101P | LEVER MECHANISM LEFT, 2xR250/55(W800) | 20 | 20 | 0 | 6100K023 | PO-SEP-8385-[74] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003360R0102P | LEVER MECHANISM RIGHT,2xR250/55 (W800) | 20 | 20 | 0 | 6100K023 | PO-SEP-8385-[75] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003624R0102 | MONOBLOCCO-SPOUT 1250A,ZS1 | 126 | 126 | 0 | 6100KDP01 | PO-SEP-8381-[10] | PO | 2025-11-30 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Europroxy FZCO | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003638P0103P | INTER LOCKING AGLE LEFT | 25 | 21 | 4 | 6100KDP01 | PO-SEP-8396-[33] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003638P0103P | INTER LOCKING AGLE LEFT | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[248] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003638P0104P | INTERLOCKING ANGLE RIGHT | 25 | 20 | 5 | 6100KDP01 | PO-SEP-8396-[42] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003638P0104P | INTERLOCKING ANGLE RIGHT | 5 | 5 | 0 | free_stock | PR-SEP-0024114-[249] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003651P0101P | INSULATING CAP | 163 | 163 | 0 | 6100K023 | PO-SEP-8385-[76] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003671P0116 | SPCEIAL SCREW M12X34/45 | 80 | 68 | 12 | 6100KDP01 | PO-SEP-8523-[9] | PO | 2025-10-23 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003671P0116 | SPCEIAL SCREW M12X34/45 | 12 | 12 | 0 | free_stock | PR-SEP-0024114-[369] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003671P0120 | SPECIAL SCREW M12X30/101 | 86 | 68 | 18 | 6100K023 | PO-SEP-8523-[4] | PO | 2025-10-23 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003671P0120 | SPECIAL SCREW M12X30/101 | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8704-[3] | PO | 2025-11-12 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003672P0101 | COVER-COPERTURA 12KV ZS1 1250A | 67 | 67 | 0 | 6100K023 | PO-SEP-8385-[83] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003861P0101 | BEARING SHAFT (ZINC CHRM) | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[432] | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8003900P0102 | COVER FOR SPOUT | 18 | 18 | 0 | free_stock | PR-SEP-0024114-[251] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 25 | 14 | 11 | free_stock | PR-SEP-0024114-[253] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004387P0101P | BOLT EARTHING M12 ZINC CHROME | 11 | 0 | 11 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004437P0103P | SHROUD (EARTHING CONTACT)GCE8004437P0103 | 40 | 40 | 0 | free_stock | PR-SEP-0024114-[372] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004471R0101P | ELECTRODE, ZS1 95kV BIL | 9 | 6 | 3 | free_stock | PR-SEP-0024114-[254] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004471R0101P | ELECTRODE, ZS1 95kV BIL | 3 | 0 | 3 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004626P0101 | SPACER 40 X 20 X 92 | 4 | 0 | 4 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004633P0101 | ANGLE LEFT ( POLY ) | 4 | 0 | 4 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004633P0102 | ANGLE RIGHT ( POLY ) | 4 | 0 | 4 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004633P0111 | ANGLE LEFT ( POLY ) | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004633P0112 | ANGLE RIGHT ( POLY ) | 1 | 0 | 1 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004944R0101 | SPOUT ZS1 (4000A) | 18 | 12 | 6 | free_stock | PR-SEP-0024114-[256] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004944R0101 | SPOUT ZS1 (4000A) | 6 | 0 | 6 | PR Required | - | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8004990P0101 | CARRIER FOR BUSBAR SHROUD | 15 | 0 | 15 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005031R0101 | BUSHING ZS1/ (3 IN 1) DEACE | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8381-[8] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Europroxy FZCO | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005041P0101P | CONTACT PIN 109mm,3150A(GCE8005041P0101) | 18 | 12 | 6 | free_stock | PR-SEP-0024114-[257] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005041P0101P | CONTACT PIN 109mm,3150A(GCE8005041P0101) | 6 | 0 | 6 | PR Required | - | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005042P0101 | CONNECTION PIECE 3150A ZS1 | 9 | 6 | 3 | free_stock | PR-SEP-0024114-[258] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005042P0101 | CONNECTION PIECE 3150A ZS1 | 3 | 0 | 3 | PR Required | - | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005049P0101 | SUPPORT (POLY ) T = SHAPE | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[259] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005112P0103P | OPERATING BOLT | 6 | 2 | 4 | free_stock | PR-SEP-0024114-[260] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005112P0103P | OPERATING BOLT | 4 | 0 | 4 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005117P0101 | CARRIER | 12 | 4 | 8 | free_stock | PR-SEP-0024114-[261] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005117P0101 | CARRIER | 8 | 0 | 8 | PR Required | - | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005136P0101 | SUPPORT (POLY) | 6 | 6 | 0 | free_stock | PR-SEP-0024114-[408] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005164P0101 | SCREENING | 54 | 36 | 18 | free_stock | PR-SEP-0024114-[262] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005164P0101 | SCREENING | 18 | 0 | 18 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005595R0102P | BUSBAR ZS D100, 12THICK,800/800, L=795 | 120 | 120 | 0 | 6100KDP01 | PO-SEP-8385-[249] | PO | 2025-10-12 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005595R0109P | Busbar D100,12mm Thick 800/1000,L=830 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8385-[250] | PO | 2025-10-12 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005595R0110P | Busbar D100,12mm Thick 800/1000,L=895 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8385-[251] | PO | 2025-10-12 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8005595R0111P | Busbar D100,12mm Thick 800/1000,L=960 | 8 | 8 | 0 | 6100KDP01 | PO-SEP-8385-[252] | PO | 2025-10-12 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8006031P0101 | COVER FOR BUSBAR JOINTS | 9 | 9 | 0 | free_stock | PR-SEP-0023556-[74] | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8006587P0101 | LOCK SCREW M6X25 ( ROUND FLAT HEAD ) | 184 | 120 | 64 | free_stock | PR-SEP-0024114-[264] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8006587P0101 | LOCK SCREW M6X25 ( ROUND FLAT HEAD ) | 64 | 0 | 64 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8007213P0101 | SHROUD ZS3.2, Middle | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8385-[255] | PO | 2025-10-12 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8007214P0101 | COVER FOR SHROUD ZS3.2, end side | 24 | 24 | 0 | 6100KDP01 | PO-SEP-8385-[259] | PO | 2025-10-12 | LAX |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 25 | 14 | 11 | free_stock | PR-SEP-0024114-[267] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010004P0101 | GUIDE RAIL LEFT 12kV | 11 | 0 | 11 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010004P0102 | GUIDE RAIL RIGHT 12kV | 25 | 12 | 13 | free_stock | PR-SEP-0024114-[268] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010004P0102 | GUIDE RAIL RIGHT 12kV | 13 | 0 | 13 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010022P0111R | SHUTTER UPPER W800 (GCE8010022P0111) | 22 | 10 | 12 | free_stock | PR-SEP-0024114-[373] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010022P0111R | SHUTTER UPPER W800 (GCE8010022P0111) | 12 | 0 | 12 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010022P0112Y | SHUTTER LOWER W800 (GCE8010022P0112) | 20 | 14 | 6 | free_stock | PR-SEP-0024114-[374] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010022P0112Y | SHUTTER LOWER W800 (GCE8010022P0112) | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010022P0113R | SHUTTER UPPER (DWG.GCE8010022P0113) | 3 | 2 | 1 | free_stock | PR-SEP-0024114-[269] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010022P0113R | SHUTTER UPPER (DWG.GCE8010022P0113) | 1 | 0 | 1 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010022P0114Y | SHUTTER LOWER (DWG.GCE8010022P0114) | 3 | 2 | 1 | free_stock | PR-SEP-0024114-[270] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010022P0114Y | SHUTTER LOWER (DWG.GCE8010022P0114) | 1 | 0 | 1 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | HALB | GCE8010023P0101 | PIN (ZINC COATED) | 92 | 76 | 16 | 6100KDP01 | PO-SEP-8523-[14] | PO | 2025-10-23 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Laser Company for Metal Industries Ltd | 6100K023 – PR for Supply of
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | HALB | GCE8010023P0101 | PIN (ZINC COATED) | 16 | 16 | 0 | free_stock | PR-SEP-0024114-[271] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 45 | 30 | 15 | free_stock | PR-SEP-0024114-[272] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 15 | 3 | 12 | free_stock | PR-SEP-0024070-[20] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010028R0102 | PRESSURE RELIEF FLAP(W800) | 12 | 0 | 12 | PR Required | - | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010028R0103 | PRESSURE RELIEF FLAP W1000 | 5 | 4 | 1 | free_stock | PR-SEP-0024114-[273] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010028R0103 | PRESSURE RELIEF FLAP W1000 | 1 | 0 | 1 | PR Required | - | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010028R0105 | PRESSURE RELIEF FLAP, REAR | 3 | 2 | 1 | free_stock | PR-SEP-0024114-[274] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010028R0105 | PRESSURE RELIEF FLAP, REAR | 1 | 0 | 1 | PR Required | - | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010028R0106 | PRESSURE RELIEF FLAP W1000 | 8 | 0 | 8 | PR Required | - | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010096P0101P | PIN 12DIA(ZINC COAT)DWG:GCE8010096P0101 | 4 | 0 | 4 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010104P0103P | BUSHING D60/49X25 | 18 | 12 | 6 | free_stock | PR-SEP-0024114-[277] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8010104P0103P | BUSHING D60/49X25 | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8011549P0101 | CT-COOLER (HEAT SINK) | 9 | 9 | 0 | 6100KDP01 | PO-SEP-8483-[3] | PO | 2025-12-31 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | AB KOMPONENTY s.r.o. | 6100K023 – PR for Supply of
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8011552P0102 | FLAT SCREEN FOR CB.MIDDLE PLATE W800 | 20 | 19 | 1 | 6100KDP01 | PO-SEP-8396-[43] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8011552P0102 | FLAT SCREEN FOR CB.MIDDLE PLATE W800 | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[399] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8011642P0101 | SPACER | 152 | 152 | 0 | free_stock | PR-SEP-0024114-[280] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013263P0101 | SHROUD | 40 | 40 | 0 | 6100KDP01 | PO-SEP-8396-[44] | PO | 2025-11-30 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | XIAMEN STARLIGHTS | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013412R0101 | PRESSURE RELIEF FLAP FOR W1000 | 3 | 2 | 1 | free_stock | PR-SEP-0024114-[284] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013412R0101 | PRESSURE RELIEF FLAP FOR W1000 | 1 | 0 | 1 | PR Required | - | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013419R0101 | FRAME FOR FLAT SCREEN COMPLETE | 3 | 3 | 0 | free_stock | PR-SEP-0024114-[286] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013430P0101 | COOLING PLATE 1 ( small ) | 9 | 6 | 3 | free_stock | PR-SEP-0024114-[289] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013430P0101 | COOLING PLATE 1 ( small ) | 3 | 0 | 3 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013431P0101 | COOLING PLATE 2 ( Big ) | 9 | 6 | 3 | free_stock | PR-SEP-0024114-[290] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013431P0101 | COOLING PLATE 2 ( Big ) | 3 | 0 | 3 | PR Required | - | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013433P0101P | SHROUD (DWG NO. GCE8013433P0101) | 6 | 4 | 2 | free_stock | PR-SEP-0024114-[291] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013433P0101P | SHROUD (DWG NO. GCE8013433P0101) | 2 | 0 | 2 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013434P0101P | SHROUD (DWG NO. GCE8013434P0101) | 6 | 4 | 2 | free_stock | PR-SEP-0024114-[292] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013434P0101P | SHROUD (DWG NO. GCE8013434P0101) | 2 | 0 | 2 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013434P0102P | SHROUD (DWG NO. GCE8013434P0102) | 6 | 4 | 2 | free_stock | PR-SEP-0024114-[293] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013434P0102P | SHROUD (DWG NO. GCE8013434P0102) | 2 | 0 | 2 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013435P0101P | SPACER DISC (GCE8013435P0101) | 48 | 32 | 16 | free_stock | PR-SEP-0024114-[294] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013435P0101P | SPACER DISC (GCE8013435P0101) | 16 | 0 | 16 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013444R0101 | PRESSURE RELIEF FLAP(W1000) | 3 | 2 | 1 | free_stock | PR-SEP-0024114-[295] | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8013444R0101 | PRESSURE RELIEF FLAP(W1000) | 1 | 0 | 1 | PR Required | - | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8487370R0100 | EARTHING CONTACT | 2 | 1 | 1 | free_stock | PR-SEP-0024114-[296] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8487370R0100 | EARTHING CONTACT | 1 | 0 | 1 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 31 | 22 | 9 | free_stock | PR-SEP-0024114-[298] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8585496P0100 | LABEL RACK OUT / IN ( ZS3.2 / ZS1 ) | 9 | 0 | 9 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8684080P0101 | EARTHING STRIP | 2 | 1 | 1 | free_stock | PR-SEP-0024114-[299] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8684080P0101 | EARTHING STRIP | 1 | 0 | 1 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE8685778P0121P | CONTACT PIN 800/1200A SIL.COAT = 72L | 6 | 0 | 6 | PR Required | - | PR |  | B |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9401556P0100 | STOP WASHER | 48 | 28 | 20 | free_stock | PR-SEP-0024114-[301] | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9401556P0100 | STOP WASHER | 20 | 0 | 20 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9401766P0107 | LOCKING MAGNET DC125 V | 24 | 24 | 0 | free_stock | PR-SEP-0024114-[302] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9476775R0100 | IND.CONTACT/ VAN FLOW SWITCH | 4 | 4 | 0 | free_stock | PR-SEP-0024114-[304] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9477367P0102 | FORK D11x20 | 9 | 4 | 5 | free_stock | PR-SEP-0024114-[305] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9477367P0102 | FORK D11x20 | 5 | 0 | 5 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9477394R0101 | CHARGING LEVER COMPLETE | 2 | 0 | 2 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCE9478476P0101 | FIXING RING | 6 | 0 | 6 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCEC830444P0101P | K-SPACER D12/4.5X8,ZS1/ZS3.2Yellow Chrom | 48 | 30 | 18 | 6100K023 | PO-SEP-8385-[65] | PO | 2025-09-21 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | GCEC830444P0101P | K-SPACER D12/4.5X8,ZS1/ZS3.2Yellow Chrom | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8385-[157] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 50 | 42 | 8 | free_stock | PR-SEP-0024114-[309] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | MV-1VCR002091G0001 | HANDLE (MANIGLIA) | 8 | 0 | 8 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | MV-600-A/S3/I/802 | Metrosil for Triple Pole Relay for 1A CT | 2 | 0 | 2 | PR Required | - | PR |  | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 46 | 46 | 0 | 6100K021 | PO-SEP-8836-[3] | PO | 2025-11-13 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | MV-ZB9016765 | resistor(0-820ohms) | 6 | 6 | 0 | 6100K018 | PO-SEP-8376-[3] | PO | 2026-01-30 | LV |  | - | 2026-04-18 | 2026-04-04 | 0 | Grid Solution Middle-East Fze | MV
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | MV2000-1685-06 | YELLOW TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 6250 | 0 | 6250 | PR Required | - | PR |  | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | MV2000-1865-01 | YELLOW TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 1000 | 0 | 1000 | PR Required | - | PR |  | LV |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1000024P0001P | BUSHING (LOCAL PUR) | 24 | 14 | 10 | free_stock | PR-SEP-0024114-[310] | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1000024P0001P | BUSHING (LOCAL PUR) | 10 | 0 | 10 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1000025P0001P | BUSHING (LOCAL PUR) | 72 | 42 | 30 | free_stock | PR-SEP-0024114-[311] | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1000025P0001P | BUSHING (LOCAL PUR) | 30 | 0 | 30 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1000026P0001P | BUSHING (LOCAL PUR) | 171 | 0 | 171 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1000047P0001 | INTERLOCKING SCOTCH | 25 | 12 | 13 | free_stock | PR-SEP-0024114-[314] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1000047P0001 | INTERLOCKING SCOTCH | 13 | 0 | 13 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1000048P0001P | PIN (LOCAL PUR) | 24 | 24 | 0 | free_stock | PR-SEP-0024114-[315] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1001813R0802P | MECHANICAL OFF BUTTON FOR VD4 - HOR | 23 | 16 | 7 | 6100KDP01 | PO-SEP-8385-[136] | PO | 2025-10-05 | C&D |  | - | 2026-04-18 | 2026-04-04 | 0 | Easy China (Xiamen) Trading Co, Ltd. | To update Promised Delivery Date
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1001813R0802P | MECHANICAL OFF BUTTON FOR VD4 - HOR | 7 | 7 | 0 | free_stock | PR-SEP-0024114-[317] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1001915P0001P | PIN | 6 | 2 | 4 | free_stock | PR-SEP-0024114-[318] | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1001915P0001P | PIN | 4 | 0 | 4 | PR Required | - | PR |  | LAX |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1001916P0001P | INTERLOCK LEVER (LOCAL PUR) | 6 | 2 | 4 | free_stock | PR-SEP-0024114-[319] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1001916P0001P | INTERLOCK LEVER (LOCAL PUR) | 4 | 0 | 4 | PR Required | - | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SCB1001982P0001 | ROLLER | 2 | 2 | 0 | free_stock | PR-SEP-0024114-[320] | PR |  | C&D |  | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SNA234000R0200 | Marker, RC810, 1 ¦ 10/1SNA234041R2600 ¦ ENTRELEC | 250 | 190 | 60 | 6100KDP01 | PO-SEP-8386-[16] | PO | 2025-11-10 | LV | Automated: Replaced 1SNA234000R0200 by SEP20333. | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SNA234000R0200 | Marker, RC810, 1 ¦ 10/1SNA234041R2600 ¦ ENTRELEC | 60 | 60 | 0 | 6100K025 | PO-SEP-8833-[37] | PO | 2025-11-13 | LV | Automated: Replaced 1SNA234000R0200 by SEP20333. | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block, TB, Disconnecting TB for CT, OTTA 6-T, Bolt W/O Spring, 0790462 ¦ OTTA 6-T P/P ¦ PHOENIX | 2022 | 2022 | 0 | 6100KDP01 | PO-SEP-8572-[1] | PO | 2025-12-15 | LV | Automated: Replaced 1YAB5355AAB0001 by SEP10052. | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1YAB5355CAB0000 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 250 | 250 | 0 | 6100K025 | PO-SEP-8792-[3] | PO | 2025-12-20 | LV | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | MARWI60236 | Marker, Numbering, Blank, UCT-TM 10 ¦ 0829142 ¦ PHOENIX | 300 | 300 | 0 | 6100K021 | PO-SEP-8792-[16] | PO | 2025-12-20 | LV | Automated: Replaced 1YAB5355HAB0000 by MARWI60236. Automated: Replaced 1YAB5355HAB0000 by MARWI60236. | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 1SNA206394R0200 | Screw, EV6I_Screw+PstWasherIP20_M6/8.RS_M4/6.RS Type: EV6I Order no: 1SNA 206 394 R0200 Color: Grey ¦ 1SNA206394R0200 ¦ ABB | 200 | 200 | 0 | 6100KDP01 | PO-SEP-8386-[29] | PO | 2025-11-10 | LV | Automated: Replaced 1YAB5355HEA0000 by 1SNA206394R0200. Automated: Replaced 1YAB5355HEA0000 by 1SNA206394R0200. | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | 25541 | HEX.RIVET NUT M10X24 ( 25541 ) | 1003 | 1003 | 0 | 6100KDP01 | PO-SEP-8645-[2] | PO | 2025-10-30 | C&D | Automated: Replaced 25541 by GCE0369214P0100. | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SEP10163 | 1.5 Red Wire Gauge Tube 1.5mm² | 250 | 0 | 250 | PR Required | - | PR |  | LV | Automated: Replaced AE2000-1865-14 by SEP10163. Automated: Replaced AE2000-1865-14 by SEP10163. | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2000-2150-01 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 38 | 37 | 1 | 6100KDP01 | PO-SEP-8388-[17] | PO | 2025-10-30 | C&D | Automated: Replaced AE2000-2150-01 by 1YAZ21500101. | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | AE2000-2150-01 | SILICON SEALANT GE1200 CLEAR MADE IN USA | 1 | 1 | 0 | free_stock | PR-SEP-0024114-[90] | PR |  | C&D | Automated: Replaced AE2000-2150-01 by 1YAZ21500101. | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2121 2519-630 | BOLT SOCKET CAP HEAD M6X50 | 9 | 9 | 0 | 6100KDP01 | PO-SEP-8378-[345] | PO | 2025-11-17 | C&D | Automated: Replaced DMS 2121 2519-630 by DMS 2121 2519-430. | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | DMS 2126 2011-113 | Nut, Hexagonal Head, M4, Stainless Steel | 68 | 68 | 0 | 6100KDP01 | PO-SEP-8378-[354] | PO | 2025-11-17 | C&D | Automated: Replaced DMS 2126 2011-113 by DF240510018. Automated: Replaced DF240510018 by SEP10896. | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SEP12186 | Lugs, Terminal Ring, 70 Sq.mm, Copper Tube Crimping ¦ China star | 48 | 48 | 0 | free_stock | PR-SEP-0024114-[150] | PR |  | C&D | Automated: Replaced DMS 2641 0087-19 by SEP12186. Automated: Replaced DMS 2641 0087-19 by SEP12186. | - | 2026-04-18 | 2026-04-04 | 0
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SEP12028 | Lugs, Terminal Female, 1.5 Sq.mm ¦ CEM-RF-F608P ¦ Cembre | 50 | 50 | 0 | 6100KDP01 | PO-SEP-8502-[17] | PO | 2025-12-31 | C&D | Automated: Replaced DMS 2658 665-6 by SEP12028. Automated: Replaced DMS 2658 665-6 by SEP12028. | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SEP12048 | Lugs, Terminal End Sleeve, 1 x 1.5 Sq.mm, Black Insulated ¦ CEM-PKE1508 ¦ Cembre | 75 | 75 | 0 | 6100K021 | PO-SEP-8894-[36] | PO | 2025-10-27 | LV | Automated: Replaced PKE 1508 by SEP12048. Automated: Replaced PKE 1508 by SEP12048. | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SEP12052 | Lugs, Terminal End Sleeve, 2 x 1.5 Sq.mm, Black Insulated ¦ CEM-PKT1508 ¦ Cembre | 275 | 275 | 0 | 6100K021 | PO-SEP-8894-[37] | PO | 2025-10-27 | LV | Automated: Replaced PKT 1508 by SEP12052. Automated: Replaced PKT 1508 by SEP12052. | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K018 | Batha : SWITCHGEAR - BATHA | SWGR | ROH | SEP12105 | Lugs, Terminal End Sleeve, 2 x 2.5 Sq.mm, Blue Insulated ¦ CEM-PKT2512 / CT225013 ¦ Cembre | 500 | 500 | 0 | 6100K021 | PO-SEP-8894-[38] | PO | 2025-10-27 | LV | Automated: Replaced PKT 2512 by SEP12105. Automated: Replaced PKT 2512 by SEP12105. | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 129A539G01 | ‭FT SWITCH, (T T T T T T T T T T)/129A539G01/FT-1‬ | 66 | 66 | 0 | 6100K021 | PO-SEP-8747-[4] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 13.8-VT-ZS1-3WDG-25VA | Voltage Transformer (RITZ) | 18 | 18 | 0 | 6100K021 | PO-SEP-8760-[11] | PO | 2025-10-27 | VT |  | - | 2026-04-18 | 2026-04-04 | 0 |  | 6100K021 AL Rayan SS 115/13.8kv SWGR CT Order
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1815230000 | 5Pole Plug 2.5mm-1815230000-Cont-loop | 50 | 50 | 0 | 6100K021 | PO-SEP-8750-[6] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1855030000 | 6Pole Plug 4mm-1855030000-AC looping | 51 | 51 | 0 | 6100K021 | PO-SEP-8750-[7] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1SFA611400R1001 | PILOT LIGHT#ML1-100R | 48 | 48 | 0 | 6100K021 | PO-SEP-8753-[36] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1SFA611400R1002 | PILOT LIGHT#ML1-100G | 48 | 48 | 0 | 6100K021 | PO-SEP-8753-[37] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1SFA611400R1003 | PILOT LIGHT#ML1-100Y | 52 | 52 | 0 | 6100K021 | PO-SEP-8753-[38] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1SFA611400R1005 | PILOT LIGHT#ML1-100W | 114 | 114 | 0 | 6100K021 | PO-SEP-8753-[39] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1SFA611605R1100 | HOLDER#MCBH-00 | 262 | 262 | 0 | 6100K021 | PO-SEP-8753-[40] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1SFA611621R1051 | LAMP BLOCK#MLBL-05R | 48 | 48 | 0 | 6100K021 | PO-SEP-8753-[41] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1SFA611621R1052 | LAMP BLOCK#MLBL-05G | 48 | 48 | 0 | 6100K021 | PO-SEP-8753-[42] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1SFA611621R1053 | LAMP BLOCK#MLBL-05Y | 52 | 52 | 0 | 6100K021 | PO-SEP-8753-[43] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1SFA611621R1055 | LAMP BLOCK#MLBL-05W | 108 | 108 | 0 | 6100K021 | PO-SEP-8753-[44] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 256 | 256 | 0 | 6100K021 | PO-SEP-8753-[45] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 256 | 256 | 0 | 6100K021 | PO-SEP-8753-[46] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1SNK900654R0000 | SC-JB8-4 Short circuit bridges - Yellow | 153 | 153 | 0 | 6100K021 | PO-SEP-8833-[40] | PO | 2025-11-13 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB000002-FDV | MIMIC DIAGRAM, INCOMER-2W,VT | 3 | 3 | 0 | 6100K021 | PO-SEP-8724-[9] | PO | 2025-11-17 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB000003-FDX | MIMIC , OUTGOING WITH EARTHING | 43 | 43 | 0 | 6100K021 | PO-SEP-8724-[8] | PO | 2025-11-16 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB000004-BTE | MIMIC BUS SEC WITH EARTHG ON RIGHT SIDE | 2 | 2 | 0 | 6100K021 | PO-SEP-8724-[19] | PO | 2025-11-16 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB000007-BME | MIMIC, BUS MET. & EARTHING-2W,VT | 1 | 1 | 0 | 6100K021 | PO-SEP-8724-[12] | PO | 2025-11-16 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB000009-BRM | MIMIC , BUS RISER & MET.-2W,VT | 2 | 2 | 0 | 6100K021 | PO-SEP-8724-[15] | PO | 2025-11-16 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5112XFS00000 | VT 3Nos PRIMARY FUSE 17.5kV, 3A, SIBA.VT PRIMARY FUSE FOR 17.5kV UG ZS1 Fuse length : 192 mm Fuse dia : 53 mm Rated Voltage: 17.5kV Rated Current: 3A Rated breaking current : 31.5 kA Frequency: 60 Hz Fuse make : SIBA Type: 30 179 11.3 | 18 | 18 | 0 | 6100K021 | PO-SEP-8827-[3] | PO | 2026-01-25 | VT fuse |  | - | 2026-04-18 | 2026-04-04 | 0 | SABANA TRADERS LLC
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 34 | 24 | 10 | 6100K021 | PO-SEP-8770-[1] | PO | 2025-10-27 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 10 | 4 | 6 | 6100K019 | PO-SEP-7386-[1] | PO | 2025-11-18 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | PP-12 / CB
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 6 | 1 | 5 | 6100KDP01 | PO-SEP-8921-[1] | PO | 2025-12-31 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | 6100KDP01 ordered to cover the changing for the BUS TI Panel VD4/PW, 170625, p210, 125VDC, 1VCD400222 ¦ 1YAB52321VW6CN00 ¦ ABB
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8506-[1] | PO | 2026-01-20 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | CB / AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB52322VW60N00 | VD4/PW 171225-p210-125VDC-ZS1-1250A @ 60Hz, in UG ZS1- with upper CTs as per NG Stanadrad | 6 | 6 | 0 | 6100K021 | PO-SEP-8770-[2] | PO | 2025-10-27 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB52333VW6CN00 | VD4/P 171240-p210-125VDC (1VCD400222) | 3 | 3 | 0 | 6100K021 | PO-SEP-8770-[3] | PO | 2025-10-27 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB52371V06CN00 | VD4/P 173225-p275-125VDC (1VCD400222) | 5 | 5 | 0 | 6100K021 | PO-SEP-8770-[4] | PO | 2025-10-27 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 48 | 48 | 0 | 6100K021 | PO-SEP-8775-[2] | PO | 2025-10-27 | A |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5320XDB1XN02 | DIGITAL VOLTMETER, Cl 1.0, 3PH4W, 5-500V, 60Hz, 150% Un CONT, 3 LINE DISPLAY LED, MODBUS ¦ SECURE DPM 96 V300 | 3 | 3 | 0 | 6100K021 | PO-SEP-8837-[4] | PO | 2025-12-30 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Washa Al Wisam Factory Company.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5320XHI1XN00 | POWER QUALITY ANALYZER, ISKRA iMC784 | 3 | 3 | 0 | 6100K021 | PO-SEP-8547-[4] | PO | 2025-10-27 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Enerziff Solutions FZCO | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 51 | 51 | 0 | 6100K021 | PO-SEP-8829-[4] | PO | 2025-10-27 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Abdullah AbuNayyan Trading Corp
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5331XXCX0000 | CAPACITOR PARKING KEY_COMELECTRIC ITALY.ELECTROMECHANICAL TRAPPED KEY INTERLOCK SWITCH Model: SR 102 R20 2/4 Key Trapped Solenoid Release Switch with IP20 Contacts. Key Free Position: 0 Degree, 4 Contacts. Key Trapped Position: 90 Degree, 4 Contacts. Label: Capacitor Bank Gate Interlock. Make: Comeletric, Italy. Door Interlock lock : KD1 SAP PART NO: 1YAB5331XXCX0000 ------------------ CAPACITOR PARKING KEY_COMELECTRIC ITALY | 3 | 0 | 3 | PR Required | - | PR |  | Customer to supply |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5331XXCX0100 | BREAKER CONTROL SWITCH (Comelectric)Breaker Control Switch3-Pole, 3-Position & spring returnDim: 51 X 51 mm Padlockable handle:Colour : Red YellowFront plate:Text Engrave : OPEN- NORMAL-CLOSELettering plate:Text Engrave : BREAKER CONTROL SWITCH Ordering Code: R601 SAM303 011 01-L078+48-30309T133 | 48 | 25 | 23 | 6100K021 | PO-SEP-8785-[7] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5331XXCX0100 | BREAKER CONTROL SWITCH (Comelectric)Breaker Control Switch3-Pole, 3-Position & spring returnDim: 51 X 51 mm Padlockable handle:Colour : Red YellowFront plate:Text Engrave : OPEN- NORMAL-CLOSELettering plate:Text Engrave : BREAKER CONTROL SWITCH Ordering Code: R601 SAM303 011 01-L078+48-30309T133 | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8398-[10] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5331XXCX0210 | CBMODE6P,4Pos.Off-Emer-Local-Rem-Padlock(COMELECTRIC), Breaker Mode Selector Switch 6-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH COMELETRIC Part No. R601 SA412 067 27-L071+48-40513T134 SAP Part no: 1YAB5331XXCX0210 | 8 | 5 | 3 | 6100K021 | PO-SEP-8785-[8] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5331XXCX0210 | CBMODE6P,4Pos.Off-Emer-Local-Rem-Padlock(COMELECTRIC), Breaker Mode Selector Switch 6-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH COMELETRIC Part No. R601 SA412 067 27-L071+48-40513T134 SAP Part no: 1YAB5331XXCX0210 | 3 | 3 | 0 | 6100K025 | PO-SEP-8785-[2] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5331XXCX0220 | OFF-EMER-LOCAL-REMOTE 4P4P, PADLCK (COMELECTRIC), Breaker Mode Selector Switch 4-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH Ordering Code: R601 SA408 067 27-L071+48-40513T134 20A, 4 pos Stayput 4 contacts in each Pos, TYPE 1: Engraving: OFF-EMERGENCY-LOCAL-REMOTE TOP PLATE: BREAKER MODE PADLOCK SAP PART NO: 1YAB5331XXCX0220 | 40 | 40 | 0 | 6100K021 | PO-SEP-8785-[9] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5331XXCX0300 | SPACE HEATER SEL. SWITCH ( COMELECTRIC )R601 SA302 112-W051+48-31090T124 20A, 3Positions without internal links 2pole,3position Engraving (OFF/Auto/Manual) OFF-zero contacts AUTO-2 contacts MANUAL-2contacts TOP PLATE (SPACE HEATER) Single hole mounting FT6 | 51 | 28 | 23 | 6100K021 | PO-SEP-8785-[10] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5331XXCX0300 | SPACE HEATER SEL. SWITCH ( COMELECTRIC )R601 SA302 112-W051+48-31090T124 20A, 3Positions without internal links 2pole,3position Engraving (OFF/Auto/Manual) OFF-zero contacts AUTO-2 contacts MANUAL-2contacts TOP PLATE (SPACE HEATER) Single hole mounting FT6 | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8398-[13] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC )R601 SAM201 071-W051+48-20547T123 20A SPRING RETAIN WITHOUT INTERNAL LINKS 2 POSITION,1POLE Engraving (OFF-TEST) TOP PLATE Engraving (LAMP TEST) | 51 | 26 | 25 | 6100K021 | PO-SEP-8785-[11] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC )R601 SAM201 071-W051+48-20547T123 20A SPRING RETAIN WITHOUT INTERNAL LINKS 2 POSITION,1POLE Engraving (OFF-TEST) TOP PLATE Engraving (LAMP TEST) | 25 | 25 | 0 | 6100K025 | PO-SEP-8785-[5] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5331XXKX0700 | Auto Re-close IN-OUT Selector Switch(COMELECTRIC),"Auto Re-close IN-OUT Selector Switch 4-Pole, 2-Positions Dim: 51 X 51 mm Padlockable handle: Colour : Black Front plate: Text Engrave : IN-OUT Lettering plate Text Engrave : A/R IN-OUT SWITCH" CA10-A723-SA0030-E 1YAB5331XXKX0700 | 38 | 22 | 16 | 6100K021 | PO-SEP-8785-[12] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5331XXKX0700 | Auto Re-close IN-OUT Selector Switch(COMELECTRIC),"Auto Re-close IN-OUT Selector Switch 4-Pole, 2-Positions Dim: 51 X 51 mm Padlockable handle: Colour : Black Front plate: Text Engrave : IN-OUT Lettering plate Text Engrave : A/R IN-OUT SWITCH" CA10-A723-SA0030-E 1YAB5331XXKX0700 | 16 | 16 | 0 | 6100KDP01 | PO-SEP-8398-[9] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5332XXAXB000 | PB Black 1NO+1NC-22 dia-1SFA611100R4076 | 108 | 100 | 8 | 6100K021 | PO-SEP-8753-[78] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5332XXAXB000 | PB Black 1NO+1NC-22 dia-1SFA611100R4076 | 8 | 8 | 0 | 6100K025 | PO-SEP-8753-[76] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5334XXAX1000 | FT-1 SW-Type 129A514G01 | 8 | 8 | 0 | 6100K021 | PO-SEP-8747-[12] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5336XXAA2E00 | MCB 3A AC -2P,2CDS252001R0317 | 5 | 5 | 0 | 6100K021 | PO-SEP-8753-[29] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5336XXAA2G00 | MCB S 202-K6 6A AC -2P - 2CDS252001R0377 | 103 | 103 | 0 | 6100K021 | PO-SEP-8753-[30] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5336XXAA2L00 | MCB 16A AC -2P - 2CDS252001R0467 | 5 | 5 | 0 | 6100K021 | PO-SEP-8753-[31] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5336XXAB2G00 | MCB 6A DC 2P S202M-K6UC -2CDS272061R0377 | 300 | 300 | 0 | 6100K021 | PO-SEP-8753-[32] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5336XXACG000 | Aux contact 2NC, S2C-HO2L-for MCB Order # 2CDS200936R0003 | 245 | 245 | 0 | 6100K021 | PO-SEP-8753-[33] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5336XXACH000 | Aux contact 1NO+1NC MCB -2CDS200936R0001 | 340 | 340 | 0 | 6100K021 | PO-SEP-8753-[34] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5336XXACJ000 | S2C-H01 - 1NC- Bottom Auxiliary Contact 2CDS200970R0031 | 75 | 75 | 0 | 6100K021 | PO-SEP-8753-[35] | PO | 2025-12-31 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XAJXXN00 | RF-4R_125Vdc_4 C/O_LED | 85 | 85 | 0 | 6100K021 | PO-SEP-8839-[3] | PO | 2026-02-28 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Innovative Systems Co. Ltd | Arteche MV
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XAJXXN01 | BJ-8RP_Bistable_125Vdc_8 C/O | 40 | 40 | 0 | 6100K021 | PO-SEP-8839-[4] | PO | 2026-02-28 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Innovative Systems Co. Ltd | Arteche MV
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XBLXXN00 | MVAJ101 RA 0802_ 125VDC (8 NO + 2 NC) | 2 | 2 | 0 | 6100K021 | PO-SEP-8841-[5] | PO | 2026-02-28 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Grid Solution Middle-East Fze | MV
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XCHXXN01 | LOCKOUT RELAY (86) TYPE 7835FD, HIGH SPEED TRIP 8ms, TRIP COIL (70-280VDC),10NO+10NC ELECTRICAL RESET COIL (100-150VDC) | 48 | 0 | 48 | PR Required | - | PR |  | LVA |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XCLXXN00 | MVAJ205 ,125VDC ) CAT No. MVAJ205TB0808A | 2 | 2 | 0 | 6100K021 | PO-SEP-8841-[6] | PO | 2026-02-28 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Grid Solution Middle-East Fze | MV
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XDAXXN00 | RXMVB 4, RK 251 401-AP | 8 | 5 | 3 | 6100K021 | PO-SEP-8751-[17] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XDAXXN00 | RXMVB 4, RK 251 401-AP | 3 | 3 | 0 | 6100K025 | PO-SEP-8751-[7] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XDAXXN01 | RXMVB2, RK 251 204-AP | 13 | 13 | 0 | 6100K021 | PO-SEP-8751-[18] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XEAXXN00 | RXMB1 6NO_110-125VDC-1MRK 000 863-AN | 16 | 10 | 6 | 6100K021 | PO-SEP-8751-[19] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XEAXXN00 | RXMB1 6NO_110-125VDC-1MRK 000 863-AN | 6 | 6 | 0 | 6100K025 | PO-SEP-8751-[9] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XFAXXN00 | RXKL1, TYPE: 1MRK 000 066-AB | 5 | 5 | 0 | 6100K021 | PO-SEP-8751-[20] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XIAXXN00 | RXSF1_DC110-125V-MV RK 271 019-AN No volt flag relay | 150 | 150 | 0 | 6100K021 | PO-SEP-8751-[21] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XJAXXN00 | THREE PHASE FUSE SUPERVISION RELAY Type : RXBA4 (ABB) ORDER NO. : RK 428 004-AA CONTACTS : 2 CHANGE OVER SELF RESET | 6 | 5 | 1 | 6100K021 | PO-SEP-8751-[2] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XJAXXN00 | THREE PHASE FUSE SUPERVISION RELAY Type : RXBA4 (ABB) ORDER NO. : RK 428 004-AA CONTACTS : 2 CHANGE OVER SELF RESET | 1 | 1 | 0 | 6100K025 | PO-SEP-8751-[4] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XNHXXN00 | TRIP LOR/ER 7840FD 20NO+20NC, 125VDC HIGH SPEED TRIP 8ms, TRIP COIL (70-280VDC), ELECTRICAL RESET COIL (100-150VDC) | 9 | 0 | 9 | PR Required | - | PR |  | LVA |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 6550 | 6550 | 0 | 6100K021 | PO-SEP-8792-[12] | PO | 2025-12-20 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 2295 | 2295 | 0 | 6100K021 | PO-SEP-8833-[1] | PO | 2025-11-13 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355AEA0001 | M 6/8.RS (SpringLoaded) 1SNA115685R1200 | 2212 | 2212 | 0 | 6100K021 | PO-SEP-8833-[6] | PO | 2025-11-13 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 16264 | 16264 | 0 | 6100K021 | PO-SEP-8833-[9] | PO | 2025-11-13 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355AFA0001 | M4/6.SNTS Spring Loaded 1SNA115229R2000 | 2295 | 2295 | 0 | 6100K021 | PO-SEP-8833-[12] | PO | 2025-11-13 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 1617 | 1617 | 0 | 6100K021 | PO-SEP-8833-[13] | PO | 2025-11-13 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355AMC0001 | Base Terminal Plug AC-DC-4mm 1848350000.Feed-through terminal block,ZT 4/4AN/2 . | 1530 | 800 | 730 | 6100K021 | PO-SEP-8750-[3] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355AMC0001 | Base Terminal Plug AC-DC-4mm 1848350000.Feed-through terminal block,ZT 4/4AN/2 . | 730 | 730 | 0 | 6100KDP01 | PO-SEP-8518-[1] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 612 | 612 | 0 | 6100K021 | PO-SEP-8750-[4] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 742 | 742 | 0 | 6100K021 | PO-SEP-8750-[5] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355CBA0000 | FEM8T6 End Sections Grey 1SNA215266R0100 | 765 | 765 | 0 | 6100K021 | PO-SEP-8833-[18] | PO | 2025-11-13 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355CEA0000 | FEMR8 End Sections Grey 1SNA116987R0200 | 1020 | 1020 | 0 | 6100K021 | PO-SEP-8833-[21] | PO | 2025-11-13 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355CFA0000 | FEM6 End Sections Grey - 1SNA118368R1600 | 510 | 510 | 0 | 6100K021 | PO-SEP-8833-[23] | PO | 2025-11-13 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355CMC0000 | Terminal End Plate 1848360000-Wiedmuller | 204 | 204 | 0 | 6100K021 | PO-SEP-8750-[37] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355CPC0000 | Terminal End Plate 1816110000-Wiedmuller | 204 | 204 | 0 | 6100K021 | PO-SEP-8750-[38] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355CTC0000 | Terminal End Plate 1816070000-Wiedmuller | 106 | 106 | 0 | 6100K021 | PO-SEP-8750-[39] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 2550 | 2250 | 300 | 6100K021 | PO-SEP-8792-[14] | PO | 2025-12-20 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 300 | 300 | 0 | 6100K025 | PO-SEP-8792-[4] | PO | 2025-12-20 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355DFA0000 | RC610-VerticalMarking 1SNA233060R0400 | 459 | 459 | 0 | 6100K021 | PO-SEP-8833-[27] | PO | 2025-11-13 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355DXC0000 | 460660001 DEK 5 FSZ 1-10 Z-Terminal 1-10 | 20600 | 10900 | 9700 | 6100K021 | PO-SEP-8750-[1] | PO | 2025-12-31 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355DXC0000 | 460660001 DEK 5 FSZ 1-10 Z-Terminal 1-10 | 9700 | 9700 | 0 | 6100KDP01 | PO-SEP-8518-[7] | PO | 2025-12-31 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355EEA0000 | JUMPER BAR "BJS8" 20 Poles | 102 | 102 | 0 | 6100K021 | PO-SEP-8833-[30] | PO | 2025-11-13 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355EFA0000 | PC61-CombTypeJumprBar10 1SNA163311R2200 | 204 | 204 | 0 | 6100K021 | PO-SEP-8833-[31] | PO | 2025-11-13 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 408 | 408 | 0 | 6100K021 | PO-SEP-8750-[40] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355HAB0002 | Zack Strip-Vertical Labeled(21-30) | 408 | 408 | 0 | 6100K021 | PO-SEP-8750-[2] | PO | 2025-12-31 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 306 | 306 | 0 | 6100K021 | PO-SEP-8750-[41] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355JPC0000 | 6Pole Plug 2.5mm-1815240000-Cont-loop | 204 | 204 | 0 | 6100K021 | PO-SEP-8750-[42] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355JTC0000 | 10Pole Plug 2.5mm-1815280000-Cont-loop | 212 | 212 | 0 | 6100K021 | PO-SEP-8750-[43] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 612 | 612 | 0 | 6100K021 | PO-SEP-8750-[44] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355KPC0000 | Locking ele. 1816130000 for ZT2.5/4AN/2 | 310 | 310 | 0 | 6100K021 | PO-SEP-8750-[45] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355LMC0000 | Coding element 1856860000 - ZT4/4AN/2 | 408 | 408 | 0 | 6100K021 | PO-SEP-8750-[46] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355LPC0000 | Coding element 1816150000 | 416 | 416 | 0 | 6100K021 | PO-SEP-8750-[47] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355MPC0000 | Strain Relief Wied mulpart # 1816140000 | 310 | 310 | 0 | 6100K021 | PO-SEP-8750-[8] | PO | 2025-12-31 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 612 | 600 | 12 | 6100K021 | PO-SEP-8792-[17] | PO | 2025-12-20 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8572-[8] | PO | 2025-12-15 | Plug socket |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB60050819P0103 | Braided HARNESS TUBE (D40) | 765 | 765 | 0 | 6100K021 | PO-SEP-8834-[4] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Dalian Jinda Industry Co.,Ltd
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 45 | 45 | 0 | 6100K021 | PO-SEP-8834-[6] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Dalian Jinda Industry Co.,Ltd
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB60050819P0106 | Braided HARNESS TUBE (D30) | 1020 | 1020 | 0 | 6100K021 | PO-SEP-8834-[9] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Dalian Jinda Industry Co.,Ltd
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB60050819P0107 | Braided HARNESS TUBE (D20) | 510 | 510 | 0 | 6100K021 | PO-SEP-8834-[10] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Dalian Jinda Industry Co.,Ltd
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 2CDS254001R0337 | MCB S204-K 4 MC -4P 2CDS254001R0337 | 138 | 138 | 0 | 6100K021 | PO-SEP-8753-[1] | PO | 2025-12-30 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 2TRE123451P0001 | 3 PIN SOCKET SWITCH,13A,250V,BSRDP-I | 5 | 5 | 0 | 6100K021 | PO-SEP-8836-[6] | PO | 2025-11-13 | LVB |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 5022 643 | COVER PROFILE, AP3 | 81.6 | 81.6 | 0 | 6100K021 | PO-SEP-8792-[18] | PO | 2025-12-20 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 1275 | 1250 | 25 | 6100K021 | PO-SEP-8792-[19] | PO | 2025-12-20 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 25 | 25 | 0 | 6100KDP01 | PO-SEP-8572-[10] | PO | 2025-12-15 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 837A407G01 | ‭FT SWITCH, (C-C C-C C-C C-C P P)/837A407G01/FT-1‬ | 51 | 51 | 0 | 6100K021 | PO-SEP-8747-[2] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 9676A14G01 | ‭FT SWITCH, (P P P P T T T P P P)/9676A14G01/FT-1‬ | 58 | 58 | 0 | 6100K021 | PO-SEP-8747-[3] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 815 | 815 | 0 | 6100K021 | PO-SEP-8836-[11] | PO | 2025-11-13 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 765 | 765 | 0 | 6100K021 | PO-SEP-8836-[14] | PO | 2025-11-13 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 66.3 | 66.3 | 0 | 6100K021 | PO-SEP-8835-[1] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | EMKA Beschlagteile Middle East FZE
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 1020 | 1000 | 20 | 6100K021 | PO-SEP-8881-[5] | PO | 2025-12-21 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8378-[232] | PO | 2025-11-17 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 306 | 306 | 0 | 6100K021 | PO-SEP-8834-[16] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Dalian Jinda Industry Co.,Ltd
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 8 | 5 | 3 | 6100K021 | PO-SEP-8754-[1] | PO | 2025-12-15 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 3 | 3 | 0 | 6100K025 | PO-SEP-8754-[2] | PO | 2025-12-15 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 51 | 26 | 25 | 6100K021 | PO-SEP-8752-[1] | PO | 2025-12-15 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 25 | 25 | 0 | 6100K025 | PO-SEP-8752-[2] | PO | 2025-12-15 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE2632-2000-33 | Spring for Door Combiflex | 1.02 | 1.02 | 0 | 6100K021 | PO-SEP-8836-[18] | PO | 2025-11-13 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 51 | 26 | 25 | 6100K021 | PO-SEP-8831-[2] | PO | 2025-11-12 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | First Telecom Industries
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 25 | 25 | 0 | 6100K025 | PO-SEP-8831-[1] | PO | 2025-11-12 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | First Telecom Industries
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 3060 | 3050 | 10 | 6100K021 | PO-SEP-8792-[20] | PO | 2025-12-20 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 10 | 10 | 0 | 6100KDP01 | PO-SEP-8572-[11] | PO | 2025-12-15 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 51 | 26 | 25 | 6100K021 | PO-SEP-8724-[5] | PO | 2025-11-16 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 25 | 25 | 0 | 6100K025 | PO-SEP-8724-[3] | PO | 2025-11-16 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DM0000000058 | Relay, Auxiliary, 2 Coils, Self Reset Contacts, Hand Reset Flag, 110-125V, DC, 2NO, 1NC, Coil ¦ RXSF1 RK 271 007-AN | 8 | 8 | 0 | 6100K021 | PO-SEP-8751-[22] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DM0000000839 | COMBIFLEX TERMINAL BASE RX4 (4U 12C) | 14 | 14 | 0 | 6100K021 | PO-SEP-8751-[24] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DM0000000852 | COMBIFLEX TERMINAL BASE RX 2H -5619625-A | 243 | 243 | 0 | 6100K021 | PO-SEP-8751-[23] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DM0000003057 | Relay, Over Current Protection, DC, 110-250V, AC 100-230V, 19BI + 15BO, With IEC 61850-8-1, 2x Optical, Type 7SJ85 ¦ P1J198095 | 3 | 3 | 0 | 6100K021 | PO-SEP-8772-[2] | PO | 2026-02-28 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Siemens Ltd. | Relays, MV
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 2154 363-1 | WASHER, LOCK 10X5X0.5 | 45 | 45 | 0 | 6100K021 | PO-SEP-8668-[10] | PO | 2025-11-13 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | FABORY Czech s.r.o.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 20400 | 19200 | 1200 | 6100K021 | PO-SEP-8881-[6] | PO | 2025-12-21 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 1200 | 1200 | 0 | 6100K025 | PO-SEP-8884-[6] | PO | 2025-12-21 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 255 | 131 | 124 | 6100K021 | PO-SEP-8881-[7] | PO | 2025-12-21 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 124 | 124 | 0 | 6100K025 | PO-SEP-8884-[7] | PO | 2025-12-21 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 51 | 27 | 24 | 6100K021 | PO-SEP-8881-[8] | PO | 2025-12-21 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 24 | 24 | 0 | 6100K025 | PO-SEP-8884-[8] | PO | 2025-12-21 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 306 | 156 | 150 | 6100K021 | PO-SEP-8881-[9] | PO | 2025-12-21 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 150 | 150 | 0 | 6100K025 | PO-SEP-8884-[9] | PO | 2025-12-21 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 2448 | 2448 | 0 | 6100K021 | PO-SEP-8925-[2] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 408 | 210 | 198 | 6100K021 | PO-SEP-8881-[10] | PO | 2025-12-21 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 198 | 198 | 0 | 6100K025 | PO-SEP-8884-[10] | PO | 2025-12-21 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 924 0010 | Combiflex wire Socket 1.5mm 1MRK002136-B | 10200 | 10200 | 0 | 6100K021 | PO-SEP-8751-[25] | PO | 2025-12-31 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 924 0020 | Combiflex wire Socket 2.5mm 1MRK002136-E | 6120 | 3300 | 2820 | 6100K021 | PO-SEP-8751-[26] | PO | 2025-12-31 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | DMS 924 0020 | Combiflex wire Socket 2.5mm 1MRK002136-E | 2820 | 2820 | 0 | 6100KDP01 | PO-SEP-8366-[17] | PO | 2025-12-31 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 12 | 6 | 6 | 6100K021 | PO-SEP-8757-[2] | PO | 2025-12-15 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Shanghai Feili Xuncheng Electrical Technology Co.,Ltd | Snap action Switch
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 6 | 6 | 0 | 6100K025 | PO-SEP-8757-[1] | PO | 2025-12-15 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | Shanghai Feili Xuncheng Electrical Technology Co.,Ltd | Snap action Switch
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | GCE0438403P0100 | SPRG. PIN 2X10 DIN EN 28748 ST | 48 | 48 | 0 | 6100K021 | PO-SEP-8668-[9] | PO | 2025-11-13 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | FABORY Czech s.r.o.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 102 | 102 | 0 | 6100K021 | PO-SEP-8821-[1] | PO | 2025-12-31 | LVC |  | - | 2026-04-18 | 2026-04-04 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | GCE0990403P0100 | VENTILATOR QK08A-2EM.50.CH WITH CAPACITO | 5 | 2 | 3 | 6100K021 | PO-SEP-8748-[1] | PO | 2025-12-31 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | ZIEHL ABEGG Middle East FZE | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | GCE0990403P0100 | VENTILATOR QK08A-2EM.50.CH WITH CAPACITO | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8361-[3] | PO | 2025-12-31 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | ZIEHL ABEGG Middle East FZE | Fans / 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | GCE0990404P0100 | RADIAL FLOW FAN QK08A-2EM.35.CF | 7 | 3 | 4 | 6100K021 | PO-SEP-8748-[2] | PO | 2025-12-31 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | ZIEHL ABEGG Middle East FZE | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | GCE0990404P0100 | RADIAL FLOW FAN QK08A-2EM.35.CF | 4 | 4 | 0 | 6100K025 | PO-SEP-8748-[4] | PO | 2025-12-31 | B |  | - | 2026-04-18 | 2026-04-04 | 0 | ZIEHL ABEGG Middle East FZE | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MARWI60236 | Zack Strip-Vertical(1-10) - 1053027:0001 | 1224 | 636 | 588 | 6100K021 | PO-SEP-8792-[16] | PO | 2025-12-20 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MARWI60236 | Zack Strip-Vertical(1-10) - 1053027:0001 | 588 | 588 | 0 | 6100K025 | PO-SEP-8792-[6] | PO | 2025-12-20 | Terminals |  | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV-CR-U125DC3 | CR-U125DC3 - 1SVR405622R8200.CR-U125DC3 Pluggable interface relay 3c Ordering Code : 1SVR405622R8200 General: Pluggable interface relay ABB. Type : CR-U125DC3L Ordering Code: OUTPUTS: 3 C/O with LED RATED VOLTAGE: 125 VDC | 3 | 3 | 0 | 6100K021 | PO-SEP-8753-[25] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV-CR-U3S | Socket -FOR 3 C/O AND MODULE TIMER | 3 | 3 | 0 | 6100K021 | PO-SEP-8753-[26] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV-CR-UH | Holder interface relay 1SVR405669R0000 | 3 | 3 | 0 | 6100K021 | PO-SEP-8753-[27] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV-CR-UT | TIME MODULE 1SVR405667R0000 | 3 | 3 | 0 | 6100K021 | PO-SEP-8753-[28] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 96 | 50 | 46 | 6100K021 | PO-SEP-8836-[3] | PO | 2025-11-13 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 46 | 46 | 0 | 6100K025 | PO-SEP-8836-[2] | PO | 2025-11-13 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | Saeed Aziz Alsomali Trading Est
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV50001 | Incomer Upper CT, INC3600-13.8-UCT ¦ ¦ RITZ | 9 | 9 | 0 | 6100K021 | PO-SEP-8760-[1] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-18 | 2026-04-04 | 0 |  | 6100K021 AL Rayan SS 115/13.8kv SWGR CT Order
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV50002 | Incomer Lower CT, INC3600-13.8-LCT ¦ ¦ RITZ | 9 | 9 | 0 | 6100K021 | PO-SEP-8760-[2] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-18 | 2026-04-04 | 0 |  | 6100K021 AL Rayan SS 115/13.8kv SWGR CT Order
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV50003 | Capacitor O/G Feeder Upper CT, CAP1250-13.8-UCT ¦ ¦ RITZ | 9 | 9 | 0 | 6100K021 | PO-SEP-8760-[3] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-18 | 2026-04-04 | 0 |  | 6100K021 AL Rayan SS 115/13.8kv SWGR CT Order
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV50004 | Capacitor O/G Feeder Lower CT, CAP1250-13.8-LCT ¦ ¦ RITZ | 9 | 9 | 0 | 6100K021 | PO-SEP-8760-[4] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-18 | 2026-04-04 | 0 |  | 6100K021 AL Rayan SS 115/13.8kv SWGR CT Order
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV50005 | Station Auxiliary Upper CT, SST630-13.8-UCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K021 | PO-SEP-8760-[5] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-18 | 2026-04-04 | 0 |  | 6100K021 AL Rayan SS 115/13.8kv SWGR CT Order
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV50006 | Station Auxiliary Lower CT, SST630-13.8-LCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K021 | PO-SEP-8760-[6] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-18 | 2026-04-04 | 0 |  | 6100K021 AL Rayan SS 115/13.8kv SWGR CT Order
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV50007 | Outgoing Plain Upper CT, OG1250-13.8-UCT ¦ ¦ RITZ | 114 | 114 | 0 | 6100K021 | PO-SEP-8760-[7] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-18 | 2026-04-04 | 0 |  | 6100K021 AL Rayan SS 115/13.8kv SWGR CT Order
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV50008 | Outgoing plain Lower CT, OG1250-13.8-LCT ¦ ¦ RITZ | 114 | 114 | 0 | 6100K021 | PO-SEP-8760-[8] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-18 | 2026-04-04 | 0 |  | 6100K021 AL Rayan SS 115/13.8kv SWGR CT Order
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV50009 | BusTie Upper CT, BS3600-13.8-UCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K021 | PO-SEP-8760-[9] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-18 | 2026-04-04 | 0 |  | 6100K021 AL Rayan SS 115/13.8kv SWGR CT Order
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | MV50010 | Bus-Tie Lower CT, BS3600-13.8-LCT ¦ ¦ RITZ | 6 | 6 | 0 | 6100K021 | PO-SEP-8760-[10] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-04-18 | 2026-04-04 | 0 |  | 6100K021 AL Rayan SS 115/13.8kv SWGR CT Order
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10038 | Humidistat, 250V, AC, MFR 012 ¦ 01220.0-00 | 51 | 51 | 0 | 6100K021 | PO-SEP-8819-[2] | PO | 2025-12-31 | LVA |  | - | 2026-04-18 | 2026-04-04 | 0 | STEGO Elektrotechnik GmbH | Humidistat, 250V, AC, MFR 012
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10162 | WHITE TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 12750 | 8603 | 4147 | free_stock | PR-SEP-0023081-[171] | PR |  | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10162 | WHITE TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 4147 | 1500 | 2647 | free_stock | PR-SEP-0024130-[175] | PR |  | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10162 | WHITE TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 2647 | 0 | 2647 | PR Required | - | PR |  | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10163 | RED TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 510 | 0 | 510 | PR Required | - | PR |  | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 765 | 555 | 210 | free_stock | PR-SEP-0023081-[167] | PR |  | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 210 | 210 | 0 | free_stock | PR-SEP-0023387-[166] | PR |  | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10298 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 510 | 316.8 | 193.2 | free_stock | PR-SEP-0023081-[168] | PR |  | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10298 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 193.2 | 34.3 | 158.9 | free_stock | PR-SEP-0023387-[167] | PR |  | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10298 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 158.9 | 0 | 158.9 | PR Required | - | PR |  | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10349 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 510 | 370 | 140 | free_stock | PR-SEP-0023081-[169] | PR |  | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10349 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 140 | 116 | 24 | free_stock | PR-SEP-0023387-[169] | PR |  | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10349 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 24 | 0 | 24 | PR Required | - | PR |  | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP10650 | WHITE TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 2040 | 0 | 2040 | PR Required | - | PR |  | LVD |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11258 | Cable, Control, 1 Core,CU/PVC, 1.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 111.5974 | 86.5711 | 25.0263 | 6100K025 | PO-SEP-8915-[1] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11258 | Cable, Control, 1 Core,CU/PVC, 1.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 25.0263 | 25.0263 | 0 | 6100KDP01 | PO-SEP-8622-[19] | PO | 2026-01-30 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11259 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 36.2691 | 1.2198 | 35.0493 | 6100K021 | PO-SEP-8915-[17] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11259 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 35.0493 | 30.8425 | 4.2069 | 6100K025 | PO-SEP-8915-[2] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11259 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 4.2069 | 4.2069 | 0 | 6100KDP01 | PO-SEP-8622-[20] | PO | 2026-01-30 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11260 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 838.0744 | 780.954 | 57.1204 | 6100K021 | PO-SEP-8915-[18] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11260 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 57.1204 | 57.1204 | 0 | 6100K025 | PO-SEP-8915-[3] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11261 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 36.2691 | 24.0623 | 12.2069 | 6100K025 | PO-SEP-8915-[4] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11261 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 12.2069 | 12.2069 | 0 | 6100KDP01 | PO-SEP-8622-[22] | PO | 2026-01-30 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11262 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 150.6565 | 139.0177 | 11.6387 | 6100K025 | PO-SEP-8915-[5] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11262 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 11.6387 | 11.6387 | 0 | 6100KDP01 | PO-SEP-8622-[23] | PO | 2026-01-30 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11263 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 94.8578 | 7.4904 | 87.3674 | 6100K021 | PO-SEP-8915-[21] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11263 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 87.3674 | 87.3674 | 0 | 6100K025 | PO-SEP-8915-[6] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11264 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 27.8993 | 2.3162 | 25.5832 | 6100K021 | PO-SEP-8915-[22] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11264 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 25.5832 | 25.5832 | 0 | 6100K025 | PO-SEP-8915-[7] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11265 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm Yellow/Green, ATC, 105°, 600/1000V , 1 x 100 m | 28.0088 | 24.5575 | 3.4512 | 6100KDP01 | PO-SEP-8622-[26] | PO | 2026-01-30 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11265 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm Yellow/Green, ATC, 105°, 600/1000V , 1 x 100 m | 3.4512 | 3.4512 | 0 | free_stock | PR-SEP-0024130-[107] | PR |  | Wire |  | - | 2026-04-18 | 2026-04-04 | 0
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11266 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 150.6565 | 12.1337 | 138.5228 | 6100K021 | PO-SEP-8915-[24] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11266 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 138.5228 | 138.5228 | 0 | 6100K025 | PO-SEP-8915-[9] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11267 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Yellow, ATC,105°, 600/1000V , 1 x 100 m | 150.6565 | 139.0177 | 11.6387 | 6100K021 | PO-SEP-8915-[25] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11267 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Yellow, ATC,105°, 600/1000V , 1 x 100 m | 11.6387 | 11.6387 | 0 | 6100KDP01 | PO-SEP-8622-[28] | PO | 2026-01-30 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11268 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 8.3698 | 8.3698 | 0 | 6100K021 | PO-SEP-8915-[26] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11269 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 11.1597 | 5.8403 | 5.3195 | 6100K021 | PO-SEP-8915-[27] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11269 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 5.3195 | 5.3195 | 0 | 6100K025 | PO-SEP-8915-[12] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11270 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 8.3698 | 8.3698 | 0 | 6100K021 | PO-SEP-8915-[29] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11271 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Yellow, ATC, 105°, 600/1000V , 1 x 100 m | 8.3698 | 8.3698 | 0 | 6100K021 | PO-SEP-8915-[30] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11272 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 11.1597 | 5.8403 | 5.3195 | 6100K021 | PO-SEP-8915-[28] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP11272 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 5.3195 | 5.3195 | 0 | 6100K025 | PO-SEP-8915-[13] | PO | 2026-01-11 | Wire |  | - | 2026-04-18 | 2026-04-04 | 0 | Al-Fanar Company Limited | Cable Items
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12004 | TERM.LUGS BLADE RF-PP 12/23 | 15300 | 15300 | 0 | 6100K021 | PO-SEP-8894-[28] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12012 | TERM.LUGS SPADE RF-U4 1.5/M4 | 6375 | 6375 | 0 | 6100K021 | PO-SEP-8894-[29] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12016 | TERM.LUGS RING RF-M4 1.5/M4 | 5100 | 5100 | 0 | 6100K021 | PO-SEP-8894-[31] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12026 | BENT LUGS TYPE RF-PPL30 | 35700 | 35700 | 0 | 6100K021 | PO-SEP-8894-[20] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12048 | END SLEEVES PKE 1508 (1x1.5sqmm , Black) | 765 | 690 | 75 | 6100K021 | PO-SEP-8894-[36] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12048 | END SLEEVES PKE 1508 (1x1.5sqmm , Black) | 75 | 75 | 0 | 6100KDP01 | PO-SEP-8541-[13] | PO | 2025-10-30 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12050 | UN-INSUL SLeve Lugs KE1510ST (1.5mm) | 1020 | 1020 | 0 | 6100K021 | PO-SEP-8894-[24] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12052 | END SLEEVES PKT 1508 (2x1.5sqmm , Black) | 765 | 490 | 275 | 6100K021 | PO-SEP-8894-[37] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12052 | END SLEEVES PKT 1508 (2x1.5sqmm , Black) | 275 | 275 | 0 | 6100KDP01 | PO-SEP-8541-[10] | PO | 2025-10-30 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12063 | TERM.LUGS BLADE BF-PP12/25 2.5MM | 5100 | 5100 | 0 | 6100K021 | PO-SEP-8894-[27] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12083 | TERM.LUGS BF-M5 (RING) | 6120 | 6120 | 0 | 6100K021 | PO-SEP-8894-[33] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12085 | WIRE LUGS RING TYPE BF-M6 2.5/M6 | 408 | 408 | 0 | 6100K021 | PO-SEP-8894-[34] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12087 | RING TYPE LUGS BF-M 8 | 408 | 408 | 0 | 6100K021 | PO-SEP-8894-[35] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12091 | BENT LUGS TYPE BF-PPL30 | 15300 | 15300 | 0 | 6100K021 | PO-SEP-8894-[22] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12103 | UN-INSUL SLEEVE Lugs for 2.5mm KE2510ST | 2550 | 2550 | 0 | 6100K021 | PO-SEP-8894-[25] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12105 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 1020 | 420 | 600 | 6100K021 | PO-SEP-8894-[38] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12105 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 600 | 600 | 0 | 6100KDP01 | PO-SEP-8541-[11] | PO | 2025-10-30 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12117 | TERM.LUGS RING BF-M4 | 10200 | 6100 | 4100 | 6100K021 | PO-SEP-8894-[32] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12117 | TERM.LUGS RING BF-M4 | 4100 | 4100 | 0 | 6100KDP01 | PO-SEP-8541-[8] | PO | 2025-10-30 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12119 | RING TYPE LUGS GF-M 5 | 1020 | 1020 | 0 | 6100KDP01 | PO-SEP-8541-[6] | PO | 2025-10-30 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12127 | BENT LUGS TYPE BF-PPL46 | 7650 | 7650 | 0 | 6100K021 | PO-SEP-8894-[21] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12129 | Un-Insul Sleeve Lugs 4.0 mm KE410ST | 2550 | 2550 | 0 | 6100K021 | PO-SEP-8894-[26] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | SEP12131 | Lugs, Sleeve 4.0/9mm ( W/O Ins.) 3200302 | 2550 | 2550 | 0 | 6100K021 | PO-SEP-8894-[23] | PO | 2025-10-27 | LVD |  | - | 2026-04-18 | 2026-04-04 | 0 | Jeesoon Terminals Co., Ltd. | 6100K020 Mahar SS SWGR Electrical components order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | VT-GUARD-13.8KV | VT Guard, Anti Ferro Resonance Unit ¦ VT-GUARD-13.8KV | 6 | 6 | 0 | 6100K021 | PO-SEP-8749-[2] | PO | 2025-12-31 | RVT |  | - | 2026-04-18 | 2026-04-04 | 0 | Abb Electrical Industriesco | VT Guard/6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1SNA234000R0200 | Marker, RC810, 1 ¦ 10/1SNA234041R2600 ¦ ENTRELEC | 510 | 510 | 0 | 6100K021 | PO-SEP-8833-[38] | PO | 2025-11-13 | Terminals | Automated: Replaced 1SNA234000R0200 by SEP20333. | - | 2026-04-18 | 2026-04-04 | 0 | Al Suhaili Trading And Development
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5340XIAXXN01 | Relay, Auxiliary, 2 Coils, Self Reset Contacts, Hand Reset Flag, 110-125V, DC, 2NO, 1NC, Coil ¦ RXSF1 RK 271 007-AN | 51 | 51 | 0 | 6100K025 | PO-SEP-8751-[3] | PO | 2025-12-31 | LVA | Automated: Replaced 1YAB5340XIAXXN01 by DM0000000058. | - | 2026-04-18 | 2026-04-04 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block, TB, Disconnecting TB for CT, OTTA 6-T, Bolt W/O Spring, 0790462 ¦ OTTA 6-T P/P ¦ PHOENIX | 4012 | 4000 | 12 | 6100K021 | PO-SEP-8792-[11] | PO | 2025-12-20 | Terminals | Automated: Replaced 1YAB5355AAB0001 by SEP10052. | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block, TB, Disconnecting TB for CT, OTTA 6-T, Bolt W/O Spring, 0790462 ¦ OTTA 6-T P/P ¦ PHOENIX | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8572-[1] | PO | 2025-12-15 | Terminals | Automated: Replaced 1YAB5355AAB0001 by SEP10052. | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355CAB0000 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 510 | 90 | 420 | 6100K021 | PO-SEP-8792-[13] | PO | 2025-12-20 | Terminals | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355CAB0000 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 420 | 186 | 234 | 6100K025 | PO-SEP-8792-[3] | PO | 2025-12-20 | Terminals | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-04-18 | 2026-04-04 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K021 | Rayan : SWITCHGEAR - Rayan | SWGR | ROH | 1YAB5355CAB0000 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 234 | 234 | 0 | free_stock | PR-SEP-0024130-[77] | PR |  | Terminals | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-04-18 | 2026-04-04 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 129A539G01 | ‭FT SWITCH, (T T T T T T T T T T)/129A539G01/FT-1‬ | 66 | 66 | 0 | 6100K025 | PO-SEP-8747-[7] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 13.8-VT-ZS1-3WDG-25VA | Voltage Transformer (RITZ) | 18 | 18 | 0 | 6100KDP01 | PO-SEP-8580-[11] | PO | 2026-01-24 | VT |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | AL Aziyziyah Project SWGR KDP01 CTs
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1815230000 | 5Pole Plug 2.5mm-1815230000-Cont-loop | 50 | 50 | 0 | 6100K025 | PO-SEP-8750-[15] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1855030000 | 6Pole Plug 4mm-1855030000-AC looping | 51 | 51 | 0 | 6100K025 | PO-SEP-8750-[16] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SFA611400R1001 | PILOT LIGHT#ML1-100R | 48 | 48 | 0 | 6100K025 | PO-SEP-8753-[14] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SFA611400R1002 | PILOT LIGHT#ML1-100G | 48 | 48 | 0 | 6100K025 | PO-SEP-8753-[15] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SFA611400R1003 | PILOT LIGHT#ML1-100Y | 52 | 52 | 0 | 6100K025 | PO-SEP-8753-[16] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SFA611400R1005 | PILOT LIGHT#ML1-100W | 114 | 114 | 0 | 6100K025 | PO-SEP-8753-[17] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SFA611605R1100 | HOLDER#MCBH-00 | 262 | 262 | 0 | 6100K025 | PO-SEP-8753-[18] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SFA611621R1051 | LAMP BLOCK#MLBL-05R | 48 | 48 | 0 | 6100K025 | PO-SEP-8753-[19] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SFA611621R1052 | LAMP BLOCK#MLBL-05G | 48 | 48 | 0 | 6100K025 | PO-SEP-8753-[20] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SFA611621R1053 | LAMP BLOCK#MLBL-05Y | 52 | 52 | 0 | 6100K025 | PO-SEP-8753-[21] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SFA611621R1055 | LAMP BLOCK#MLBL-05W | 108 | 108 | 0 | 6100K025 | PO-SEP-8753-[22] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SFA611630R1001 | DIODE BLOCK#MDB-1001 | 256 | 256 | 0 | 6100K025 | PO-SEP-8753-[23] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SFA616920R8005 | KA1-8005 Lens | 256 | 256 | 0 | 6100K025 | PO-SEP-8753-[24] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SNA206394R0200 | Screw, EV6I_Screw+PstWasherIP20_M6/8.RS_M4/6.RS Type: EV6I Order no: 1SNA 206 394 R0200 Color: Grey ¦ 1SNA206394R0200 ¦ ABB | 408 | 408 | 0 | 6100K025 | PO-SEP-8833-[34] | PO | 2025-11-13 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SNK900654R0000 | SC-JB8-4 Short circuit bridges - Yellow | 153 | 153 | 0 | 6100K025 | PO-SEP-8833-[42] | PO | 2025-11-13 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB000002-FDV | MIMIC DIAGRAM, INCOMER-2W,VT | 3 | 3 | 0 | 6100K025 | PO-SEP-8724-[10] | PO | 2025-11-16 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB000003-FDX | MIMIC , OUTGOING WITH EARTHING | 43 | 43 | 0 | 6100K025 | PO-SEP-8724-[7] | PO | 2025-11-16 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB000004-BTE | MIMIC BUS SEC WITH EARTHG ON RIGHT SIDE | 2 | 2 | 0 | 6100K025 | PO-SEP-8724-[18] | PO | 2025-11-16 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB000007-BME | MIMIC, BUS MET. & EARTHING-2W,VT | 1 | 1 | 0 | 6100K025 | PO-SEP-8724-[14] | PO | 2025-11-16 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB000009-BRM | MIMIC , BUS RISER & MET.-2W,VT | 2 | 2 | 0 | 6100K025 | PO-SEP-8724-[17] | PO | 2025-11-16 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5112XFS00000 | VT 3Nos PRIMARY FUSE 17.5kV, 3A, SIBA.VT PRIMARY FUSE FOR 17.5kV UG ZS1 Fuse length : 192 mm Fuse dia : 53 mm Rated Voltage: 17.5kV Rated Current: 3A Rated breaking current : 31.5 kA Frequency: 60 Hz Fuse make : SIBA Type: 30 179 11.3 | 18 | 18 | 0 | 6100K025 | PO-SEP-8827-[1] | PO | 2026-01-25 | VT fuse |  | - | 2026-05-15 | 2026-05-01 | 0 | SABANA TRADERS LLC
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB52321VW6CN00 | VD4/PW 170625-p210-125VDC (1VCD400222) | 34 | 34 | 0 | 6100KDP01 | PO-SEP-8506-[1] | PO | 2026-01-20 | A |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | CB / AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB52322VW60N00 | VD4/PW 171225-p210-125VDC-ZS1-1250A @ 60Hz, in UG ZS1- with upper CTs as per NG Stanadrad | 6 | 4 | 2 | 6100K025 | PO-SEP-8773-[2] | PO | 2025-10-23 | A |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB52322VW60N00 | VD4/PW 171225-p210-125VDC-ZS1-1250A @ 60Hz, in UG ZS1- with upper CTs as per NG Stanadrad | 2 | 1 | 1 | 6100K020 | PO-SEP-8776-[2] | PO | 2025-10-23 | A |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | 6100K020 Mahar SS SWGR Electrical components order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB52322VW60N00 | VD4/PW 171225-p210-125VDC-ZS1-1250A @ 60Hz, in UG ZS1- with upper CTs as per NG Stanadrad | 1 | 1 | 0 | 6100K023 | PO-SEP-8359-[2] | PO | 2026-01-20 | A |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | CBs / 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB52333VW6CN00 | VD4/P 171240-p210-125VDC (1VCD400222) | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8506-[2] | PO | 2026-01-20 | A |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | CB / AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB52371V06CN00 | VD4/P 173225-p275-125VDC (1VCD400222) | 5 | 1 | 4 | 6100K019 | PO-SEP-7386-[2] | PO | 2025-11-18 | A |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | PP-12 / CB
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB52371V06CN00 | VD4/P 173225-p275-125VDC (1VCD400222) | 4 | 4 | 0 | 6100KDP01 | PO-SEP-8506-[3] | PO | 2026-01-20 | A |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | CB / AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 48 | 1 | 47 | 6100K025 | PO-SEP-8775-[1] | PO | 2025-10-23 | A |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5310XFAXXN28 | REF 620_NBFNAAAANEA1BNN11G | 47 | 47 | 0 | 6100KDP01 | PO-SEP-8360-[2] | PO | 2025-12-07 | A |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | Relay /Aziziyah & 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5320XDB1XN02 | DIGITAL VOLTMETER, Cl 1.0, 3PH4W, 5-500V, 60Hz, 150% Un CONT, 3 LINE DISPLAY LED, MODBUS ¦ SECURE DPM 96 V300 | 3 | 3 | 0 | 6100K025 | PO-SEP-8837-[2] | PO | 2025-12-30 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Washa Al Wisam Factory Company.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5320XHI1XN00 | POWER QUALITY ANALYZER, ISKRA iMC784 | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8547-[1] | PO | 2025-12-02 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Enerziff Solutions FZCO | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 51 | 23 | 28 | 6100K025 | PO-SEP-8829-[2] | PO | 2025-10-23 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Abdullah AbuNayyan Trading Corp
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB53303XRX0000 | THERMOSTAT 24,48,60,115 & 230V,SK 3110 | 28 | 28 | 0 | 6100KDP01 | PO-SEP-8550-[1] | PO | 2026-10-03 | LVA |  | - | 2026-05-15 | 2026-05-01 | 155 | Abdullah AbuNayyan Trading Corp | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope). | 20 | 22-10-2025
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5331XXCX0000 | CAPACITOR PARKING KEY_COMELECTRIC ITALY.ELECTROMECHANICAL TRAPPED KEY INTERLOCK SWITCH Model: SR 102 R20 2/4 Key Trapped Solenoid Release Switch with IP20 Contacts. Key Free Position: 0 Degree, 4 Contacts. Key Trapped Position: 90 Degree, 4 Contacts. Label: Capacitor Bank Gate Interlock. Make: Comeletric, Italy. Door Interlock lock : KD1 SAP PART NO: 1YAB5331XXCX0000 ------------------ CAPACITOR PARKING KEY_COMELECTRIC ITALY | 3 | 0 | 3 | PR Required | - | PR |  | Customer to supply |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5331XXCX0100 | BREAKER CONTROL SWITCH (Comelectric)Breaker Control Switch3-Pole, 3-Position & spring returnDim: 51 X 51 mm Padlockable handle:Colour : Red YellowFront plate:Text Engrave : OPEN- NORMAL-CLOSELettering plate:Text Engrave : BREAKER CONTROL SWITCH Ordering Code: R601 SAM303 011 01-L078+48-30309T133 | 48 | 27 | 21 | 6100K025 | PO-SEP-8785-[1] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Aman Engineering FZC
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5331XXCX0100 | BREAKER CONTROL SWITCH (Comelectric)Breaker Control Switch3-Pole, 3-Position & spring returnDim: 51 X 51 mm Padlockable handle:Colour : Red YellowFront plate:Text Engrave : OPEN- NORMAL-CLOSELettering plate:Text Engrave : BREAKER CONTROL SWITCH Ordering Code: R601 SAM303 011 01-L078+48-30309T133 | 21 | 21 | 0 | 6100KDP01 | PO-SEP-8398-[10] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5331XXCX0210 | CBMODE6P,4Pos.Off-Emer-Local-Rem-Padlock(COMELECTRIC), Breaker Mode Selector Switch 6-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH COMELETRIC Part No. R601 SA412 067 27-L071+48-40513T134 SAP Part no: 1YAB5331XXCX0210 | 8 | 1 | 7 | 6100K019 | PO-SEP-8398-[8] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5331XXCX0210 | CBMODE6P,4Pos.Off-Emer-Local-Rem-Padlock(COMELECTRIC), Breaker Mode Selector Switch 6-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH COMELETRIC Part No. R601 SA412 067 27-L071+48-40513T134 SAP Part no: 1YAB5331XXCX0210 | 7 | 7 | 0 | free_stock | PR-SEP-0024130-[37] | PR |  | LVB |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5331XXCX0220 | OFF-EMER-LOCAL-REMOTE 4P4P, PADLCK (COMELECTRIC), Breaker Mode Selector Switch 4-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH Ordering Code: R601 SA408 067 27-L071+48-40513T134 20A, 4 pos Stayput 4 contacts in each Pos, TYPE 1: Engraving: OFF-EMERGENCY-LOCAL-REMOTE TOP PLATE: BREAKER MODE PADLOCK SAP PART NO: 1YAB5331XXCX0220 | 40 | 20 | 20 | 6100K025 | PO-SEP-8785-[3] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Aman Engineering FZC
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5331XXCX0220 | OFF-EMER-LOCAL-REMOTE 4P4P, PADLCK (COMELECTRIC), Breaker Mode Selector Switch 4-Poles, 4-Positions Padlockable in each position Stop at last position: YES Handle Color: Black Front plate: Text engrave : Cam Position 270, Text = OFF Cam Position 330, Text = EMERGENCY Cam Position 30, Text = LOCAL Cam Position 90, Text = REMOTE Lettering plate Text engrave : BREAKER MODE SWITCH Ordering Code: R601 SA408 067 27-L071+48-40513T134 20A, 4 pos Stayput 4 contacts in each Pos, TYPE 1: Engraving: OFF-EMERGENCY-LOCAL-REMOTE TOP PLATE: BREAKER MODE PADLOCK SAP PART NO: 1YAB5331XXCX0220 | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8398-[17] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5331XXCX0300 | SPACE HEATER SEL. SWITCH ( COMELECTRIC )R601 SA302 112-W051+48-31090T124 20A, 3Positions without internal links 2pole,3position Engraving (OFF/Auto/Manual) OFF-zero contacts AUTO-2 contacts MANUAL-2contacts TOP PLATE (SPACE HEATER) Single hole mounting FT6 | 51 | 26 | 25 | 6100K025 | PO-SEP-8785-[4] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Aman Engineering FZC
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5331XXCX0300 | SPACE HEATER SEL. SWITCH ( COMELECTRIC )R601 SA302 112-W051+48-31090T124 20A, 3Positions without internal links 2pole,3position Engraving (OFF/Auto/Manual) OFF-zero contacts AUTO-2 contacts MANUAL-2contacts TOP PLATE (SPACE HEATER) Single hole mounting FT6 | 25 | 25 | 0 | 6100KDP01 | PO-SEP-8398-[13] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC )R601 SAM201 071-W051+48-20547T123 20A SPRING RETAIN WITHOUT INTERNAL LINKS 2 POSITION,1POLE Engraving (OFF-TEST) TOP PLATE Engraving (LAMP TEST) | 51 | 26 | 25 | 6100K025 | PO-SEP-8785-[5] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Aman Engineering FZC
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5331XXCX0400 | LAMP TEST SWITCH ( COMELECTRIC )R601 SAM201 071-W051+48-20547T123 20A SPRING RETAIN WITHOUT INTERNAL LINKS 2 POSITION,1POLE Engraving (OFF-TEST) TOP PLATE Engraving (LAMP TEST) | 25 | 25 | 0 | 6100KDP01 | PO-SEP-8398-[14] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5331XXKX0700 | Auto Re-close IN-OUT Selector Switch(COMELECTRIC),"Auto Re-close IN-OUT Selector Switch 4-Pole, 2-Positions Dim: 51 X 51 mm Padlockable handle: Colour : Black Front plate: Text Engrave : IN-OUT Lettering plate Text Engrave : A/R IN-OUT SWITCH" CA10-A723-SA0030-E 1YAB5331XXKX0700 | 38 | 18 | 20 | 6100K025 | PO-SEP-8785-[6] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Aman Engineering FZC
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5331XXKX0700 | Auto Re-close IN-OUT Selector Switch(COMELECTRIC),"Auto Re-close IN-OUT Selector Switch 4-Pole, 2-Positions Dim: 51 X 51 mm Padlockable handle: Colour : Black Front plate: Text Engrave : IN-OUT Lettering plate Text Engrave : A/R IN-OUT SWITCH" CA10-A723-SA0030-E 1YAB5331XXKX0700 | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8398-[9] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Aman Engineering FZC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5332XXAXB000 | PB Black 1NO+1NC-22 dia-1SFA611100R4076 | 108 | 36 | 72 | 6100K025 | PO-SEP-8753-[76] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5332XXAXB000 | PB Black 1NO+1NC-22 dia-1SFA611100R4076 | 72 | 72 | 0 | free_stock | PR-SEP-0024130-[42] | PR |  | LVB |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5334XXAX1000 | FT-1 SW-Type 129A514G01 | 8 | 8 | 0 | 6100K025 | PO-SEP-8747-[11] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5336XXAA2E00 | MCB 3A AC -2P,2CDS252001R0317 | 5 | 5 | 0 | 6100K025 | PO-SEP-8753-[7] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5336XXAA2G00 | MCB S 202-K6 6A AC -2P - 2CDS252001R0377 | 103 | 103 | 0 | 6100K025 | PO-SEP-8753-[8] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5336XXAA2L00 | MCB 16A AC -2P - 2CDS252001R0467 | 5 | 5 | 0 | 6100K025 | PO-SEP-8753-[9] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5336XXAB2G00 | MCB 6A DC 2P S202M-K6UC -2CDS272061R0377 | 300 | 300 | 0 | 6100K025 | PO-SEP-8753-[10] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5336XXACG000 | Aux contact 2NC, S2C-HO2L-for MCB Order # 2CDS200936R0003 | 245 | 245 | 0 | 6100K025 | PO-SEP-8753-[11] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5336XXACH000 | Aux contact 1NO+1NC MCB -2CDS200936R0001 | 340 | 340 | 0 | 6100K025 | PO-SEP-8753-[12] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5336XXACJ000 | S2C-H01 - 1NC- Bottom Auxiliary Contact 2CDS200970R0031 | 75 | 75 | 0 | 6100K025 | PO-SEP-8753-[13] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XAJXXN00 | RF-4R_125Vdc_4 C/O_LED | 85 | 85 | 0 | 6100K025 | PO-SEP-8839-[5] | PO | 2026-02-28 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Innovative Systems Co. Ltd | Arteche MV
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XAJXXN01 | BJ-8RP_Bistable_125Vdc_8 C/O | 40 | 40 | 0 | 6100K025 | PO-SEP-8839-[6] | PO | 2026-02-28 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Innovative Systems Co. Ltd | Arteche MV
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XBLXXN00 | MVAJ101 RA 0802_ 125VDC (8 NO + 2 NC) | 2 | 2 | 0 | 6100K025 | PO-SEP-8841-[7] | PO | 2026-02-28 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Grid Solution Middle-East Fze | MV
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XCHXXN01 | LOCKOUT RELAY (86) TYPE 7835FD, HIGH SPEED TRIP 8ms, TRIP COIL (70-280VDC),10NO+10NC ELECTRICAL RESET COIL (100-150VDC) | 48 | 0 | 48 | PR Required | - | PR |  | LVA |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XCLXXN00 | MVAJ205 ,125VDC ) CAT No. MVAJ205TB0808A | 2 | 2 | 0 | 6100K025 | PO-SEP-8841-[8] | PO | 2026-02-28 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Grid Solution Middle-East Fze | MV
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XDAXXN00 | RXMVB 4, RK 251 401-AP | 8 | 5 | 3 | 6100K025 | PO-SEP-8751-[7] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XDAXXN00 | RXMVB 4, RK 251 401-AP | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8366-[6] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XDAXXN01 | RXMVB2, RK 251 204-AP | 13 | 13 | 0 | 6100K025 | PO-SEP-8751-[8] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XEAXXN00 | RXMB1 6NO_110-125VDC-1MRK 000 863-AN | 16 | 10 | 6 | 6100K025 | PO-SEP-8751-[9] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XEAXXN00 | RXMB1 6NO_110-125VDC-1MRK 000 863-AN | 6 | 6 | 0 | 6100KDP01 | PO-SEP-8366-[8] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XFAXXN00 | RXKL1, TYPE: 1MRK 000 066-AB | 5 | 2 | 3 | 6100K025 | PO-SEP-8751-[10] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XFAXXN00 | RXKL1, TYPE: 1MRK 000 066-AB | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8366-[9] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XIAXXN00 | RXSF1_DC110-125V-MV RK 271 019-AN No volt flag relay | 150 | 77 | 73 | 6100K025 | PO-SEP-8751-[11] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XIAXXN00 | RXSF1_DC110-125V-MV RK 271 019-AN No volt flag relay | 73 | 73 | 0 | 6100KDP01 | PO-SEP-8366-[10] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XJAXXN00 | THREE PHASE FUSE SUPERVISION RELAY Type : RXBA4 (ABB) ORDER NO. : RK 428 004-AA CONTACTS : 2 CHANGE OVER SELF RESET | 6 | 1 | 5 | 6100K025 | PO-SEP-8751-[4] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XJAXXN00 | THREE PHASE FUSE SUPERVISION RELAY Type : RXBA4 (ABB) ORDER NO. : RK 428 004-AA CONTACTS : 2 CHANGE OVER SELF RESET | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8297-[5] | PO | 2026-01-08 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | PP-12 RELAY BASE AND COMBIFLEX BOX
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XNHXXN00 | TRIP LOR/ER 7840FD 20NO+20NC, 125VDC HIGH SPEED TRIP 8ms, TRIP COIL (70-280VDC), ELECTRICAL RESET COIL (100-150VDC) | 9 | 0 | 9 | PR Required | - | PR |  | LVA |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355AAB0002 | TERMINAL BLOCK OTTA 6 - 0790433 | 6550 | 6550 | 0 | 6100K025 | PO-SEP-8792-[2] | PO | 2025-12-20 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355ABA0001 | Terminal Block,6SWG, :Lugs,D-6/8.ST1.RS | 2295 | 2295 | 0 | 6100K025 | PO-SEP-8833-[3] | PO | 2025-11-13 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355AEA0001 | M 6/8.RS (SpringLoaded) 1SNA115685R1200 | 2212 | 2212 | 0 | 6100K025 | PO-SEP-8833-[4] | PO | 2025-11-13 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355AEA1112 | M 4/6.RS- SpringLoaded 1SNA115930R1300 | 16264 | 16264 | 0 | 6100K025 | PO-SEP-8833-[7] | PO | 2025-11-13 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355AFA0001 | M4/6.SNTS Spring Loaded 1SNA115229R2000 | 2295 | 2295 | 0 | 6100K025 | PO-SEP-8833-[11] | PO | 2025-11-13 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355AMA0001 | D 6/8.ST1.RS AC/DC - 1SNA115914R0700 | 1617 | 1617 | 0 | 6100K025 | PO-SEP-8833-[15] | PO | 2025-11-13 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355AMC0001 | Base Terminal Plug AC-DC-4mm 1848350000.Feed-through terminal block,ZT 4/4AN/2 . | 1530 | 860 | 670 | 6100K025 | PO-SEP-8750-[12] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355AMC0001 | Base Terminal Plug AC-DC-4mm 1848350000.Feed-through terminal block,ZT 4/4AN/2 . | 670 | 670 | 0 | 6100KDP01 | PO-SEP-8518-[1] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355APC0001 | Base Terminal 2Deck- Plug In E-Sw-2.5mm | 612 | 612 | 0 | 6100K025 | PO-SEP-8750-[13] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 742 | 386 | 356 | 6100K025 | PO-SEP-8750-[14] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355ATC0001 | Base Terminal Plug for Alrm & VT 2.5mm | 356 | 356 | 0 | 6100KDP01 | PO-SEP-8518-[3] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355CBA0000 | FEM8T6 End Sections Grey 1SNA215266R0100 | 765 | 765 | 0 | 6100K025 | PO-SEP-8833-[16] | PO | 2025-11-13 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355CEA0000 | FEMR8 End Sections Grey 1SNA116987R0200 | 1020 | 1020 | 0 | 6100K025 | PO-SEP-8833-[20] | PO | 2025-11-13 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355CFA0000 | FEM6 End Sections Grey - 1SNA118368R1600 | 510 | 510 | 0 | 6100K025 | PO-SEP-8833-[22] | PO | 2025-11-13 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355CMC0000 | Terminal End Plate 1848360000-Wiedmuller | 204 | 150 | 54 | 6100K025 | PO-SEP-8750-[26] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355CMC0000 | Terminal End Plate 1848360000-Wiedmuller | 54 | 54 | 0 | 6100KDP01 | PO-SEP-8518-[4] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355CPC0000 | Terminal End Plate 1816110000-Wiedmuller | 204 | 204 | 0 | 6100K025 | PO-SEP-8750-[27] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355CTC0000 | Terminal End Plate 1816070000-Wiedmuller | 106 | 106 | 0 | 6100K025 | PO-SEP-8750-[28] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 2550 | 2250 | 300 | 6100K025 | PO-SEP-8792-[4] | PO | 2025-12-20 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355CXB0000 | End Clamp, E/UK - 1201442 | 300 | 300 | 0 | free_stock | PR-SEP-0024130-[81] | PR |  | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355DFA0000 | RC610-VerticalMarking 1SNA233060R0400 | 459 | 459 | 0 | 6100K025 | PO-SEP-8833-[25] | PO | 2025-11-13 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355DXC0000 | 460660001 DEK 5 FSZ 1-10 Z-Terminal 1-10 | 20600 | 11700 | 8900 | 6100K025 | PO-SEP-8750-[10] | PO | 2025-12-31 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355DXC0000 | 460660001 DEK 5 FSZ 1-10 Z-Terminal 1-10 | 8900 | 8900 | 0 | 6100KDP01 | PO-SEP-8518-[7] | PO | 2025-12-31 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355EEA0000 | JUMPER BAR "BJS8" 20 Poles | 102 | 102 | 0 | 6100K025 | PO-SEP-8833-[29] | PO | 2025-11-13 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355EFA0000 | PC61-CombTypeJumprBar10 1SNA163311R2200 | 204 | 204 | 0 | 6100K025 | PO-SEP-8833-[33] | PO | 2025-11-13 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 408 | 220 | 188 | 6100K025 | PO-SEP-8750-[29] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355GPC0000 | 2Pole cross connectn.plugable-1693800000 | 188 | 188 | 0 | 6100KDP01 | PO-SEP-8518-[8] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355HAB0002 | Zack Strip-Vertical Labeled(21-30) | 408 | 408 | 0 | 6100K025 | PO-SEP-8750-[11] | PO | 2025-12-31 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355JMC0000 | 10Pole Plug 4mm-1855070000-DC looping | 306 | 306 | 0 | 6100K025 | PO-SEP-8750-[30] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355JPC0000 | 6Pole Plug 2.5mm-1815240000-Cont-loop | 204 | 204 | 0 | 6100K025 | PO-SEP-8750-[31] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355JTC0000 | 10Pole Plug 2.5mm-1815280000-Cont-loop | 212 | 212 | 0 | 6100K025 | PO-SEP-8750-[32] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355KMC0000 | Locking element 185525000 for ZT4/4AN/2 | 612 | 612 | 0 | 6100K025 | PO-SEP-8750-[33] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355KPC0000 | Locking ele. 1816130000 for ZT2.5/4AN/2 | 310 | 310 | 0 | 6100K025 | PO-SEP-8750-[34] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355LMC0000 | Coding element 1856860000 - ZT4/4AN/2 | 408 | 408 | 0 | 6100K025 | PO-SEP-8750-[35] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355LPC0000 | Coding element 1816150000 | 416 | 416 | 0 | 6100K025 | PO-SEP-8750-[36] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355MPC0000 | Strain Relief Wied mulpart # 1816140000 | 310 | 310 | 0 | 6100K025 | PO-SEP-8750-[17] | PO | 2025-12-31 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | WEIDMULLER MIDDLE EAST (FZE) | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 612 | 600 | 12 | 6100K025 | PO-SEP-8792-[7] | PO | 2025-12-20 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355ZAB0000 | Insertion Bridge, EB 10-OTTA6 - 0790420 | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8572-[8] | PO | 2025-12-15 | Plug socket |  | - | 2026-05-15 | 2026-05-01 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB60050819P0103 | Braided HARNESS TUBE (D40) | 765 | 190 | 575 | 6100K025 | PO-SEP-8834-[5] | PO | 2025-10-23 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Dalian Jinda Industry Co.,Ltd
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB60050819P0103 | Braided HARNESS TUBE (D40) | 575 | 575 | 0 | 6100KDP01 | PO-SEP-8378-[259] | PO | 2025-11-17 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB60050819P0104 | Braided HARNESS TUBE (D50) | 51 | 51 | 0 | 6100K025 | PO-SEP-8834-[7] | PO | 2025-10-23 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Dalian Jinda Industry Co.,Ltd
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB60050819P0106 | Braided HARNESS TUBE (D30) | 1020 | 120 | 900 | 6100K025 | PO-SEP-8834-[8] | PO | 2025-10-23 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Dalian Jinda Industry Co.,Ltd
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB60050819P0106 | Braided HARNESS TUBE (D30) | 900 | 900 | 0 | 6100KDP01 | PO-SEP-8378-[261] | PO | 2025-11-17 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB60050819P0107 | Braided HARNESS TUBE (D20) | 510 | 60 | 450 | 6100K025 | PO-SEP-8834-[11] | PO | 2025-10-23 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Dalian Jinda Industry Co.,Ltd
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB60050819P0107 | Braided HARNESS TUBE (D20) | 450 | 450 | 0 | 6100KDP01 | PO-SEP-8378-[262] | PO | 2025-11-17 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 2CDS254001R0337 | MCB S204-K 4 MC -4P 2CDS254001R0337 | 138 | 138 | 0 | 6100K025 | PO-SEP-8753-[77] | PO | 2025-12-31 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 2TRE123451P0001 | 3 PIN SOCKET SWITCH,13A,250V,BSRDP-I | 5 | 4 | 1 | 6100K025 | PO-SEP-8836-[5] | PO | 2025-11-13 | LVB |  | - | 2026-05-15 | 2026-05-01 | 0 | Saeed Aziz Alsomali Trading Est
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 2TRE123451P0001 | 3 PIN SOCKET SWITCH,13A,250V,BSRDP-I | 1 | 1 | 0 | free_stock | PR-SEP-0024130-[69] | PR |  | LVB |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 5022 643 | COVER PROFILE, AP3 | 81.6 | 81.6 | 0 | 6100K025 | PO-SEP-8792-[8] | PO | 2025-12-20 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 1275 | 1250 | 25 | 6100K025 | PO-SEP-8792-[9] | PO | 2025-12-20 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 5022 656 | COVER PROFILE SUPPORT, AP3-TU | 25 | 25 | 0 | 6100KDP01 | PO-SEP-8572-[10] | PO | 2025-12-15 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 837A407G01 | ‭FT SWITCH, (C-C C-C C-C C-C P P)/837A407G01/FT-1‬ | 51 | 51 | 0 | 6100K025 | PO-SEP-8747-[5] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 9676A14G01 | ‭FT SWITCH, (P P P P T T T P P P)/9676A14G01/FT-1‬ | 58 | 58 | 0 | 6100K025 | PO-SEP-8747-[6] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | FT Switch/ 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE 2636 4000-001 | INSULATION SLEEVE,6MMDIA. | 815 | 815 | 0 | 6100K025 | PO-SEP-8836-[12] | PO | 2025-11-13 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Saeed Aziz Alsomali Trading Est
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE 2636 4000-002 | ADHESIVE MOUNTING BASE | 765 | 765 | 0 | 6100K025 | PO-SEP-8836-[13] | PO | 2025-11-13 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Saeed Aziz Alsomali Trading Est
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2000-2150-06 | SELF STICK RUBBER FOAM | 66.3 | 66.3 | 0 | 6100K025 | PO-SEP-8835-[2] | PO | 2025-10-23 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | EMKA Beschlagteile Middle East FZE
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 1020 | 1000 | 20 | 6100K025 | PO-SEP-8884-[5] | PO | 2025-12-21 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2000-2166-03 | TIE WRAP/PLT4I-C0/371MM | 20 | 20 | 0 | 6100KDP01 | PO-SEP-8378-[232] | PO | 2025-11-17 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 306 | 76 | 230 | 6100K025 | PO-SEP-8834-[15] | PO | 2025-10-23 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Dalian Jinda Industry Co.,Ltd
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2000-6884-01 | EQUIPMENT FRAME CLAMP | 230 | 230 | 0 | 6100KDP01 | PO-SEP-8378-[233] | PO | 2025-11-17 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 8 | 1 | 7 | 6100K025 | PO-SEP-8754-[2] | PO | 2025-12-15 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 7 | 3 | 4 | 6100KDP01 | PO-SEP-8368-[9] | PO | 2025-12-15 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 4 | 3 | 1 | 6100KDP01 | PO-SEP-8368-[7] | PO | 2025-12-15 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | OPTIMAL CONNECTIVITY LLC | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2522-2000-02 | HOUSING, 0930016-0301, HAN-E16 (West/South) | 1 | 1 | 0 | free_stock | PR-SEP-0024130-[149] | PR |  | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 51 | 26 | 25 | 6100K025 | PO-SEP-8752-[2] | PO | 2025-12-15 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2632-2000-13 | LOCKING PIN RELAY BOX | 25 | 25 | 0 | 6100KDP01 | PO-SEP-8484-[4] | PO | 2025-12-15 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | AL NAKHEEL GREEN STEEL WORKS | 6100K023 – PR for Supply of
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2632-2000-33 | Spring for Door Combiflex | 1.02 | 1.02 | 0 | 6100K025 | PO-SEP-8836-[17] | PO | 2025-11-13 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Saeed Aziz Alsomali Trading Est
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 51 | 4 | 47 | 6100K025 | PO-SEP-8831-[1] | PO | 2025-11-12 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | First Telecom Industries
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE2632-2000-AAP | BOX ASSEMBLY 60C, RHGX 20 (PAINT RAL) | 47 | 47 | 0 | 6100KDP01 | PO-SEP-8402-[69] | PO | 2025-11-17 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | First Telecom Industries | 6100K023 – PR for Supply of MV 13.8 kV Switchgear (SWGR) for Halfmoon 115/13.8 kV Substation (SS). This PR covers 1st lot of mechanical bulk materials required for the SWGR SS, i
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 3060 | 3050 | 10 | 6100K025 | PO-SEP-8792-[10] | PO | 2025-12-20 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AE5380-2000-04 | END COVER D-OTTA6 - 790417 | 10 | 10 | 0 | 6100KDP01 | PO-SEP-8572-[11] | PO | 2025-12-15 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 51 | 7 | 44 | 6100K025 | PO-SEP-8724-[3] | PO | 2025-11-16 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Azm and Tumooh Trading Establishment | Al Azizyah Project SS 6100KDP01 Mechanical Bulk Lot 5.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | AL-FOIL-A4-PLAIN | Aluminum Foil-A4size Plain-Self Adhesive | 44 | 44 | 0 | free_stock | PR-SEP-0024130-[154] | PR |  | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DM0000000058 | Relay, Auxiliary, 2 Coils, Self Reset Contacts, Hand Reset Flag, 110-125V, DC, 2NO, 1NC, Coil ¦ RXSF1 RK 271 007-AN | 8 | 8 | 0 | 6100K025 | PO-SEP-8751-[12] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DM0000000839 | COMBIFLEX TERMINAL BASE RX4 (4U 12C) | 14 | 14 | 0 | 6100K025 | PO-SEP-8751-[14] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DM0000000852 | COMBIFLEX TERMINAL BASE RX 2H -5619625-A | 243 | 243 | 0 | 6100K025 | PO-SEP-8751-[13] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DM0000003057 | Relay, Over Current Protection, DC, 110-250V, AC 100-230V, 19BI + 15BO, With IEC 61850-8-1, 2x Optical, Type 7SJ85 ¦ P1J198095 | 3 | 3 | 0 | 6100K025 | PO-SEP-8772-[1] | PO | 2026-02-28 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Siemens Ltd. | Relays, MV
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DM0000003059 | ‭CT SUPERVISION RELAY, 40msec DELAY, 125V DC, 4NC (TYPE: AR901) / 7PG1110-7AE10-0AF0‬ | 2 | 2 | 0 | 6010J605 | PO-SEP-5281-[14] | PO | 2025-11-15 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Siemens Ltd. | J599,J600,J605
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 2154 363-1 | WASHER, LOCK 10X5X0.5 | 51 | 51 | 0 | 6100K025 | PO-SEP-8668-[11] | PO | 2025-11-13 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | FABORY Czech s.r.o.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 20400 | 19200 | 1200 | 6100K025 | PO-SEP-8884-[6] | PO | 2025-12-21 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 2166 2056-3 | CABLE TIE WRAP KSS-CV140S | 1200 | 1200 | 0 | 6100KDP01 | PO-SEP-6812-[139] | PO | 2025-12-31 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | China Star (Dalian) Industry Co., Ltd. | 6100KDP01 // PP-12 (Mechanical Parts) for 07 Panels with Accessories
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 255 | 132 | 123 | 6100K025 | PO-SEP-8884-[7] | PO | 2025-12-21 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 2166 5011-10 | WIRE CHANNEL SIZE 48X100(1box=40meters) | 123 | 123 | 0 | 6100KDP01 | PO-SEP-8502-[11] | PO | 2025-12-31 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 51 | 28 | 23 | 6100K025 | PO-SEP-8884-[8] | PO | 2025-12-21 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 2166 5011-11 | WIRE CHANNEL SIZE 150X100(1box=12meter) | 23 | 23 | 0 | 6100KDP01 | PO-SEP-8502-[12] | PO | 2025-12-31 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 306 | 156 | 150 | 6100K025 | PO-SEP-8884-[9] | PO | 2025-12-21 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 2175 2012-25 | MOUNTNG RAIL OMEGA 35X15 02150 | 150 | 150 | 0 | 6100KDP01 | PO-SEP-8502-[13] | PO | 2025-12-31 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 2448 | 252 | 2196 | 6100K025 | PO-SEP-8925-[1] | PO | 2025-10-23 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 2641 2026-7 | FORK SPADE BF-U4 2.5/M4 | 2196 | 2196 | 0 | 6100KDP01 | PO-SEP-8502-[14] | PO | 2025-12-31 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 408 | 212 | 196 | 6100K025 | PO-SEP-8884-[10] | PO | 2025-12-21 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | 6100K025 DMM AZYZIYAH SWGR SS Electrical Componentes
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 2686 7001-1 | SPIRAL TUBE. KS15, 15MM DIA | 196 | 196 | 0 | 6100KDP01 | PO-SEP-8502-[15] | PO | 2025-12-31 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | Tube, White, Inner Diameter 4 mm, 2.5 Wire ¦ ¦ KSS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 924 0010 | Combiflex wire Socket 1.5mm 1MRK002136-B | 10200 | 5400 | 4800 | 6100K025 | PO-SEP-8751-[15] | PO | 2025-12-31 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 924 0010 | Combiflex wire Socket 1.5mm 1MRK002136-B | 4800 | 4800 | 0 | 6100KDP01 | PO-SEP-8366-[16] | PO | 2025-12-31 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 924 0020 | Combiflex wire Socket 2.5mm 1MRK002136-E | 6120 | 3800 | 2320 | 6100K025 | PO-SEP-8751-[16] | PO | 2025-12-31 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | DMS 924 0020 | Combiflex wire Socket 2.5mm 1MRK002136-E | 2320 | 2320 | 0 | 6100KDP01 | PO-SEP-8366-[17] | PO | 2025-12-31 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 12 | 2 | 10 | 6100KDP01 | PO-SEP-8362-[3] | PO | 2025-12-15 | B |  | - | 2026-05-15 | 2026-05-01 | 0 | Shanghai Feili Xuncheng Electrical Technology Co.,Ltd | Snap action/ 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 10 | 2 | 8 | 6100KDP01 | PO-SEP-8362-[4] | PO | 2025-12-15 | B |  | - | 2026-05-15 | 2026-05-01 | 0 | Shanghai Feili Xuncheng Electrical Technology Co.,Ltd | Snap action/ 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 8 | 3 | 5 | free_stock | PR-SEP-0024114-[152] | PR |  | B |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | E5090512100 | SNAP ACTION SWITCH CO S800 e 41 | 5 | 0 | 5 | PR Required | - | PR |  | B |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | GCE0438403P0100 | SPRG. PIN 2X10 DIN EN 28748 ST | 51 | 51 | 0 | 6100K025 | PO-SEP-8668-[7] | PO | 2025-11-13 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | FABORY Czech s.r.o.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | GCE0990162P0101 | PANEL HEATER 240V,50W-Boxin-3Met.Cable | 102 | 102 | 0 | 6100K025 | PO-SEP-8821-[3] | PO | 2025-12-31 | LVC |  | - | 2026-05-15 | 2026-05-01 | 0 | Changsha Electric Controlling Auxiliaries Factory
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | GCE0990403P0100 | VENTILATOR QK08A-2EM.50.CH WITH CAPACITO | 5 | 2 | 3 | 6100K025 | PO-SEP-8748-[3] | PO | 2025-12-31 | B |  | - | 2026-05-15 | 2026-05-01 | 0 | ZIEHL ABEGG Middle East FZE | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | GCE0990403P0100 | VENTILATOR QK08A-2EM.50.CH WITH CAPACITO | 3 | 3 | 0 | 6100KDP01 | PO-SEP-8361-[5] | PO | 2025-12-31 | B |  | - | 2026-05-15 | 2026-05-01 | 0 | ZIEHL ABEGG Middle East FZE | Fans / 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | GCE0990404P0100 | RADIAL FLOW FAN QK08A-2EM.35.CF | 7 | 2 | 5 | 6100K025 | PO-SEP-8748-[4] | PO | 2025-12-31 | B |  | - | 2026-05-15 | 2026-05-01 | 0 | ZIEHL ABEGG Middle East FZE | 6100K021 AL RAYAN SS SWGR Electrical Componentes Order.
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | GCE0990404P0100 | RADIAL FLOW FAN QK08A-2EM.35.CF | 5 | 5 | 0 | 6100KDP01 | PO-SEP-8361-[4] | PO | 2025-12-31 | B |  | - | 2026-05-15 | 2026-05-01 | 0 | ZIEHL ABEGG Middle East FZE | Fans / 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MARWI60236 | Zack Strip-Vertical(1-10) - 1053027:0001 | 1224 | 140 | 1084 | 6100K025 | PO-SEP-8792-[6] | PO | 2025-12-20 | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MARWI60236 | Zack Strip-Vertical(1-10) - 1053027:0001 | 1084 | 0 | 1084 | PR Required | - | PR |  | Terminals |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV-CR-U125DC3 | CR-U125DC3 - 1SVR405622R8200.CR-U125DC3 Pluggable interface relay 3c Ordering Code : 1SVR405622R8200 General: Pluggable interface relay ABB. Type : CR-U125DC3L Ordering Code: OUTPUTS: 3 C/O with LED RATED VOLTAGE: 125 VDC | 3 | 3 | 0 | 6100K025 | PO-SEP-8753-[3] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV-CR-U3S | Socket -FOR 3 C/O AND MODULE TIMER | 3 | 3 | 0 | 6100K025 | PO-SEP-8753-[4] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV-CR-UH | Holder interface relay 1SVR405669R0000 | 3 | 3 | 0 | 6100K025 | PO-SEP-8753-[5] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV-CR-UT | TIME MODULE 1SVR405667R0000 | 3 | 3 | 0 | 6100K025 | PO-SEP-8753-[6] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | To update Promised Delivery Date
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 96 | 8 | 88 | 6100K025 | PO-SEP-8836-[2] | PO | 2025-11-13 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | Saeed Aziz Alsomali Trading Est
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV-TR272-22KOHM5W | RESISTOR TR272- 110V TRIP COIL | 88 | 88 | 0 | free_stock | PR-SEP-0024130-[31] | PR |  | LVA |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50001 | Incomer Upper CT, INC3600-13.8-UCT ¦ ¦ RITZ | 9 | 9 | 0 | 6100K025 | PO-SEP-8756-[1] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50002 | Incomer Lower CT, INC3600-13.8-LCT ¦ ¦ RITZ | 9 | 3 | 6 | 6100K025 | PO-SEP-8756-[2] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50002 | Incomer Lower CT, INC3600-13.8-LCT ¦ ¦ RITZ | 6 | 6 | 0 | free_stock | PO-SEP-8758-[2] | PO | 2025-10-26 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | 6100K023 Halfmoon SS SWGR CT/Order
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50003 | Capacitor O/G Feeder Upper CT, CAP1250-13.8-UCT ¦ ¦ RITZ | 9 | 3 | 6 | 6100K025 | PO-SEP-8756-[3] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50003 | Capacitor O/G Feeder Upper CT, CAP1250-13.8-UCT ¦ ¦ RITZ | 6 | 6 | 0 | free_stock | PO-SEP-8758-[3] | PO | 2025-10-26 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | 6100K023 Halfmoon SS SWGR CT/Order
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50004 | Capacitor O/G Feeder Lower CT, CAP1250-13.8-LCT ¦ ¦ RITZ | 9 | 3 | 6 | 6100K025 | PO-SEP-8756-[4] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50004 | Capacitor O/G Feeder Lower CT, CAP1250-13.8-LCT ¦ ¦ RITZ | 6 | 6 | 0 | free_stock | PO-SEP-8758-[4] | PO | 2025-10-26 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | 6100K023 Halfmoon SS SWGR CT/Order
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50005 | Station Auxiliary Upper CT, SST630-13.8-UCT ¦ ¦ RITZ | 6 | 6 | 0 | free_stock | PO-SEP-8758-[5] | PO | 2025-10-26 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | 6100K023 Halfmoon SS SWGR CT/Order
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50006 | Station Auxiliary Lower CT, SST630-13.8-LCT ¦ ¦ RITZ | 6 | 6 | 0 | free_stock | PO-SEP-8758-[6] | PO | 2025-10-26 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | 6100K023 Halfmoon SS SWGR CT/Order
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50007 | Outgoing Plain Upper CT, OG1250-13.8-UCT ¦ ¦ RITZ | 114 | 18 | 96 | 6100K025 | PO-SEP-8756-[7] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50007 | Outgoing Plain Upper CT, OG1250-13.8-UCT ¦ ¦ RITZ | 96 | 96 | 0 | free_stock | PO-SEP-8758-[7] | PO | 2025-10-26 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | 6100K023 Halfmoon SS SWGR CT/Order
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50008 | Outgoing plain Lower CT, OG1250-13.8-LCT ¦ ¦ RITZ | 114 | 18 | 96 | 6100K025 | PO-SEP-8756-[8] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50008 | Outgoing plain Lower CT, OG1250-13.8-LCT ¦ ¦ RITZ | 96 | 96 | 0 | free_stock | PO-SEP-8758-[8] | PO | 2025-10-26 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | 6100K023 Halfmoon SS SWGR CT/Order
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50009 | BusTie Upper CT, BS3600-13.8-UCT ¦ ¦ RITZ | 6 | 3 | 3 | 6100K025 | PO-SEP-8756-[9] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50009 | BusTie Upper CT, BS3600-13.8-UCT ¦ ¦ RITZ | 3 | 3 | 0 | free_stock | PO-SEP-8758-[9] | PO | 2025-10-26 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | 6100K023 Halfmoon SS SWGR CT/Order
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50010 | Bus-Tie Lower CT, BS3600-13.8-LCT ¦ ¦ RITZ | 6 | 3 | 3 | 6100K025 | PO-SEP-8756-[10] | PO | 2025-10-23 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | CT 6100K025 AZYZIYAH DMM SWGR SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | MV50010 | Bus-Tie Lower CT, BS3600-13.8-LCT ¦ ¦ RITZ | 3 | 3 | 0 | free_stock | PO-SEP-8758-[10] | PO | 2025-10-26 | Electrical_Transformers |  | - | 2026-05-15 | 2026-05-01 | 0 |  | 6100K023 Halfmoon SS SWGR CT/Order
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP10038 | Humidistat, 250V, AC, MFR 012 ¦ 01220.0-00 | 51 | 17 | 34 | 6100K025 | PO-SEP-8819-[1] | PO | 2025-12-31 | LVA |  | - | 2026-05-15 | 2026-05-01 | 0 | STEGO Elektrotechnik GmbH | Humidistat, 250V, AC, MFR 012
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP10038 | Humidistat, 250V, AC, MFR 012 ¦ 01220.0-00 | 34 | 34 | 0 | free_stock | PR-SEP-0024130-[12] | PR |  | LVA |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP10162 | WHITE TUBE,INNER DIA. 3.5 MM (1.5 WIRE) | 12750 | 0 | 12750 | PR Required | - | PR |  | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP10163 | RED TUBE, INNER DIA. 3.5MM (1.5 WIRE) | 510 | 0 | 510 | PR Required | - | PR |  | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 765 | 43 | 722 | free_stock | PR-SEP-0023387-[166] | PR |  | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP10165 | WHITE TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 722 | 0 | 722 | PR Required | - | PR |  | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP10298 | RED TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 510 | 0 | 510 | PR Required | - | PR |  | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP10349 | RED TUBE, INNER DIA. 5.0MM (4.0 WIRE) | 510 | 0 | 510 | PR Required | - | PR |  | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP10650 | WHITE TUBE, INNER DIA. 4.0MM (2.5 WIRE) | 2040 | 0 | 2040 | PR Required | - | PR |  | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11258 | Cable, Control, 1 Core,CU/PVC, 1.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 111.5974 | 75.9737 | 35.6236 | 6100KDP01 | PO-SEP-8622-[19] | PO | 2026-01-30 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11258 | Cable, Control, 1 Core,CU/PVC, 1.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 35.6236 | 35.6236 | 0 | free_stock | PR-SEP-0024130-[100] | PR |  | Wire |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11259 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 36.2691 | 30.7931 | 5.476 | 6100KDP01 | PO-SEP-8622-[20] | PO | 2026-01-30 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11259 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 5.476 | 5.476 | 0 | free_stock | PR-SEP-0024130-[101] | PR |  | Wire |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11260 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 838.0744 | 6.4989 | 831.5755 | 6100K025 | PO-SEP-8915-[3] | PO | 2026-01-11 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11260 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 831.5755 | 831.5755 | 0 | 6100KDP01 | PO-SEP-8622-[21] | PO | 2026-01-30 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11261 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 36.2691 | 20.7931 | 15.476 | 6100KDP01 | PO-SEP-8622-[22] | PO | 2026-01-30 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11261 | Cable, Control, 1 Core, CU/PVC, 1.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 15.476 | 15.476 | 0 | free_stock | PR-SEP-0024130-[103] | PR |  | Wire |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11262 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 150.6565 | 134.3613 | 16.2952 | 6100KDP01 | PO-SEP-8622-[23] | PO | 2026-01-30 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11262 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 16.2952 | 16.2952 | 0 | free_stock | PR-SEP-0024130-[104] | PR |  | Wire |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11263 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 94.8578 | 1.3744 | 93.4834 | 6100K025 | PO-SEP-8915-[6] | PO | 2026-01-11 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11263 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 93.4834 | 93.4834 | 0 | 6100KDP01 | PO-SEP-8622-[24] | PO | 2026-01-30 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11264 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 27.8993 | 1.988 | 25.9114 | 6100K025 | PO-SEP-8915-[7] | PO | 2026-01-11 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11264 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 25.9114 | 25.9114 | 0 | 6100KDP01 | PO-SEP-8622-[25] | PO | 2026-01-30 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11265 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm Yellow/Green, ATC, 105°, 600/1000V , 1 x 100 m | 28.0088 | 28.0088 | 0 | free_stock | PR-SEP-0024130-[107] | PR |  | Wire |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11266 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 150.6565 | 2.3613 | 148.2952 | 6100K025 | PO-SEP-8915-[9] | PO | 2026-01-11 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11266 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 148.2952 | 148.2952 | 0 | 6100KDP01 | PO-SEP-8622-[27] | PO | 2026-01-30 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11267 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Yellow, ATC,105°, 600/1000V , 1 x 100 m | 150.6565 | 134.3613 | 16.2952 | 6100KDP01 | PO-SEP-8622-[28] | PO | 2026-01-30 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items - KDP01 & K023
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11267 | Cable, Control, 1 Core, CU/PVC, 2.5 Sq.mm, Yellow, ATC,105°, 600/1000V , 1 x 100 m | 16.2952 | 16.2952 | 0 | free_stock | PR-SEP-0024130-[109] | PR |  | Wire |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11268 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Blue, ATC, 105°, 600/1000V , 1 x 100 m | 8.3698 | 8.3698 | 0 | 6100K025 | PO-SEP-8915-[11] | PO | 2026-01-11 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11269 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Black, ATC, 105°, 600/1000V , 1 x 100 m | 11.1597 | 11.1597 | 0 | 6100K025 | PO-SEP-8915-[12] | PO | 2026-01-11 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11270 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Red, ATC, 105°, 600/1000V , 1 x 100 m | 8.3698 | 8.3698 | 0 | 6100K025 | PO-SEP-8915-[14] | PO | 2026-01-11 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11271 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Yellow, ATC, 105°, 600/1000V , 1 x 100 m | 8.3698 | 8.3698 | 0 | 6100K025 | PO-SEP-8915-[15] | PO | 2026-01-11 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP11272 | Cable, Power, 1 Core, CU/PVC, 4.0 Sq.mm, Grey, ATC, 105°, 600/1000V , 1 x 100 m | 11.1597 | 11.1597 | 0 | 6100K025 | PO-SEP-8915-[13] | PO | 2026-01-11 | Wire |  | - | 2026-05-15 | 2026-05-01 | 0 | Al-Fanar Company Limited | Cable Items
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12004 | TERM.LUGS BLADE RF-PP 12/23 | 15300 | 15300 | 0 | 6100KDP01 | PO-SEP-8541-[5] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12012 | TERM.LUGS SPADE RF-U4 1.5/M4 | 6375 | 6375 | 0 | 6100KDP01 | PO-SEP-8541-[17] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12016 | TERM.LUGS RING RF-M4 1.5/M4 | 5100 | 5100 | 0 | 6100KDP01 | PO-SEP-8541-[7] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12048 | END SLEEVES PKE 1508 (1x1.5sqmm , Black) | 765 | 765 | 0 | 6100KDP01 | PO-SEP-8541-[13] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12050 | UN-INSUL SLeve Lugs KE1510ST (1.5mm) | 1020 | 1020 | 0 | 6100KDP01 | PO-SEP-8541-[1] | PO | 2025-10-29 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12052 | END SLEEVES PKT 1508 (2x1.5sqmm , Black) | 765 | 725 | 40 | 6100KDP01 | PO-SEP-8541-[10] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12052 | END SLEEVES PKT 1508 (2x1.5sqmm , Black) | 40 | 40 | 0 | 6100K023 | PO-SEP-8418-[19] | PO | 2025-11-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12063 | TERM.LUGS BLADE BF-PP12/25 2.5MM | 5100 | 5100 | 0 | 6100KDP01 | PO-SEP-8541-[4] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12083 | TERM.LUGS BF-M5 (RING) | 6120 | 6120 | 0 | 6100KDP01 | PO-SEP-8541-[18] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12085 | WIRE LUGS RING TYPE BF-M6 2.5/M6 | 408 | 408 | 0 | 6100KDP01 | PO-SEP-8541-[12] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12087 | RING TYPE LUGS BF-M 8 | 408 | 408 | 0 | 6100KDP01 | PO-SEP-8541-[9] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12103 | UN-INSUL SLEEVE Lugs for 2.5mm KE2510ST | 2550 | 2550 | 0 | 6100KDP01 | PO-SEP-8541-[2] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12105 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 1020 | 900 | 120 | 6100KDP01 | PO-SEP-8541-[11] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12105 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 120 | 80 | 40 | 6100K023 | PO-SEP-8418-[18] | PO | 2025-11-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | 6100K023Halfmoon SWGR Project, All Electrical Components (ABB, Hitachi & Bulk) to Supply of MV 13.8 kV SWGR For Halfmoon 115/13.8kv SS
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12105 | END SLEEVES PKT 2512 (2x2.5sqmm , Blue) | 40 | 40 | 0 | free_stock | PR-SEP-0024130-[179] | PR |  | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12117 | TERM.LUGS RING BF-M4 | 10200 | 6400 | 3800 | 6100KDP01 | PO-SEP-8541-[8] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12117 | TERM.LUGS RING BF-M4 | 3800 | 3800 | 0 | free_stock | PR-SEP-0024130-[169] | PR |  | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12119 | RING TYPE LUGS GF-M 5 | 1020 | 432 | 588 | 6100KDP01 | PO-SEP-8541-[6] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12119 | RING TYPE LUGS GF-M 5 | 588 | 588 | 0 | free_stock | PR-SEP-0024130-[167] | PR |  | LVD |  | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12129 | Un-Insul Sleeve Lugs 4.0 mm KE410ST | 2550 | 2550 | 0 | 6100KDP01 | PO-SEP-8541-[3] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12131 | Lugs, Sleeve 4.0/9mm ( W/O Ins.) 3200302 | 2550 | 2550 | 0 | 6100KDP01 | PO-SEP-8541-[14] | PO | 2025-10-30 | LVD |  | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | VT-GUARD-13.8KV | VT Guard, Anti Ferro Resonance Unit ¦ VT-GUARD-13.8KV | 6 | 6 | 0 | 6100K025 | PO-SEP-8713-[2] | PO | 2025-12-15 | RVT |  | - | 2026-05-15 | 2026-05-01 | 0 | Abb Electrical Industriesco | Al Azyziyah SS 6100KDP01. VT Guard, Anti Ferro Reso{}ce Unit ¦ VT-GUARD
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SNA234000R0200 | Marker, RC810, 1 ¦ 10/1SNA234041R2600 ¦ ENTRELEC | 510 | 450 | 60 | 6100K025 | PO-SEP-8833-[37] | PO | 2025-11-13 | Terminals | Automated: Replaced 1SNA234000R0200 by SEP20333. | - | 2026-05-15 | 2026-05-01 | 0 | Al Suhaili Trading And Development
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1SNA234000R0200 | Marker, RC810, 1 ¦ 10/1SNA234041R2600 ¦ ENTRELEC | 60 | 60 | 0 | free_stock | PR-SEP-0024130-[89] | PR |  | Terminals | Automated: Replaced 1SNA234000R0200 by SEP20333. | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5340XIAXXN01 | Relay, Auxiliary, 2 Coils, Self Reset Contacts, Hand Reset Flag, 110-125V, DC, 2NO, 1NC, Coil ¦ RXSF1 RK 271 007-AN | 51 | 51 | 0 | 6100KDP01 | PO-SEP-8297-[3] | PO | 2026-01-08 | LVA | Automated: Replaced 1YAB5340XIAXXN01 by DM0000000058. | - | 2026-05-15 | 2026-05-01 | 0 | Hitachi Energy Ltd | PP-12 RELAY BASE AND COMBIFLEX BOX
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block, TB, Disconnecting TB for CT, OTTA 6-T, Bolt W/O Spring, 0790462 ¦ OTTA 6-T P/P ¦ PHOENIX | 4012 | 4000 | 12 | 6100K025 | PO-SEP-8792-[1] | PO | 2025-12-20 | Terminals | Automated: Replaced 1YAB5355AAB0001 by SEP10052. | - | 2026-05-15 | 2026-05-01 | 0 | Phoenix Contact Trading LLC | PHOENIX ITEMS FOR MV SWGR- 6100K025 DMM AZYZIYAH SWGR SS / 6100K021 AL RAYAN SS SWGR /6100K020 Mahar SS SWGR
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355AAB0001 | Terminal Block, TB, Disconnecting TB for CT, OTTA 6-T, Bolt W/O Spring, 0790462 ¦ OTTA 6-T P/P ¦ PHOENIX | 12 | 12 | 0 | 6100KDP01 | PO-SEP-8572-[1] | PO | 2025-12-15 | Terminals | Automated: Replaced 1YAB5355AAB0001 by SEP10052. | - | 2026-05-15 | 2026-05-01 | 0 | Phoenix Contact Trading LLC | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | 1YAB5355CAB0000 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 510 | 236 | 274 | free_stock | PR-SEP-0024130-[77] | PR |  | Terminals | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | RMU000000260 | Parition, Terminal, Current, D-OTTA6-T ¦ 0790459 ¦ PHOENIX | 274 | 0 | 274 | PR Required | - | PR |  | Terminals | Automated: Replaced 1YAB5355CAB0000 by RMU000000260. Automated: Replaced 1YAB5355CAB0000 by RMU000000260. | - | 2026-05-15 | 2026-05-01 | 0
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12026 | Lugs, Terminal Hook, 1.5 Sq.mm ¦ CEM-RF-PPL30 ¦ Cembre | 35000 | 35000 | 0 | 6100KDP01 | PO-SEP-8541-[19] | PO | 2025-10-30 | LVD | Automated: Replaced 1YAB5355HXB0000 by SEP12026. Automated: Replaced 1YAB5355HXB0000 by SEP12026. | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12127 | Lugs, Terminal Hook, 4.0 Sq.mm ¦ CEM-GF-PPL46 ¦ Cembre | 7450 | 7450 | 0 | 6100KDP01 | PO-SEP-8541-[15] | PO | 2025-10-30 | LVD | Automated: Replaced 1YAB5355HXB0001 by SEP12127. Automated: Replaced 1YAB5355HXB0001 by SEP12127. | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).
6100K025 | Aziziyah DMM : SWITCHGEAR - Aziziyah DMM | SWGR | ROH | SEP12091 | Lugs, Terminal Hook, 2.5 Sq.mm ¦ CEM-BF-PPL30 ¦ Cembre | 15000 | 15000 | 0 | 6100KDP01 | PO-SEP-8541-[16] | PO | 2025-10-30 | LVD | Automated: Replaced 1YAB5355HXB0002 by SEP12091. Automated: Replaced 1YAB5355HXB0002 by SEP12091. | - | 2026-05-15 | 2026-05-01 | 0 | Sana For Electric And Telephone Co | AL Azyziyah 6100KDP01, Supply of Electrical Components – 1st Lot for SWGR under Dummy Project 6100KDP01 – Al Azyziyah Project (SEC Scope).